## Sheet1
id | createDatetimeUTC | createDatetimeLocal | createdByPrincipal | lastUpdateDatetimeUTC | lastUpdateDatetimeLocal | lastUpdatedByPrincipal | category | version_id | version_isCurrentVersion | version_isActive | version_changeDatetimeUTC | version_changeDatetimeLocal | version_title | version_versionNumber | version_isSupplyChain | version_workGroup | version_startDatetimeUTC | version_endDatetimeUTC | version_startDatetimeLocal | version_endDatetimeLocal | version_preShutDateTime | version_postShutDateTime | version_preShutDateTimeLocal | version_postShutDateTimeLocal | version_durationHours | version_description | version_versionComments | version_sapRevision | version_equipment | version_keyContacts | version_impactedSites | version_linkedShuts | version_majorTasks | version_projects | version_siteConstraints | version_status.name | version_changeType.name | version_changedByPrincipal.principalGUID | version_changedByPrincipal.displayName | version_type.name | version_site.name | version_localTimezone.name | version_site | version_workGroup.name
57746 | 2023-08-17T06:29:58+00:00 | 2023-08-17T14:29:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2023-08-17T06:30:18+00:00 | 2023-08-17T14:30:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | {"name": "Fixed Plant"} | 175364 | TRUE | TRUE | 2023-08-17T06:30:18+00:00 | 2023-08-17T14:30:18+08:00 | #57746 - YAN: 24hrs - PLANT 1 DRY PLANT | 2.0 | TRUE |  | 2028-01-06T22:00:00+00:00 | 2028-01-07T22:00:00+00:00 | 2028-01-07T06:00:00+08:00 | 2028-01-08T06:00:00+08:00 |  |  |  |  | 24.00 | 24hr - Dry Plant Screen Outage - 2 Run PC1 t at 50% for screen panel C/O. Screen to be worked on;YSC07, YSC03 & YSC04 |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | abefcdab-0000-0000-0000-00000000003d | Clare Campbell-Cooke | Scheduled | YAN | Australia/Perth
61957 | 2024-06-14T00:54:05+00:00 | 2024-06-14T08:54:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2024-06-14T01:20:30+00:00 | 2024-06-14T09:20:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | {"name": "Fixed Plant"} | 207370 | TRUE | TRUE | 2024-06-14T01:20:30+00:00 | 2024-06-14T09:20:30+08:00 | #61957 - CLA: 36hrs - CLA PLT TC 4 | 2.0 | FALSE |  | 2026-12-20T22:00:00+00:00 | 2026-12-22T10:00:00+00:00 | 2026-12-21T06:00:00+08:00 | 2026-12-22T18:00:00+08:00 |  |  |  |  | 36.00 | STD IAM Maintenance |  |  | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | abefcdab-0000-0000-0000-00000000031b | Ray Boskell | Scheduled | CLA | Australia/Perth
83544 | 2026-07-21T05:39:39.8622968+00:00 | 2026-07-21T13:39:39.8622968+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | 2026-07-21T05:39:39.8622968+00:00 | 2026-07-21T13:39:39.8622968+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | {"name": "System"} | 330184 | TRUE | TRUE | 2026-07-21T05:39:39.8622968+00:00 | 2026-07-21T13:39:39.8622968+08:00 | #83544 - SYSTEM: 6hrs - TW: CENTRAL CORRIDOR | 1.0 | TRUE |  | 2026-12-03T23:00:00+00:00 | 2026-12-04T05:00:00+00:00 | 2026-12-04T07:00:00+08:00 | 2026-12-04T13:00:00+08:00 |  |  |  |  | 6.00 | 6hr Dual Track Closure Emu to Gull (IAM50 & IAM01 & IAM02 & IAM03 & IAM04 & IAM05 & IAM06)) MLTP 89.2km Level Crossing GCP Upgrade - D5/5 |  |  | [{"equipmentGUID": "", "code": "TRACK WORK IMPACTING CENTRAL CORRIDOR", "name": "TW: Central Corridor", "assetClass": {"name": "Rail Network"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "emailAddress": "Bradley.Gallagher@riotinto.com", "displayName": "Bradley Gallagher"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "649e69a1-9850-4527-be76-b6ff02b32dd7", "emailAddress": "Tori.Antonovich@riotinto.com", "displayName": "Antonovich, Tori (RTIO)"}}] | [{"name": "PDO"}, {"name": "MDO"}, {"name": "WAN"}, {"name": "YAN"}, {"name": "MTP"}, {"name": "HD1"}, {"name": "BM4"}, {"name": "HD4"}, {"name": "CLB"}, {"name": "NBWT"}, {"name": "PPT"}, {"name": "BM2"}, {"name": "CLA"}, {"name": "EII"}, {"name": "GDI"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Create | e66894fa-d615-4ac5-8967-f24780e04d56 | Gallagher, Bradley (RTIO) | Site Constraint |  | Australia/Perth
83545 | 2026-07-21T05:39:39.8624365+00:00 | 2026-07-21T13:39:39.8624365+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | 2026-07-21T05:39:39.8624365+00:00 | 2026-07-21T13:39:39.8624365+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | {"name": "System"} | 330185 | TRUE | TRUE | 2026-07-21T05:39:39.8624365+00:00 | 2026-07-21T13:39:39.8624365+08:00 | #83545 - SYSTEM: 48hrs - TW: EP EAST PILBARA | 1.0 | TRUE |  | 2026-12-08T22:30:00+00:00 | 2026-12-10T22:30:00+00:00 | 2026-12-09T06:30:00+08:00 | 2026-12-11T06:30:00+08:00 |  |  |  |  | 48.00 | 48hr MLYA Shut Bellbird to Marandoo (30) Prior to the shut trains will be stored south of Marandoo to feed EP sites while the shut is on. |  |  | [{"equipmentGUID": "", "code": "TRACK WORK IMPACTING EP", "name": "TW: EP East Pilbara", "assetClass": {"name": "Rail Network"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "emailAddress": "Bradley.Gallagher@riotinto.com", "displayName": "Bradley Gallagher"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "649e69a1-9850-4527-be76-b6ff02b32dd7", "emailAddress": "Tori.Antonovich@riotinto.com", "displayName": "Antonovich, Tori (RTIO)"}}] | [{"name": "MDO"}, {"name": "WAN"}, {"name": "YAN"}, {"name": "HD1"}, {"name": "HD4"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Create | e66894fa-d615-4ac5-8967-f24780e04d56 | Gallagher, Bradley (RTIO) | Site Constraint |  | Australia/Perth
73402 | 2025-11-24T09:58:33.3178621+00:00 | 2025-11-24T17:58:33.3178621+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | 2025-11-24T09:58:33.3178621+00:00 | 2025-11-24T17:58:33.3178621+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | {"name": "System"} | 276650 | TRUE | TRUE | 2025-11-24T09:58:33.3178621+00:00 | 2025-11-24T17:58:33.3178621+08:00 | #73402 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | FALSE |  | 2026-12-14T20:00:00+00:00 | 2026-12-15T18:00:00+00:00 | 2026-12-15T04:00:00+08:00 | 2026-12-16T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. |  |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "YAN"}] | [] | [] | [] | [] | Approved | Create | e76be1a2-087e-4b54-8c65-7825375ab7d2 | Chia, Daniel (RTIO-WORKPAC) | Scheduled |  | Australia/Perth
73431 | 2025-11-24T23:35:04.9593376+00:00 | 2025-11-25T07:35:04.9593376+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | 2025-11-24T23:35:04.9593376+00:00 | 2025-11-25T07:35:04.9593376+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | {"name": "System"} | 276682 | TRUE | TRUE | 2025-11-24T23:35:04.9593376+00:00 | 2025-11-25T07:35:04.9593376+08:00 | #73431 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | FALSE |  | 2027-05-17T20:00:00+00:00 | 2027-05-18T18:00:00+00:00 | 2027-05-18T04:00:00+08:00 | 2027-05-19T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. |  |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "RVJ"}, {"name": "RVA"}] | [{"relationshipType": null, "shut": {"shutId": 44698, "shutVersionId": 334191, "title": "#44698 - RVA: 144hrs - PLANT: RVA DRY", "startDatetimeUTC": "2027-05-22T03:00:00+00:00", "endDatetimeUTC": "2027-05-28T03:00:00+00:00"}}] | [] | [] | [] | Approved | Create | e76be1a2-087e-4b54-8c65-7825375ab7d2 | Chia, Daniel (RTIO-WORKPAC) | Scheduled |  | Australia/Perth
60594 | 2024-02-15T05:50:59+00:00 | 2024-02-15T13:50:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-02-25T08:33:07.6770914+00:00 | 2026-02-25T16:33:07.6770914+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 289617 | TRUE | TRUE | 2026-02-25T08:33:07.6770914+00:00 | 2026-02-25T16:33:07.6770914+08:00 | #60594 - CLB: 156hrs - CD7C - END RING DUST SEALS & COVERS | 7.0 | TRUE |  | 2027-08-21T10:00:00+00:00 | 2027-08-27T22:00:00+00:00 | 2027-08-21T18:00:00+08:00 | 2027-08-28T06:00:00+08:00 |  |  |  |  | 156.00 | CD7C - End Ring Dust Seals & Covers | Moved from Wk8 to Wk33 swapped with Rolling Rail C/O due to condition |  | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "423b6bb1-0045-43ea-9031-297314d2eb65", "emailAddress": "Scott.Clamp@riotinto.com", "displayName": "Scott Clamp"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43641 | 2021-11-01T23:45:26+00:00 | 2021-11-02T07:45:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-17T04:00:59.3651046+00:00 | 2025-11-17T12:00:59.3651046+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 275869 | TRUE | TRUE | 2025-11-17T04:00:59.3651046+00:00 | 2025-11-17T12:00:59.3651046+08:00 | #43641 - CLB: 72hrs - STACKER: CLB 12 | 4.0 | FALSE |  | 2028-01-02T22:00:00+00:00 | 2028-01-05T22:00:00+00:00 | 2028-01-03T06:00:00+08:00 | 2028-01-06T06:00:00+08:00 |  |  |  |  | 72.00 | Standard IMS Shut | IAM Refresh | SCBY2751 | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43717 | 2021-11-02T01:52:10+00:00 | 2021-11-02T09:52:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-17T06:59:36.5720427+00:00 | 2025-11-17T14:59:36.5720427+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 276058 | TRUE | TRUE | 2025-11-17T06:59:36.5720427+00:00 | 2025-11-17T14:59:36.5720427+08:00 | #43717 - CLA: 250hrs - STACKER: CLA 02 | 7.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IMS Shut | IAM Refresh |  | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43514 | 2021-11-01T22:56:13+00:00 | 2021-11-02T06:56:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-17T08:53:32.632858+00:00 | 2025-11-17T16:53:32.632858+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 276212 | TRUE | TRUE | 2025-11-17T08:53:32.632858+00:00 | 2025-11-17T16:53:32.632858+08:00 | #43514 - CLA: 138hrs - RECLAIMER: CLA 03 | 5.0 | FALSE |  | 2027-09-20T04:00:00+00:00 | 2027-09-25T22:00:00+00:00 | 2027-09-20T12:00:00+08:00 | 2027-09-26T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance | IAM Refresh | SCAY2736 | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45742, "shutVersionId": 333126, "title": "#45742 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING", "startDatetimeUTC": "2027-09-20T22:00:00+00:00", "endDatetimeUTC": "2027-09-22T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43703 | 2021-11-02T00:03:15+00:00 | 2021-11-02T08:03:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-26T00:38:44.4577539+00:00 | 2025-11-26T08:38:44.4577539+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277565 | TRUE | TRUE | 2025-11-26T00:38:44.4577539+00:00 | 2025-11-26T08:38:44.4577539+08:00 | #43703 - CLB: 72hrs - CONVEYOR: CLB 500 LINK | 7.0 | TRUE |  | 2027-08-22T10:00:00+00:00 | 2027-08-25T10:00:00+00:00 | 2027-08-22T18:00:00+08:00 | 2027-08-25T18:00:00+08:00 |  |  |  |  | 72.00 | Contact Shutdown Coordinator regarding shuttle positions for CLB dumper and stacker alignment Standard IMS Shut | IAM Refresh | SCBI2731 | [{"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43475 | 2021-11-01T22:49:41+00:00 | 2021-11-02T06:49:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-11T01:31:10.2535053+00:00 | 2025-11-11T09:31:10.2535053+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 273808 | TRUE | TRUE | 2025-11-11T01:31:10.2535053+00:00 | 2025-11-11T09:31:10.2535053+08:00 | #43475 - CLA: 114hrs - BERTH: CLA 01 | 7.0 | FALSE |  | 2027-08-30T10:00:00+00:00 | 2027-09-04T04:00:00+00:00 | 2027-08-30T18:00:00+08:00 | 2027-09-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut | IAM Refresh | SCAO2734 | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43476 | 2021-11-01T22:49:41+00:00 | 2021-11-02T06:49:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-11T01:31:10.6392293+00:00 | 2025-11-11T09:31:10.6392293+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 273810 | TRUE | TRUE | 2025-11-11T01:31:10.6392293+00:00 | 2025-11-11T09:31:10.6392293+08:00 | #43476 - CLA: 114hrs - BERTH: CLA 02 | 7.0 | FALSE |  | 2027-08-30T10:00:00+00:00 | 2027-09-04T04:00:00+00:00 | 2027-08-30T18:00:00+08:00 | 2027-09-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut | IAM Refresh | SCAO2734 | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43580 | 2021-11-01T23:00:02+00:00 | 2021-11-02T07:00:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-11T01:31:11.0094786+00:00 | 2025-11-11T09:31:11.0094786+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 273812 | TRUE | TRUE | 2025-11-11T01:31:11.0094786+00:00 | 2025-11-11T09:31:11.0094786+08:00 | #43580 - CLA: 126hrs - SCREENHOUSE: CLA LUMP RESCREENING PLANT 02 | 6.0 | FALSE |  | 2027-08-30T10:00:00+00:00 | 2027-09-04T16:00:00+00:00 | 2027-08-30T18:00:00+08:00 | 2027-09-05T00:00:00+08:00 |  |  |  |  | 126.00 | Standard IMS Shut | IAM Refresh | SCAO2734 | [{"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43643 | 2021-11-01T23:47:32+00:00 | 2021-11-02T07:47:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-25T07:25:39.2595835+00:00 | 2025-11-25T15:25:39.2595835+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277184 | TRUE | TRUE | 2025-11-25T07:25:39.2595835+00:00 | 2025-11-25T15:25:39.2595835+08:00 | #43643 - CLB: 120hrs - RECLAIMER: CLB 11 | 5.0 | FALSE |  | 2027-09-12T22:00:00+00:00 | 2027-09-17T22:00:00+00:00 | 2027-09-13T06:00:00+08:00 | 2027-09-18T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IMS Shut | IAM Refresh | SCBY2739 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43656 | 2021-11-01T23:50:06+00:00 | 2021-11-02T07:50:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-25T07:42:51.9610997+00:00 | 2025-11-25T15:42:51.9610997+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277256 | TRUE | TRUE | 2025-11-25T07:42:51.9610997+00:00 | 2025-11-25T15:42:51.9610997+08:00 | #43656 - CLB: 120hrs - RECLAIMER: CLB 12 | 5.0 | FALSE |  | 2027-10-10T22:00:00+00:00 | 2027-10-15T22:00:00+00:00 | 2027-10-11T06:00:00+08:00 | 2027-10-16T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBY2745 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43628 | 2021-11-01T23:42:37+00:00 | 2021-11-02T07:42:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-11-26T00:50:45.0422925+00:00 | 2025-11-26T08:50:45.0422925+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277735 | TRUE | TRUE | 2025-11-26T00:50:45.0422925+00:00 | 2025-11-26T08:50:45.0422925+08:00 | #43628 - CLB: 106hrs - CAR DUMPER: CLB 6C | 8.0 | TRUE |  | 2027-10-04T10:00:00+00:00 | 2027-10-08T20:00:00+00:00 | 2027-10-04T18:00:00+08:00 | 2027-10-09T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | wrong week | SCBI2738 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43503 | 2021-11-01T22:54:46+00:00 | 2021-11-02T06:54:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-12-03T02:19:18.4868076+00:00 | 2025-12-03T10:19:18.4868076+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 278542 | TRUE | TRUE | 2025-12-03T02:19:18.4868076+00:00 | 2025-12-03T10:19:18.4868076+08:00 | #43503 - CLA: 108hrs - STACKER: CLA 04 | 5.0 | FALSE |  | 2028-01-16T22:00:00+00:00 | 2028-01-21T10:00:00+00:00 | 2028-01-17T06:00:00+08:00 | 2028-01-21T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | IAM Refresh | SCAY2752 | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
43499 | 2021-11-01T22:54:41+00:00 | 2021-11-02T06:54:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-12-03T02:19:18.8415741+00:00 | 2025-12-03T10:19:18.8415741+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 278544 | TRUE | TRUE | 2025-12-03T02:19:18.8415741+00:00 | 2025-12-03T10:19:18.8415741+08:00 | #43499 - CLA: 138hrs - RECLAIMER: CLA 01 | 5.0 | FALSE |  | 2028-01-17T04:00:00+00:00 | 2028-01-22T22:00:00+00:00 | 2028-01-17T12:00:00+08:00 | 2028-01-23T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance | IAM Refresh | SCAY2752 | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
71819 | 2025-10-30T00:44:23.701338+00:00 | 2025-10-30T08:44:23.701338+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:23.9074341+00:00 | 2025-10-30T08:44:23.9074341+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266276 | TRUE | TRUE | 2025-10-30T00:44:23.9074341+00:00 | 2025-10-30T08:44:23.9074341+08:00 | #71819 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-04-03T22:00:00+00:00 | 2027-04-04T04:00:00+00:00 | 2027-04-04T06:00:00+08:00 | 2027-04-04T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71820 | 2025-10-30T00:44:24.2642851+00:00 | 2025-10-30T08:44:24.2642851+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:24.4677244+00:00 | 2025-10-30T08:44:24.4677244+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266278 | TRUE | TRUE | 2025-10-30T00:44:24.4677244+00:00 | 2025-10-30T08:44:24.4677244+08:00 | #71820 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-04-10T22:00:00+00:00 | 2027-04-11T04:00:00+00:00 | 2027-04-11T06:00:00+08:00 | 2027-04-11T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71821 | 2025-10-30T00:44:24.8542917+00:00 | 2025-10-30T08:44:24.8542917+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:25.0560462+00:00 | 2025-10-30T08:44:25.0560462+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266280 | TRUE | TRUE | 2025-10-30T00:44:25.0560462+00:00 | 2025-10-30T08:44:25.0560462+08:00 | #71821 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-04-17T22:00:00+00:00 | 2027-04-18T04:00:00+00:00 | 2027-04-18T06:00:00+08:00 | 2027-04-18T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71822 | 2025-10-30T00:44:25.4241515+00:00 | 2025-10-30T08:44:25.4241515+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:25.6347264+00:00 | 2025-10-30T08:44:25.6347264+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266282 | TRUE | TRUE | 2025-10-30T00:44:25.6347264+00:00 | 2025-10-30T08:44:25.6347264+08:00 | #71822 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-04-24T22:00:00+00:00 | 2027-04-25T04:00:00+00:00 | 2027-04-25T06:00:00+08:00 | 2027-04-25T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71823 | 2025-10-30T00:44:25.9823432+00:00 | 2025-10-30T08:44:25.9823432+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:26.1887481+00:00 | 2025-10-30T08:44:26.1887481+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266284 | TRUE | TRUE | 2025-10-30T00:44:26.1887481+00:00 | 2025-10-30T08:44:26.1887481+08:00 | #71823 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-05-01T22:00:00+00:00 | 2027-05-02T04:00:00+00:00 | 2027-05-02T06:00:00+08:00 | 2027-05-02T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71824 | 2025-10-30T00:44:26.5611554+00:00 | 2025-10-30T08:44:26.5611554+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:26.7954727+00:00 | 2025-10-30T08:44:26.7954727+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266286 | TRUE | TRUE | 2025-10-30T00:44:26.7954727+00:00 | 2025-10-30T08:44:26.7954727+08:00 | #71824 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-05-08T22:00:00+00:00 | 2027-05-09T04:00:00+00:00 | 2027-05-09T06:00:00+08:00 | 2027-05-09T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71825 | 2025-10-30T00:44:27.1730517+00:00 | 2025-10-30T08:44:27.1730517+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:27.3961424+00:00 | 2025-10-30T08:44:27.3961424+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266288 | TRUE | TRUE | 2025-10-30T00:44:27.3961424+00:00 | 2025-10-30T08:44:27.3961424+08:00 | #71825 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-05-15T22:00:00+00:00 | 2027-05-16T04:00:00+00:00 | 2027-05-16T06:00:00+08:00 | 2027-05-16T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71826 | 2025-10-30T00:44:27.7681787+00:00 | 2025-10-30T08:44:27.7681787+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:27.9779943+00:00 | 2025-10-30T08:44:27.9779943+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266290 | TRUE | TRUE | 2025-10-30T00:44:27.9779943+00:00 | 2025-10-30T08:44:27.9779943+08:00 | #71826 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-05-22T22:00:00+00:00 | 2027-05-23T04:00:00+00:00 | 2027-05-23T06:00:00+08:00 | 2027-05-23T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71827 | 2025-10-30T00:44:28.3493691+00:00 | 2025-10-30T08:44:28.3493691+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:28.5460461+00:00 | 2025-10-30T08:44:28.5460461+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266292 | TRUE | TRUE | 2025-10-30T00:44:28.5460461+00:00 | 2025-10-30T08:44:28.5460461+08:00 | #71827 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-05-29T22:00:00+00:00 | 2027-05-30T04:00:00+00:00 | 2027-05-30T06:00:00+08:00 | 2027-05-30T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71828 | 2025-10-30T00:44:28.920546+00:00 | 2025-10-30T08:44:28.920546+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:29.1376284+00:00 | 2025-10-30T08:44:29.1376284+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266294 | TRUE | TRUE | 2025-10-30T00:44:29.1376284+00:00 | 2025-10-30T08:44:29.1376284+08:00 | #71828 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-06-05T22:00:00+00:00 | 2027-06-06T04:00:00+00:00 | 2027-06-06T06:00:00+08:00 | 2027-06-06T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71829 | 2025-10-30T00:44:29.5231684+00:00 | 2025-10-30T08:44:29.5231684+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:29.7490868+00:00 | 2025-10-30T08:44:29.7490868+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266296 | TRUE | TRUE | 2025-10-30T00:44:29.7490868+00:00 | 2025-10-30T08:44:29.7490868+08:00 | #71829 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-06-12T22:00:00+00:00 | 2027-06-13T04:00:00+00:00 | 2027-06-13T06:00:00+08:00 | 2027-06-13T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71830 | 2025-10-30T00:44:30.1305164+00:00 | 2025-10-30T08:44:30.1305164+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:30.3365251+00:00 | 2025-10-30T08:44:30.3365251+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266298 | TRUE | TRUE | 2025-10-30T00:44:30.3365251+00:00 | 2025-10-30T08:44:30.3365251+08:00 | #71830 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-06-19T22:00:00+00:00 | 2027-06-20T04:00:00+00:00 | 2027-06-20T06:00:00+08:00 | 2027-06-20T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71841 | 2025-10-30T00:44:36.9257011+00:00 | 2025-10-30T08:44:36.9257011+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:37.1651969+00:00 | 2025-10-30T08:44:37.1651969+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266320 | TRUE | TRUE | 2025-10-30T00:44:37.1651969+00:00 | 2025-10-30T08:44:37.1651969+08:00 | #71841 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-09-04T22:00:00+00:00 | 2027-09-05T04:00:00+00:00 | 2027-09-05T06:00:00+08:00 | 2027-09-05T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71842 | 2025-10-30T00:44:37.5724243+00:00 | 2025-10-30T08:44:37.5724243+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:37.8109425+00:00 | 2025-10-30T08:44:37.8109425+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266322 | TRUE | TRUE | 2025-10-30T00:44:37.8109425+00:00 | 2025-10-30T08:44:37.8109425+08:00 | #71842 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-09-11T22:00:00+00:00 | 2027-09-12T04:00:00+00:00 | 2027-09-12T06:00:00+08:00 | 2027-09-12T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71843 | 2025-10-30T00:44:38.2111144+00:00 | 2025-10-30T08:44:38.2111144+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:38.4561569+00:00 | 2025-10-30T08:44:38.4561569+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266324 | TRUE | TRUE | 2025-10-30T00:44:38.4561569+00:00 | 2025-10-30T08:44:38.4561569+08:00 | #71843 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-09-18T22:00:00+00:00 | 2027-09-19T04:00:00+00:00 | 2027-09-19T06:00:00+08:00 | 2027-09-19T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71844 | 2025-10-30T00:44:38.8687385+00:00 | 2025-10-30T08:44:38.8687385+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:39.1187285+00:00 | 2025-10-30T08:44:39.1187285+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266326 | TRUE | TRUE | 2025-10-30T00:44:39.1187285+00:00 | 2025-10-30T08:44:39.1187285+08:00 | #71844 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-09-25T22:00:00+00:00 | 2027-09-26T04:00:00+00:00 | 2027-09-26T06:00:00+08:00 | 2027-09-26T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71845 | 2025-10-30T00:44:39.5206789+00:00 | 2025-10-30T08:44:39.5206789+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:39.7919691+00:00 | 2025-10-30T08:44:39.7919691+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266328 | TRUE | TRUE | 2025-10-30T00:44:39.7919691+00:00 | 2025-10-30T08:44:39.7919691+08:00 | #71845 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-10-02T22:00:00+00:00 | 2027-10-03T04:00:00+00:00 | 2027-10-03T06:00:00+08:00 | 2027-10-03T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71846 | 2025-10-30T00:44:40.1946398+00:00 | 2025-10-30T08:44:40.1946398+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:40.443948+00:00 | 2025-10-30T08:44:40.443948+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266330 | TRUE | TRUE | 2025-10-30T00:44:40.443948+00:00 | 2025-10-30T08:44:40.443948+08:00 | #71846 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-10-09T22:00:00+00:00 | 2027-10-10T04:00:00+00:00 | 2027-10-10T06:00:00+08:00 | 2027-10-10T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71847 | 2025-10-30T00:44:40.8518063+00:00 | 2025-10-30T08:44:40.8518063+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:41.0994621+00:00 | 2025-10-30T08:44:41.0994621+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266332 | TRUE | TRUE | 2025-10-30T00:44:41.0994621+00:00 | 2025-10-30T08:44:41.0994621+08:00 | #71847 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-10-16T22:00:00+00:00 | 2027-10-17T04:00:00+00:00 | 2027-10-17T06:00:00+08:00 | 2027-10-17T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71848 | 2025-10-30T00:44:41.5047899+00:00 | 2025-10-30T08:44:41.5047899+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:41.7538437+00:00 | 2025-10-30T08:44:41.7538437+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266334 | TRUE | TRUE | 2025-10-30T00:44:41.7538437+00:00 | 2025-10-30T08:44:41.7538437+08:00 | #71848 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-10-23T22:00:00+00:00 | 2027-10-24T04:00:00+00:00 | 2027-10-24T06:00:00+08:00 | 2027-10-24T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71849 | 2025-10-30T00:44:42.1472528+00:00 | 2025-10-30T08:44:42.1472528+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:42.4053979+00:00 | 2025-10-30T08:44:42.4053979+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266336 | TRUE | TRUE | 2025-10-30T00:44:42.4053979+00:00 | 2025-10-30T08:44:42.4053979+08:00 | #71849 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-10-30T22:00:00+00:00 | 2027-10-31T04:00:00+00:00 | 2027-10-31T06:00:00+08:00 | 2027-10-31T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71850 | 2025-10-30T00:44:42.8574652+00:00 | 2025-10-30T08:44:42.8574652+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:43.1224907+00:00 | 2025-10-30T08:44:43.1224907+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266338 | TRUE | TRUE | 2025-10-30T00:44:43.1224907+00:00 | 2025-10-30T08:44:43.1224907+08:00 | #71850 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-11-06T22:00:00+00:00 | 2027-11-07T04:00:00+00:00 | 2027-11-07T06:00:00+08:00 | 2027-11-07T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71851 | 2025-10-30T00:44:43.5410455+00:00 | 2025-10-30T08:44:43.5410455+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:43.8191268+00:00 | 2025-10-30T08:44:43.8191268+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266340 | TRUE | TRUE | 2025-10-30T00:44:43.8191268+00:00 | 2025-10-30T08:44:43.8191268+08:00 | #71851 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-11-13T22:00:00+00:00 | 2027-11-14T04:00:00+00:00 | 2027-11-14T06:00:00+08:00 | 2027-11-14T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71852 | 2025-10-30T00:44:44.2438739+00:00 | 2025-10-30T08:44:44.2438739+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:44.5267+00:00 | 2025-10-30T08:44:44.5267+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266342 | TRUE | TRUE | 2025-10-30T00:44:44.5267+00:00 | 2025-10-30T08:44:44.5267+08:00 | #71852 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-11-20T22:00:00+00:00 | 2027-11-21T04:00:00+00:00 | 2027-11-21T06:00:00+08:00 | 2027-11-21T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72460 | 2025-10-30T07:09:14.6391883+00:00 | 2025-10-30T15:09:14.6391883+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:09:14.8133756+00:00 | 2025-10-30T15:09:14.8133756+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268423 | TRUE | TRUE | 2025-10-30T07:09:14.8133756+00:00 | 2025-10-30T15:09:14.8133756+08:00 | #72460 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-08-02T11:30:00+00:00 | 2027-08-02T15:30:00+00:00 | 2027-08-02T19:30:00+08:00 | 2027-08-02T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72461 | 2025-10-30T07:09:15.2439881+00:00 | 2025-10-30T15:09:15.2439881+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:09:15.4247517+00:00 | 2025-10-30T15:09:15.4247517+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268425 | TRUE | TRUE | 2025-10-30T07:09:15.4247517+00:00 | 2025-10-30T15:09:15.4247517+08:00 | #72461 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-11-01T11:30:00+00:00 | 2027-11-01T15:30:00+00:00 | 2027-11-01T19:30:00+08:00 | 2027-11-01T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72482 | 2025-10-30T07:13:11.6478356+00:00 | 2025-10-30T15:13:11.6478356+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:13:12.1365733+00:00 | 2025-10-30T15:13:12.1365733+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268467 | TRUE | TRUE | 2025-10-30T07:13:12.1365733+00:00 | 2025-10-30T15:13:12.1365733+08:00 | #72482 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-02-04T23:30:00+00:00 | 2027-02-05T03:30:00+00:00 | 2027-02-05T07:30:00+08:00 | 2027-02-05T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72483 | 2025-10-30T07:13:12.4406322+00:00 | 2025-10-30T15:13:12.4406322+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:13:12.5822492+00:00 | 2025-10-30T15:13:12.5822492+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268469 | TRUE | TRUE | 2025-10-30T07:13:12.5822492+00:00 | 2025-10-30T15:13:12.5822492+08:00 | #72483 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-05-06T23:30:00+00:00 | 2027-05-07T03:30:00+00:00 | 2027-05-07T07:30:00+08:00 | 2027-05-07T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72484 | 2025-10-30T07:13:12.8921701+00:00 | 2025-10-30T15:13:12.8921701+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:13:13.0326863+00:00 | 2025-10-30T15:13:13.0326863+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268471 | TRUE | TRUE | 2025-10-30T07:13:13.0326863+00:00 | 2025-10-30T15:13:13.0326863+08:00 | #72484 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-08-05T23:30:00+00:00 | 2027-08-06T03:30:00+00:00 | 2027-08-06T07:30:00+08:00 | 2027-08-06T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72485 | 2025-10-30T07:13:13.3568929+00:00 | 2025-10-30T15:13:13.3568929+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:13:13.4857088+00:00 | 2025-10-30T15:13:13.4857088+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268473 | TRUE | TRUE | 2025-10-30T07:13:13.4857088+00:00 | 2025-10-30T15:13:13.4857088+08:00 | #72485 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-11-04T23:30:00+00:00 | 2027-11-05T03:30:00+00:00 | 2027-11-05T07:30:00+08:00 | 2027-11-05T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72506 | 2025-10-30T07:14:41.6168039+00:00 | 2025-10-30T15:14:41.6168039+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:14:42.2395599+00:00 | 2025-10-30T15:14:42.2395599+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268515 | TRUE | TRUE | 2025-10-30T07:14:42.2395599+00:00 | 2025-10-30T15:14:42.2395599+08:00 | #72506 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-02-08T11:30:00+00:00 | 2027-02-08T15:30:00+00:00 | 2027-02-08T19:30:00+08:00 | 2027-02-08T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72507 | 2025-10-30T07:14:42.5924061+00:00 | 2025-10-30T15:14:42.5924061+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:14:42.7777437+00:00 | 2025-10-30T15:14:42.7777437+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268517 | TRUE | TRUE | 2025-10-30T07:14:42.7777437+00:00 | 2025-10-30T15:14:42.7777437+08:00 | #72507 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-05-10T11:30:00+00:00 | 2027-05-10T15:30:00+00:00 | 2027-05-10T19:30:00+08:00 | 2027-05-10T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72508 | 2025-10-30T07:14:43.1274077+00:00 | 2025-10-30T15:14:43.1274077+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:14:43.3167059+00:00 | 2025-10-30T15:14:43.3167059+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268519 | TRUE | TRUE | 2025-10-30T07:14:43.3167059+00:00 | 2025-10-30T15:14:43.3167059+08:00 | #72508 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-08-09T11:30:00+00:00 | 2027-08-09T15:30:00+00:00 | 2027-08-09T19:30:00+08:00 | 2027-08-09T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72509 | 2025-10-30T07:14:43.6694588+00:00 | 2025-10-30T15:14:43.6694588+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:14:43.8622341+00:00 | 2025-10-30T15:14:43.8622341+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268521 | TRUE | TRUE | 2025-10-30T07:14:43.8622341+00:00 | 2025-10-30T15:14:43.8622341+08:00 | #72509 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-11-08T11:30:00+00:00 | 2027-11-08T15:30:00+00:00 | 2027-11-08T19:30:00+08:00 | 2027-11-08T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72595 | 2025-10-30T08:21:36.1644644+00:00 | 2025-10-30T16:21:36.1644644+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T08:21:36.6331987+00:00 | 2025-10-30T16:21:36.6331987+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268692 | TRUE | TRUE | 2025-10-30T08:21:36.6331987+00:00 | 2025-10-30T16:21:36.6331987+08:00 | #72595 - NBWT: 108hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-01-28T11:30:00+00:00 | 2027-02-01T23:30:00+00:00 | 2027-01-28T19:30:00+08:00 | 2027-02-02T07:30:00+08:00 |  |  |  |  | 108.00 | PC01 shut |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72597 | 2025-10-30T08:21:37.4031828+00:00 | 2025-10-30T16:21:37.4031828+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T08:21:37.5373848+00:00 | 2025-10-30T16:21:37.5373848+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268696 | TRUE | TRUE | 2025-10-30T08:21:37.5373848+00:00 | 2025-10-30T16:21:37.5373848+08:00 | #72597 - NBWT: 108hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-29T11:30:00+00:00 | 2027-08-02T23:30:00+00:00 | 2027-07-29T19:30:00+08:00 | 2027-08-03T07:30:00+08:00 |  |  |  |  | 108.00 | PC01 shut |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72599 | 2025-10-30T08:21:38.3156679+00:00 | 2025-10-30T16:21:38.3156679+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T08:21:38.4599084+00:00 | 2025-10-30T16:21:38.4599084+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268700 | TRUE | TRUE | 2025-10-30T08:21:38.4599084+00:00 | 2025-10-30T16:21:38.4599084+08:00 | #72599 - NBWT: 108hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2028-01-27T11:30:00+00:00 | 2028-01-31T23:30:00+00:00 | 2028-01-27T19:30:00+08:00 | 2028-02-01T07:30:00+08:00 |  |  |  |  | 108.00 | PC01 shut |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
74859 | 2026-01-22T03:30:55.8241404+00:00 | 2026-01-22T11:30:55.8241404+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-03T08:09:31.4662571+00:00 | 2026-06-03T16:09:31.4662571+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 327173 | TRUE | TRUE | 2026-06-03T08:09:31.4662571+00:00 | 2026-06-03T16:09:31.4662571+08:00 | #74859 - NBWT: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE | 2.0 | TRUE |  | 2027-07-01T22:00:00+00:00 | 2027-07-02T22:00:00+00:00 | 2027-07-02T06:00:00+08:00 | 2027-07-03T06:00:00+08:00 |  |  |  |  | 24.00 | project to upgrade the existing bulk substation at Brockman, which includes the installation of a new transformer to maintain N 1 redundancy following increased power demand from several projects, including BS1. As part of the upgrade, a new bus tie panel is required in the existing 33 kV switchboard (BMS701). Completing this work will necessitate isolating the switchboard for approximately 24 hours, resulting in a full power outage across the region. Our intention is to align this isolation with a planned shutdown at B4. Bus tie panel installation scheduled for completion on 3 July 2027. Power to B2/GNAM will be affected during this period. | Brought forward one day to offset from HD4 TLO shut and any EP track maintenance. Agreed with project Vernon and project team |  | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}, {"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}, {"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}, {"equipmentGUID": "1814b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD03", "name": "Module - Plant: NBWT 03", "assetClass": {"name": "Module"}}, {"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "86c8f151-77c0-4ee8-aa98-962f4cd8f0f3", "emailAddress": "Vernon.Williams@riotinto.com", "displayName": "Williams, Vernon (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44182, "shutVersionId": 335051, "title": "#44182 - BM4: 168hrs - PLANT: BM4", "startDatetimeUTC": "2027-06-30T04:00:00+00:00", "endDatetimeUTC": "2027-07-07T04:00:00+00:00"}}] | [] | [{"code": "P-0508792", "name": "Brockman Bulk Substation Upgrade - Region Power Outage", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | NBWT | Australia/Perth
74858 | 2026-01-22T03:28:05.6053915+00:00 | 2026-01-22T11:28:05.6053915+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-03T08:09:31.7918383+00:00 | 2026-06-03T16:09:31.7918383+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 327174 | TRUE | TRUE | 2026-06-03T08:09:31.7918383+00:00 | 2026-06-03T16:09:31.7918383+08:00 | #74858 - BM2: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE | 2.0 | TRUE |  | 2027-07-01T22:00:00+00:00 | 2027-07-02T22:00:00+00:00 | 2027-07-02T06:00:00+08:00 | 2027-07-03T06:00:00+08:00 |  |  |  |  | 24.00 | project to upgrade the existing bulk substation at Brockman, which includes the installation of a new transformer to maintain N 1 redundancy following increased power demand from several projects, including BS1. As part of the upgrade, a new bus tie panel is required in the existing 33 kV switchboard (BMS701). Completing this work will necessitate isolating the switchboard for approximately 24 hours, resulting in a full power outage across the region. Our intention is to align this isolation with a planned shutdown at B4. Bus tie panel installation scheduled for completion on 3 July 2027. Power to B2/GNAM will be affected during this period. | Brought forward one day to offset from HD4 TLO shut and any EP track maintenance. Agreed with project Vernon and project team |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "86c8f151-77c0-4ee8-aa98-962f4cd8f0f3", "emailAddress": "Vernon.Williams@riotinto.com", "displayName": "Williams, Vernon (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44182, "shutVersionId": 335051, "title": "#44182 - BM4: 168hrs - PLANT: BM4", "startDatetimeUTC": "2027-06-30T04:00:00+00:00", "endDatetimeUTC": "2027-07-07T04:00:00+00:00"}}] | [] | [{"code": "P-0508792", "name": "BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM2 | Australia/Perth
74857 | 2026-01-22T03:25:34.8226924+00:00 | 2026-01-22T11:25:34.8226924+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-03T08:09:32.0336588+00:00 | 2026-06-03T16:09:32.0336588+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 327175 | TRUE | TRUE | 2026-06-03T08:09:32.0336588+00:00 | 2026-06-03T16:09:32.0336588+08:00 | #74857 - BM4: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE | 2.0 | TRUE |  | 2027-07-01T22:00:00+00:00 | 2027-07-02T22:00:00+00:00 | 2027-07-02T06:00:00+08:00 | 2027-07-03T06:00:00+08:00 |  |  |  |  | 24.00 | project to upgrade the existing bulk substation at Brockman, which includes the installation of a new transformer to maintain N 1 redundancy following increased power demand from several projects, including BS1. As part of the upgrade, a new bus tie panel is required in the existing 33 kV switchboard (BMS701). Completing this work will necessitate isolating the switchboard for approximately 24 hours, resulting in a full power outage across the region. Our intention is to align this isolation with a planned shutdown at B4. Bus tie panel installation scheduled for completion on 3 July 2027. Power to B2/GNAM will be affected during this period. | Brought forward one day to offset from HD4 TLO shut and any EP track maintenance. Agreed with project Vernon and project team |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "86c8f151-77c0-4ee8-aa98-962f4cd8f0f3", "emailAddress": "Vernon.Williams@riotinto.com", "displayName": "Williams, Vernon (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44182, "shutVersionId": 335051, "title": "#44182 - BM4: 168hrs - PLANT: BM4", "startDatetimeUTC": "2027-06-30T04:00:00+00:00", "endDatetimeUTC": "2027-07-07T04:00:00+00:00"}}] | [] | [{"code": "P-0508792", "name": "Brockman Bulk Substation Upgrade - Regional Power Outage", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
81641 | 2026-03-11T05:26:16.1500383+00:00 | 2026-03-11T13:26:16.1500383+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-03-11T05:26:16.591849+00:00 | 2026-03-11T13:26:16.591849+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 320967 | TRUE | TRUE | 2026-03-11T05:26:16.591849+00:00 | 2026-03-11T13:26:16.591849+08:00 | #81641 - EII: 130hrs - SL1E CORROSION CONTROL | 1.0 | TRUE |  | 2028-01-25T20:00:00+00:00 | 2028-01-31T06:00:00+00:00 | 2028-01-26T04:00:00+08:00 | 2028-01-31T14:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control |  |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
71807 | 2025-10-30T00:44:17.3599835+00:00 | 2025-10-30T08:44:17.3599835+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:17.7720404+00:00 | 2025-10-30T08:44:17.7720404+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266252 | TRUE | TRUE | 2025-10-30T00:44:17.7720404+00:00 | 2025-10-30T08:44:17.7720404+08:00 | #71807 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-01-09T22:00:00+00:00 | 2027-01-10T04:00:00+00:00 | 2027-01-10T06:00:00+08:00 | 2027-01-10T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71808 | 2025-10-30T00:44:18.1061128+00:00 | 2025-10-30T08:44:18.1061128+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:18.2522488+00:00 | 2025-10-30T08:44:18.2522488+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266254 | TRUE | TRUE | 2025-10-30T00:44:18.2522488+00:00 | 2025-10-30T08:44:18.2522488+08:00 | #71808 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-01-16T22:00:00+00:00 | 2027-01-17T04:00:00+00:00 | 2027-01-17T06:00:00+08:00 | 2027-01-17T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71809 | 2025-10-30T00:44:18.5686128+00:00 | 2025-10-30T08:44:18.5686128+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:18.7145492+00:00 | 2025-10-30T08:44:18.7145492+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266256 | TRUE | TRUE | 2025-10-30T00:44:18.7145492+00:00 | 2025-10-30T08:44:18.7145492+08:00 | #71809 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-01-23T22:00:00+00:00 | 2027-01-24T04:00:00+00:00 | 2027-01-24T06:00:00+08:00 | 2027-01-24T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71810 | 2025-10-30T00:44:19.0387279+00:00 | 2025-10-30T08:44:19.0387279+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:19.1952052+00:00 | 2025-10-30T08:44:19.1952052+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266258 | TRUE | TRUE | 2025-10-30T00:44:19.1952052+00:00 | 2025-10-30T08:44:19.1952052+08:00 | #71810 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-01-30T22:00:00+00:00 | 2027-01-31T04:00:00+00:00 | 2027-01-31T06:00:00+08:00 | 2027-01-31T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71811 | 2025-10-30T00:44:19.5142117+00:00 | 2025-10-30T08:44:19.5142117+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:19.6646268+00:00 | 2025-10-30T08:44:19.6646268+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266260 | TRUE | TRUE | 2025-10-30T00:44:19.6646268+00:00 | 2025-10-30T08:44:19.6646268+08:00 | #71811 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-02-06T22:00:00+00:00 | 2027-02-07T04:00:00+00:00 | 2027-02-07T06:00:00+08:00 | 2027-02-07T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71812 | 2025-10-30T00:44:20.0885503+00:00 | 2025-10-30T08:44:20.0885503+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:20.2330873+00:00 | 2025-10-30T08:44:20.2330873+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266262 | TRUE | TRUE | 2025-10-30T00:44:20.2330873+00:00 | 2025-10-30T08:44:20.2330873+08:00 | #71812 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-02-13T22:00:00+00:00 | 2027-02-14T04:00:00+00:00 | 2027-02-14T06:00:00+08:00 | 2027-02-14T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71813 | 2025-10-30T00:44:20.5777591+00:00 | 2025-10-30T08:44:20.5777591+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:20.7450535+00:00 | 2025-10-30T08:44:20.7450535+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266264 | TRUE | TRUE | 2025-10-30T00:44:20.7450535+00:00 | 2025-10-30T08:44:20.7450535+08:00 | #71813 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-02-20T22:00:00+00:00 | 2027-02-21T04:00:00+00:00 | 2027-02-21T06:00:00+08:00 | 2027-02-21T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71814 | 2025-10-30T00:44:21.0943309+00:00 | 2025-10-30T08:44:21.0943309+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:21.2763412+00:00 | 2025-10-30T08:44:21.2763412+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266266 | TRUE | TRUE | 2025-10-30T00:44:21.2763412+00:00 | 2025-10-30T08:44:21.2763412+08:00 | #71814 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-02-27T22:00:00+00:00 | 2027-02-28T04:00:00+00:00 | 2027-02-28T06:00:00+08:00 | 2027-02-28T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71815 | 2025-10-30T00:44:21.6156467+00:00 | 2025-10-30T08:44:21.6156467+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:21.7790265+00:00 | 2025-10-30T08:44:21.7790265+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266268 | TRUE | TRUE | 2025-10-30T00:44:21.7790265+00:00 | 2025-10-30T08:44:21.7790265+08:00 | #71815 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-03-06T22:00:00+00:00 | 2027-03-07T04:00:00+00:00 | 2027-03-07T06:00:00+08:00 | 2027-03-07T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71816 | 2025-10-30T00:44:22.1205084+00:00 | 2025-10-30T08:44:22.1205084+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:22.294777+00:00 | 2025-10-30T08:44:22.294777+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266270 | TRUE | TRUE | 2025-10-30T00:44:22.294777+00:00 | 2025-10-30T08:44:22.294777+08:00 | #71816 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-03-13T22:00:00+00:00 | 2027-03-14T04:00:00+00:00 | 2027-03-14T06:00:00+08:00 | 2027-03-14T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71817 | 2025-10-30T00:44:22.643926+00:00 | 2025-10-30T08:44:22.643926+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:22.813779+00:00 | 2025-10-30T08:44:22.813779+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266272 | TRUE | TRUE | 2025-10-30T00:44:22.813779+00:00 | 2025-10-30T08:44:22.813779+08:00 | #71817 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-03-20T22:00:00+00:00 | 2027-03-21T04:00:00+00:00 | 2027-03-21T06:00:00+08:00 | 2027-03-21T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71818 | 2025-10-30T00:44:23.1687696+00:00 | 2025-10-30T08:44:23.1687696+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:23.3417523+00:00 | 2025-10-30T08:44:23.3417523+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266274 | TRUE | TRUE | 2025-10-30T00:44:23.3417523+00:00 | 2025-10-30T08:44:23.3417523+08:00 | #71818 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-03-27T22:00:00+00:00 | 2027-03-28T04:00:00+00:00 | 2027-03-28T06:00:00+08:00 | 2027-03-28T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71831 | 2025-10-30T00:44:30.7456844+00:00 | 2025-10-30T08:44:30.7456844+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:30.9414585+00:00 | 2025-10-30T08:44:30.9414585+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266300 | TRUE | TRUE | 2025-10-30T00:44:30.9414585+00:00 | 2025-10-30T08:44:30.9414585+08:00 | #71831 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-06-26T22:00:00+00:00 | 2027-06-27T04:00:00+00:00 | 2027-06-27T06:00:00+08:00 | 2027-06-27T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71832 | 2025-10-30T00:44:31.3163856+00:00 | 2025-10-30T08:44:31.3163856+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:31.5387407+00:00 | 2025-10-30T08:44:31.5387407+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266302 | TRUE | TRUE | 2025-10-30T00:44:31.5387407+00:00 | 2025-10-30T08:44:31.5387407+08:00 | #71832 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-07-03T22:00:00+00:00 | 2027-07-04T04:00:00+00:00 | 2027-07-04T06:00:00+08:00 | 2027-07-04T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71833 | 2025-10-30T00:44:31.9327817+00:00 | 2025-10-30T08:44:31.9327817+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:32.139767+00:00 | 2025-10-30T08:44:32.139767+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266304 | TRUE | TRUE | 2025-10-30T00:44:32.139767+00:00 | 2025-10-30T08:44:32.139767+08:00 | #71833 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-07-10T22:00:00+00:00 | 2027-07-11T04:00:00+00:00 | 2027-07-11T06:00:00+08:00 | 2027-07-11T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71834 | 2025-10-30T00:44:32.4988927+00:00 | 2025-10-30T08:44:32.4988927+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:32.7058316+00:00 | 2025-10-30T08:44:32.7058316+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266306 | TRUE | TRUE | 2025-10-30T00:44:32.7058316+00:00 | 2025-10-30T08:44:32.7058316+08:00 | #71834 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-07-17T22:00:00+00:00 | 2027-07-18T04:00:00+00:00 | 2027-07-18T06:00:00+08:00 | 2027-07-18T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71835 | 2025-10-30T00:44:33.0760553+00:00 | 2025-10-30T08:44:33.0760553+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:33.3062958+00:00 | 2025-10-30T08:44:33.3062958+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266308 | TRUE | TRUE | 2025-10-30T00:44:33.3062958+00:00 | 2025-10-30T08:44:33.3062958+08:00 | #71835 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-07-24T22:00:00+00:00 | 2027-07-25T04:00:00+00:00 | 2027-07-25T06:00:00+08:00 | 2027-07-25T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71836 | 2025-10-30T00:44:33.6946236+00:00 | 2025-10-30T08:44:33.6946236+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:33.9557767+00:00 | 2025-10-30T08:44:33.9557767+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266310 | TRUE | TRUE | 2025-10-30T00:44:33.9557767+00:00 | 2025-10-30T08:44:33.9557767+08:00 | #71836 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-07-31T22:00:00+00:00 | 2027-08-01T04:00:00+00:00 | 2027-08-01T06:00:00+08:00 | 2027-08-01T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71837 | 2025-10-30T00:44:34.3410515+00:00 | 2025-10-30T08:44:34.3410515+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:34.5803203+00:00 | 2025-10-30T08:44:34.5803203+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266312 | TRUE | TRUE | 2025-10-30T00:44:34.5803203+00:00 | 2025-10-30T08:44:34.5803203+08:00 | #71837 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-08-07T22:00:00+00:00 | 2027-08-08T04:00:00+00:00 | 2027-08-08T06:00:00+08:00 | 2027-08-08T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71838 | 2025-10-30T00:44:35.004376+00:00 | 2025-10-30T08:44:35.004376+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:35.2369666+00:00 | 2025-10-30T08:44:35.2369666+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266314 | TRUE | TRUE | 2025-10-30T00:44:35.2369666+00:00 | 2025-10-30T08:44:35.2369666+08:00 | #71838 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-08-14T22:00:00+00:00 | 2027-08-15T04:00:00+00:00 | 2027-08-15T06:00:00+08:00 | 2027-08-15T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71839 | 2025-10-30T00:44:35.6081696+00:00 | 2025-10-30T08:44:35.6081696+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:35.8403745+00:00 | 2025-10-30T08:44:35.8403745+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266316 | TRUE | TRUE | 2025-10-30T00:44:35.8403745+00:00 | 2025-10-30T08:44:35.8403745+08:00 | #71839 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-08-21T22:00:00+00:00 | 2027-08-22T04:00:00+00:00 | 2027-08-22T06:00:00+08:00 | 2027-08-22T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71840 | 2025-10-30T00:44:36.2259276+00:00 | 2025-10-30T08:44:36.2259276+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:36.5278882+00:00 | 2025-10-30T08:44:36.5278882+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266318 | TRUE | TRUE | 2025-10-30T00:44:36.5278882+00:00 | 2025-10-30T08:44:36.5278882+08:00 | #71840 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-08-28T22:00:00+00:00 | 2027-08-29T04:00:00+00:00 | 2027-08-29T06:00:00+08:00 | 2027-08-29T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71853 | 2025-10-30T00:44:44.9607542+00:00 | 2025-10-30T08:44:44.9607542+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:45.2451148+00:00 | 2025-10-30T08:44:45.2451148+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266344 | TRUE | TRUE | 2025-10-30T00:44:45.2451148+00:00 | 2025-10-30T08:44:45.2451148+08:00 | #71853 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-11-27T22:00:00+00:00 | 2027-11-28T04:00:00+00:00 | 2027-11-28T06:00:00+08:00 | 2027-11-28T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71854 | 2025-10-30T00:44:45.6477635+00:00 | 2025-10-30T08:44:45.6477635+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:45.9189433+00:00 | 2025-10-30T08:44:45.9189433+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266346 | TRUE | TRUE | 2025-10-30T00:44:45.9189433+00:00 | 2025-10-30T08:44:45.9189433+08:00 | #71854 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-12-04T22:00:00+00:00 | 2027-12-05T04:00:00+00:00 | 2027-12-05T06:00:00+08:00 | 2027-12-05T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71855 | 2025-10-30T00:44:46.3372779+00:00 | 2025-10-30T08:44:46.3372779+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:46.610729+00:00 | 2025-10-30T08:44:46.610729+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266348 | TRUE | TRUE | 2025-10-30T00:44:46.610729+00:00 | 2025-10-30T08:44:46.610729+08:00 | #71855 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-12-11T22:00:00+00:00 | 2027-12-12T04:00:00+00:00 | 2027-12-12T06:00:00+08:00 | 2027-12-12T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71856 | 2025-10-30T00:44:47.0328776+00:00 | 2025-10-30T08:44:47.0328776+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:47.3024442+00:00 | 2025-10-30T08:44:47.3024442+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266350 | TRUE | TRUE | 2025-10-30T00:44:47.3024442+00:00 | 2025-10-30T08:44:47.3024442+08:00 | #71856 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-12-18T22:00:00+00:00 | 2027-12-19T04:00:00+00:00 | 2027-12-19T06:00:00+08:00 | 2027-12-19T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71857 | 2025-10-30T00:44:47.7247978+00:00 | 2025-10-30T08:44:47.7247978+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:48.0123737+00:00 | 2025-10-30T08:44:48.0123737+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266352 | TRUE | TRUE | 2025-10-30T00:44:48.0123737+00:00 | 2025-10-30T08:44:48.0123737+08:00 | #71857 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-12-25T22:00:00+00:00 | 2027-12-26T04:00:00+00:00 | 2027-12-26T06:00:00+08:00 | 2027-12-26T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71858 | 2025-10-30T00:44:48.439491+00:00 | 2025-10-30T08:44:48.439491+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:48.7131541+00:00 | 2025-10-30T08:44:48.7131541+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266354 | TRUE | TRUE | 2025-10-30T00:44:48.7131541+00:00 | 2025-10-30T08:44:48.7131541+08:00 | #71858 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2028-01-01T22:00:00+00:00 | 2028-01-02T04:00:00+00:00 | 2028-01-02T06:00:00+08:00 | 2028-01-02T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71859 | 2025-10-30T00:44:49.126802+00:00 | 2025-10-30T08:44:49.126802+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:49.3980327+00:00 | 2025-10-30T08:44:49.3980327+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266356 | TRUE | TRUE | 2025-10-30T00:44:49.3980327+00:00 | 2025-10-30T08:44:49.3980327+08:00 | #71859 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2028-01-08T22:00:00+00:00 | 2028-01-09T04:00:00+00:00 | 2028-01-09T06:00:00+08:00 | 2028-01-09T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71860 | 2025-10-30T00:44:49.8274235+00:00 | 2025-10-30T08:44:49.8274235+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:50.1036101+00:00 | 2025-10-30T08:44:50.1036101+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266358 | TRUE | TRUE | 2025-10-30T00:44:50.1036101+00:00 | 2025-10-30T08:44:50.1036101+08:00 | #71860 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2028-01-15T22:00:00+00:00 | 2028-01-16T04:00:00+00:00 | 2028-01-16T06:00:00+08:00 | 2028-01-16T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71861 | 2025-10-30T00:44:50.5694735+00:00 | 2025-10-30T08:44:50.5694735+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:50.8449829+00:00 | 2025-10-30T08:44:50.8449829+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266360 | TRUE | TRUE | 2025-10-30T00:44:50.8449829+00:00 | 2025-10-30T08:44:50.8449829+08:00 | #71861 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2028-01-22T22:00:00+00:00 | 2028-01-23T04:00:00+00:00 | 2028-01-23T06:00:00+08:00 | 2028-01-23T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71862 | 2025-10-30T00:44:51.2831012+00:00 | 2025-10-30T08:44:51.2831012+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T00:44:51.5655865+00:00 | 2025-10-30T08:44:51.5655865+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266362 | TRUE | TRUE | 2025-10-30T00:44:51.5655865+00:00 | 2025-10-30T08:44:51.5655865+08:00 | #71862 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2028-01-29T22:00:00+00:00 | 2028-01-30T04:00:00+00:00 | 2028-01-30T06:00:00+08:00 | 2028-01-30T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
70586 | 2025-10-15T08:31:49.2234596+00:00 | 2025-10-15T16:31:49.2234596+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:49.3846106+00:00 | 2025-10-15T16:31:49.3846106+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257670 | TRUE | TRUE | 2025-10-15T08:31:49.3846106+00:00 | 2025-10-15T16:31:49.3846106+08:00 | #70586 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-03-10T22:00:00+00:00 | 2027-03-11T02:00:00+00:00 | 2027-03-11T06:00:00+08:00 | 2027-03-11T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70587 | 2025-10-15T08:31:49.7164995+00:00 | 2025-10-15T16:31:49.7164995+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:49.8790891+00:00 | 2025-10-15T16:31:49.8790891+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257672 | TRUE | TRUE | 2025-10-15T08:31:49.8790891+00:00 | 2025-10-15T16:31:49.8790891+08:00 | #70587 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-04-21T22:00:00+00:00 | 2027-04-22T02:00:00+00:00 | 2027-04-22T06:00:00+08:00 | 2027-04-22T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70588 | 2025-10-15T08:31:50.211967+00:00 | 2025-10-15T16:31:50.211967+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:50.3831118+00:00 | 2025-10-15T16:31:50.3831118+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257674 | TRUE | TRUE | 2025-10-15T08:31:50.3831118+00:00 | 2025-10-15T16:31:50.3831118+08:00 | #70588 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-06-02T22:00:00+00:00 | 2027-06-03T02:00:00+00:00 | 2027-06-03T06:00:00+08:00 | 2027-06-03T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70589 | 2025-10-15T08:31:50.719693+00:00 | 2025-10-15T16:31:50.719693+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:50.8936969+00:00 | 2025-10-15T16:31:50.8936969+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257676 | TRUE | TRUE | 2025-10-15T08:31:50.8936969+00:00 | 2025-10-15T16:31:50.8936969+08:00 | #70589 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-07-14T22:00:00+00:00 | 2027-07-15T02:00:00+00:00 | 2027-07-15T06:00:00+08:00 | 2027-07-15T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70590 | 2025-10-15T08:31:51.2358416+00:00 | 2025-10-15T16:31:51.2358416+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:51.4102245+00:00 | 2025-10-15T16:31:51.4102245+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257678 | TRUE | TRUE | 2025-10-15T08:31:51.4102245+00:00 | 2025-10-15T16:31:51.4102245+08:00 | #70590 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-08-25T22:00:00+00:00 | 2027-08-26T02:00:00+00:00 | 2027-08-26T06:00:00+08:00 | 2027-08-26T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70591 | 2025-10-15T08:31:51.7510964+00:00 | 2025-10-15T16:31:51.7510964+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:51.931011+00:00 | 2025-10-15T16:31:51.931011+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257680 | TRUE | TRUE | 2025-10-15T08:31:51.931011+00:00 | 2025-10-15T16:31:51.931011+08:00 | #70591 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-10-06T22:00:00+00:00 | 2027-10-07T02:00:00+00:00 | 2027-10-07T06:00:00+08:00 | 2027-10-07T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70592 | 2025-10-15T08:31:52.2643776+00:00 | 2025-10-15T16:31:52.2643776+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:52.4475365+00:00 | 2025-10-15T16:31:52.4475365+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257682 | TRUE | TRUE | 2025-10-15T08:31:52.4475365+00:00 | 2025-10-15T16:31:52.4475365+08:00 | #70592 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-11-17T22:00:00+00:00 | 2027-11-18T02:00:00+00:00 | 2027-11-18T06:00:00+08:00 | 2027-11-18T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70593 | 2025-10-15T08:31:52.7910974+00:00 | 2025-10-15T16:31:52.7910974+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:52.9813591+00:00 | 2025-10-15T16:31:52.9813591+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257684 | TRUE | TRUE | 2025-10-15T08:31:52.9813591+00:00 | 2025-10-15T16:31:52.9813591+08:00 | #70593 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-12-29T22:00:00+00:00 | 2027-12-30T02:00:00+00:00 | 2027-12-30T06:00:00+08:00 | 2027-12-30T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
69259 | 2025-10-09T00:53:34.0616044+00:00 | 2025-10-09T08:53:34.0616044+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-09T05:59:59.0019036+00:00 | 2025-10-09T13:59:59.0019036+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 252237 | TRUE | TRUE | 2025-10-09T05:59:59.0019036+00:00 | 2025-10-09T13:59:59.0019036+08:00 | #69259 - PPT: 2hrs - SL3P: INSTALL SCAFFOLD BARRIER 215P/116P | 3.0 | TRUE |  | 2027-02-15T02:00:00+00:00 | 2027-02-15T04:00:00+00:00 | 2027-02-15T10:00:00+08:00 | 2027-02-15T12:00:00+08:00 |  |  |  |  | 2.00 | Install scaffold barrier in 215P/116P to complete 116P skirt liner maintenance | corrected date |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a10e71a-5a7b-4405-8777-b88a1561de62", "emailAddress": "Steven.Medling@riotinto.com", "displayName": "Medling, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
69260 | 2025-10-09T00:53:34.5311916+00:00 | 2025-10-09T08:53:34.5311916+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-09T02:28:16.0103406+00:00 | 2025-10-09T10:28:16.0103406+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249733 | TRUE | TRUE | 2025-10-09T02:28:16.0103406+00:00 | 2025-10-09T10:28:16.0103406+08:00 | #69260 - PPT: 2hrs - SL3P: INSTALL SCAFFOLD BARRIER 215P/116P | 1.0 | TRUE |  | 2027-05-17T02:00:00+00:00 | 2027-05-17T04:00:00+00:00 | 2027-05-17T10:00:00+08:00 | 2027-05-17T12:00:00+08:00 |  |  |  |  | 2.00 | Install scaffold barrier in 215P/116P to complete 116P skirt liner maintenance |  |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a10e71a-5a7b-4405-8777-b88a1561de62", "emailAddress": "Steven.Medling@riotinto.com", "displayName": "Medling, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
69261 | 2025-10-09T00:53:34.7212944+00:00 | 2025-10-09T08:53:34.7212944+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-09T02:29:07.3743212+00:00 | 2025-10-09T10:29:07.3743212+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249781 | TRUE | TRUE | 2025-10-09T02:29:07.3743212+00:00 | 2025-10-09T10:29:07.3743212+08:00 | #69261 - PPT: 2hrs - SL3P: INSTALL SCAFFOLD BARRIER 215P/116P | 1.0 | TRUE |  | 2027-08-16T02:00:00+00:00 | 2027-08-16T04:00:00+00:00 | 2027-08-16T10:00:00+08:00 | 2027-08-16T12:00:00+08:00 |  |  |  |  | 2.00 | Install scaffold barrier in 215P/116P to complete 116P skirt liner maintenance |  |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a10e71a-5a7b-4405-8777-b88a1561de62", "emailAddress": "Steven.Medling@riotinto.com", "displayName": "Medling, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
75317 | 2026-02-20T08:17:11.328305+00:00 | 2026-02-20T16:17:11.328305+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-03-19T00:16:54.952201+00:00 | 2026-03-19T08:16:54.952201+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 321962 | TRUE | TRUE | 2026-03-19T00:16:54.952201+00:00 | 2026-03-19T08:16:54.952201+08:00 | #75317 - BM4: 48hrs - PC3 BS1 COMMISSIONING PURPOSES | 2.0 | TRUE |  | 2027-05-21T04:00:00+00:00 | 2027-05-23T04:00:00+00:00 | 2027-05-21T12:00:00+08:00 | 2027-05-23T12:00:00+08:00 |  |  |  |  | 48.00 | PC3 BS1 COMMISSIONING PURPOSES | Aligning start time better for washdown and isolations |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "75e58665-df36-4c22-a1bf-f2e34c72461c", "emailAddress": "Kathy.Lau@riotinto.com", "displayName": "Lau, Kathy (RTIO)"}}] | [] | [] | [] | [{"code": "x", "name": "PC3 BS1 COMMISSIONING", "projectTeam": {"name": "D&T"}, "totalProjectTime": "48"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
74854 | 2026-01-22T03:12:42.8728983+00:00 | 2026-01-22T11:12:42.8728983+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-01-22T05:33:45.3571168+00:00 | 2026-01-22T13:33:45.3571168+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 285035 | TRUE | TRUE | 2026-01-22T05:33:45.3571168+00:00 | 2026-01-22T13:33:45.3571168+08:00 | #74854 - HD1: 24hrs - HD1 TOTAL POWER OUTAGE PLT & TLO | 2.0 | TRUE |  | 2027-06-13T23:00:00+00:00 | 2027-06-14T23:00:00+00:00 | 2027-06-14T07:00:00+08:00 | 2027-06-15T07:00:00+08:00 |  |  |  |  | 24.00 | Total HD1 and HD4 Power Outage for 220KV Transmission line relocation project. Legal obligation to move it, or else RTIO will be up for legal action with BHP, BHP completing their work around May 2027. They need to do their work first. | Moved to following week so misaligns from Tom Price TLo shuts to avoid having 3 TLO shuts out together |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "6717ee47-4b9a-ee11-a847-000d3acacefd", "code": "HD1PLTNTH", "name": "Plant: HD1 North", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3435fe41-b611-47b6-bda3-daca7f6d2d35", "emailAddress": "Kenneth.Woo@riotinto.com", "displayName": "Kenneth Woo"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44412, "shutVersionId": 329407, "title": "#44412 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH", "startDatetimeUTC": "2027-06-10T10:00:00+00:00", "endDatetimeUTC": "2027-06-15T10:00:00+00:00"}}] | [] | [{"code": "P-0510529", "name": "Greater Hope Downs 220KV Transmission Line Relocation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | HD1 | Australia/Perth
72339 | 2025-10-30T06:26:26.1443485+00:00 | 2025-10-30T14:26:26.1443485+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:26:26.2921523+00:00 | 2025-10-30T14:26:26.2921523+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268145 | TRUE | TRUE | 2025-10-30T06:26:26.2921523+00:00 | 2025-10-30T14:26:26.2921523+08:00 | #72339 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-04-21T18:00:00+00:00 | 2027-04-21T22:00:00+00:00 | 2027-04-22T02:00:00+08:00 | 2027-04-22T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72341 | 2025-10-30T06:26:27.1655933+00:00 | 2025-10-30T14:26:27.1655933+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:26:27.5222507+00:00 | 2025-10-30T14:26:27.5222507+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268149 | TRUE | TRUE | 2025-10-30T06:26:27.5222507+00:00 | 2025-10-30T14:26:27.5222507+08:00 | #72341 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-10-20T18:00:00+00:00 | 2027-10-20T22:00:00+00:00 | 2027-10-21T02:00:00+08:00 | 2027-10-21T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72394 | 2025-10-30T06:53:39.9356852+00:00 | 2025-10-30T14:53:39.9356852+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:53:40.4060656+00:00 | 2025-10-30T14:53:40.4060656+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268287 | TRUE | TRUE | 2025-10-30T06:53:40.4060656+00:00 | 2025-10-30T14:53:40.4060656+08:00 | #72394 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-01-24T18:00:00+00:00 | 2027-01-24T22:00:00+00:00 | 2027-01-25T02:00:00+08:00 | 2027-01-25T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72395 | 2025-10-30T06:53:40.7138794+00:00 | 2025-10-30T14:53:40.7138794+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:53:40.8339691+00:00 | 2025-10-30T14:53:40.8339691+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268289 | TRUE | TRUE | 2025-10-30T06:53:40.8339691+00:00 | 2025-10-30T14:53:40.8339691+08:00 | #72395 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-04-25T18:00:00+00:00 | 2027-04-25T22:00:00+00:00 | 2027-04-26T02:00:00+08:00 | 2027-04-26T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72396 | 2025-10-30T06:53:41.1507435+00:00 | 2025-10-30T14:53:41.1507435+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:53:41.2815186+00:00 | 2025-10-30T14:53:41.2815186+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268291 | TRUE | TRUE | 2025-10-30T06:53:41.2815186+00:00 | 2025-10-30T14:53:41.2815186+08:00 | #72396 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-07-25T18:00:00+00:00 | 2027-07-25T22:00:00+00:00 | 2027-07-26T02:00:00+08:00 | 2027-07-26T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72397 | 2025-10-30T06:53:41.596095+00:00 | 2025-10-30T14:53:41.596095+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:53:41.7244225+00:00 | 2025-10-30T14:53:41.7244225+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268293 | TRUE | TRUE | 2025-10-30T06:53:41.7244225+00:00 | 2025-10-30T14:53:41.7244225+08:00 | #72397 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-10-24T18:00:00+00:00 | 2027-10-24T22:00:00+00:00 | 2027-10-25T02:00:00+08:00 | 2027-10-25T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72398 | 2025-10-30T06:53:42.0659387+00:00 | 2025-10-30T14:53:42.0659387+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T06:53:42.2088197+00:00 | 2025-10-30T14:53:42.2088197+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268295 | TRUE | TRUE | 2025-10-30T06:53:42.2088197+00:00 | 2025-10-30T14:53:42.2088197+08:00 | #72398 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2028-01-23T18:00:00+00:00 | 2028-01-23T22:00:00+00:00 | 2028-01-24T02:00:00+08:00 | 2028-01-24T06:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72434 | 2025-10-30T07:06:31.795388+00:00 | 2025-10-30T15:06:31.795388+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:06:32.3136025+00:00 | 2025-10-30T15:06:32.3136025+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268371 | TRUE | TRUE | 2025-10-30T07:06:32.3136025+00:00 | 2025-10-30T15:06:32.3136025+08:00 | #72434 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-01-28T23:30:00+00:00 | 2027-01-29T03:30:00+00:00 | 2027-01-29T07:30:00+08:00 | 2027-01-29T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72435 | 2025-10-30T07:06:32.6151326+00:00 | 2025-10-30T15:06:32.6151326+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:06:32.7481978+00:00 | 2025-10-30T15:06:32.7481978+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268373 | TRUE | TRUE | 2025-10-30T07:06:32.7481978+00:00 | 2025-10-30T15:06:32.7481978+08:00 | #72435 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-04-29T23:30:00+00:00 | 2027-04-30T03:30:00+00:00 | 2027-04-30T07:30:00+08:00 | 2027-04-30T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72436 | 2025-10-30T07:06:33.0448977+00:00 | 2025-10-30T15:06:33.0448977+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:06:33.1711657+00:00 | 2025-10-30T15:06:33.1711657+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268375 | TRUE | TRUE | 2025-10-30T07:06:33.1711657+00:00 | 2025-10-30T15:06:33.1711657+08:00 | #72436 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-07-29T23:30:00+00:00 | 2027-07-30T03:30:00+00:00 | 2027-07-30T07:30:00+08:00 | 2027-07-30T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72437 | 2025-10-30T07:06:33.489551+00:00 | 2025-10-30T15:06:33.489551+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:06:33.6165562+00:00 | 2025-10-30T15:06:33.6165562+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268377 | TRUE | TRUE | 2025-10-30T07:06:33.6165562+00:00 | 2025-10-30T15:06:33.6165562+08:00 | #72437 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-10-28T23:30:00+00:00 | 2027-10-29T03:30:00+00:00 | 2027-10-29T07:30:00+08:00 | 2027-10-29T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72438 | 2025-10-30T07:06:33.9413723+00:00 | 2025-10-30T15:06:33.9413723+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:06:34.0922245+00:00 | 2025-10-30T15:06:34.0922245+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268379 | TRUE | TRUE | 2025-10-30T07:06:34.0922245+00:00 | 2025-10-30T15:06:34.0922245+08:00 | #72438 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2028-01-27T23:30:00+00:00 | 2028-01-28T03:30:00+00:00 | 2028-01-28T07:30:00+08:00 | 2028-01-28T11:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72458 | 2025-10-30T07:09:12.7648229+00:00 | 2025-10-30T15:09:12.7648229+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:09:13.4660175+00:00 | 2025-10-30T15:09:13.4660175+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268419 | TRUE | TRUE | 2025-10-30T07:09:13.4660175+00:00 | 2025-10-30T15:09:13.4660175+08:00 | #72458 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-02-01T11:30:00+00:00 | 2027-02-01T15:30:00+00:00 | 2027-02-01T19:30:00+08:00 | 2027-02-01T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
72459 | 2025-10-30T07:09:13.8601058+00:00 | 2025-10-30T15:09:13.8601058+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-30T07:09:14.2759808+00:00 | 2025-10-30T15:09:14.2759808+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 268421 | TRUE | TRUE | 2025-10-30T07:09:14.2759808+00:00 | 2025-10-30T15:09:14.2759808+08:00 | #72459 - NBWT: 4hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-05-03T11:30:00+00:00 | 2027-05-03T15:30:00+00:00 | 2027-05-03T19:30:00+08:00 | 2027-05-03T23:30:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
71534 | 2025-10-28T02:08:21.7482285+00:00 | 2025-10-28T10:08:21.7482285+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:22.8640906+00:00 | 2025-10-28T10:37:22.8640906+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264995 | TRUE | TRUE | 2025-10-28T02:37:22.8640906+00:00 | 2025-10-28T10:37:22.8640906+08:00 | #71534 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-02-03T23:00:00+00:00 | 2027-02-04T01:00:00+00:00 | 2027-02-04T07:00:00+08:00 | 2027-02-04T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71535 | 2025-10-28T02:08:21.9360565+00:00 | 2025-10-28T10:08:21.9360565+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:23.756384+00:00 | 2025-10-28T10:37:23.756384+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264996 | TRUE | TRUE | 2025-10-28T02:37:23.756384+00:00 | 2025-10-28T10:37:23.756384+08:00 | #71535 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-03-03T23:00:00+00:00 | 2027-03-04T01:00:00+00:00 | 2027-03-04T07:00:00+08:00 | 2027-03-04T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71537 | 2025-10-28T02:08:22.3188258+00:00 | 2025-10-28T10:08:22.3188258+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:25.5387933+00:00 | 2025-10-28T10:37:25.5387933+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264998 | TRUE | TRUE | 2025-10-28T02:37:25.5387933+00:00 | 2025-10-28T10:37:25.5387933+08:00 | #71537 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-05-05T23:00:00+00:00 | 2027-05-06T01:00:00+00:00 | 2027-05-06T07:00:00+08:00 | 2027-05-06T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71538 | 2025-10-28T02:08:22.504639+00:00 | 2025-10-28T10:08:22.504639+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:26.4330425+00:00 | 2025-10-28T10:37:26.4330425+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264999 | TRUE | TRUE | 2025-10-28T02:37:26.4330425+00:00 | 2025-10-28T10:37:26.4330425+08:00 | #71538 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-06-02T23:00:00+00:00 | 2027-06-03T01:00:00+00:00 | 2027-06-03T07:00:00+08:00 | 2027-06-03T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71540 | 2025-10-28T02:08:22.9116078+00:00 | 2025-10-28T10:08:22.9116078+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:28.2379374+00:00 | 2025-10-28T10:37:28.2379374+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 265001 | TRUE | TRUE | 2025-10-28T02:37:28.2379374+00:00 | 2025-10-28T10:37:28.2379374+08:00 | #71540 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-08-04T23:00:00+00:00 | 2027-08-05T01:00:00+00:00 | 2027-08-05T07:00:00+08:00 | 2027-08-05T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71541 | 2025-10-28T02:08:23.1168359+00:00 | 2025-10-28T10:08:23.1168359+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:29.1456472+00:00 | 2025-10-28T10:37:29.1456472+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 265002 | TRUE | TRUE | 2025-10-28T02:37:29.1456472+00:00 | 2025-10-28T10:37:29.1456472+08:00 | #71541 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-09-01T23:00:00+00:00 | 2027-09-02T01:00:00+00:00 | 2027-09-02T07:00:00+08:00 | 2027-09-02T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71543 | 2025-10-28T02:08:23.5448726+00:00 | 2025-10-28T10:08:23.5448726+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:30.9893396+00:00 | 2025-10-28T10:37:30.9893396+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 265004 | TRUE | TRUE | 2025-10-28T02:37:30.9893396+00:00 | 2025-10-28T10:37:30.9893396+08:00 | #71543 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-11-03T23:00:00+00:00 | 2027-11-04T01:00:00+00:00 | 2027-11-04T07:00:00+08:00 | 2027-11-04T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
71544 | 2025-10-28T02:08:23.7895761+00:00 | 2025-10-28T10:08:23.7895761+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-28T02:37:32.0288304+00:00 | 2025-10-28T10:37:32.0288304+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 265005 | TRUE | TRUE | 2025-10-28T02:37:32.0288304+00:00 | 2025-10-28T10:37:32.0288304+08:00 | #71544 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 03 | 1.0 | FALSE |  | 2027-12-01T23:00:00+00:00 | 2027-12-02T01:00:00+00:00 | 2027-12-02T07:00:00+08:00 | 2027-12-02T09:00:00+08:00 |  |  |  |  | 2.00 | IAM Standard Maintenance |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
69262 | 2025-10-09T00:53:34.9218524+00:00 | 2025-10-09T08:53:34.9218524+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-09T02:30:28.8570339+00:00 | 2025-10-09T10:30:28.8570339+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249840 | TRUE | TRUE | 2025-10-09T02:30:28.8570339+00:00 | 2025-10-09T10:30:28.8570339+08:00 | #69262 - PPT: 2hrs - SL3P: INSTALL SCAFFOLD BARRIER 215P/116P | 1.0 | TRUE |  | 2027-11-15T02:00:00+00:00 | 2027-11-15T04:00:00+00:00 | 2027-11-15T10:00:00+08:00 | 2027-11-15T12:00:00+08:00 |  |  |  |  | 2.00 | Install scaffold barrier in 215P/116P to complete 116P skirt liner maintenance |  |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a10e71a-5a7b-4405-8777-b88a1561de62", "emailAddress": "Steven.Medling@riotinto.com", "displayName": "Medling, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
71545 | 2025-10-28T02:08:23.9887195+00:00 | 2025-10-28T10:08:23.9887195+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-03-24T08:36:06.527416+00:00 | 2026-03-24T16:36:06.527416+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 324096 | TRUE | TRUE | 2026-03-24T08:36:06.527416+00:00 | 2026-03-24T16:36:06.527416+08:00 | #71545 - BM4: 126hrs - CRUSHER - PRIMARY: BM4 03 | 3.0 | TRUE |  | 2027-12-29T22:00:00+00:00 | 2028-01-04T04:00:00+00:00 | 2027-12-30T06:00:00+08:00 | 2028-01-04T12:00:00+08:00 |  |  |  |  | 126.00 | IAM Standard Maintenance | Correcting Error should be aligned with PC2 start and end time |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
69643 | 2025-10-14T02:52:48.7566111+00:00 | 2025-10-14T10:52:48.7566111+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-14T02:52:49.2975124+00:00 | 2025-10-14T10:52:49.2975124+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 254394 | TRUE | TRUE | 2025-10-14T02:52:49.2975124+00:00 | 2025-10-14T10:52:49.2975124+08:00 | #69643 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0220 NO. 1 | 1.0 | TRUE |  | 2027-02-18T04:00:00+00:00 | 2027-02-21T10:00:00+00:00 | 2027-02-18T12:00:00+08:00 | 2027-02-21T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0220 Liners & Cylinders Additional Info: CR0220 Overhaul |  |  | [{"equipmentGUID": "a531f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0220", "name": "Crusher - Secondary: BM2 0220 No. 1", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM2 | Australia/Perth
69645 | 2025-10-14T02:52:49.6619019+00:00 | 2025-10-14T10:52:49.6619019+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-14T02:52:49.8562222+00:00 | 2025-10-14T10:52:49.8562222+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 254398 | TRUE | TRUE | 2025-10-14T02:52:49.8562222+00:00 | 2025-10-14T10:52:49.8562222+08:00 | #69645 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0220 NO. 1 | 1.0 | TRUE |  | 2027-05-20T04:00:00+00:00 | 2027-05-23T10:00:00+00:00 | 2027-05-20T12:00:00+08:00 | 2027-05-23T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0220 Liners & Cylinders Additional Info: CR0220 Overhaul |  |  | [{"equipmentGUID": "a531f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0220", "name": "Crusher - Secondary: BM2 0220 No. 1", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM2 | Australia/Perth
69647 | 2025-10-14T02:52:50.2464745+00:00 | 2025-10-14T10:52:50.2464745+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-14T02:52:50.4591556+00:00 | 2025-10-14T10:52:50.4591556+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 254402 | TRUE | TRUE | 2025-10-14T02:52:50.4591556+00:00 | 2025-10-14T10:52:50.4591556+08:00 | #69647 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0220 NO. 1 | 1.0 | TRUE |  | 2027-08-19T04:00:00+00:00 | 2027-08-22T10:00:00+00:00 | 2027-08-19T12:00:00+08:00 | 2027-08-22T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0220 Liners & Cylinders Additional Info: CR0220 Overhaul |  |  | [{"equipmentGUID": "a531f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0220", "name": "Crusher - Secondary: BM2 0220 No. 1", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM2 | Australia/Perth
69649 | 2025-10-14T02:52:50.8831247+00:00 | 2025-10-14T10:52:50.8831247+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-14T02:52:51.0930119+00:00 | 2025-10-14T10:52:51.0930119+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 254406 | TRUE | TRUE | 2025-10-14T02:52:51.0930119+00:00 | 2025-10-14T10:52:51.0930119+08:00 | #69649 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0220 NO. 1 | 1.0 | TRUE |  | 2027-11-18T04:00:00+00:00 | 2027-11-21T10:00:00+00:00 | 2027-11-18T12:00:00+08:00 | 2027-11-21T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0220 Liners & Cylinders Additional Info: CR0220 Overhaul |  |  | [{"equipmentGUID": "a531f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0220", "name": "Crusher - Secondary: BM2 0220 No. 1", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM2 | Australia/Perth
70584 | 2025-10-15T08:31:48.2627465+00:00 | 2025-10-15T16:31:48.2627465+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:48.4125662+00:00 | 2025-10-15T16:31:48.4125662+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257666 | TRUE | TRUE | 2025-10-15T08:31:48.4125662+00:00 | 2025-10-15T16:31:48.4125662+08:00 | #70584 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2026-12-16T22:00:00+00:00 | 2026-12-17T02:00:00+00:00 | 2026-12-17T06:00:00+08:00 | 2026-12-17T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
70585 | 2025-10-15T08:31:48.7344287+00:00 | 2025-10-15T16:31:48.7344287+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-15T08:31:48.8948791+00:00 | 2025-10-15T16:31:48.8948791+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257668 | TRUE | TRUE | 2025-10-15T08:31:48.8948791+00:00 | 2025-10-15T16:31:48.8948791+08:00 | #70585 - MTP: 4hrs - CRUSHER - PRIMARY: MTP 02 | 1.0 | FALSE |  | 2027-01-27T22:00:00+00:00 | 2027-01-28T02:00:00+00:00 | 2027-01-28T06:00:00+08:00 | 2027-01-28T10:00:00+08:00 |  |  |  |  | 4.00 | PC2 Brush Checks |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "2f3c09fa-2857-48f9-baff-932cd4ef4552", "emailAddress": "Samantha.Pumphrey@riotinto.com", "displayName": "Pumphrey, Samantha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
84036 | 2026-09-29T08:20:09.7442606+00:00 | 2026-09-29T16:20:09.7442606+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T07:47:46.0983803+00:00 | 2026-10-01T15:47:46.0983803+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 334914 | TRUE | TRUE | 2026-10-01T07:47:46.0983803+00:00 | 2026-10-01T15:47:46.0983803+08:00 | #84036 - CLA: 672hrs - BERTH 1 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-01-19T22:00:00+00:00 | 2027-02-16T22:00:00+00:00 | 2027-01-20T06:00:00+08:00 | 2027-02-17T06:00:00+08:00 |  |  |  |  | 672.00 | Berth 1 Marine SI works to align with CLAHDO SL2C |  |  | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
66808 | 2025-03-12T02:00:39.6275421+00:00 | 2025-03-12T10:00:39.6275421+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-02-27T06:36:18.6298463+00:00 | 2026-02-27T14:36:18.6298463+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 290091 | TRUE | TRUE | 2026-02-27T06:36:18.6298463+00:00 | 2026-02-27T14:36:18.6298463+08:00 | #66808 - PPT: 966hrs - BERTH 3 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 5.0 | FALSE |  | 2027-09-04T16:00:00+00:00 | 2027-10-14T22:00:00+00:00 | 2027-09-05T00:00:00+08:00 | 2027-10-15T06:00:00+08:00 |  |  |  |  | 966.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works - Aligned to CD3P Car Dumper Cell Replacement. | Adjusted start time to align better with dumper cell which pushed back 2 weeks |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "bc521488-59eb-4d88-8834-d789fcc969eb", "emailAddress": "Lewis.Buckland@riotinto.com", "displayName": "Buckland, Lewis (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | PPT | Australia/Perth
73664 | 2025-11-26T05:04:05.3743459+00:00 | 2025-11-26T13:04:05.3743459+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-02-26T00:19:55.6387741+00:00 | 2026-02-26T08:19:55.6387741+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 289730 | TRUE | TRUE | 2026-02-26T00:19:55.6387741+00:00 | 2026-02-26T08:19:55.6387741+08:00 | #73664 - PPT: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 3.0 | FALSE |  | 2027-03-23T16:00:00+00:00 | 2027-04-06T16:00:00+00:00 | 2027-03-24T00:00:00+08:00 | 2027-04-07T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works | Adjusting start to reduce direct change outs |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "bc521488-59eb-4d88-8834-d789fcc969eb", "emailAddress": "Lewis.Buckland@riotinto.com", "displayName": "Buckland, Lewis (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | PPT | Australia/Perth
73666 | 2025-11-26T05:21:28.8144143+00:00 | 2025-11-26T13:21:28.8144143+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-02-25T07:01:48.9600887+00:00 | 2026-02-25T15:01:48.9600887+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 289579 | TRUE | TRUE | 2026-02-25T07:01:48.9600887+00:00 | 2026-02-25T15:01:48.9600887+08:00 | #73666 - CLA: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 2.0 | FALSE |  | 2027-08-25T16:00:00+00:00 | 2027-09-08T16:00:00+00:00 | 2027-08-26T00:00:00+08:00 | 2027-09-09T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works. | Aligning so max 4 days on each side of shiploader shut to reduce impact from direct change outs ref Shelby/William Forecasting |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
67189 | 2025-04-30T06:24:51.8560054+00:00 | 2025-04-30T14:24:51.8560054+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | 2025-10-27T03:04:56.6931645+00:00 | 2025-10-27T11:04:56.6931645+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264249 | TRUE | TRUE | 2025-10-27T03:04:56.6931645+00:00 | 2025-10-27T11:04:56.6931645+08:00 | #67189 - WTS: 216hrs - CRUSHER - PRIMARY: WTS2 04 | 3.0 | TRUE |  | 2026-11-28T11:00:00+00:00 | 2026-12-07T11:00:00+00:00 | 2026-11-28T19:00:00+08:00 | 2026-12-07T19:00:00+08:00 |  |  |  |  | 216.00 | WTS PC4 system taken out 48Hrs before Major Shutdown to increase Tool time and help with preps | Increased 48hrs to total PC4 downtime duration as PC4 start is being offset from other PC group shut ref David Sturzaker. Have removed from group shut and the PC4 shut has its own shut now. | SWT2648 | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8f45a5a6-0c67-47de-9bc5-0a5295f781c7", "emailAddress": "Mick.Smith@riotinto.com", "displayName": "Smith, Mick (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1d74bc4f-c982-493a-b2ee-61bcfd74ded5", "emailAddress": "Simon.Burke@riotinto.com", "displayName": "Burke, Simon (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f0978c4b-943c-4507-8c2d-b58a1c286342", "emailAddress": "Ian.Mercer3@riotinto.com", "displayName": "Mercer, Ian (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4cd5de57-fbb8-4db6-8c51-b0e6e0b4856b", "emailAddress": "Jesse.Williams@riotinto.com", "displayName": "Williams, Jesse (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WTS | Australia/Perth
84038 | 2026-09-29T08:39:15.6592322+00:00 | 2026-09-29T16:39:15.6592322+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T07:59:40.0865815+00:00 | 2026-10-01T15:59:40.0865815+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 334924 | TRUE | TRUE | 2026-10-01T07:59:40.0865815+00:00 | 2026-10-01T15:59:40.0865815+08:00 | #84038 - CLA: 672hrs - BERTH 4 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-02-28T22:00:00+00:00 | 2027-03-28T22:00:00+00:00 | 2027-03-01T06:00:00+08:00 | 2027-03-29T06:00:00+08:00 |  |  |  |  | 672.00 | Berth 4 to align with CLAHDO SL3C |  |  | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
84037 | 2026-09-29T08:36:30.978434+00:00 | 2026-09-29T16:36:30.978434+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T07:59:40.2800222+00:00 | 2026-10-01T15:59:40.2800222+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 334925 | TRUE | TRUE | 2026-10-01T07:59:40.2800222+00:00 | 2026-10-01T15:59:40.2800222+08:00 | #84037 - CLA: 672hrs - BERTH 3 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-02-28T22:00:00+00:00 | 2027-03-28T22:00:00+00:00 | 2027-03-01T06:00:00+08:00 | 2027-03-29T06:00:00+08:00 |  |  |  |  | 672.00 | Berth 3 to align with CLAHDO SL3C |  |  | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
63711 | 2024-08-23T00:34:39+00:00 | 2024-08-23T08:34:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-03-04T05:56:03.2952074+00:00 | 2026-03-04T13:56:03.2952074+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 290463 | TRUE | TRUE | 2026-03-04T05:56:03.2952074+00:00 | 2026-03-04T13:56:03.2952074+08:00 | #63711 - PPT: 984hrs - PPSS RCL3P REPLACEMENT - RCL6P LOAD COMMISSIONING | 4.0 | FALSE |  | 2027-05-30T16:00:00+00:00 | 2027-07-10T16:00:00+00:00 | 2027-05-31T00:00:00+08:00 | 2027-07-11T00:00:00+08:00 |  |  |  |  | 984.00 | PPSS Ramp up duration is 41 days equates to ~16 days of production loss. | Changed to show the entire commissioning duration so it is visible |  | [{"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [] | [] | [{"code": "X", "name": "PPSS PPT RECLAIMER REPLACEMENT", "projectTeam": {"name": "D&T"}, "totalProjectTime": "984"}] | [{"name": "Reduced Rates"}] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Site Constraint | PPT | Australia/Perth
62238 | 2024-07-04T01:58:05+00:00 | 2024-07-04T09:58:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2025-10-09T02:29:18.5097448+00:00 | 2025-10-09T10:29:18.5097448+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249790 | TRUE | TRUE | 2025-10-09T02:29:18.5097448+00:00 | 2025-10-09T10:29:18.5097448+08:00 | #62238 - PPT: 2hrs - REMOVE SCAFFOLD BARRIER 215P/116P | 3.0 | TRUE |  | 2027-08-20T13:00:00+00:00 | 2027-08-20T15:00:00+00:00 | 2027-08-20T21:00:00+08:00 | 2027-08-20T23:00:00+08:00 |  |  |  |  | 2.00 | Remove scaffold barrier 215P/116P Remove scaffold barrier in 215P/116P to complete 116P skirt liner maintenance | IAM Refresh |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
62240 | 2024-07-04T01:58:08+00:00 | 2024-07-04T09:58:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2025-10-09T02:30:30.1976833+00:00 | 2025-10-09T10:30:30.1976833+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249841 | TRUE | TRUE | 2025-10-09T02:30:30.1976833+00:00 | 2025-10-09T10:30:30.1976833+08:00 | #62240 - PPT: 2hrs - REMOVE SCAFFOLD BARRIER 215P/116P | 3.0 | TRUE |  | 2027-11-19T13:00:00+00:00 | 2027-11-19T15:00:00+00:00 | 2027-11-19T21:00:00+08:00 | 2027-11-19T23:00:00+08:00 |  |  |  |  | 2.00 | Remove scaffold barrier 215P/116P Remove scaffold barrier in 215P/116P to complete 116P skirt liner maintenance | IAM Refresh |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
62234 | 2024-07-04T01:58:01+00:00 | 2024-07-04T09:58:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2025-10-09T06:00:22.6204369+00:00 | 2025-10-09T14:00:22.6204369+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 252239 | TRUE | TRUE | 2025-10-09T06:00:22.6204369+00:00 | 2025-10-09T14:00:22.6204369+08:00 | #62234 - PPT: 2hrs - REMOVE SCAFFOLD BARRIER 215P/116P | 3.0 | TRUE |  | 2027-02-19T13:00:00+00:00 | 2027-02-19T15:00:00+00:00 | 2027-02-19T21:00:00+08:00 | 2027-02-19T23:00:00+08:00 |  |  |  |  | 2.00 | Remove scaffold barrier 215P/116P Remove scaffold barrier in 215P/116P to complete 116P skirt liner maintenance | wrong week |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
62236 | 2024-07-04T01:58:04+00:00 | 2024-07-04T09:58:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2025-10-09T06:03:15.3906203+00:00 | 2025-10-09T14:03:15.3906203+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 252248 | TRUE | TRUE | 2025-10-09T06:03:15.3906203+00:00 | 2025-10-09T14:03:15.3906203+08:00 | #62236 - PPT: 2hrs - REMOVE SCAFFOLD BARRIER 215P/116P | 3.0 | TRUE |  | 2027-05-21T13:00:00+00:00 | 2027-05-21T15:00:00+00:00 | 2027-05-21T21:00:00+08:00 | 2027-05-21T23:00:00+08:00 |  |  |  |  | 2.00 | Remove scaffold barrier 215P/116P Remove scaffold barrier in 215P/116P to complete 116P skirt liner maintenance | wrong week |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
53596 | 2022-11-15T07:07:17+00:00 | 2022-11-15T15:07:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000004a5", "displayName": "Scott A Barlow"} | 2025-10-16T01:27:51.9608559+00:00 | 2025-10-16T09:27:51.9608559+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258093 | TRUE | TRUE | 2025-10-16T01:27:51.9608559+00:00 | 2025-10-16T09:27:51.9608559+08:00 | #53596 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 6.0 | TRUE |  | 2027-12-09T20:00:00+00:00 | 2027-12-10T08:00:00+00:00 | 2027-12-10T04:00:00+08:00 | 2027-12-10T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut. | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
60495 | 2024-02-06T05:43:16+00:00 | 2024-02-06T13:43:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-02-09T06:27:38.1153757+00:00 | 2026-02-09T14:27:38.1153757+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 286475 | TRUE | TRUE | 2026-02-09T06:27:38.1153757+00:00 | 2026-02-09T14:27:38.1153757+08:00 | #60495 - CLA: 264hrs - SL3C – WHARF SUB1 MAJOR WORKS (SUS CAP) | 7.0 | TRUE |  | 2027-08-01T04:00:00+00:00 | 2027-08-12T04:00:00+00:00 | 2027-08-01T12:00:00+08:00 | 2027-08-12T12:00:00+08:00 |  |  |  |  | 264.00 | Sus Cap project – Wharf Sub 1 HV switchgear replacement affecting SL3C, Berths 3 & 4. Berth 2 will also be affected if the LV power distribution work is not completed prior to shut | Moved to Q3 aligned to CD2C and before large plant shut. shut was moved out of 2026 and was unable to align with the extended CLAHDO SL3C shut as they were already completing the SL3C sub in that shut |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}, {"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "eeb6b438-cda3-4178-a69b-874a613b24b8", "emailAddress": "Mohamoud.Sagaale@riotinto.com", "displayName": "Sagaale, Mohamoud (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43584, "shutVersionId": 332092, "title": "#43584 - CLA: 114hrs - SLD3 IAM", "startDatetimeUTC": "2027-08-07T10:00:00+00:00", "endDatetimeUTC": "2027-08-12T04:00:00+00:00"}}] | [] | [{"code": "P-0603621", "name": "HV SWITCHGEAR", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "264"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
56407 | 2023-07-13T07:29:42+00:00 | 2023-07-13T15:29:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2025-11-26T00:43:42.8054344+00:00 | 2025-11-26T08:43:42.8054344+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277651 | TRUE | TRUE | 2025-11-26T00:43:42.8054344+00:00 | 2025-11-26T08:43:42.8054344+08:00 | #56407 - CLB: 106hrs - CONVEYOR: CLB C04 | 4.0 | TRUE |  | 2027-08-22T10:00:00+00:00 | 2027-08-26T20:00:00+00:00 | 2027-08-22T18:00:00+08:00 | 2027-08-27T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "4a6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV04", "name": "Conveyor: CLB C04", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
64959 | 2024-10-04T02:59:45+00:00 | 2024-10-04T10:59:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T06:03:52.0459778+00:00 | 2025-11-04T14:03:52.0459778+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271653 | TRUE | TRUE | 2025-11-04T06:03:52.0459778+00:00 | 2025-11-04T14:03:52.0459778+08:00 | #64959 - EII: 72hrs - SCREENHOUSE: EII 1E | 5.0 | FALSE |  | 2027-08-26T22:00:00+00:00 | 2027-08-29T22:00:00+00:00 | 2027-08-27T06:00:00+08:00 | 2027-08-30T06:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
64960 | 2024-10-04T02:59:47+00:00 | 2024-10-04T10:59:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T06:03:52.2675433+00:00 | 2025-11-04T14:03:52.2675433+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271655 | TRUE | TRUE | 2025-11-04T06:03:52.2675433+00:00 | 2025-11-04T14:03:52.2675433+08:00 | #64960 - EII: 72hrs - SCREENHOUSE: EII 1E | 7.0 | FALSE |  | 2027-11-25T22:00:00+00:00 | 2027-11-28T22:00:00+00:00 | 2027-11-26T06:00:00+08:00 | 2027-11-29T06:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
65416 | 2024-10-21T04:11:30+00:00 | 2024-10-21T12:11:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-01-29T00:57:44.9256767+00:00 | 2026-01-29T08:57:44.9256767+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 285237 | TRUE | TRUE | 2026-01-29T00:57:44.9256767+00:00 | 2026-01-29T08:57:44.9256767+08:00 | #65416 - CLA: 336hrs - BERTH 3 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 4.0 | FALSE |  | 2027-07-29T16:00:00+00:00 | 2027-08-12T16:00:00+00:00 | 2027-07-30T00:00:00+08:00 | 2027-08-13T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 2 Marine Structural Life Extension Berth Works | aligning better with shiploader shut |  | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "a3bee640-7a84-4b54-ab0d-d9d6cdf2a523", "emailAddress": "Fabien.Cogordan@riotinto.com", "displayName": "Cogordan, Fabien (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
60667 | 2024-02-16T04:40:34+00:00 | 2024-02-16T12:40:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-10-09T06:38:05.9504432+00:00 | 2025-10-09T14:38:05.9504432+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 252401 | TRUE | TRUE | 2025-10-09T06:38:05.9504432+00:00 | 2025-10-09T14:38:05.9504432+08:00 | #60667 - CLA: 100hrs - SL3C - DEFECTS SHUT | 4.1 | TRUE |  | 2028-01-02T16:00:00+00:00 | 2028-01-06T20:00:00+00:00 | 2028-01-03T00:00:00+08:00 | 2028-01-07T04:00:00+08:00 |  |  |  |  | 100.00 | Contingency Placeholder - Placement to be confirmed/adjusted or removed in QF timeframe with IOPs team. Do not place work or align with this shut prior to QF confirmation |  |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Placeholder | CLA | Australia/Perth
64207 | 2024-09-16T04:28:39+00:00 | 2024-09-16T12:28:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:41.2637285+00:00 | 2025-11-04T13:15:41.2637285+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271225 | TRUE | TRUE | 2025-11-04T05:15:41.2637285+00:00 | 2025-11-04T13:15:41.2637285+08:00 | #64207 - EII: 130hrs - SCREENHOUSE: EII 1E | 4.0 | FALSE |  | 2027-04-22T10:00:00+00:00 | 2027-04-27T20:00:00+00:00 | 2027-04-22T18:00:00+08:00 | 2027-04-28T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
64208 | 2024-09-16T04:28:40+00:00 | 2024-09-16T12:28:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:42.5617389+00:00 | 2025-11-04T13:15:42.5617389+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271233 | TRUE | TRUE | 2025-11-04T05:15:42.5617389+00:00 | 2025-11-04T13:15:42.5617389+08:00 | #64208 - EII: 130hrs - SCREENHOUSE: EII 1E | 4.0 | FALSE |  | 2027-07-22T10:00:00+00:00 | 2027-07-27T20:00:00+00:00 | 2027-07-22T18:00:00+08:00 | 2027-07-28T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
64209 | 2024-09-16T04:28:42+00:00 | 2024-09-16T12:28:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:44.0105064+00:00 | 2025-11-04T13:15:44.0105064+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271241 | TRUE | TRUE | 2025-11-04T05:15:44.0105064+00:00 | 2025-11-04T13:15:44.0105064+08:00 | #64209 - EII: 130hrs - SCREENHOUSE: EII 1E | 4.0 | FALSE |  | 2027-10-21T10:00:00+00:00 | 2027-10-26T20:00:00+00:00 | 2027-10-21T18:00:00+08:00 | 2027-10-27T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
49033 | 2022-11-01T06:36:04+00:00 | 2022-11-01T14:36:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:44.7547984+00:00 | 2025-11-04T13:15:44.7547984+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271245 | TRUE | TRUE | 2025-11-04T05:15:44.7547984+00:00 | 2025-11-04T13:15:44.7547984+08:00 | #49033 - EII: 130hrs - BERTH: EII | 6.0 | FALSE |  | 2028-01-20T10:00:00+00:00 | 2028-01-25T20:00:00+00:00 | 2028-01-20T18:00:00+08:00 | 2028-01-26T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "", "code": "EIIBTH", "name": "Berth: EII", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
49172 | 2022-11-01T22:33:13+00:00 | 2022-11-02T06:33:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:45.1524561+00:00 | 2025-11-04T13:15:45.1524561+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271247 | TRUE | TRUE | 2025-11-04T05:15:45.1524561+00:00 | 2025-11-04T13:15:45.1524561+08:00 | #49172 - EII: 130hrs - BERTH: EII LAYBY | 6.0 | FALSE |  | 2028-01-20T10:00:00+00:00 | 2028-01-25T20:00:00+00:00 | 2028-01-20T18:00:00+08:00 | 2028-01-26T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "", "code": "EIIBTHLAYBY", "name": "Berth: EII Layby", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
64210 | 2024-09-16T04:28:43+00:00 | 2024-09-16T12:28:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-04T05:15:45.5572955+00:00 | 2025-11-04T13:15:45.5572955+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271249 | TRUE | TRUE | 2025-11-04T05:15:45.5572955+00:00 | 2025-11-04T13:15:45.5572955+08:00 | #64210 - EII: 130hrs - SCREENHOUSE: EII 1E | 4.0 | FALSE |  | 2028-01-20T10:00:00+00:00 | 2028-01-25T20:00:00+00:00 | 2028-01-20T18:00:00+08:00 | 2028-01-26T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
52715 | 2022-11-07T23:33:40+00:00 | 2022-11-08T07:33:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:09.9976229+00:00 | 2025-10-09T10:29:09.9976229+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249783 | TRUE | TRUE | 2025-10-09T02:29:09.9976229+00:00 | 2025-10-09T10:29:09.9976229+08:00 | #52715 - CLA: 250hrs - PLANT: CLA RUBBLE 03 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52747 | 2022-11-07T23:36:19+00:00 | 2022-11-08T07:36:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:11.3652808+00:00 | 2025-10-09T10:29:11.3652808+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249784 | TRUE | TRUE | 2025-10-09T02:29:11.3652808+00:00 | 2025-10-09T10:29:11.3652808+08:00 | #52747 - CLA: 250hrs - CRUSHER - SECONDARY: CLA CIRCUIT 01 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52779 | 2022-11-07T23:37:35+00:00 | 2022-11-08T07:37:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:12.7558603+00:00 | 2025-10-09T10:29:12.7558603+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249785 | TRUE | TRUE | 2025-10-09T02:29:12.7558603+00:00 | 2025-10-09T10:29:12.7558603+08:00 | #52779 - CLA: 250hrs - CRUSHER - SECONDARY: CLA CIRCUIT 03 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52811 | 2022-11-07T23:38:50+00:00 | 2022-11-08T07:38:50+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:13.841114+00:00 | 2025-10-09T10:29:13.841114+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249786 | TRUE | TRUE | 2025-10-09T02:29:13.841114+00:00 | 2025-10-09T10:29:13.841114+08:00 | #52811 - CLA: 250hrs - CRUSHER - TERTIARY: CLA CIRCUIT 01 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52843 | 2022-11-07T23:40:06+00:00 | 2022-11-08T07:40:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:15.1599007+00:00 | 2025-10-09T10:29:15.1599007+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249787 | TRUE | TRUE | 2025-10-09T02:29:15.1599007+00:00 | 2025-10-09T10:29:15.1599007+08:00 | #52843 - CLA: 250hrs - CRUSHER - TERTIARY: CLA CIRCUIT 03 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52875 | 2022-11-08T00:23:54+00:00 | 2022-11-08T08:23:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:16.2466598+00:00 | 2025-10-09T10:29:16.2466598+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249788 | TRUE | TRUE | 2025-10-09T02:29:16.2466598+00:00 | 2025-10-09T10:29:16.2466598+08:00 | #52875 - CLA: 250hrs - CRUSHER - SECONDARY: CLA CIRCUIT 02 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9817ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT02", "name": "Crusher - Secondary: CLA Circuit 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52934 | 2022-11-08T00:26:02+00:00 | 2022-11-08T08:26:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:29:17.3614719+00:00 | 2025-10-09T10:29:17.3614719+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249789 | TRUE | TRUE | 2025-10-09T02:29:17.3614719+00:00 | 2025-10-09T10:29:17.3614719+08:00 | #52934 - CLA: 250hrs - CRUSHER - TERTIARY: CLA CIRCUIT 04 | 5.0 | FALSE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52748 | 2022-11-07T23:36:21+00:00 | 2022-11-08T07:36:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:34.2063498+00:00 | 2025-10-09T10:30:34.2063498+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249844 | TRUE | TRUE | 2025-10-09T02:30:34.2063498+00:00 | 2025-10-09T10:30:34.2063498+08:00 | #52748 - CLA: 130hrs - CRUSHER - SECONDARY: CLA CIRCUIT 01 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52780 | 2022-11-07T23:37:41+00:00 | 2022-11-08T07:37:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:35.4830896+00:00 | 2025-10-09T10:30:35.4830896+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249845 | TRUE | TRUE | 2025-10-09T02:30:35.4830896+00:00 | 2025-10-09T10:30:35.4830896+08:00 | #52780 - CLA: 130hrs - CRUSHER - SECONDARY: CLA CIRCUIT 03 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52812 | 2022-11-07T23:38:51+00:00 | 2022-11-08T07:38:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:36.7297243+00:00 | 2025-10-09T10:30:36.7297243+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249846 | TRUE | TRUE | 2025-10-09T02:30:36.7297243+00:00 | 2025-10-09T10:30:36.7297243+08:00 | #52812 - CLA: 130hrs - CRUSHER - TERTIARY: CLA CIRCUIT 01 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52844 | 2022-11-07T23:40:11+00:00 | 2022-11-08T07:40:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:37.9856591+00:00 | 2025-10-09T10:30:37.9856591+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249847 | TRUE | TRUE | 2025-10-09T02:30:37.9856591+00:00 | 2025-10-09T10:30:37.9856591+08:00 | #52844 - CLA: 130hrs - CRUSHER - TERTIARY: CLA CIRCUIT 03 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52876 | 2022-11-08T00:23:55+00:00 | 2022-11-08T08:23:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:39.2780815+00:00 | 2025-10-09T10:30:39.2780815+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249848 | TRUE | TRUE | 2025-10-09T02:30:39.2780815+00:00 | 2025-10-09T10:30:39.2780815+08:00 | #52876 - CLA: 130hrs - CRUSHER - SECONDARY: CLA CIRCUIT 02 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9817ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT02", "name": "Crusher - Secondary: CLA Circuit 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52935 | 2022-11-08T00:26:05+00:00 | 2022-11-08T08:26:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-09T02:30:40.5269161+00:00 | 2025-10-09T10:30:40.5269161+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 249849 | TRUE | TRUE | 2025-10-09T02:30:40.5269161+00:00 | 2025-10-09T10:30:40.5269161+08:00 | #52935 - CLA: 130hrs - CRUSHER - TERTIARY: CLA CIRCUIT 04 | 3.0 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52650 | 2022-11-07T05:59:54+00:00 | 2022-11-07T13:59:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-12-03T04:08:45.5121574+00:00 | 2025-12-03T12:08:45.5121574+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 278748 | TRUE | TRUE | 2025-12-03T04:08:45.5121574+00:00 | 2025-12-03T12:08:45.5121574+08:00 | #52650 - CLA: 120hrs - STACKER: CLA 05 | 4.0 | FALSE |  | 2028-01-28T22:00:00+00:00 | 2028-02-02T22:00:00+00:00 | 2028-01-29T06:00:00+08:00 | 2028-02-03T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCAY2807 | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
52458 | 2022-11-07T05:49:38+00:00 | 2022-11-07T13:49:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-12-03T04:08:45.9014754+00:00 | 2025-12-03T12:08:45.9014754+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 278750 | TRUE | TRUE | 2025-12-03T04:08:45.9014754+00:00 | 2025-12-03T12:08:45.9014754+08:00 | #52458 - CLA: 150hrs - RECLAIMER: CLA 02 | 5.0 | FALSE |  | 2028-01-29T04:00:00+00:00 | 2028-02-04T10:00:00+00:00 | 2028-01-29T12:00:00+08:00 | 2028-02-04T18:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance | IAM Refresh | SCAY2807 | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
46614 | 2022-06-01T09:36:02+00:00 | 2022-06-01T17:36:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-11-25T07:42:52.1562704+00:00 | 2025-11-25T15:42:52.1562704+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277258 | TRUE | TRUE | 2025-11-25T07:42:52.1562704+00:00 | 2025-11-25T15:42:52.1562704+08:00 | #46614 - CLB: 120hrs - RECLAIMER: CLB 12 | 4.0 | FALSE |  | 2028-01-09T22:00:00+00:00 | 2028-01-14T22:00:00+00:00 | 2028-01-10T06:00:00+08:00 | 2028-01-15T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBY2806 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
46626 | 2022-06-01T09:39:53+00:00 | 2022-06-01T17:39:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-11-25T08:20:30.7902853+00:00 | 2025-11-25T16:20:30.7902853+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277327 | TRUE | TRUE | 2025-11-25T08:20:30.7902853+00:00 | 2025-11-25T16:20:30.7902853+08:00 | #46626 - CLB: 120hrs - RECLAIMER: CLB 13 | 6.0 | FALSE |  | 2028-01-23T22:00:00+00:00 | 2028-01-28T22:00:00+00:00 | 2028-01-24T06:00:00+08:00 | 2028-01-29T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBY2808 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
46622 | 2022-06-01T09:36:11+00:00 | 2022-06-01T17:36:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-11-25T09:04:07.2924616+00:00 | 2025-11-25T17:04:07.2924616+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 277475 | TRUE | TRUE | 2025-11-25T09:04:07.2924616+00:00 | 2025-11-25T17:04:07.2924616+08:00 | #46622 - CLB: 72hrs - STACKER: CLB 14 | 5.0 | FALSE |  | 2028-01-23T22:00:00+00:00 | 2028-01-26T22:00:00+00:00 | 2028-01-24T06:00:00+08:00 | 2028-01-27T06:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | IAM Refresh | SCBY2801 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
51962 | 2022-11-07T05:13:08+00:00 | 2022-11-07T13:13:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-11-11T06:44:54.418013+00:00 | 2025-11-11T14:44:54.418013+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 274365 | TRUE | TRUE | 2025-11-11T06:44:54.418013+00:00 | 2025-11-11T14:44:54.418013+08:00 | #51962 - CLA: 120hrs - CAR DUMPER: CLA 2C | 4.0 | TRUE |  | 2028-01-29T10:00:00+00:00 | 2028-02-03T10:00:00+00:00 | 2028-01-29T18:00:00+08:00 | 2028-02-03T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
46574 | 2022-06-01T09:07:04+00:00 | 2022-06-01T17:07:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-27T02:05:39.6954771+00:00 | 2025-10-27T10:05:39.6954771+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263618 | TRUE | TRUE | 2025-10-27T02:05:39.6954771+00:00 | 2025-10-27T10:05:39.6954771+08:00 | #46574 - CLB: 120hrs - BERTH: CLB 07 | 5.0 | FALSE |  | 2028-01-10T10:00:00+00:00 | 2028-01-15T10:00:00+00:00 | 2028-01-10T18:00:00+08:00 | 2028-01-15T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2802 | [{"equipmentGUID": "", "code": "CLBBTH07", "name": "Berth: CLB 07", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
46575 | 2022-06-01T09:07:05+00:00 | 2022-06-01T17:07:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-27T02:05:40.1928283+00:00 | 2025-10-27T10:05:40.1928283+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263620 | TRUE | TRUE | 2025-10-27T02:05:40.1928283+00:00 | 2025-10-27T10:05:40.1928283+08:00 | #46575 - CLB: 120hrs - BERTH: CLB 08 | 5.0 | FALSE |  | 2028-01-10T10:00:00+00:00 | 2028-01-15T10:00:00+00:00 | 2028-01-10T18:00:00+08:00 | 2028-01-15T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2802 | [{"equipmentGUID": "", "code": "CLBBTH08", "name": "Berth: CLB 08", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
46657 | 2022-06-01T09:43:36+00:00 | 2022-06-01T17:43:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-27T02:05:40.6756084+00:00 | 2025-10-27T10:05:40.6756084+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263622 | TRUE | TRUE | 2025-10-27T02:05:40.6756084+00:00 | 2025-10-27T10:05:40.6756084+08:00 | #46657 - CLB: 120hrs - SHIPLOADER: CLB 12C | 5.0 | TRUE |  | 2028-01-10T10:00:00+00:00 | 2028-01-15T10:00:00+00:00 | 2028-01-10T18:00:00+08:00 | 2028-01-15T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2802 | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
46661 | 2022-06-01T09:43:42+00:00 | 2022-06-01T17:43:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2025-10-27T02:05:41.138301+00:00 | 2025-10-27T10:05:41.138301+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263624 | TRUE | TRUE | 2025-10-27T02:05:41.138301+00:00 | 2025-10-27T10:05:41.138301+08:00 | #46661 - CLB: 120hrs - SCREENHOUSE: CLB 06 OUTLOADING | 5.0 | FALSE |  | 2028-01-10T10:00:00+00:00 | 2028-01-15T10:00:00+00:00 | 2028-01-10T18:00:00+08:00 | 2028-01-15T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2802 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
28409 | 2018-03-15T02:32:55+00:00 | 2018-03-15T10:32:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000070b", "displayName": "Glenn Hall"} | 2025-10-16T01:27:48.2064508+00:00 | 2025-10-16T09:27:48.2064508+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258069 | TRUE | TRUE | 2025-10-16T01:27:48.2064508+00:00 | 2025-10-16T09:27:48.2064508+08:00 | #28409 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 7.0 | TRUE |  | 2027-08-12T20:00:00+00:00 | 2027-08-13T08:00:00+00:00 | 2027-08-13T04:00:00+08:00 | 2027-08-13T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
28407 | 2018-03-15T02:32:51+00:00 | 2018-03-15T10:32:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000070b", "displayName": "Glenn Hall"} | 2025-10-16T01:27:46.182363+00:00 | 2025-10-16T09:27:46.182363+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258053 | TRUE | TRUE | 2025-10-16T01:27:46.182363+00:00 | 2025-10-16T09:27:46.182363+08:00 | #28407 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 7.0 | TRUE |  | 2027-05-13T20:00:00+00:00 | 2027-05-14T08:00:00+00:00 | 2027-05-14T04:00:00+08:00 | 2027-05-14T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
60796 | 2024-02-26T02:45:20+00:00 | 2024-02-26T10:45:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-03-06T07:34:05.1202681+00:00 | 2026-03-06T15:34:05.1202681+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 320661 | TRUE | TRUE | 2026-03-06T07:34:05.1202681+00:00 | 2026-03-06T15:34:05.1202681+08:00 | #60796 - PPT: 336hrs - BERTH 5 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 8.0 | FALSE |  | 2027-08-10T16:00:00+00:00 | 2027-08-24T16:00:00+00:00 | 2027-08-11T00:00:00+08:00 | 2027-08-25T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works | Adjusted start time to reduce direct change requirements |  | [{"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "bc521488-59eb-4d88-8834-d789fcc969eb", "emailAddress": "Lewis.Buckland@riotinto.com", "displayName": "Buckland, Lewis (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | PPT | Australia/Perth
65418 | 2024-10-21T04:16:17+00:00 | 2024-10-21T12:16:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-02-26T00:56:28.0057283+00:00 | 2026-02-26T08:56:28.0057283+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 289744 | TRUE | TRUE | 2026-02-26T00:56:28.0057283+00:00 | 2026-02-26T08:56:28.0057283+08:00 | #65418 - CLA: 336hrs - BERTH 4 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 7.0 | FALSE |  | 2027-11-02T16:00:00+00:00 | 2027-11-16T16:00:00+00:00 | 2027-11-03T00:00:00+08:00 | 2027-11-17T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 2 Marine Structural Life Extension Berth Works | Adjusted start time to reduce direct change outs |  | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "a3bee640-7a84-4b54-ab0d-d9d6cdf2a523", "emailAddress": "Fabien.Cogordan@riotinto.com", "displayName": "Cogordan, Fabien (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | CLA | Australia/Perth
44470 | 2021-11-25T03:10:01+00:00 | 2021-11-25T11:10:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-11-06T04:53:17.7154196+00:00 | 2025-11-06T12:53:17.7154196+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 272438 | TRUE | TRUE | 2025-11-06T04:53:17.7154196+00:00 | 2025-11-06T12:53:17.7154196+08:00 | #44470 - PPT: 130hrs - SHIPLOADER: PPT 3P | 5.0 | TRUE |  | 2027-06-27T04:00:00+00:00 | 2027-07-02T14:00:00+00:00 | 2027-06-27T12:00:00+08:00 | 2027-07-02T22:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
49120 | 2022-11-01T07:09:42+00:00 | 2022-11-01T15:09:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-11-06T04:53:17.8882516+00:00 | 2025-11-06T12:53:17.8882516+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 272440 | TRUE | TRUE | 2025-11-06T04:53:17.8882516+00:00 | 2025-11-06T12:53:17.8882516+08:00 | #49120 - PPT: 130hrs - BERTH: PPT 02 | 5.0 | FALSE |  | 2027-06-27T04:00:00+00:00 | 2027-07-02T14:00:00+00:00 | 2027-06-27T12:00:00+08:00 | 2027-07-02T22:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
49136 | 2022-11-01T07:10:11+00:00 | 2022-11-01T15:10:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-11-06T04:53:18.0657252+00:00 | 2025-11-06T12:53:18.0657252+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 272442 | TRUE | TRUE | 2025-11-06T04:53:18.0657252+00:00 | 2025-11-06T12:53:18.0657252+08:00 | #49136 - PPT: 130hrs - BERTH: PPT 03 | 5.0 | FALSE |  | 2027-06-27T04:00:00+00:00 | 2027-07-02T14:00:00+00:00 | 2027-06-27T12:00:00+08:00 | 2027-07-02T22:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
44423 | 2021-11-25T02:57:05+00:00 | 2021-11-25T10:57:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-27T09:29:15.3411322+00:00 | 2025-10-27T17:29:15.3411322+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264588 | TRUE | TRUE | 2025-10-27T09:29:15.3411322+00:00 | 2025-10-27T17:29:15.3411322+08:00 | #44423 - PPT: 106hrs - CAR DUMPER: PPT 3P | 6.0 | TRUE |  | 2027-09-20T10:00:00+00:00 | 2027-09-24T20:00:00+00:00 | 2027-09-20T18:00:00+08:00 | 2027-09-25T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
44381 | 2021-11-25T01:53:31+00:00 | 2021-11-25T09:53:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-20T03:40:27.5332574+00:00 | 2025-10-20T11:40:27.5332574+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260809 | TRUE | TRUE | 2025-10-20T03:40:27.5332574+00:00 | 2025-10-20T11:40:27.5332574+08:00 | #44381 - EII: 106hrs - CAR DUMPER: EII 2E | 7.0 | TRUE |  | 2028-01-17T10:00:00+00:00 | 2028-01-21T20:00:00+00:00 | 2028-01-17T18:00:00+08:00 | 2028-01-22T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cf432606-a42e-449b-b28a-08e3cff7b5e4", "emailAddress": "Trevor.Fawcett@riotinto.com", "displayName": "Trevor Fawcett"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
44397 | 2021-11-25T02:01:12+00:00 | 2021-11-25T10:01:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-11-04T05:15:44.3748176+00:00 | 2025-11-04T13:15:44.3748176+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 271243 | TRUE | TRUE | 2025-11-04T05:15:44.3748176+00:00 | 2025-11-04T13:15:44.3748176+08:00 | #44397 - EII: 130hrs - SHIPLOADER: EII 1E | 6.0 | TRUE |  | 2028-01-20T10:00:00+00:00 | 2028-01-25T20:00:00+00:00 | 2028-01-20T18:00:00+08:00 | 2028-01-26T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | EII | Australia/Perth
43636 | 2021-11-01T23:45:13+00:00 | 2021-11-02T07:45:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-23T02:24:38.9094377+00:00 | 2025-10-23T10:24:38.9094377+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263159 | TRUE | TRUE | 2025-10-23T02:24:38.9094377+00:00 | 2025-10-23T10:24:38.9094377+08:00 | #43636 - CLB: 106hrs - CAR DUMPER: CLB 7C | 7.0 | TRUE |  | 2027-08-23T10:00:00+00:00 | 2027-08-27T20:00:00+00:00 | 2027-08-23T18:00:00+08:00 | 2027-08-28T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh | SCBI2736 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43629 | 2021-11-01T23:42:40+00:00 | 2021-11-02T07:42:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-23T02:24:40.2600214+00:00 | 2025-10-23T10:24:40.2600214+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263169 | TRUE | TRUE | 2025-10-23T02:24:40.2600214+00:00 | 2025-10-23T10:24:40.2600214+08:00 | #43629 - CLB: 106hrs - CAR DUMPER: CLB 6C | 6.0 | TRUE |  | 2028-01-03T10:00:00+00:00 | 2028-01-07T20:00:00+00:00 | 2028-01-03T18:00:00+08:00 | 2028-01-08T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh | SCBI2751 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43693 | 2021-11-02T00:01:17+00:00 | 2021-11-02T08:01:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:28.0935558+00:00 | 2025-10-27T10:05:28.0935558+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263558 | TRUE | TRUE | 2025-10-27T02:05:28.0935558+00:00 | 2025-10-27T10:05:28.0935558+08:00 | #43693 - CLB: 120hrs - SCREENHOUSE: CLB 06 OUTLOADING | 6.0 | FALSE |  | 2027-01-11T10:00:00+00:00 | 2027-01-16T10:00:00+00:00 | 2027-01-11T18:00:00+08:00 | 2027-01-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2702 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43606 | 2021-11-01T23:22:19+00:00 | 2021-11-02T07:22:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:34.4204767+00:00 | 2025-10-27T10:05:34.4204767+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263594 | TRUE | TRUE | 2025-10-27T02:05:34.4204767+00:00 | 2025-10-27T10:05:34.4204767+08:00 | #43606 - CLB: 120hrs - BERTH: CLB 05 | 7.0 | FALSE |  | 2027-09-13T10:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-13T18:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2735 | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43607 | 2021-11-01T23:22:19+00:00 | 2021-11-02T07:22:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:34.8688353+00:00 | 2025-10-27T10:05:34.8688353+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263596 | TRUE | TRUE | 2025-10-27T02:05:34.8688353+00:00 | 2025-10-27T10:05:34.8688353+08:00 | #43607 - CLB: 120hrs - BERTH: CLB 06 | 7.0 | FALSE |  | 2027-09-13T10:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-13T18:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2735 | [{"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43678 | 2021-11-01T23:59:12+00:00 | 2021-11-02T07:59:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:35.2689236+00:00 | 2025-10-27T10:05:35.2689236+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263598 | TRUE | TRUE | 2025-10-27T02:05:35.2689236+00:00 | 2025-10-27T10:05:35.2689236+08:00 | #43678 - CLB: 120hrs - SHIPLOADER: CLB 11C | 7.0 | TRUE |  | 2027-09-13T10:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-13T18:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2735 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43673, "shutVersionId": 335902, "title": "#43673 - CLB: 84hrs - RETURN FINES IAM", "startDatetimeUTC": "2027-09-14T10:00:00+00:00", "endDatetimeUTC": "2027-09-17T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43686 | 2021-11-01T23:59:23+00:00 | 2021-11-02T07:59:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:35.6647105+00:00 | 2025-10-27T10:05:35.6647105+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263600 | TRUE | TRUE | 2025-10-27T02:05:35.6647105+00:00 | 2025-10-27T10:05:35.6647105+08:00 | #43686 - CLB: 120hrs - SCREENHOUSE: CLB 05 OUTLOADING | 7.0 | FALSE |  | 2027-09-13T10:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-13T18:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2735 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43616 | 2021-11-01T23:30:19+00:00 | 2021-11-02T07:30:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:36.0726798+00:00 | 2025-10-27T10:05:36.0726798+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263602 | TRUE | TRUE | 2025-10-27T02:05:36.0726798+00:00 | 2025-10-27T10:05:36.0726798+08:00 | #43616 - CLB: 120hrs - BERTH: CLB 07 | 7.0 | FALSE |  | 2027-10-11T10:00:00+00:00 | 2027-10-16T10:00:00+00:00 | 2027-10-11T18:00:00+08:00 | 2027-10-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2741 | [{"equipmentGUID": "", "code": "CLBBTH07", "name": "Berth: CLB 07", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43617 | 2021-11-01T23:30:20+00:00 | 2021-11-02T07:30:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:36.5038473+00:00 | 2025-10-27T10:05:36.5038473+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263604 | TRUE | TRUE | 2025-10-27T02:05:36.5038473+00:00 | 2025-10-27T10:05:36.5038473+08:00 | #43617 - CLB: 120hrs - BERTH: CLB 08 | 7.0 | FALSE |  | 2027-10-11T10:00:00+00:00 | 2027-10-16T10:00:00+00:00 | 2027-10-11T18:00:00+08:00 | 2027-10-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2741 | [{"equipmentGUID": "", "code": "CLBBTH08", "name": "Berth: CLB 08", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
43699 | 2021-11-02T00:01:27+00:00 | 2021-11-02T08:01:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-27T02:05:37.3526765+00:00 | 2025-10-27T10:05:37.3526765+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 263608 | TRUE | TRUE | 2025-10-27T02:05:37.3526765+00:00 | 2025-10-27T10:05:37.3526765+08:00 | #43699 - CLB: 120hrs - SCREENHOUSE: CLB 06 OUTLOADING | 7.0 | FALSE |  | 2027-10-11T10:00:00+00:00 | 2027-10-16T10:00:00+00:00 | 2027-10-11T18:00:00+08:00 | 2027-10-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh | SCBO2741 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLB | Australia/Perth
64262 | 2024-09-18T01:52:44+00:00 | 2024-09-18T09:52:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-05-23T05:40:44.616005+00:00 | 2025-05-23T13:40:44.616005+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "System"} | 239207 | TRUE | TRUE | 2025-05-23T05:40:44.616005+00:00 | 2025-05-23T13:40:44.616005+08:00 | #64262 - SYSTEM: 24hrs - HD1 & HD4 TOTAL POWER OUTAGE - 220KV TRANSMISSION LINE RELOCATION | 4.0 | TRUE |  | 2027-06-23T23:00:00+00:00 | 2027-06-24T23:00:00+00:00 | 2027-06-24T07:00:00+08:00 | 2027-06-25T07:00:00+08:00 |  |  |  |  | 24.00 | Total HD1 and HD4 Power Outage for 220KV Transmission line relocation project. Legal obligation to move it, or else RTIO will be up for legal action with BHP, BHP completing their work around May 2027. | New dates have become available from Project team |  | [{"equipmentGUID": "", "code": "220KV POWER", "name": "220KV POWER OUTAGE", "assetClass": {"name": "Unknown - Fixed Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3435fe41-b611-47b6-bda3-daca7f6d2d35", "emailAddress": "Kenneth.Woo@riotinto.com", "displayName": "Kenneth Woo"}}] | [{"name": "HD1"}, {"name": "HD4"}] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects |  | Australia/Perth
48431 | 2022-09-20T03:04:54+00:00 | 2022-09-20T11:04:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T07:28:18.1379381+00:00 | 2025-11-03T15:28:18.1379381+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270437 | TRUE | TRUE | 2025-11-03T07:28:18.1379381+00:00 | 2025-11-03T15:28:18.1379381+08:00 | #48431 - YAN: 144hrs - CRUSHER - PRIMARY: YAN PRIMARY SIZER 201 PLANT 02 & CRUSHER - PRIMARY: YAN PRIMARY SIZER 301 PLANT 03 | 6.0 | TRUE |  | 2028-01-20T11:00:00+00:00 | 2028-01-26T11:00:00+00:00 | 2028-01-20T19:00:00+08:00 | 2028-01-26T19:00:00+08:00 |  |  |  |  | 144.00 | Loop Shut | IAM Refresh |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "c5f6d490-1651-4210-9710-9db046dd7c02", "emailAddress": "Brendan.Smith3@riotinto.com", "displayName": "Smith, Brendan (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
58769 | 2023-09-26T02:14:37+00:00 | 2023-09-26T10:14:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T10:36:49.2667073+00:00 | 2025-11-03T18:36:49.2667073+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270519 | TRUE | TRUE | 2025-11-03T10:36:49.2667073+00:00 | 2025-11-03T18:36:49.2667073+08:00 | #58769 - YAN: 20hrs - PLANT: YAN 03 (JSE) | 3.0 | TRUE |  | 2028-01-19T15:00:00+00:00 | 2028-01-20T11:00:00+00:00 | 2028-01-19T23:00:00+08:00 | 2028-01-20T19:00:00+08:00 |  |  |  |  | 20.00 | 20hr - Loop Shut Preps Additional Info: JSE running in Bypass | IAM Refresh |  | [{"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "c5f6d490-1651-4210-9710-9db046dd7c02", "emailAddress": "Brendan.Smith3@riotinto.com", "displayName": "Smith, Brendan (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
57613 | 2023-08-16T08:31:34+00:00 | 2023-08-16T16:31:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-04T01:38:03.4157269+00:00 | 2025-11-04T09:38:03.4157269+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270668 | TRUE | TRUE | 2025-11-04T01:38:03.4157269+00:00 | 2025-11-04T09:38:03.4157269+08:00 | #57613 - YAN: 108hrs - STACKER: YAN 02 | 5.0 | FALSE |  | 2027-11-26T11:00:00+00:00 | 2027-11-30T23:00:00+00:00 | 2027-11-26T19:00:00+08:00 | 2027-12-01T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 2 shut | IAM Refresh |  | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "658c3d8f-ecb6-4991-a18d-a00c9f1b1fae", "emailAddress": "Paul.Bradley4@riotinto.com", "displayName": "Paul Bradley"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
57616 | 2023-08-16T08:32:37+00:00 | 2023-08-16T16:32:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-04T01:38:03.7557569+00:00 | 2025-11-04T09:38:03.7557569+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270670 | TRUE | TRUE | 2025-11-04T01:38:03.7557569+00:00 | 2025-11-04T09:38:03.7557569+08:00 | #57616 - YAN: 108hrs - STACKER: YAN 03 | 5.0 | FALSE |  | 2028-01-27T11:00:00+00:00 | 2028-01-31T23:00:00+00:00 | 2028-01-27T19:00:00+08:00 | 2028-02-01T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 3 shut | IAM Refresh |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
44332 | 2021-11-23T10:26:21+00:00 | 2021-11-23T18:26:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T05:05:11.3374351+00:00 | 2025-10-17T13:05:11.3374351+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260014 | TRUE | TRUE | 2025-10-17T05:05:11.3374351+00:00 | 2025-10-17T13:05:11.3374351+08:00 | #44332 - WAN: 84hrs - TRAIN LOADOUT: WAN | 11.0 | TRUE |  | 2027-01-20T10:30:00+00:00 | 2027-01-23T22:30:00+00:00 | 2027-01-20T18:30:00+08:00 | 2027-01-24T06:30:00+08:00 |  |  |  |  | 84.00 | Standard 84hrs Maintenance. | IAM Refresh |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
44335 | 2021-11-23T10:28:13+00:00 | 2021-11-23T18:28:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T05:05:14.1034718+00:00 | 2025-10-17T13:05:14.1034718+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260017 | TRUE | TRUE | 2025-10-17T05:05:14.1034718+00:00 | 2025-10-17T13:05:14.1034718+08:00 | #44335 - WAN: 84hrs - TRAIN LOADOUT: WAN | 11.0 | TRUE |  | 2027-04-21T10:30:00+00:00 | 2027-04-24T22:30:00+00:00 | 2027-04-21T18:30:00+08:00 | 2027-04-25T06:30:00+08:00 |  |  |  |  | 84.00 | Standard IMS 84hrs Maintenance | IAM Refresh |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
44333 | 2021-11-23T10:27:07+00:00 | 2021-11-23T18:27:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T05:05:16.9005729+00:00 | 2025-10-17T13:05:16.9005729+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260020 | TRUE | TRUE | 2025-10-17T05:05:16.9005729+00:00 | 2025-10-17T13:05:16.9005729+08:00 | #44333 - WAN: 84hrs - TRAIN LOADOUT: WAN | 12.0 | TRUE |  | 2027-07-21T10:30:00+00:00 | 2027-07-24T22:30:00+00:00 | 2027-07-21T18:30:00+08:00 | 2027-07-25T06:30:00+08:00 |  |  |  |  | 84.00 | Standard 84hrs Maintenance reduced back to 84 hours based on rev 2 of 10 year plan | IAM Refresh |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
48003 | 2022-09-08T04:18:25+00:00 | 2022-09-08T12:18:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T05:05:21.7440159+00:00 | 2025-10-17T13:05:21.7440159+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260025 | TRUE | TRUE | 2025-10-17T05:05:21.7440159+00:00 | 2025-10-17T13:05:21.7440159+08:00 | #48003 - WAN: 120hrs - PLANT: WAN | 8.0 | TRUE |  | 2028-01-13T10:30:00+00:00 | 2028-01-18T10:30:00+00:00 | 2028-01-13T18:30:00+08:00 | 2028-01-18T18:30:00+08:00 |  |  |  |  | 120.00 | Standard IMS 120hrs Maintenance | IAM Refresh |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
48004 | 2022-09-08T04:18:59+00:00 | 2022-09-08T12:18:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T05:05:22.7093345+00:00 | 2025-10-17T13:05:22.7093345+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 260026 | TRUE | TRUE | 2025-10-17T05:05:22.7093345+00:00 | 2025-10-17T13:05:22.7093345+08:00 | #48004 - WAN: 84hrs - TRAIN LOADOUT: WAN | 9.0 | TRUE |  | 2028-01-19T10:30:00+00:00 | 2028-01-22T22:30:00+00:00 | 2028-01-19T18:30:00+08:00 | 2028-01-23T06:30:00+08:00 |  |  |  |  | 84.00 | Standard IMS 120hrs Maintenance. | IAM Refresh |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
44198 | 2021-11-23T07:03:31+00:00 | 2021-11-23T15:03:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:46.4116045+00:00 | 2025-10-16T09:27:46.4116045+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258055 | TRUE | TRUE | 2025-10-16T01:27:46.4116045+00:00 | 2025-10-16T09:27:46.4116045+08:00 | #44198 - BM4: 2hrs - PLANT: BM4 | 8.0 | TRUE |  | 2027-06-02T23:00:00+00:00 | 2027-06-03T01:00:00+00:00 | 2027-06-03T07:00:00+08:00 | 2027-06-03T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44226 | 2021-11-23T07:25:11+00:00 | 2021-11-23T15:25:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:46.6571333+00:00 | 2025-10-16T09:27:46.6571333+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258057 | TRUE | TRUE | 2025-10-16T01:27:46.6571333+00:00 | 2025-10-16T09:27:46.6571333+08:00 | #44226 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-06-02T23:00:00+00:00 | 2027-06-03T01:00:00+00:00 | 2027-06-03T07:00:00+08:00 | 2027-06-03T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44227 | 2021-11-23T07:25:15+00:00 | 2021-11-23T15:25:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:46.9017088+00:00 | 2025-10-16T09:27:46.9017088+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258059 | TRUE | TRUE | 2025-10-16T01:27:46.9017088+00:00 | 2025-10-16T09:27:46.9017088+08:00 | #44227 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-06-02T23:00:00+00:00 | 2027-06-03T01:00:00+00:00 | 2027-06-03T07:00:00+08:00 | 2027-06-03T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44165 | 2021-11-23T03:33:52+00:00 | 2021-11-23T11:33:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:47.1478053+00:00 | 2025-10-16T09:27:47.1478053+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258061 | TRUE | TRUE | 2025-10-16T01:27:47.1478053+00:00 | 2025-10-16T09:27:47.1478053+08:00 | #44165 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 7.0 | TRUE |  | 2027-06-10T20:00:00+00:00 | 2027-06-11T08:00:00+00:00 | 2027-06-11T04:00:00+08:00 | 2027-06-11T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44202 | 2021-11-23T07:05:57+00:00 | 2021-11-23T15:05:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:47.4074466+00:00 | 2025-10-16T09:27:47.4074466+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258063 | TRUE | TRUE | 2025-10-16T01:27:47.4074466+00:00 | 2025-10-16T09:27:47.4074466+08:00 | #44202 - BM4: 2hrs - PLANT: BM4 | 7.0 | TRUE |  | 2027-08-04T23:00:00+00:00 | 2027-08-05T01:00:00+00:00 | 2027-08-05T07:00:00+08:00 | 2027-08-05T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44234 | 2021-11-23T07:25:26+00:00 | 2021-11-23T15:25:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:47.6686918+00:00 | 2025-10-16T09:27:47.6686918+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258065 | TRUE | TRUE | 2025-10-16T01:27:47.6686918+00:00 | 2025-10-16T09:27:47.6686918+08:00 | #44234 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 6.0 | TRUE |  | 2027-08-04T23:00:00+00:00 | 2027-08-05T01:00:00+00:00 | 2027-08-05T07:00:00+08:00 | 2027-08-05T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44235 | 2021-11-23T07:25:26+00:00 | 2021-11-23T15:25:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:47.9279542+00:00 | 2025-10-16T09:27:47.9279542+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258067 | TRUE | TRUE | 2025-10-16T01:27:47.9279542+00:00 | 2025-10-16T09:27:47.9279542+08:00 | #44235 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 6.0 | TRUE |  | 2027-08-04T23:00:00+00:00 | 2027-08-05T01:00:00+00:00 | 2027-08-05T07:00:00+08:00 | 2027-08-05T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44225 | 2021-11-23T07:25:11+00:00 | 2021-11-23T15:25:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:45.9561164+00:00 | 2025-10-16T09:27:45.9561164+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258051 | TRUE | TRUE | 2025-10-16T01:27:45.9561164+00:00 | 2025-10-16T09:27:45.9561164+08:00 | #44225 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-05-05T23:00:00+00:00 | 2027-05-06T01:00:00+00:00 | 2027-05-06T07:00:00+08:00 | 2027-05-06T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44174 | 2021-11-23T06:35:21+00:00 | 2021-11-23T14:35:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T05:56:50.8642801+00:00 | 2025-10-16T13:56:50.8642801+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258745 | TRUE | TRUE | 2025-10-16T05:56:50.8642801+00:00 | 2025-10-16T13:56:50.8642801+08:00 | #44174 - BM4: 96hrs - TRAIN LOADOUT: BM4 | 10.0 | TRUE |  | 2027-04-06T16:00:00+00:00 | 2027-04-10T16:00:00+00:00 | 2027-04-07T00:00:00+08:00 | 2027-04-11T00:00:00+08:00 |  |  |  |  | 96.00 | TLO 96hr shut | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "59d8802c-59d8-4611-8554-9744f197061c", "emailAddress": "Christopher.Templeton@riotinto.com", "displayName": "Templeton, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44175 | 2021-11-23T06:38:32+00:00 | 2021-11-23T14:38:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T05:56:51.0272299+00:00 | 2025-10-16T13:56:51.0272299+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258747 | TRUE | TRUE | 2025-10-16T05:56:51.0272299+00:00 | 2025-10-16T13:56:51.0272299+08:00 | #44175 - BM4: 96hrs - TRAIN LOADOUT: BM4 | 10.0 | TRUE |  | 2027-07-06T16:00:00+00:00 | 2027-07-10T16:00:00+00:00 | 2027-07-07T00:00:00+08:00 | 2027-07-11T00:00:00+08:00 |  |  |  |  | 96.00 | TLO 96hr shut | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "59d8802c-59d8-4611-8554-9744f197061c", "emailAddress": "Christopher.Templeton@riotinto.com", "displayName": "Templeton, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44177 | 2021-11-23T06:46:47+00:00 | 2021-11-23T14:46:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T05:56:51.2108463+00:00 | 2025-10-16T13:56:51.2108463+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258749 | TRUE | TRUE | 2025-10-16T05:56:51.2108463+00:00 | 2025-10-16T13:56:51.2108463+08:00 | #44177 - BM4: 96hrs - TRAIN LOADOUT: BM4 | 13.0 | TRUE |  | 2027-10-05T16:00:00+00:00 | 2027-10-09T16:00:00+00:00 | 2027-10-06T00:00:00+08:00 | 2027-10-10T00:00:00+08:00 |  |  |  |  | 96.00 | TLO 96hr shut Reduced back to 96hr as reclaimer is now to be changed out in 2028 I | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "59d8802c-59d8-4611-8554-9744f197061c", "emailAddress": "Christopher.Templeton@riotinto.com", "displayName": "Templeton, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44178 | 2021-11-23T06:47:18+00:00 | 2021-11-23T14:47:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T05:56:51.3923736+00:00 | 2025-10-16T13:56:51.3923736+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258751 | TRUE | TRUE | 2025-10-16T05:56:51.3923736+00:00 | 2025-10-16T13:56:51.3923736+08:00 | #44178 - BM4: 96hrs - TRAIN LOADOUT: BM4 | 11.0 | TRUE |  | 2028-01-04T16:00:00+00:00 | 2028-01-08T16:00:00+00:00 | 2028-01-05T00:00:00+08:00 | 2028-01-09T00:00:00+08:00 |  |  |  |  | 96.00 | TLO 96hr shut. | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "59d8802c-59d8-4611-8554-9744f197061c", "emailAddress": "Christopher.Templeton@riotinto.com", "displayName": "Templeton, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44190 | 2021-11-23T06:57:26+00:00 | 2021-11-23T14:57:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T07:19:19.181499+00:00 | 2025-10-16T15:19:19.181499+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258933 | TRUE | TRUE | 2025-10-16T07:19:19.181499+00:00 | 2025-10-16T15:19:19.181499+08:00 | #44190 - BM4: 126hrs - CRUSHER - PRIMARY: BM4 02 | 9.0 | TRUE |  | 2027-12-29T22:00:00+00:00 | 2028-01-04T04:00:00+00:00 | 2027-12-30T06:00:00+08:00 | 2028-01-04T12:00:00+08:00 |  |  |  |  | 126.00 | Baseline changed from 96h to 126h as per MOC 113812 | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44188 | 2021-11-23T06:55:57+00:00 | 2021-11-23T14:55:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T07:19:19.5280627+00:00 | 2025-10-16T15:19:19.5280627+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258935 | TRUE | TRUE | 2025-10-16T07:19:19.5280627+00:00 | 2025-10-16T15:19:19.5280627+08:00 | #44188 - BM4: 120hrs - PLANT: BM4 | 9.0 | TRUE |  | 2027-12-30T04:00:00+00:00 | 2028-01-04T04:00:00+00:00 | 2027-12-30T12:00:00+08:00 | 2028-01-04T12:00:00+08:00 |  |  |  |  | 120.00 | Baseline changed from 96h to 126h as per MOC 113812 | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44189 | 2021-11-23T06:56:41+00:00 | 2021-11-23T14:56:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T07:19:19.8836359+00:00 | 2025-10-16T15:19:19.8836359+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258937 | TRUE | TRUE | 2025-10-16T07:19:19.8836359+00:00 | 2025-10-16T15:19:19.8836359+08:00 | #44189 - BM4: 120hrs - CRUSHER - PRIMARY: BM4 01 | 9.0 | TRUE |  | 2027-12-30T04:00:00+00:00 | 2028-01-04T04:00:00+00:00 | 2027-12-30T12:00:00+08:00 | 2028-01-04T12:00:00+08:00 |  |  |  |  | 120.00 | Baseline changed from 96h to 126h as per MOC 113812 | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44420 | 2021-11-25T02:43:23+00:00 | 2021-11-25T10:43:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T08:47:08.1967285+00:00 | 2025-10-16T16:47:08.1967285+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 259736 | TRUE | TRUE | 2025-10-16T08:47:08.1967285+00:00 | 2025-10-16T16:47:08.1967285+08:00 | #44420 - BM4: 36hrs - RCL YEARLY STAT INSPECTIONS | 5.0 | TRUE |  | 2027-05-06T22:00:00+00:00 | 2027-05-08T10:00:00+00:00 | 2027-05-07T06:00:00+08:00 | 2027-05-08T18:00:00+08:00 |  |  |  |  | 36.00 | Provisional date for 36hr Yearly Stat inspections ref Mohammed Ahmed | timing tweak |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44173 | 2021-11-23T06:33:50+00:00 | 2021-11-23T14:33:50+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T00:50:55.9228748+00:00 | 2025-10-17T08:50:55.9228748+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 259847 | TRUE | TRUE | 2025-10-17T00:50:55.9228748+00:00 | 2025-10-17T08:50:55.9228748+08:00 | #44173 - BM4: 96hrs - TRAIN LOADOUT: BM4 | 13.0 | TRUE |  | 2027-01-05T16:00:00+00:00 | 2027-01-09T16:00:00+00:00 | 2027-01-06T00:00:00+08:00 | 2027-01-10T00:00:00+08:00 |  |  |  |  | 96.00 | TLO 96hr shut | wrong year |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44193 | 2021-11-23T07:00:48+00:00 | 2021-11-23T15:00:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:43.9947248+00:00 | 2025-10-16T09:27:43.9947248+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258031 | TRUE | TRUE | 2025-10-16T01:27:43.9947248+00:00 | 2025-10-16T09:27:43.9947248+08:00 | #44193 - BM4: 2hrs - PLANT: BM4 | 7.0 | TRUE |  | 2027-02-03T23:00:00+00:00 | 2027-02-04T01:00:00+00:00 | 2027-02-04T07:00:00+08:00 | 2027-02-04T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44216 | 2021-11-23T07:24:56+00:00 | 2021-11-23T15:24:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:44.1656425+00:00 | 2025-10-16T09:27:44.1656425+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258033 | TRUE | TRUE | 2025-10-16T01:27:44.1656425+00:00 | 2025-10-16T09:27:44.1656425+08:00 | #44216 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 6.0 | TRUE |  | 2027-02-03T23:00:00+00:00 | 2027-02-04T01:00:00+00:00 | 2027-02-04T07:00:00+08:00 | 2027-02-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44217 | 2021-11-23T07:24:56+00:00 | 2021-11-23T15:24:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:44.3418711+00:00 | 2025-10-16T09:27:44.3418711+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258035 | TRUE | TRUE | 2025-10-16T01:27:44.3418711+00:00 | 2025-10-16T09:27:44.3418711+08:00 | #44217 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 6.0 | TRUE |  | 2027-02-03T23:00:00+00:00 | 2027-02-04T01:00:00+00:00 | 2027-02-04T07:00:00+08:00 | 2027-02-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44195 | 2021-11-23T07:02:07+00:00 | 2021-11-23T15:02:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:44.7120086+00:00 | 2025-10-16T09:27:44.7120086+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258039 | TRUE | TRUE | 2025-10-16T01:27:44.7120086+00:00 | 2025-10-16T09:27:44.7120086+08:00 | #44195 - BM4: 2hrs - PLANT: BM4 | 8.0 | TRUE |  | 2027-03-03T23:00:00+00:00 | 2027-03-04T01:00:00+00:00 | 2027-03-04T07:00:00+08:00 | 2027-03-04T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44220 | 2021-11-23T07:25:01+00:00 | 2021-11-23T15:25:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:44.9114341+00:00 | 2025-10-16T09:27:44.9114341+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258041 | TRUE | TRUE | 2025-10-16T01:27:44.9114341+00:00 | 2025-10-16T09:27:44.9114341+08:00 | #44220 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-03-03T23:00:00+00:00 | 2027-03-04T01:00:00+00:00 | 2027-03-04T07:00:00+08:00 | 2027-03-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44221 | 2021-11-23T07:25:05+00:00 | 2021-11-23T15:25:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:45.1111034+00:00 | 2025-10-16T09:27:45.1111034+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258043 | TRUE | TRUE | 2025-10-16T01:27:45.1111034+00:00 | 2025-10-16T09:27:45.1111034+08:00 | #44221 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-03-03T23:00:00+00:00 | 2027-03-04T01:00:00+00:00 | 2027-03-04T07:00:00+08:00 | 2027-03-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44197 | 2021-11-23T07:03:03+00:00 | 2021-11-23T15:03:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:45.5249477+00:00 | 2025-10-16T09:27:45.5249477+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258047 | TRUE | TRUE | 2025-10-16T01:27:45.5249477+00:00 | 2025-10-16T09:27:45.5249477+08:00 | #44197 - BM4: 2hrs - PLANT: BM4 | 8.0 | TRUE |  | 2027-05-05T23:00:00+00:00 | 2027-05-06T01:00:00+00:00 | 2027-05-06T07:00:00+08:00 | 2027-05-06T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44224 | 2021-11-23T07:25:10+00:00 | 2021-11-23T15:25:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:45.7351916+00:00 | 2025-10-16T09:27:45.7351916+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258049 | TRUE | TRUE | 2025-10-16T01:27:45.7351916+00:00 | 2025-10-16T09:27:45.7351916+08:00 | #44224 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-05-05T23:00:00+00:00 | 2027-05-06T01:00:00+00:00 | 2027-05-06T07:00:00+08:00 | 2027-05-06T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44203 | 2021-11-23T07:06:33+00:00 | 2021-11-23T15:06:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:48.4969018+00:00 | 2025-10-16T09:27:48.4969018+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258071 | TRUE | TRUE | 2025-10-16T01:27:48.4969018+00:00 | 2025-10-16T09:27:48.4969018+08:00 | #44203 - BM4: 2hrs - PLANT: BM4 | 8.0 | TRUE |  | 2027-09-01T23:00:00+00:00 | 2027-09-02T01:00:00+00:00 | 2027-09-02T07:00:00+08:00 | 2027-09-02T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44236 | 2021-11-23T07:25:30+00:00 | 2021-11-23T15:25:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:48.7738553+00:00 | 2025-10-16T09:27:48.7738553+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258073 | TRUE | TRUE | 2025-10-16T01:27:48.7738553+00:00 | 2025-10-16T09:27:48.7738553+08:00 | #44236 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-09-01T23:00:00+00:00 | 2027-09-02T01:00:00+00:00 | 2027-09-02T07:00:00+08:00 | 2027-09-02T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44237 | 2021-11-23T07:25:31+00:00 | 2021-11-23T15:25:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:49.0795055+00:00 | 2025-10-16T09:27:49.0795055+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258075 | TRUE | TRUE | 2025-10-16T01:27:49.0795055+00:00 | 2025-10-16T09:27:49.0795055+08:00 | #44237 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-09-01T23:00:00+00:00 | 2027-09-02T01:00:00+00:00 | 2027-09-02T07:00:00+08:00 | 2027-09-02T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44166 | 2021-11-23T03:34:28+00:00 | 2021-11-23T11:34:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:49.3699818+00:00 | 2025-10-16T09:27:49.3699818+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258077 | TRUE | TRUE | 2025-10-16T01:27:49.3699818+00:00 | 2025-10-16T09:27:49.3699818+08:00 | #44166 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 8.0 | TRUE |  | 2027-09-09T20:00:00+00:00 | 2027-09-10T08:00:00+00:00 | 2027-09-10T04:00:00+08:00 | 2027-09-10T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut. | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44206 | 2021-11-23T07:24:42+00:00 | 2021-11-23T15:24:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:49.6722399+00:00 | 2025-10-16T09:27:49.6722399+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258079 | TRUE | TRUE | 2025-10-16T01:27:49.6722399+00:00 | 2025-10-16T09:27:49.6722399+08:00 | #44206 - BM4: 2hrs - PLANT: BM4 | 7.0 | TRUE |  | 2027-11-03T23:00:00+00:00 | 2027-11-04T01:00:00+00:00 | 2027-11-04T07:00:00+08:00 | 2027-11-04T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44207 | 2021-11-23T07:24:43+00:00 | 2021-11-23T15:24:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:49.9752107+00:00 | 2025-10-16T09:27:49.9752107+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258081 | TRUE | TRUE | 2025-10-16T01:27:49.9752107+00:00 | 2025-10-16T09:27:49.9752107+08:00 | #44207 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-11-03T23:00:00+00:00 | 2027-11-04T01:00:00+00:00 | 2027-11-04T07:00:00+08:00 | 2027-11-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44208 | 2021-11-23T07:24:43+00:00 | 2021-11-23T15:24:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:50.3005526+00:00 | 2025-10-16T09:27:50.3005526+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258083 | TRUE | TRUE | 2025-10-16T01:27:50.3005526+00:00 | 2025-10-16T09:27:50.3005526+08:00 | #44208 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-11-03T23:00:00+00:00 | 2027-11-04T01:00:00+00:00 | 2027-11-04T07:00:00+08:00 | 2027-11-04T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44167 | 2021-11-23T03:35:36+00:00 | 2021-11-23T11:35:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:50.6249487+00:00 | 2025-10-16T09:27:50.6249487+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258085 | TRUE | TRUE | 2025-10-16T01:27:50.6249487+00:00 | 2025-10-16T09:27:50.6249487+08:00 | #44167 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 8.0 | TRUE |  | 2027-11-11T20:00:00+00:00 | 2027-11-12T08:00:00+00:00 | 2027-11-12T04:00:00+08:00 | 2027-11-12T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut. | IAM Refresh |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44209 | 2021-11-23T07:24:45+00:00 | 2021-11-23T15:24:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:50.9532481+00:00 | 2025-10-16T09:27:50.9532481+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258087 | TRUE | TRUE | 2025-10-16T01:27:50.9532481+00:00 | 2025-10-16T09:27:50.9532481+08:00 | #44209 - BM4: 2hrs - PLANT: BM4 | 7.0 | TRUE |  | 2027-12-01T23:00:00+00:00 | 2027-12-02T01:00:00+00:00 | 2027-12-02T07:00:00+08:00 | 2027-12-02T09:00:00+08:00 |  |  |  |  | 2.00 | Common Plant Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44210 | 2021-11-23T07:24:46+00:00 | 2021-11-23T15:24:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:51.2824607+00:00 | 2025-10-16T09:27:51.2824607+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258089 | TRUE | TRUE | 2025-10-16T01:27:51.2824607+00:00 | 2025-10-16T09:27:51.2824607+08:00 | #44210 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 01 | 7.0 | TRUE |  | 2027-12-01T23:00:00+00:00 | 2027-12-02T01:00:00+00:00 | 2027-12-02T07:00:00+08:00 | 2027-12-02T09:00:00+08:00 |  |  |  |  | 2.00 | PC1 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44211 | 2021-11-23T07:24:46+00:00 | 2021-11-23T15:24:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T01:27:51.6193684+00:00 | 2025-10-16T09:27:51.6193684+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 258091 | TRUE | TRUE | 2025-10-16T01:27:51.6193684+00:00 | 2025-10-16T09:27:51.6193684+08:00 | #44211 - BM4: 2hrs - CRUSHER - PRIMARY: BM4 02 | 7.0 | TRUE |  | 2027-12-01T23:00:00+00:00 | 2027-12-02T01:00:00+00:00 | 2027-12-02T07:00:00+08:00 | 2027-12-02T09:00:00+08:00 |  |  |  |  | 2.00 | PC2 Fortnightly mini shut | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | BM4 | Australia/Perth
44934 | 2021-11-30T08:28:29+00:00 | 2021-11-30T16:28:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T00:35:31.1931113+00:00 | 2025-10-16T08:35:31.1931113+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257976 | TRUE | TRUE | 2025-10-16T00:35:31.1931113+00:00 | 2025-10-16T08:35:31.1931113+08:00 | #44934 - MTP: 168hrs - TRAIN LOADOUT: MTP FINES | 9.0 | TRUE |  | 2027-09-08T11:00:00+00:00 | 2027-09-15T11:00:00+00:00 | 2027-09-08T19:00:00+08:00 | 2027-09-15T19:00:00+08:00 |  |  |  |  | 168.00 | Fines TLO shut. | Change to aline with the new IAM |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
44722 | 2021-11-26T04:26:47+00:00 | 2021-11-26T12:26:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T04:32:04.4515859+00:00 | 2026-03-13T12:32:04.4515859+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 321182 | TRUE | TRUE | 2026-03-13T04:32:04.4515859+00:00 | 2026-03-13T12:32:04.4515859+08:00 | #44722 - RVA: 192hrs - PLANT: RVA WET | 11.2 | TRUE |  | 2027-05-22T03:00:00+00:00 | 2027-05-30T03:00:00+00:00 | 2027-05-22T11:00:00+08:00 | 2027-05-30T11:00:00+08:00 |  |  |  |  | 192.00 | RVA WET PLANT SHUT - required for trunnion alignments C/O Apron Feeder Components AF2402 |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | RVA | Australia/Perth
41281 | 2021-05-19T07:45:28+00:00 | 2021-05-19T15:45:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-20T05:22:46.5697719+00:00 | 2026-03-20T13:22:46.5697719+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 322602 | TRUE | TRUE | 2026-03-20T05:22:46.5697719+00:00 | 2026-03-20T13:22:46.5697719+08:00 | #41281 - HD1: 84hrs - TRAIN LOADOUT: HD1 | 13.1 | TRUE |  | 2027-03-16T16:00:00+00:00 | 2027-03-20T04:00:00+00:00 | 2027-03-17T00:00:00+08:00 | 2027-03-20T12:00:00+08:00 |  |  |  |  | 84.00 | HD1 TLO Shut |  |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a7aaecea-901b-42c3-bfe5-631002e540c0", "emailAddress": "Ryan.Smith2@riotinto.com", "displayName": "Ryan Smith"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | HD1 | Australia/Perth
64263 | 2024-09-18T01:55:24+00:00 | 2024-09-18T09:55:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-20T06:18:36.8941552+00:00 | 2026-03-20T14:18:36.8941552+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 322630 | TRUE | TRUE | 2026-03-20T06:18:36.8941552+00:00 | 2026-03-20T14:18:36.8941552+08:00 | #64263 - HD4: 24hrs - HD4 TOTAL POWER OUTAGE PLT & TLO | 5.1 | TRUE |  | 2027-06-13T23:00:00+00:00 | 2027-06-14T23:00:00+00:00 | 2027-06-14T07:00:00+08:00 | 2027-06-15T07:00:00+08:00 |  |  |  |  | 24.00 | Total HD1 and HD4 Power Outage for 220KV Transmission line relocation project. Legal obligation to move it, or else RTIO will be up for legal action with BHP, BHP completing their work around May 2027. They need to do their work first. |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44412, "shutVersionId": 329407, "title": "#44412 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH", "startDatetimeUTC": "2027-06-10T10:00:00+00:00", "endDatetimeUTC": "2027-06-15T10:00:00+00:00"}}] | [] | [{"code": "P-0510529", "name": "Greater Hope Downs 220KV Transmission Line Relocation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | HD4 | Australia/Perth
41737 | 2021-05-25T07:22:16+00:00 | 2021-05-25T15:22:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-19T23:00:08.0652432+00:00 | 2026-03-20T07:00:08.0652432+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 322423 | TRUE | TRUE | 2026-03-19T23:00:08.0652432+00:00 | 2026-03-20T07:00:08.0652432+08:00 | #41737 - MTP: 168hrs - TRAIN LOADOUT: MTP FINES | 10.0 | TRUE |  | 2027-03-10T11:00:00+00:00 | 2027-03-17T11:00:00+00:00 | 2027-03-10T19:00:00+08:00 | 2027-03-17T19:00:00+08:00 |  |  |  |  | 168.00 | Fines TLO shut | Approved in error any change to strategy requires an MOC |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
44336 | 2021-11-23T10:28:42+00:00 | 2021-11-23T18:28:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-02-06T02:57:57.5546469+00:00 | 2026-02-06T10:57:57.5546469+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 286238 | TRUE | TRUE | 2026-02-06T02:57:57.5546469+00:00 | 2026-02-06T10:57:57.5546469+08:00 | #44336 - WAN: 84hrs - TRAIN LOADOUT: WAN | 11.1 | TRUE |  | 2027-10-20T10:30:00+00:00 | 2027-10-23T22:30:00+00:00 | 2027-10-20T18:30:00+08:00 | 2027-10-24T06:30:00+08:00 |  |  |  |  | 84.00 | Standard IMS 84hrs Maintenance. |  |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WAN | Australia/Perth
65353 | 2024-10-14T05:17:58+00:00 | 2024-10-14T13:17:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-20T06:26:37.9118275+00:00 | 2026-10-20T14:26:37.9118275+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 336228 | TRUE | TRUE | 2026-10-20T06:26:37.9118275+00:00 | 2026-10-20T14:26:37.9118275+08:00 | #65353 - BM4: 405.5hrs - BS1 PROJECT - SHUT #9 PC2 | 8.0 | TRUE |  | 2027-03-20T06:30:00+00:00 | 2027-04-06T04:00:00+00:00 | 2027-03-20T14:30:00+08:00 | 2027-04-06T12:00:00+08:00 |  |  |  |  | 405.50 | BS1 BCV210 drive base remediation and further project works | Extension was supposed to be front end. ISP approved from a capacity perspective. Accommodation and labour availability checked and confirmed by Craig McDonald |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [{"code": "X", "name": "BS1 Project", "projectTeam": {"name": "D&T"}, "totalProjectTime": "336"}] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
47373 | 2022-08-10T07:18:55+00:00 | 2022-08-10T15:18:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-01-22T03:05:29.2793284+00:00 | 2026-01-22T11:05:29.2793284+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 284420 | TRUE | TRUE | 2026-01-22T03:05:29.2793284+00:00 | 2026-01-22T11:05:29.2793284+08:00 | #47373 - HD1: 84hrs - TRAIN LOADOUT: HD1 | 8.2 | TRUE |  | 2027-06-15T16:00:00+00:00 | 2027-06-19T04:00:00+00:00 | 2027-06-16T00:00:00+08:00 | 2027-06-19T12:00:00+08:00 |  |  |  |  | 84.00 | HD1 TLO Shut |  |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a7aaecea-901b-42c3-bfe5-631002e540c0", "emailAddress": "Ryan.Smith2@riotinto.com", "displayName": "Ryan Smith"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | HD1 | Australia/Perth
54971 | 2023-04-19T00:21:48+00:00 | 2023-04-19T08:21:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-29T07:13:13.5543115+00:00 | 2025-10-29T15:13:13.5543115+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266091 | TRUE | TRUE | 2025-10-29T07:13:13.5543115+00:00 | 2025-10-29T15:13:13.5543115+08:00 | #54971 - MDO: 24hrs - PLANT: MDO | 5.0 | TRUE |  | 2027-03-26T16:00:00+00:00 | 2027-03-27T16:00:00+00:00 | 2027-03-27T00:00:00+08:00 | 2027-03-28T00:00:00+08:00 |  |  |  |  | 24.00 | MDO PLT Pitstop for screen panel change out urgent works and 6wkly stat inspections. NO external labour required. Panel B crew | IAM Refresh |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "92e03300-186e-4df2-ae9a-ed947e5d5622", "emailAddress": "Jeff.sadler@riotinto.com", "displayName": "Jeff Sadler"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MDO | Australia/Perth
54972 | 2023-04-19T00:21:48+00:00 | 2023-04-19T08:21:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-29T07:13:13.8586876+00:00 | 2025-10-29T15:13:13.8586876+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266093 | TRUE | TRUE | 2025-10-29T07:13:13.8586876+00:00 | 2025-10-29T15:13:13.8586876+08:00 | #54972 - MDO: 24hrs - PLANT: MDO | 5.0 | TRUE |  | 2027-06-25T16:00:00+00:00 | 2027-06-26T16:00:00+00:00 | 2027-06-26T00:00:00+08:00 | 2027-06-27T00:00:00+08:00 |  |  |  |  | 24.00 | MDO PLT Pitstop for screen panel change out urgent works and 6wkly stat inspections. NO external labour required. Panel B crew | IAM Refresh |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "92e03300-186e-4df2-ae9a-ed947e5d5622", "emailAddress": "Jeff.sadler@riotinto.com", "displayName": "Jeff Sadler"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MDO | Australia/Perth
54933 | 2023-04-19T00:20:34+00:00 | 2023-04-19T08:20:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-29T07:13:14.158944+00:00 | 2025-10-29T15:13:14.158944+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266095 | TRUE | TRUE | 2025-10-29T07:13:14.158944+00:00 | 2025-10-29T15:13:14.158944+08:00 | #54933 - MDO: 24hrs - PLANT: MDO | 5.0 | TRUE |  | 2027-09-24T16:00:00+00:00 | 2027-09-25T16:00:00+00:00 | 2027-09-25T00:00:00+08:00 | 2027-09-26T00:00:00+08:00 |  |  |  |  | 24.00 | MDO PLT Pitstop for screen panel change out urgent works and 6wkly stat inspections. NO external labour required. Panel B crew | IAM Refresh |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "92e03300-186e-4df2-ae9a-ed947e5d5622", "emailAddress": "Jeff.sadler@riotinto.com", "displayName": "Jeff Sadler"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MDO | Australia/Perth
54934 | 2023-04-19T00:20:37+00:00 | 2023-04-19T08:20:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-29T07:13:14.4881265+00:00 | 2025-10-29T15:13:14.4881265+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 266097 | TRUE | TRUE | 2025-10-29T07:13:14.4881265+00:00 | 2025-10-29T15:13:14.4881265+08:00 | #54934 - MDO: 24hrs - PLANT: MDO | 5.0 | TRUE |  | 2027-12-24T16:00:00+00:00 | 2027-12-25T16:00:00+00:00 | 2027-12-25T00:00:00+08:00 | 2027-12-26T00:00:00+08:00 |  |  |  |  | 24.00 | MDO PLT Pitstop for screen panel change out urgent works and 6wkly stat inspections. NO external labour required. Panel B crew | IAM Refresh |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "92e03300-186e-4df2-ae9a-ed947e5d5622", "emailAddress": "Jeff.sadler@riotinto.com", "displayName": "Jeff Sadler"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MDO | Australia/Perth
45340 | 2021-12-13T08:25:10+00:00 | 2021-12-13T16:25:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:19.3668433+00:00 | 2025-10-30T14:09:19.3668433+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267869 | TRUE | TRUE | 2025-10-30T06:09:19.3668433+00:00 | 2025-10-30T14:09:19.3668433+08:00 | #45340 - NBWT: 108hrs - MODULE - PLANT: NBWT 01 | 7.0 | TRUE |  | 2027-01-28T11:30:00+00:00 | 2027-02-01T23:30:00+00:00 | 2027-01-28T19:30:00+08:00 | 2027-02-02T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 1 maintenance | IAM Refresh |  | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45341 | 2021-12-13T08:25:10+00:00 | 2021-12-13T16:25:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:19.6372559+00:00 | 2025-10-30T14:09:19.6372559+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267871 | TRUE | TRUE | 2025-10-30T06:09:19.6372559+00:00 | 2025-10-30T14:09:19.6372559+08:00 | #45341 - NBWT: 108hrs - MODULE - PLANT: NBWT 02 | 7.0 | TRUE |  | 2027-01-28T17:30:00+00:00 | 2027-02-02T05:30:00+00:00 | 2027-01-29T01:30:00+08:00 | 2027-02-02T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 2 maintenance | IAM Refresh |  | [{"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45384 | 2021-12-13T08:26:24+00:00 | 2021-12-13T16:26:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:19.9029144+00:00 | 2025-10-30T14:09:19.9029144+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267873 | TRUE | TRUE | 2025-10-30T06:09:19.9029144+00:00 | 2025-10-30T14:09:19.9029144+08:00 | #45384 - NBWT: 108hrs - MODULE - PLANT: NBWT 03 | 7.0 | TRUE |  | 2027-02-04T11:30:00+00:00 | 2027-02-08T23:30:00+00:00 | 2027-02-04T19:30:00+08:00 | 2027-02-09T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 3 maintenance | IAM Refresh |  | [{"equipmentGUID": "1814b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD03", "name": "Module - Plant: NBWT 03", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45385 | 2021-12-13T08:26:25+00:00 | 2021-12-13T16:26:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:20.1691345+00:00 | 2025-10-30T14:09:20.1691345+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267875 | TRUE | TRUE | 2025-10-30T06:09:20.1691345+00:00 | 2025-10-30T14:09:20.1691345+08:00 | #45385 - NBWT: 108hrs - MODULE - PLANT: NBWT 04 | 7.0 | TRUE |  | 2027-02-04T17:30:00+00:00 | 2027-02-09T05:30:00+00:00 | 2027-02-05T01:30:00+08:00 | 2027-02-09T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 4 maintenance | IAM Refresh |  | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45343 | 2021-12-13T08:25:15+00:00 | 2021-12-13T16:25:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:20.457684+00:00 | 2025-10-30T14:09:20.457684+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267877 | TRUE | TRUE | 2025-10-30T06:09:20.457684+00:00 | 2025-10-30T14:09:20.457684+08:00 | #45343 - NBWT: 108hrs - MODULE - PLANT: NBWT 02 | 7.0 | TRUE |  | 2027-04-29T17:30:00+00:00 | 2027-05-04T05:30:00+00:00 | 2027-04-30T01:30:00+08:00 | 2027-05-04T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 2 maintenance | IAM Refresh |  | [{"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45345 | 2021-12-13T08:25:19+00:00 | 2021-12-13T16:25:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:20.7479221+00:00 | 2025-10-30T14:09:20.7479221+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267879 | TRUE | TRUE | 2025-10-30T06:09:20.7479221+00:00 | 2025-10-30T14:09:20.7479221+08:00 | #45345 - NBWT: 108hrs - MODULE - PLANT: NBWT 02 | 7.0 | TRUE |  | 2027-07-29T17:30:00+00:00 | 2027-08-03T05:30:00+00:00 | 2027-07-30T01:30:00+08:00 | 2027-08-03T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 2 maintenance | IAM Refresh |  | [{"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45388 | 2021-12-13T08:26:30+00:00 | 2021-12-13T16:26:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:21.0454595+00:00 | 2025-10-30T14:09:21.0454595+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267881 | TRUE | TRUE | 2025-10-30T06:09:21.0454595+00:00 | 2025-10-30T14:09:21.0454595+08:00 | #45388 - NBWT: 108hrs - MODULE - PLANT: NBWT 03 | 7.0 | TRUE |  | 2027-08-05T11:30:00+00:00 | 2027-08-09T23:30:00+00:00 | 2027-08-05T19:30:00+08:00 | 2027-08-10T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 3 maintenance | IAM Refresh |  | [{"equipmentGUID": "1814b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD03", "name": "Module - Plant: NBWT 03", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45348 | 2021-12-13T08:25:24+00:00 | 2021-12-13T16:25:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:21.3585758+00:00 | 2025-10-30T14:09:21.3585758+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267883 | TRUE | TRUE | 2025-10-30T06:09:21.3585758+00:00 | 2025-10-30T14:09:21.3585758+08:00 | #45348 - NBWT: 108hrs - MODULE - PLANT: NBWT 01 | 6.0 | TRUE |  | 2028-01-27T11:30:00+00:00 | 2028-01-31T23:30:00+00:00 | 2028-01-27T19:30:00+08:00 | 2028-02-01T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 1 maintenance | IAM Refresh |  | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
45349 | 2021-12-13T08:25:25+00:00 | 2021-12-13T16:25:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-30T06:09:21.6710418+00:00 | 2025-10-30T14:09:21.6710418+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 267885 | TRUE | TRUE | 2025-10-30T06:09:21.6710418+00:00 | 2025-10-30T14:09:21.6710418+08:00 | #45349 - NBWT: 108hrs - MODULE - PLANT: NBWT 02 | 6.0 | TRUE |  | 2028-01-27T17:30:00+00:00 | 2028-02-01T05:30:00+00:00 | 2028-01-28T01:30:00+08:00 | 2028-02-01T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 2 maintenance | IAM Refresh |  | [{"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | NBWT | Australia/Perth
48163 | 2022-09-15T06:09:43+00:00 | 2022-09-15T14:09:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-31T07:35:09.016837+00:00 | 2025-10-31T15:35:09.016837+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 269441 | TRUE | TRUE | 2025-10-31T07:35:09.016837+00:00 | 2025-10-31T15:35:09.016837+08:00 | #48163 - PDO: 132hrs - RECLAIMER: PDO 01 | 8.0 | FALSE |  | 2028-01-12T22:00:00+00:00 | 2028-01-18T10:00:00+00:00 | 2028-01-13T06:00:00+08:00 | 2028-01-18T18:00:00+08:00 |  |  |  |  | 132.00 | Reclaimer 1 Shut | IAM Refresh |  | [{"equipmentGUID": "fe61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC01", "name": "Reclaimer: PDO 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "emailAddress": "Ola.Hempseed@riotinto.com", "displayName": "Hempseed, Ola (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PDO | Australia/Perth
48321 | 2022-09-16T02:26:16+00:00 | 2022-09-16T10:26:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-31T08:22:22.5524834+00:00 | 2025-10-31T16:22:22.5524834+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 269588 | TRUE | TRUE | 2025-10-31T08:22:22.5524834+00:00 | 2025-10-31T16:22:22.5524834+08:00 | #48321 - PDO: 78hrs - MODULE - PLANT: PDO FINES A | 5.0 | FALSE |  | 2028-01-03T22:00:00+00:00 | 2028-01-07T04:00:00+00:00 | 2028-01-04T06:00:00+08:00 | 2028-01-07T12:00:00+08:00 |  |  |  |  | 78.00 | PLT FPLT MOD A | IAM Refresh |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "emailAddress": "Ola.Hempseed@riotinto.com", "displayName": "Hempseed, Ola (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PDO | Australia/Perth
48318 | 2022-09-16T02:11:21+00:00 | 2022-09-16T10:11:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-31T08:29:21.233519+00:00 | 2025-10-31T16:29:21.233519+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 269660 | TRUE | TRUE | 2025-10-31T08:29:21.233519+00:00 | 2025-10-31T16:29:21.233519+08:00 | #48318 - PDO: 84hrs - MODULE - PLANT: PDO FINES B | 5.0 | FALSE |  | 2028-01-03T22:00:00+00:00 | 2028-01-07T10:00:00+00:00 | 2028-01-04T06:00:00+08:00 | 2028-01-07T18:00:00+08:00 |  |  |  |  | 84.00 | PLT FPLT MOD B | IAM Refresh |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "emailAddress": "Ola.Hempseed@riotinto.com", "displayName": "Hempseed, Ola (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PDO | Australia/Perth
48319 | 2022-09-16T02:12:08+00:00 | 2022-09-16T10:12:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-31T08:35:44.3323157+00:00 | 2025-10-31T16:35:44.3323157+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 269732 | TRUE | TRUE | 2025-10-31T08:35:44.3323157+00:00 | 2025-10-31T16:35:44.3323157+08:00 | #48319 - PDO: 84hrs - MODULE - PLANT: PDO FINES C | 5.0 | FALSE |  | 2028-01-06T22:00:00+00:00 | 2028-01-10T10:00:00+00:00 | 2028-01-07T06:00:00+08:00 | 2028-01-10T18:00:00+08:00 |  |  |  |  | 84.00 | PLT FPLT MOD C | IAM Refresh |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "emailAddress": "Ola.Hempseed@riotinto.com", "displayName": "Hempseed, Ola (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PDO | Australia/Perth
48322 | 2022-09-16T02:26:57+00:00 | 2022-09-16T10:26:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-31T08:40:46.2122582+00:00 | 2025-10-31T16:40:46.2122582+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 269804 | TRUE | TRUE | 2025-10-31T08:40:46.2122582+00:00 | 2025-10-31T16:40:46.2122582+08:00 | #48322 - PDO: 78hrs - MODULE - PLANT: PDO FINES D | 5.0 | FALSE |  | 2028-01-07T04:00:00+00:00 | 2028-01-10T10:00:00+00:00 | 2028-01-07T12:00:00+08:00 | 2028-01-10T18:00:00+08:00 |  |  |  |  | 78.00 | PLT FPLT MOD D | IAM Refresh |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "emailAddress": "Ola.Hempseed@riotinto.com", "displayName": "Hempseed, Ola (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PDO | Australia/Perth
45163 | 2021-12-01T06:10:07+00:00 | 2021-12-01T14:10:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:30:11.2328015+00:00 | 2025-11-03T11:30:11.2328015+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270122 | TRUE | TRUE | 2025-11-03T03:30:11.2328015+00:00 | 2025-11-03T11:30:11.2328015+08:00 | #45163 - YAN: 120hrs - TRAIN LOADOUT: YAN 02 | 9.0 | TRUE |  | 2028-01-27T11:00:00+00:00 | 2028-02-01T11:00:00+00:00 | 2028-01-27T19:00:00+08:00 | 2028-02-01T19:00:00+08:00 |  |  |  |  | 120.00 | TLO2 and Reclaimer 2 Shut | IAM Refresh |  | [{"equipmentGUID": "5ae5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO02", "name": "Train Loadout: YAN 02", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
45162 | 2021-12-01T06:09:15+00:00 | 2021-12-01T14:09:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:30:12.522089+00:00 | 2025-11-03T11:30:12.522089+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270123 | TRUE | TRUE | 2025-11-03T03:30:12.522089+00:00 | 2025-11-03T11:30:12.522089+08:00 | #45162 - YAN: 120hrs - TRAIN LOADOUT: YAN 01 | 9.0 | TRUE |  | 2028-01-28T11:00:00+00:00 | 2028-02-02T11:00:00+00:00 | 2028-01-28T19:00:00+08:00 | 2028-02-02T19:00:00+08:00 |  |  |  |  | 120.00 | TLO1 and Reclaimer 1 Shut. | IAM Refresh |  | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5d241ce5-dfd0-4f00-b422-5aa5c40554aa", "emailAddress": "Ian.Westcott@riotinto.com", "displayName": "Ian Westcott"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
44964 | 2021-12-01T00:53:41+00:00 | 2021-12-01T08:53:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-27T03:04:57.4299487+00:00 | 2025-10-27T11:04:57.4299487+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 264250 | TRUE | TRUE | 2025-10-27T03:04:57.4299487+00:00 | 2025-10-27T11:04:57.4299487+08:00 | #44964 - WTS: 168hrs - CONVEYOR: WTS1 OVERLAND & CRUSHER - PRIMARY: WTS1 03 | 10.0 | TRUE |  | 2026-11-30T11:00:00+00:00 | 2026-12-07T11:00:00+00:00 | 2026-11-30T19:00:00+08:00 | 2026-12-07T19:00:00+08:00 |  |  |  |  | 168.00 | WTS1 PLT PC4 | Removed from group shut as it has its own shut now going down a bit earlier that the rest |  | [{"equipmentGUID": "185e242f-6f9d-ee11-a847-000d3acacefd", "code": "WTS1CVOLCV", "name": "Conveyor: WTS1 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | WTS | Australia/Perth
44853 | 2021-11-30T04:02:57+00:00 | 2021-11-30T12:02:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:29:40.6527865+00:00 | 2025-11-03T11:29:40.6527865+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270092 | TRUE | TRUE | 2025-11-03T03:29:40.6527865+00:00 | 2025-11-03T11:29:40.6527865+08:00 | #44853 - YAN: 120hrs - TRAIN LOADOUT: YAN 02 | 8.0 | TRUE |  | 2027-04-29T11:00:00+00:00 | 2027-05-04T11:00:00+00:00 | 2027-04-29T19:00:00+08:00 | 2027-05-04T19:00:00+08:00 |  |  |  |  | 120.00 | TLO2 and Reclaimer 2 Shut | IAM Refresh |  | [{"equipmentGUID": "5ae5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO02", "name": "Train Loadout: YAN 02", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5d241ce5-dfd0-4f00-b422-5aa5c40554aa", "emailAddress": "Ian.Westcott@riotinto.com", "displayName": "Ian Westcott"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
54739 | 2023-03-24T11:15:25+00:00 | 2023-03-24T19:15:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:29:51.1742503+00:00 | 2025-11-03T11:29:51.1742503+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270103 | TRUE | TRUE | 2025-11-03T03:29:51.1742503+00:00 | 2025-11-03T11:29:51.1742503+08:00 | #54739 - YAN: 120hrs - TRAIN LOADOUT: YAN 02 | 7.0 | TRUE |  | 2027-07-29T11:00:00+00:00 | 2027-08-03T11:00:00+00:00 | 2027-07-29T19:00:00+08:00 | 2027-08-03T19:00:00+08:00 |  |  |  |  | 120.00 | TLO2 and Reclaimer 2 Shut | IAM Refresh |  | [{"equipmentGUID": "5ae5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO02", "name": "Train Loadout: YAN 02", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5d241ce5-dfd0-4f00-b422-5aa5c40554aa", "emailAddress": "Ian.Westcott@riotinto.com", "displayName": "Ian Westcott"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
44854 | 2021-11-30T04:02:58+00:00 | 2021-11-30T12:02:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:30:01.3481595+00:00 | 2025-11-03T11:30:01.3481595+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270113 | TRUE | TRUE | 2025-11-03T03:30:01.3481595+00:00 | 2025-11-03T11:30:01.3481595+08:00 | #44854 - YAN: 120hrs - TRAIN LOADOUT: YAN 02 | 9.0 | TRUE |  | 2027-10-28T11:00:00+00:00 | 2027-11-02T11:00:00+00:00 | 2027-10-28T19:00:00+08:00 | 2027-11-02T19:00:00+08:00 |  |  |  |  | 120.00 | TLO2 and Reclaimer 2 Shut | IAM Refresh |  | [{"equipmentGUID": "5ae5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO02", "name": "Train Loadout: YAN 02", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5d241ce5-dfd0-4f00-b422-5aa5c40554aa", "emailAddress": "Ian.Westcott@riotinto.com", "displayName": "Ian Westcott"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bcc4e7b-58c8-4536-879a-3c2ca5e8d79b", "emailAddress": "roger.pargin@riotinto.com", "displayName": "Roger Pargin"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
44839 | 2021-11-30T04:02:32+00:00 | 2021-11-30T12:02:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-03T03:30:02.9373574+00:00 | 2025-11-03T11:30:02.9373574+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 270114 | TRUE | TRUE | 2025-11-03T03:30:02.9373574+00:00 | 2025-11-03T11:30:02.9373574+08:00 | #44839 - YAN: 120hrs - TRAIN LOADOUT: YAN 01 | 8.0 | TRUE |  | 2027-10-29T11:00:00+00:00 | 2027-11-03T11:00:00+00:00 | 2027-10-29T19:00:00+08:00 | 2027-11-03T19:00:00+08:00 |  |  |  |  | 120.00 | TLO1 and Reclaimer 1 Shut | IAM Refresh |  | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5d241ce5-dfd0-4f00-b422-5aa5c40554aa", "emailAddress": "Ian.Westcott@riotinto.com", "displayName": "Ian Westcott"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2b745019-6c8b-47f3-bf03-dd14f2dc18f8", "emailAddress": "Trent.Hodges@riotinto.com", "displayName": "Trent Hodges"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | YAN | Australia/Perth
45706 | 2022-01-20T09:40:51+00:00 | 2022-01-20T17:40:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-13T07:23:21.0566208+00:00 | 2025-11-13T15:23:21.0566208+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 275119 | TRUE | TRUE | 2025-11-13T07:23:21.0566208+00:00 | 2025-11-13T15:23:21.0566208+08:00 | #45706 - PPT: 130hrs - RECLAIMER: PPT 2P | 8.0 | FALSE |  | 2028-01-02T22:00:00+00:00 | 2028-01-08T08:00:00+00:00 | 2028-01-03T06:00:00+08:00 | 2028-01-08T16:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | IAM Refresh |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 82856, "shutVersionId": 327906, "title": "#82856 - PPT: 130hrs - PPSS - REC2P SMPT STRUCTURAL MODIFICATIONS", "startDatetimeUTC": "2028-01-02T22:00:00+00:00", "endDatetimeUTC": "2028-01-08T08:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
45683 | 2022-01-20T08:57:41+00:00 | 2022-01-20T16:57:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-14T01:19:44.3692189+00:00 | 2025-11-14T09:19:44.3692189+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 275397 | TRUE | TRUE | 2025-11-14T01:19:44.3692189+00:00 | 2025-11-14T09:19:44.3692189+08:00 | #45683 - PPT: 106hrs - STACKER: PPT 3P | 4.0 | FALSE |  | 2027-12-05T22:00:00+00:00 | 2027-12-10T08:00:00+00:00 | 2027-12-06T06:00:00+08:00 | 2027-12-10T16:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance 107P | IAM Refresh |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
45679 | 2022-01-20T08:47:37+00:00 | 2022-01-20T16:47:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-14T03:49:37.2201932+00:00 | 2025-11-14T11:49:37.2201932+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 275647 | TRUE | TRUE | 2025-11-14T03:49:37.2201932+00:00 | 2025-11-14T11:49:37.2201932+08:00 | #45679 - PPT: 106hrs - STACKER: PPT 6P | 6.0 | FALSE |  | 2027-08-08T22:00:00+00:00 | 2027-08-13T08:00:00+00:00 | 2027-08-09T06:00:00+08:00 | 2027-08-13T16:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance 103P, 3P | IAM Refresh |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
83685 | 2026-08-12T04:49:02.2892818+00:00 | 2026-08-12T12:49:02.2892818+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-26T02:22:02.1166891+00:00 | 2026-08-26T10:22:02.1166891+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 331824 | TRUE | TRUE | 2026-08-26T02:22:02.1166891+00:00 | 2026-08-26T10:22:02.1166891+08:00 | #83685 - CLA: 172hrs - STK1 LUFF CYLINDER C/O | 1.1 | TRUE |  | 2027-08-18T10:00:00+00:00 | 2027-08-25T14:00:00+00:00 | 2027-08-18T18:00:00+08:00 | 2027-08-25T22:00:00+08:00 |  |  |  |  | 172.00 | STK1 Luff Cylinder C/O - 172hrs with no line boring contingency |  |  | [{"equipmentGUID": "65ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST01", "name": "Stacker: CLA 01 RV Coarse Ore", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "92be881f-21e8-4f3b-9878-563f46d06441", "emailAddress": "Duane.Evans@riotinto.com", "displayName": "Duane Evans"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 56360, "shutVersionId": 332097, "title": "#56360 - CLA: 250hrs - STK1 IAM", "startDatetimeUTC": "2027-08-18T10:00:00+00:00", "endDatetimeUTC": "2027-08-28T20:00:00+00:00"}}] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | CLA | Australia/Perth
68955 | 2025-09-05T05:11:44.0315329+00:00 | 2025-09-05T13:11:44.0315329+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-15T05:57:36.7728571+00:00 | 2025-10-15T13:57:36.7728571+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 257614 | TRUE | TRUE | 2025-10-15T05:57:36.7728571+00:00 | 2025-10-15T13:57:36.7728571+08:00 | #68955 - MTP: 68hrs - CRUSHER - TERTIARY: MTP 01 HIGH GRADE | 3.0 | FALSE |  | 2026-12-25T16:00:00+00:00 | 2026-12-28T12:00:00+00:00 | 2026-12-26T00:00:00+08:00 | 2026-12-28T20:00:00+08:00 |  |  |  |  | 68.00 | 1TC Tert Crusher Module Maintenance | wrong date |  | [{"equipmentGUID": "7734f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS01", "name": "Crusher - Tertiary: MTP 01 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | MTP | Australia/Perth
71710 | 2025-10-28T05:36:17.3185054+00:00 | 2025-10-28T13:36:17.3185054+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2025-11-06T04:32:53.6741032+00:00 | 2025-11-06T12:32:53.6741032+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 272435 | TRUE | TRUE | 2025-11-06T04:32:53.6741032+00:00 | 2025-11-06T12:32:53.6741032+08:00 | #71710 - PPT: 106hrs - BIN: PPT 03 SURGE & SCREENHOUSE: PPT 3P | 2.0 | FALSE |  | 2027-06-07T18:00:00+00:00 | 2027-06-12T04:00:00+00:00 | 2027-06-08T02:00:00+08:00 | 2027-06-12T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | IAM Refresh |  | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
71711 | 2025-10-28T05:36:17.6975397+00:00 | 2025-10-28T13:36:17.6975397+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2025-11-25T02:52:13.3661262+00:00 | 2025-11-25T10:52:13.3661262+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 276700 | TRUE | TRUE | 2025-11-25T02:52:13.3661262+00:00 | 2025-11-25T10:52:13.3661262+08:00 | #71711 - PPT: 106hrs - BIN: PPT 03 SURGE & SCREENHOUSE: PPT 3P | 2.0 | FALSE |  | 2027-09-06T18:00:00+00:00 | 2027-09-11T04:00:00+00:00 | 2027-09-07T02:00:00+08:00 | 2027-09-11T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | IAM Refresh |  | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
71712 | 2025-10-28T05:36:18.0829297+00:00 | 2025-10-28T13:36:18.0829297+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2025-11-25T02:52:13.7755704+00:00 | 2025-11-25T10:52:13.7755704+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 276704 | TRUE | TRUE | 2025-11-25T02:52:13.7755704+00:00 | 2025-11-25T10:52:13.7755704+08:00 | #71712 - PPT: 106hrs - BIN: PPT 03 SURGE & SCREENHOUSE: PPT 3P | 2.0 | FALSE |  | 2027-12-06T18:00:00+00:00 | 2027-12-11T04:00:00+00:00 | 2027-12-07T02:00:00+08:00 | 2027-12-11T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | IAM Refresh |  | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Scheduled | PPT | Australia/Perth
84089 | 2026-10-02T01:32:32.4495945+00:00 | 2026-10-02T09:32:32.4495945+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | 2026-10-02T13:06:50.4310081+00:00 | 2026-10-02T21:06:50.4310081+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 335210 | TRUE | TRUE | 2026-10-02T13:06:50.4310081+00:00 | 2026-10-02T21:06:50.4310081+08:00 | #84089 - BM4: 48hrs - BS1 PC3 COMMISSIONING OUTAGE | 1.1 | TRUE |  | 2027-04-15T22:00:00+00:00 | 2027-04-17T22:00:00+00:00 | 2027-04-16T06:00:00+08:00 | 2027-04-18T06:00:00+08:00 |  |  |  |  | 48.00 | BS1 PC3 Commissioning Outage |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
84090 | 2026-10-02T01:40:31.4162093+00:00 | 2026-10-02T09:40:31.4162093+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | 2026-10-02T13:07:55.476444+00:00 | 2026-10-02T21:07:55.476444+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 335211 | TRUE | TRUE | 2026-10-02T13:07:55.476444+00:00 | 2026-10-02T21:07:55.476444+08:00 | #84090 - BM4: 48hrs - BS1 PC3 COMMISSIONING OUTAGE | 1.1 | TRUE |  | 2027-04-25T22:00:00+00:00 | 2027-04-27T22:00:00+00:00 | 2027-04-26T06:00:00+08:00 | 2027-04-28T06:00:00+08:00 |  |  |  |  | 48.00 | BS1 PC3 Commissioning Outage |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
84091 | 2026-10-02T01:44:12.9662474+00:00 | 2026-10-02T09:44:12.9662474+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | 2026-10-02T13:08:34.332014+00:00 | 2026-10-02T21:08:34.332014+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 335212 | TRUE | TRUE | 2026-10-02T13:08:34.332014+00:00 | 2026-10-02T21:08:34.332014+08:00 | #84091 - BM4: 48hrs - BS1 PC3 COMMISSIONING OUTAGE | 1.1 | TRUE |  | 2027-05-07T22:00:00+00:00 | 2027-05-09T22:00:00+00:00 | 2027-05-08T06:00:00+08:00 | 2027-05-10T06:00:00+08:00 |  |  |  |  | 48.00 | BS1 PC3 Commissioning Outage |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
84092 | 2026-10-02T01:45:19.7687345+00:00 | 2026-10-02T09:45:19.7687345+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | 2026-10-02T13:09:18.9383486+00:00 | 2026-10-02T21:09:18.9383486+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | {"name": "Fixed Plant"} | 335213 | TRUE | TRUE | 2026-10-02T13:09:18.9383486+00:00 | 2026-10-02T21:09:18.9383486+08:00 | #84092 - BM4: 48hrs - BS1 PC3 COMMISSIONING OUTAGE. | 1.1 | TRUE |  | 2027-05-25T22:00:00+00:00 | 2027-05-27T22:00:00+00:00 | 2027-05-26T06:00:00+08:00 | 2027-05-28T06:00:00+08:00 |  |  |  |  | 48.00 | BS1 PC3 Commissioning Outage. |  |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 03d795ee-90c4-4b6f-a129-052c82e6ff79 | Campbell-Cooke, Clare (RTIO) | Major Projects | BM4 | Australia/Perth
84486 | 2026-10-15T06:56:00.0981643+00:00 | 2026-10-15T14:56:00.0981643+08:00 | {"principalGUID": "17d27aa3-617e-45b7-914d-26c04048c6be", "displayName": "Bray, Darren (RTIO)"} | 2026-10-19T08:30:18.1474654+00:00 | 2026-10-19T16:30:18.1474654+08:00 | {"principalGUID": "17d27aa3-617e-45b7-914d-26c04048c6be", "displayName": "Bray, Darren (RTIO)"} | {"name": "Fixed Plant"} | 336201 | TRUE | TRUE | 2026-10-19T08:30:18.1474654+00:00 | 2026-10-19T16:30:18.1474654+08:00 | #84486 - YAN: 2160hrs - TLO1 STRUCTURAL REMEDIATION WORKS | 1.0 | TRUE |  | 2026-11-01T22:00:00+00:00 | 2027-01-30T22:00:00+00:00 | 2026-11-02T06:00:00+08:00 | 2027-01-31T06:00:00+08:00 |  |  |  |  | 2160.00 | TLO1 Structural Remediation Works MSF Outage to continue after the TLO2 shut and until the structural remediation works have been completed on TLO1 |  |  | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "a6bb4002-2aaf-4143-958f-79a5fef43190", "emailAddress": "Andrew.Griffiths@riotinto.com", "displayName": "Griffiths, Andrew (RTIO)"}}] | [] | [] | [{"name": "TLO Major Works"}] | [] | [] | Approved | Create | 17d27aa3-617e-45b7-914d-26c04048c6be | Bray, Darren (RTIO) | Major Projects | YAN | Australia/Perth
83983 | 2026-09-23T05:10:36.2630804+00:00 | 2026-09-23T13:10:36.2630804+08:00 | {"principalGUID": "f4ec87d0-8bce-4225-8e94-785512b80676", "displayName": "Oakes, Callan (RTIO)"} | 2026-09-23T05:22:36.9055355+00:00 | 2026-09-23T13:22:36.9055355+08:00 | {"principalGUID": "f4ec87d0-8bce-4225-8e94-785512b80676", "displayName": "Oakes, Callan (RTIO)"} | {"name": "Fixed Plant"} | 334050 | TRUE | TRUE | 2026-09-23T05:22:36.9055355+00:00 | 2026-09-23T13:22:36.9055355+08:00 | #83983 - CLB: 96hrs - RECLAIMER: CLB 13 | 1.0 | FALSE |  | 2026-12-08T22:00:00+00:00 | 2026-12-12T22:00:00+00:00 | 2026-12-09T06:00:00+08:00 | 2026-12-13T06:00:00+08:00 |  |  |  |  | 96.00 | C/O Recl Conv Belt 26WK CV533 To de risk week 45 RC13 IAM belt Co has been moved to week 50. Belt thickness testing will be done before to determine if belt can be pushed to week 6. |  | SCBY2650 | [{"equipmentGUID": "96e5bff1-4a8c-ee11-a847-000d3acacefd", "code": "CLBCV533", "name": "Conveyor: CLB 533 Boom Reclaimer 13", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2a42633f-49c4-410a-bf5b-22613a2fb2fd", "emailAddress": "SamuelJason.DuBois@riotinto.com", "displayName": "Du Bois, Samuel Jason (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Create | f4ec87d0-8bce-4225-8e94-785512b80676 | Oakes, Callan (RTIO) | Scheduled | CLB | Australia/Perth
84490 | 2026-10-15T23:49:38.7672231+00:00 | 2026-10-16T07:49:38.7672231+08:00 | {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "displayName": "Stacey, Rohan (RTIO)"} | 2026-10-21T01:05:44.2282218+00:00 | 2026-10-21T09:05:44.2282218+08:00 | {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "displayName": "Stacey, Rohan (RTIO)"} | {"name": "Fixed Plant"} | 336243 | TRUE | TRUE | 2026-10-21T01:05:44.2282218+00:00 | 2026-10-21T09:05:44.2282218+08:00 | #84490 - YAN: 1hrs - CRUSHER - PRIMARY: YAN PRIMARY SIZER 201 PLANT 02 & CRUSHER - PRIMARY: YAN PRIMARY SIZER 301 PLANT 03 | 1.0 | TRUE |  | 2026-12-08T10:00:00+00:00 | 2026-12-08T11:00:00+00:00 | 2026-12-08T18:00:00+08:00 | 2026-12-08T19:00:00+08:00 |  |  |  |  | 1.00 | YBN31 Open KNIFE GATE post STK2 Shut |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 274da65a-a894-4ff4-b5c0-7b4ac9dfb393 | Stacey, Rohan (RTIO) | Scheduled | YAN | Australia/Perth
73302 | 2025-11-12T21:56:00.9508075+00:00 | 2025-11-13T05:56:00.9508075+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-10-21T00:55:09.6284924+00:00 | 2026-10-21T08:55:09.6284924+08:00 | {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "displayName": "Stacey, Rohan (RTIO)"} | {"name": "Fixed Plant"} | 336241 | TRUE | TRUE | 2026-10-21T00:55:09.6284924+00:00 | 2026-10-21T08:55:09.6284924+08:00 | #73302 - YAN: 1hrs - YBN31 CLOSE KNIFE GATE | 2.0 | TRUE |  | 2026-12-03T23:00:00+00:00 | 2026-12-04T00:00:00+00:00 | 2026-12-04T07:00:00+08:00 | 2026-12-04T08:00:00+08:00 |  |  |  |  | 1.00 | YBN31 CLOSE KNIFE GATE pre STK2 Shut | just pushing the start to align with the amended stacker shut timing |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 274da65a-a894-4ff4-b5c0-7b4ac9dfb393 | Stacey, Rohan (RTIO) | Scheduled | YAN | Australia/Perth
57605 | 2023-08-16T08:28:36+00:00 | 2023-08-16T16:28:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-21T00:56:11.4956699+00:00 | 2026-10-21T08:56:11.4956699+08:00 | {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "displayName": "Stacey, Rohan (RTIO)"} | {"name": "Fixed Plant"} | 336242 | TRUE | TRUE | 2026-10-21T00:56:11.4956699+00:00 | 2026-10-21T08:56:11.4956699+08:00 | #57605 - YAN: 108hrs - STACKER: YAN 02 | 8.0 | FALSE |  | 2026-12-03T23:00:00+00:00 | 2026-12-08T11:00:00+00:00 | 2026-12-04T07:00:00+08:00 | 2026-12-08T19:00:00+08:00 |  |  |  |  | 108.00 | Stacker 2 shut | just delaying the start 12 hrs to allow a small gap between the JSE stream shut for isolations & washdowns |  | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 274da65a-a894-4ff4-b5c0-7b4ac9dfb393 | Stacey, Rohan (RTIO) | Scheduled | YAN | Australia/Perth
58835 | 2023-09-26T08:50:27+00:00 | 2023-09-26T16:50:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-21T06:30:23.1001563+00:00 | 2026-09-21T14:30:23.1001563+08:00 | {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "displayName": "Stacey, Rohan (RTIO)"} | {"name": "Fixed Plant"} | 333659 | TRUE | TRUE | 2026-09-21T06:30:23.1001563+00:00 | 2026-09-21T14:30:23.1001563+08:00 | #58835 - YAN: 137hrs - JSE MODULAR 303 SHUT | 9.0 | FALSE |  | 2026-12-03T11:00:00+00:00 | 2026-12-09T04:00:00+00:00 | 2026-12-03T19:00:00+08:00 | 2026-12-09T12:00:00+08:00 |  |  |  |  | 137.00 | JSE Modular 303 | Scrubber liner change out requires increased duration. Nil SOP impact as PC2 running | SJSE2649 | [{"equipmentGUID": "7efbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB303", "name": "Scrubber: YAN 303", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 274da65a-a894-4ff4-b5c0-7b4ac9dfb393 | Stacey, Rohan (RTIO) | Scheduled | YAN | Australia/Perth
53162 | 2022-11-14T07:21:52+00:00 | 2022-11-14T15:21:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:39:55.6632061+00:00 | 2026-09-30T15:39:55.6632061+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 334707 | TRUE | TRUE | 2026-09-30T07:39:55.6632061+00:00 | 2026-09-30T15:39:55.6632061+08:00 | #53162 - CLA: 672hrs - CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER | 14.0 | TRUE |  | 2027-02-28T22:00:00+00:00 | 2027-03-28T22:00:00+00:00 | 2027-03-01T06:00:00+08:00 | 2027-03-29T06:00:00+08:00 |  |  |  |  | 672.00 | CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER PLACEHOLDER | Requested changes to CLAHDO shut start date 24/02 - 01/03 |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "cc6c96ea-6b8c-46ea-a62e-93cce43e9f17", "emailAddress": "Parsa.Rad@riotinto.com", "displayName": "Farjadrad, Parsa (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "0c7844c7-02f6-4f4a-af42-9b17b0a1ac0e", "emailAddress": "Trent.Boulos@riotinto.com", "displayName": "Boulos, Trent (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84197, "shutVersionId": 335408, "title": "#84197 - CLA: 72hrs - CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER", "startDatetimeUTC": "2027-03-28T22:00:00+00:00", "endDatetimeUTC": "2027-03-31T22:00:00+00:00"}}] | [] | [{"code": "P-0511336", "name": "CLAHDO", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "672"}] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Major Projects | CLA | Australia/Perth
39288 | 2020-12-18T05:02:35+00:00 | 2020-12-18T13:02:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-10T03:43:38.0055575+00:00 | 2025-10-10T11:43:38.0055575+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 252556 | TRUE | TRUE | 2025-10-10T03:43:38.0055575+00:00 | 2025-10-10T11:43:38.0055575+08:00 | #39288 - CLA: 108hrs - STACKER: CLA 03 | 2.0 | FALSE |  | 2026-12-14T04:00:00+00:00 | 2026-12-18T16:00:00+00:00 | 2026-12-14T12:00:00+08:00 | 2026-12-19T00:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Align Stacker: CLA 03 moved from Wk49 - Wk51 |  | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45739, "shutVersionId": 260148, "title": "#45739 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING & SCREENHOUSE: CLA LUMP RESCREENING PLANT 02", "startDatetimeUTC": "2026-12-14T22:00:00+00:00", "endDatetimeUTC": "2026-12-16T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
39269 | 2020-12-18T05:02:04+00:00 | 2020-12-18T13:02:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-10T03:43:38.880151+00:00 | 2025-10-10T11:43:38.880151+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 252557 | TRUE | TRUE | 2025-10-10T03:43:38.880151+00:00 | 2025-10-10T11:43:38.880151+08:00 | #39269 - CLA: 138hrs - RECLAIMER: CLA 03 | 2.0 | FALSE |  | 2026-12-14T04:00:00+00:00 | 2026-12-19T22:00:00+00:00 | 2026-12-14T12:00:00+08:00 | 2026-12-20T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance | Align Reclaimer: CLA 03 with St03 moved from Wk49 - Wk51 |  | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45739, "shutVersionId": 260148, "title": "#45739 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING & SCREENHOUSE: CLA LUMP RESCREENING PLANT 02", "startDatetimeUTC": "2026-12-14T22:00:00+00:00", "endDatetimeUTC": "2026-12-16T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
39212 | 2020-12-18T04:54:44+00:00 | 2020-12-18T12:54:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-10T03:43:39.7438412+00:00 | 2025-10-10T11:43:39.7438412+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 252558 | TRUE | TRUE | 2025-10-10T03:43:39.7438412+00:00 | 2025-10-10T11:43:39.7438412+08:00 | #39212 - CLA: 84hrs - CRUSHER - SECONDARY: CLA CIRCUIT 01 | 3.0 | FALSE |  | 2026-12-24T04:00:00+00:00 | 2026-12-27T16:00:00+00:00 | 2026-12-24T12:00:00+08:00 | 2026-12-28T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Align Crusher - Secondary: CLA Circuit 01 moved from Wk51 -Wk52 |  | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
39097 | 2020-12-18T04:30:42+00:00 | 2020-12-18T12:30:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2025-10-10T03:43:40.5986077+00:00 | 2025-10-10T11:43:40.5986077+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 252559 | TRUE | TRUE | 2025-10-10T03:43:40.5986077+00:00 | 2025-10-10T11:43:40.5986077+08:00 | #39097 - CLA: 84hrs - CRUSHER - TERTIARY: CLA CIRCUIT 03 | 2.0 | FALSE |  | 2026-12-24T04:00:00+00:00 | 2026-12-27T16:00:00+00:00 | 2026-12-24T12:00:00+08:00 | 2026-12-28T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Align Crusher - Tertiary: CLA Circuit 03 Moved from Wk50 - Wk52 |  | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
63811 | 2024-08-27T07:40:37+00:00 | 2024-08-27T15:40:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-01-23T06:46:01.7014106+00:00 | 2026-01-23T14:46:01.7014106+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 285103 | TRUE | TRUE | 2026-01-23T06:46:01.7014106+00:00 | 2026-01-23T14:46:01.7014106+08:00 | #63811 - CLA: 336hrs - BERTH 1 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 6.0 | FALSE |  | 2026-11-23T10:00:00+00:00 | 2026-12-07T10:00:00+00:00 | 2026-11-23T18:00:00+08:00 | 2026-12-07T18:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works | Aligning with CLADHO outage changes |  | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000001763", "emailAddress": "Alex.TengHuiChung@riotinto.com", "displayName": "Alex Teng"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ef880946-3b06-4b26-9fc6-1ff97d2c207c", "emailAddress": "Kieran.Dart@riotinto.com", "displayName": "Kieran Dart"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-", "name": "MARINE STRUCTURAL INTEGRITY WORKS", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Major Projects | CLA | Australia/Perth
38811 | 2020-12-18T03:49:14+00:00 | 2020-12-18T11:49:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-03-23T06:20:32.5104898+00:00 | 2026-03-23T14:20:32.5104898+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 323929 | TRUE | TRUE | 2026-03-23T06:20:32.5104898+00:00 | 2026-03-23T14:20:32.5104898+08:00 | #38811 - CLB: 280hrs - CD5C CATENARY CABLE C/O | 7.0 | TRUE |  | 2026-11-24T04:00:00+00:00 | 2026-12-05T20:00:00+00:00 | 2026-11-24T12:00:00+08:00 | 2026-12-06T04:00:00+08:00 |  |  |  |  | 280.00 | CD5C Catenary Cable C/O | Realign Catenary Cable Replacement start 24/11 to reduce SL11 impact with CD3P overlap |  | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}] | [] | [] | [{"name": "Catenary Cable Install"}, {"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
60493 | 2024-02-06T05:21:55+00:00 | 2024-02-06T13:21:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-09-30T07:39:55.3948318+00:00 | 2026-09-30T15:39:55.3948318+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 334705 | TRUE | TRUE | 2026-09-30T07:39:55.3948318+00:00 | 2026-09-30T15:39:55.3948318+08:00 | #60493 - CLA: 408hrs - SL3C SUB MAJOR WORKS (SUS CAP) | 11.0 | TRUE |  | 2027-03-11T22:00:00+00:00 | 2027-03-28T22:00:00+00:00 | 2027-03-12T06:00:00+08:00 | 2027-03-29T06:00:00+08:00 |  |  |  |  | 408.00 | Sus Cap project SL3C Sub HV switchgear replacement affecting SL3C | Request outage start time change due to CLADHO timing from 07/03 - 12/03 |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "eeb6b438-cda3-4178-a69b-874a613b24b8", "emailAddress": "Mohamoud.Sagaale@riotinto.com", "displayName": "Sagaale, Mohamoud (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603621", "name": "HV SWITCHGEAR", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "408"}] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Major Projects | CLA | Australia/Perth
60492 | 2024-02-06T05:17:49+00:00 | 2024-02-06T13:17:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-09-30T07:39:55.538892+00:00 | 2026-09-30T15:39:55.538892+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 334706 | TRUE | TRUE | 2026-09-30T07:39:55.538892+00:00 | 2026-09-30T15:39:55.538892+08:00 | #60492 - CLA: 288hrs - SL2C WHARF SUB2 MAJOR WORKS (SUS CAP) | 10.0 | TRUE |  | 2027-02-04T22:00:00+00:00 | 2027-02-16T22:00:00+00:00 | 2027-02-05T06:00:00+08:00 | 2027-02-17T06:00:00+08:00 |  |  |  |  | 288.00 | Sus Cap Project – Wharf Sub 2 HV Switchgear replacement affecting SL2C, Berth 1, Berth 2. Note: Berth 3 will only be affected if LV works in 2025 do not get completed Contact Mohamoud Sagaale 0451919896 | Requested to change outage start time due to CLAHDO timing 31/01 - 05/02 |  | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}, {"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b79d0458-4b6b-4c43-bb07-46bcb5d85e72", "emailAddress": "Chia.Wong@riotinto.com", "displayName": "Chia Wong"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "eeb6b438-cda3-4178-a69b-874a613b24b8", "emailAddress": "Mohamoud.Sagaale@riotinto.com", "displayName": "Sagaale, Mohamoud (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603621", "name": "HV SWITCHGEAR WHARF SUB 2", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "288"}] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Major Projects | CLA | Australia/Perth
61656 | 2024-05-23T18:55:17+00:00 | 2024-05-24T02:55:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-03-23T06:20:32.2185995+00:00 | 2026-03-23T14:20:32.2185995+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 323928 | TRUE | TRUE | 2026-03-23T06:20:32.2185995+00:00 | 2026-03-23T14:20:32.2185995+08:00 | #61656 - CLB: 96hrs - SL11_RMP - CORROSION & STRUCTURAL REPAIRS | 8.0 | TRUE |  | 2026-12-03T10:00:00+00:00 | 2026-12-07T10:00:00+00:00 | 2026-12-03T18:00:00+08:00 | 2026-12-07T18:00:00+08:00 |  |  |  |  | 96.00 | Standalone outage 96hrs SL11_RMP - Corrosion & Structural Repairs Contact Mat Mckiernan 0400141769 Brad Ross 0400949892 | Realign 96hr corrosion control outage from 12/12 - 03/12 reduce SL11 impact with CD3P overlap |  | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "423b6bb1-0045-43ea-9031-297314d2eb65", "emailAddress": "Scott.Clamp@riotinto.com", "displayName": "Scott Clamp"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
84196 | 2026-10-07T05:05:24.9844491+00:00 | 2026-10-07T13:05:24.9844491+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-07T05:18:39.0905151+00:00 | 2026-10-07T13:18:39.0905151+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335407 | TRUE | TRUE | 2026-10-07T05:18:39.0905151+00:00 | 2026-10-07T13:18:39.0905151+08:00 | #84196 - CLA: 72hrs - CLAHDO SL2C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER | 1.0 | TRUE |  | 2027-02-16T22:00:00+00:00 | 2027-02-19T22:00:00+00:00 | 2027-02-17T06:00:00+08:00 | 2027-02-20T06:00:00+08:00 |  |  |  |  | 72.00 | CLAHDO SL2C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER This is for commissioning of the sample facility and SL boom drives. |  |  | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "77ff7bae-c300-4540-a51e-b11b36f72e81", "emailAddress": "Michael.Gillam@riotinto.com", "displayName": "Michael Gillam"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "cc6c96ea-6b8c-46ea-a62e-93cce43e9f17", "emailAddress": "Parsa.Rad@riotinto.com", "displayName": "Farjadrad, Parsa (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "0c7844c7-02f6-4f4a-af42-9b17b0a1ac0e", "emailAddress": "Trent.Boulos@riotinto.com", "displayName": "Boulos, Trent (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 53161, "shutVersionId": 335939, "title": "#53161 - CLA: 672hrs - CLAHDO SL2C BM WORKS & SAMPLE STATION CUT OVER", "startDatetimeUTC": "2027-01-19T22:00:00+00:00", "endDatetimeUTC": "2027-02-16T22:00:00+00:00"}}] | [] | [{"code": "P-0511336", "name": "CLAHDO", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [{"name": "Reduced Rates"}] | Approved | Create | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Site Constraint | CLA | Australia/Perth
84197 | 2026-10-07T05:09:52.9937551+00:00 | 2026-10-07T13:09:52.9937551+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-07T05:18:39.3458376+00:00 | 2026-10-07T13:18:39.3458376+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335408 | TRUE | TRUE | 2026-10-07T05:18:39.3458376+00:00 | 2026-10-07T13:18:39.3458376+08:00 | #84197 - CLA: 72hrs - CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER | 1.0 | TRUE |  | 2027-03-28T22:00:00+00:00 | 2027-03-31T22:00:00+00:00 | 2027-03-29T06:00:00+08:00 | 2027-04-01T06:00:00+08:00 |  |  |  |  | 72.00 | CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER This is for commissioning of the sample facility and SL boom drives. |  |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "77ff7bae-c300-4540-a51e-b11b36f72e81", "emailAddress": "Michael.Gillam@riotinto.com", "displayName": "Michael Gillam"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "cc6c96ea-6b8c-46ea-a62e-93cce43e9f17", "emailAddress": "Parsa.Rad@riotinto.com", "displayName": "Farjadrad, Parsa (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "0c7844c7-02f6-4f4a-af42-9b17b0a1ac0e", "emailAddress": "Trent.Boulos@riotinto.com", "displayName": "Boulos, Trent (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 53162, "shutVersionId": 334707, "title": "#53162 - CLA: 672hrs - CLAHDO SL3C BM WORKS AND SAMPLE STATION CUT OVER", "startDatetimeUTC": "2027-02-28T22:00:00+00:00", "endDatetimeUTC": "2027-03-28T22:00:00+00:00"}}] | [] | [{"code": "P-0511336", "name": "CLAHDO", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "24"}] | [{"name": "Reduced Rates"}] | Approved | Create | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Site Constraint | CLA | Australia/Perth
75054 | 2026-02-01T23:07:02.2722595+00:00 | 2026-02-02T07:07:02.2722595+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-07T05:25:41.5409773+00:00 | 2026-10-07T13:25:41.5409773+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335409 | TRUE | TRUE | 2026-10-07T05:25:41.5409773+00:00 | 2026-10-07T13:25:41.5409773+08:00 | #75054 - CLA: 172hrs - ST05 DUAL LUFF CYLINDER C/O - ON CONDITION | 4.0 | FALSE |  | 2027-11-03T22:00:00+00:00 | 2027-11-11T02:00:00+00:00 | 2027-11-04T06:00:00+08:00 | 2027-11-11T10:00:00+08:00 |  |  |  |  | 172.00 | ST05 DUAL LUFF CYLINDER C/O - Shim placed in 2025 Contact Brian Kimber 0417801218 | Due to the number of projects that is happening in this period to alleviate that condensed level of scheduled work and resources the proposal is to move Stk5 Luff cylinder C/O to November |  | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
76486 | 2026-02-26T08:10:16.8291531+00:00 | 2026-02-26T16:10:16.8291531+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-03-23T06:02:12.2408926+00:00 | 2026-03-23T14:02:12.2408926+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 323920 | TRUE | TRUE | 2026-03-23T06:02:12.2408926+00:00 | 2026-03-23T14:02:12.2408926+08:00 | #76486 - CLB: 96hrs - BERTH: CLB 05 & BERTH: CLB 06 | 2.0 | FALSE |  | 2026-12-03T10:00:00+00:00 | 2026-12-07T10:00:00+00:00 | 2026-12-03T18:00:00+08:00 | 2026-12-07T18:00:00+08:00 |  |  |  |  | 96.00 | Berths off line due to SL11 RMP work 96h | Align with 96h Corrosion Control outage moved due to impact with CD3P |  | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}, {"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1826e4b1-0a2b-4a12-acbb-fe9230f8d186", "emailAddress": "Renee.Moretti@riotinto.com", "displayName": "Moretti, Renee (RTIO)"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "788c7b27-9bb6-4959-8c3e-6418bb5992f6", "emailAddress": "Robert.Connell@riotinto.com", "displayName": "Connell, Robert (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
76487 | 2026-02-26T08:15:29.2003932+00:00 | 2026-02-26T16:15:29.2003932+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-03-23T06:02:12.3728692+00:00 | 2026-03-23T14:02:12.3728692+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 323921 | TRUE | TRUE | 2026-03-23T06:02:12.3728692+00:00 | 2026-03-23T14:02:12.3728692+08:00 | #76487 - CLB: 96hrs - SCREENHOUSE: CLB 05 OUTLOADING | 2.0 | FALSE |  | 2026-12-03T10:00:00+00:00 | 2026-12-07T10:00:00+00:00 | 2026-12-03T18:00:00+08:00 | 2026-12-07T18:00:00+08:00 |  |  |  |  | 96.00 | Align with SL11 Corrosion repairs | Align with 96h Corrosion Control outage moved due to impact with CD3P |  | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ad335d87-3c53-4798-8bef-230f0198a8f1", "emailAddress": "dwayne.clarke@riotinto.com", "displayName": "Clarke, Dwayne (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43575 | 2021-11-01T22:59:56+00:00 | 2021-11-02T06:59:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-02-21T02:48:17.7641421+00:00 | 2026-02-21T10:48:17.7641421+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 287697 | TRUE | TRUE | 2026-02-21T02:48:17.7641421+00:00 | 2026-02-21T10:48:17.7641421+08:00 | #43575 - CLA: 114hrs - SHIPLOADER: CLA 2C | 8.1 | TRUE |  | 2027-08-30T10:00:00+00:00 | 2027-09-04T04:00:00+00:00 | 2027-08-30T18:00:00+08:00 | 2027-09-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2734 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLA | Australia/Perth
61854 | 2024-06-06T08:47:59+00:00 | 2024-06-06T16:47:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-10-20T04:01:53.5020407+00:00 | 2026-10-20T12:01:53.5020407+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 336212 | TRUE | TRUE | 2026-10-20T04:01:53.5020407+00:00 | 2026-10-20T12:01:53.5020407+08:00 | #61854 - CLB: 97hrs - SAFETY PLC UPGRADE SSL2 | 5.0 | FALSE |  | 2027-04-12T10:00:00+00:00 | 2027-04-16T11:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-16T19:00:00+08:00 |  |  |  |  | 97.00 | Safety PLC Upgrade QOL2, SSL2 Additional Info: Contact Chris Dekens 0408 132 036 | Moved outage to Wk15 this was due to the SL12 outage being reduce and needing to remove scope from the shut |  | [{"equipmentGUID": "7d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSACCT02", "name": "Sample Station: CLB Circuit 02 Outloading SCH06", "assetClass": {"name": "Sample Station"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bf5e7a01-d427-4505-a20a-b12f8af23d67", "emailAddress": "Chris.Dekens@riotinto.com", "displayName": "Christopher Dekens"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
61853 | 2024-06-06T08:42:43+00:00 | 2024-06-06T16:42:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-10-20T04:01:53.685231+00:00 | 2026-10-20T12:01:53.685231+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 336213 | TRUE | TRUE | 2026-10-20T04:01:53.685231+00:00 | 2026-10-20T12:01:53.685231+08:00 | #61853 - CLB: 48hrs - SAFETY PLC UPGRADE QOSUB1, SL11,SL12,SSL1,SSL2 | 7.0 | TRUE |  | 2027-04-12T10:00:00+00:00 | 2027-04-14T10:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-14T18:00:00+08:00 |  |  |  |  | 48.00 | Safety PLC Upgrade QOSub1,SL11, SL12, SSL1, SSL2. Aligned with dual Shiploader outage Additional Info: Contact Chris Dekens 0408 132 036 | Aligning to Wk15 2027 due SL outage as Wk41 had changed this was due to the SL12 outage being reduce and needing to remove scope from the shut |  | [{"equipmentGUID": "7f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSACCT01", "name": "Sample Station: CLB Circuit 01 Outloading SCH05", "assetClass": {"name": "Sample Station"}}, {"equipmentGUID": "7d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSACCT02", "name": "Sample Station: CLB Circuit 02 Outloading SCH06", "assetClass": {"name": "Sample Station"}}, {"equipmentGUID": "8567fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBSAQ01", "name": "Substation: CLB Sampling Q01 ", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bf5e7a01-d427-4505-a20a-b12f8af23d67", "emailAddress": "Chris.Dekens@riotinto.com", "displayName": "Christopher Dekens"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43694 | 2021-11-02T00:01:18+00:00 | 2021-11-02T08:01:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:54.4061325+00:00 | 2026-10-02T15:11:54.4061325+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335178 | TRUE | TRUE | 2026-10-02T07:11:54.4061325+00:00 | 2026-10-02T15:11:54.4061325+08:00 | #43694 - CLB: 48hrs - SH6 FINES ONLY | 7.0 | FALSE |  | 2027-03-23T16:00:00+00:00 | 2027-03-25T16:00:00+00:00 | 2027-03-24T00:00:00+08:00 | 2027-03-26T00:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH6 Fines Loading Only | Increasing offset from SH6/SL12 shut Updated Equipment Change | SCBO2713 | [{"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43683 | 2021-11-01T23:59:18+00:00 | 2021-11-02T07:59:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:54.5882892+00:00 | 2026-10-02T15:11:54.5882892+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335179 | TRUE | TRUE | 2026-10-02T07:11:54.5882892+00:00 | 2026-10-02T15:11:54.5882892+08:00 | #43683 - CLB: 48hrs - SH5 FINES ONLY | 6.0 | FALSE |  | 2027-05-14T18:00:00+00:00 | 2027-05-16T18:00:00+00:00 | 2027-05-15T02:00:00+08:00 | 2027-05-17T02:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH5 Fines Loading Only | Increasing offset from RC11/SL11 shut Updated Equipment Change | SCBO2720 | [{"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43696 | 2021-11-02T00:01:22+00:00 | 2021-11-02T08:01:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:54.7748157+00:00 | 2026-10-02T15:11:54.7748157+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335180 | TRUE | TRUE | 2026-10-02T07:11:54.7748157+00:00 | 2026-10-02T15:11:54.7748157+08:00 | #43696 - CLB: 48hrs - SH6 FINES ONLY | 6.0 | FALSE |  | 2027-06-25T16:00:00+00:00 | 2027-06-27T16:00:00+00:00 | 2027-06-26T00:00:00+08:00 | 2027-06-28T00:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH6 Fines Loading Only | Increasing offset from RC12/SL12 shut Updated Equipment Change | SCBO2726 | [{"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43685 | 2021-11-01T23:59:22+00:00 | 2021-11-02T07:59:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:54.956197+00:00 | 2026-10-02T15:11:54.956197+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335181 | TRUE | TRUE | 2026-10-02T07:11:54.956197+00:00 | 2026-10-02T15:11:54.956197+08:00 | #43685 - CLB: 48hrs - SH5 FINES ONLY | 6.0 | FALSE |  | 2027-08-13T18:00:00+00:00 | 2027-08-15T18:00:00+00:00 | 2027-08-14T02:00:00+08:00 | 2027-08-16T02:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH5 Fines Loading Only | Moving away from the plant shut Updated Equipment Change | SCBO2733 | [{"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43698 | 2021-11-02T00:01:27+00:00 | 2021-11-02T08:01:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:55.1492163+00:00 | 2026-10-02T15:11:55.1492163+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335182 | TRUE | TRUE | 2026-10-02T07:11:55.1492163+00:00 | 2026-10-02T15:11:55.1492163+08:00 | #43698 - CLB: 48hrs - SH6 FINES ONLY | 6.0 | FALSE |  | 2027-09-24T16:00:00+00:00 | 2027-09-26T16:00:00+00:00 | 2027-09-25T00:00:00+08:00 | 2027-09-27T00:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH6 Fines Loading Only | Increasing offset from RC12/SL12 shut Updated Equipment Change | SCBO2739 | [{"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43687 | 2021-11-01T23:59:27+00:00 | 2021-11-02T07:59:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:55.3446639+00:00 | 2026-10-02T15:11:55.3446639+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335183 | TRUE | TRUE | 2026-10-02T07:11:55.3446639+00:00 | 2026-10-02T15:11:55.3446639+08:00 | #43687 - CLB: 48hrs - SH5 FINES ONLY | 6.0 | FALSE |  | 2027-11-12T18:00:00+00:00 | 2027-11-14T18:00:00+00:00 | 2027-11-13T02:00:00+08:00 | 2027-11-15T02:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH5 Fines Loading Only | increasing offset from RC11/SL11 shut Updated Equipment Change | SCBO2746 | [{"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
43700 | 2021-11-02T00:01:28+00:00 | 2021-11-02T08:01:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:11:55.5590419+00:00 | 2026-10-02T15:11:55.5590419+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 335184 | TRUE | TRUE | 2026-10-02T07:11:55.5590419+00:00 | 2026-10-02T15:11:55.5590419+08:00 | #43700 - CLB: 48hrs - SH6 FINES ONLY | 6.0 | FALSE |  | 2027-12-28T16:00:00+00:00 | 2027-12-30T16:00:00+00:00 | 2027-12-29T00:00:00+08:00 | 2027-12-31T00:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH6 Fines Loading Only | Adjusting shut equipment criteria | SCBO2752 | [{"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
71804 | 2025-10-29T12:36:36.2495011+00:00 | 2025-10-29T20:36:36.2495011+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-03-23T06:02:12.519662+00:00 | 2026-03-23T14:02:12.519662+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | {"name": "Fixed Plant"} | 323922 | TRUE | TRUE | 2026-03-23T06:02:12.519662+00:00 | 2026-03-23T14:02:12.519662+08:00 | #71804 - CLB: 250hrs - CLB CD5C BIN LINER PROJECT | 2.0 | TRUE |  | 2026-11-24T04:00:00+00:00 | 2026-12-04T14:00:00+00:00 | 2026-11-24T12:00:00+08:00 | 2026-12-04T22:00:00+08:00 |  |  |  |  | 250.00 | CLB CD5C Bin Liner Project | Realign Bin Liner Project start 24/11 reduce SL11 impact with CD3P overlap |  | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ad335d87-3c53-4798-8bef-230f0198a8f1", "emailAddress": "dwayne.clarke@riotinto.com", "displayName": "Clarke, Dwayne (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "55436276-1baf-407b-bb99-9599270ea9ef", "emailAddress": "Adam.Parsons@riotinto.com", "displayName": "Parsons, Adam (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 76ece3aa-944d-4ce5-b660-14e60dba1fa4 | Ellis, Robert 1 (RTIO) | Scheduled | CLB | Australia/Perth
83321 | 2026-07-02T05:06:19.5588444+00:00 | 2026-07-02T13:06:19.5588444+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:23:20.1016705+00:00 | 2026-07-29T10:23:20.1016705+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330490 | TRUE | TRUE | 2026-07-29T02:23:20.1016705+00:00 | 2026-07-29T10:23:20.1016705+08:00 | #83321 - WAN: 120hrs - 06R268 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-02-14T22:00:00+00:00 | 2027-02-19T22:00:00+00:00 | 2027-02-15T06:00:00+08:00 | 2027-02-20T06:00:00+08:00 |  |  |  |  | 120.00 | 06R268 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R268 | [{"equipmentGUID": "5729f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R268", "name": "06R268 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83320 | 2026-07-02T05:06:19.5587389+00:00 | 2026-07-02T13:06:19.5587389+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:24:13.8692258+00:00 | 2026-07-29T10:24:13.8692258+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330491 | TRUE | TRUE | 2026-07-29T02:24:13.8692258+00:00 | 2026-07-29T10:24:13.8692258+08:00 | #83320 - HD4: 120hrs - 06D391 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-03-14T22:00:00+00:00 | 2027-03-19T22:00:00+00:00 | 2027-03-15T06:00:00+08:00 | 2027-03-20T06:00:00+08:00 |  |  |  |  | 120.00 | 06D391 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06D391 | [{"equipmentGUID": "c126f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D391", "name": "06D391 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83324 | 2026-07-02T05:06:19.5591561+00:00 | 2026-07-02T13:06:19.5591561+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:25:51.8389064+00:00 | 2026-07-29T10:25:51.8389064+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330492 | TRUE | TRUE | 2026-07-29T02:25:51.8389064+00:00 | 2026-07-29T10:25:51.8389064+08:00 | #83324 - BM2: 120hrs - 06H328 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-05-23T22:00:00+00:00 | 2027-05-28T22:00:00+00:00 | 2027-05-24T06:00:00+08:00 | 2027-05-29T06:00:00+08:00 |  |  |  |  | 120.00 | 06H328 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H328 | [{"equipmentGUID": "3eece8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H328", "name": "06H328 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83329 | 2026-07-02T05:06:19.5596644+00:00 | 2026-07-02T13:06:19.5596644+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:27:21.9661373+00:00 | 2026-07-29T10:27:21.9661373+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330493 | TRUE | TRUE | 2026-07-29T02:27:21.9661373+00:00 | 2026-07-29T10:27:21.9661373+08:00 | #83329 - BM2: 120hrs - 06H793 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-06-13T22:00:00+00:00 | 2027-06-18T22:00:00+00:00 | 2027-06-14T06:00:00+08:00 | 2027-06-19T06:00:00+08:00 |  |  |  |  | 120.00 | 06H793 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H793 | [{"equipmentGUID": "623bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H793", "name": "06H793 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83328 | 2026-07-02T05:06:19.5595603+00:00 | 2026-07-02T13:06:19.5595603+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:28:33.9920968+00:00 | 2026-07-29T10:28:33.9920968+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330494 | TRUE | TRUE | 2026-07-29T02:28:33.9920968+00:00 | 2026-07-29T10:28:33.9920968+08:00 | #83328 - BM2: 120hrs - 06H794 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-06-06T22:00:00+00:00 | 2027-06-11T22:00:00+00:00 | 2027-06-07T06:00:00+08:00 | 2027-06-12T06:00:00+08:00 |  |  |  |  | 120.00 | 06H794 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H794 | [{"equipmentGUID": "d51bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H794", "name": "06H794 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83330 | 2026-07-02T05:06:19.5597627+00:00 | 2026-07-02T13:06:19.5597627+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:33:00.7556073+00:00 | 2026-07-29T10:33:00.7556073+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330496 | TRUE | TRUE | 2026-07-29T02:33:00.7556073+00:00 | 2026-07-29T10:33:00.7556073+08:00 | #83330 - WAN: 120hrs - 06R269 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-05-02T22:00:00+00:00 | 2027-05-07T22:00:00+00:00 | 2027-05-03T06:00:00+08:00 | 2027-05-08T06:00:00+08:00 |  |  |  |  | 120.00 | 06R269 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R269 | [{"equipmentGUID": "cc30f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R269", "name": "06R269 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83323 | 2026-07-02T05:06:19.5590474+00:00 | 2026-07-02T13:06:19.5590474+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:34:04.68087+00:00 | 2026-07-29T10:34:04.68087+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330498 | TRUE | TRUE | 2026-07-29T02:34:04.68087+00:00 | 2026-07-29T10:34:04.68087+08:00 | #83323 - WAN: 120hrs - 06R271 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-04-25T22:00:00+00:00 | 2027-04-30T22:00:00+00:00 | 2027-04-26T06:00:00+08:00 | 2027-05-01T06:00:00+08:00 |  |  |  |  | 120.00 | 06R271 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R271 | [{"equipmentGUID": "0915f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R271", "name": "06R271 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83322 | 2026-07-02T05:06:19.5589481+00:00 | 2026-07-02T13:06:19.5589481+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:35:11.6071404+00:00 | 2026-07-29T10:35:11.6071404+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330499 | TRUE | TRUE | 2026-07-29T02:35:11.6071404+00:00 | 2026-07-29T10:35:11.6071404+08:00 | #83322 - HD4: 120hrs - 06D28 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-05-02T22:00:00+00:00 | 2027-05-07T22:00:00+00:00 | 2027-05-03T06:00:00+08:00 | 2027-05-08T06:00:00+08:00 |  |  |  |  | 120.00 | 06D28 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06D28 | [{"equipmentGUID": "d610f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D28", "name": "06D28 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83326 | 2026-07-02T05:06:19.5593615+00:00 | 2026-07-02T13:06:19.5593615+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:36:16.7010376+00:00 | 2026-07-29T10:36:16.7010376+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330500 | TRUE | TRUE | 2026-07-29T02:36:16.7010376+00:00 | 2026-07-29T10:36:16.7010376+08:00 | #83326 - HD4: 120hrs - 06D594 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-06-06T22:00:00+00:00 | 2027-06-11T22:00:00+00:00 | 2027-06-07T06:00:00+08:00 | 2027-06-12T06:00:00+08:00 |  |  |  |  | 120.00 | 06D594 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06D594 | [{"equipmentGUID": "2dcf00c0-7c7b-ee11-a846-000d3acacefd", "code": "06D594", "name": "06D594 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83332 | 2026-07-02T05:06:19.5599648+00:00 | 2026-07-02T13:06:19.5599648+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:37:11.8794693+00:00 | 2026-07-29T10:37:11.8794693+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330501 | TRUE | TRUE | 2026-07-29T02:37:11.8794693+00:00 | 2026-07-29T10:37:11.8794693+08:00 | #83332 - HD4: 120hrs - 06D779 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-07-18T22:00:00+00:00 | 2027-07-23T22:00:00+00:00 | 2027-07-19T06:00:00+08:00 | 2027-07-24T06:00:00+08:00 |  |  |  |  | 120.00 | 06D779 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06D779 | [{"equipmentGUID": "a729f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D779", "name": "06D779 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83331 | 2026-07-02T05:06:19.5598639+00:00 | 2026-07-02T13:06:19.5598639+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:38:25.286778+00:00 | 2026-07-29T10:38:25.286778+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330502 | TRUE | TRUE | 2026-07-29T02:38:25.286778+00:00 | 2026-07-29T10:38:25.286778+08:00 | #83331 - HD4: 120hrs - 06H869 KOMATSU 830E-1AC HAUL TRUCK | 2.0 | FALSE |  | 2027-03-21T22:00:00+00:00 | 2027-03-26T22:00:00+00:00 | 2027-03-22T06:00:00+08:00 | 2027-03-27T06:00:00+08:00 |  |  |  |  | 120.00 | 06H869 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H869 | [{"equipmentGUID": "af2af6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H869", "name": "06H869 Komatsu 830E-1AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83340 | 2026-07-02T05:06:19.5609557+00:00 | 2026-07-02T13:06:19.5609557+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:39:38.1162019+00:00 | 2026-07-29T10:39:38.1162019+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330503 | TRUE | TRUE | 2026-07-29T02:39:38.1162019+00:00 | 2026-07-29T10:39:38.1162019+08:00 | #83340 - RVA: 120hrs - 06D36 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-01-17T22:00:00+00:00 | 2027-01-22T22:00:00+00:00 | 2027-01-18T06:00:00+08:00 | 2027-01-23T06:00:00+08:00 |  |  |  |  | 120.00 | 06D36 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06D36 | [{"equipmentGUID": "0b11f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D36", "name": "06D36 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | RVA | Australia/Perth |  | Site Team
83334 | 2026-07-02T05:06:19.5601659+00:00 | 2026-07-02T13:06:19.5601659+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:41:09.4246403+00:00 | 2026-07-29T10:41:09.4246403+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330505 | TRUE | TRUE | 2026-07-29T02:41:09.4246403+00:00 | 2026-07-29T10:41:09.4246403+08:00 | #83334 - RVA: 120hrs - 06R605 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-02-21T22:00:00+00:00 | 2027-02-26T22:00:00+00:00 | 2027-02-22T06:00:00+08:00 | 2027-02-27T06:00:00+08:00 |  |  |  |  | 120.00 | 06R605 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R605 | [{"equipmentGUID": "ec26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R605", "name": "06R605 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | RVA | Australia/Perth |  | Site Team
83335 | 2026-07-02T05:06:19.5602644+00:00 | 2026-07-02T13:06:19.5602644+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:42:20.4497422+00:00 | 2026-07-29T10:42:20.4497422+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330507 | TRUE | TRUE | 2026-07-29T02:42:20.4497422+00:00 | 2026-07-29T10:42:20.4497422+08:00 | #83335 - BM2: 120hrs - 06H782 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-09-05T22:00:00+00:00 | 2027-09-10T22:00:00+00:00 | 2027-09-06T06:00:00+08:00 | 2027-09-11T06:00:00+08:00 |  |  |  |  | 120.00 | 06H782 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H782 | [{"equipmentGUID": "ccdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H782", "name": "06H782 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83342 | 2026-07-02T05:06:19.561243+00:00 | 2026-07-02T13:06:19.561243+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:43:08.1960031+00:00 | 2026-07-29T10:43:08.1960031+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330508 | TRUE | TRUE | 2026-07-29T02:43:08.1960031+00:00 | 2026-07-29T10:43:08.1960031+08:00 | #83342 - BM2: 120hrs - 06H835 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-10T22:00:00+00:00 | 2027-10-15T22:00:00+00:00 | 2027-10-11T06:00:00+08:00 | 2027-10-16T06:00:00+08:00 |  |  |  |  | 120.00 | 06H835 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H835 | [{"equipmentGUID": "86d600c0-7c7b-ee11-a846-000d3acacefd", "code": "06H835", "name": "06H835 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83336 | 2026-07-02T05:06:19.5603656+00:00 | 2026-07-02T13:06:19.5603656+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:44:11.3974804+00:00 | 2026-07-29T10:44:11.3974804+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330509 | TRUE | TRUE | 2026-07-29T02:44:11.3974804+00:00 | 2026-07-29T10:44:11.3974804+08:00 | #83336 - BM2: 120hrs - 06H851 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-08-08T22:00:00+00:00 | 2027-08-13T22:00:00+00:00 | 2027-08-09T06:00:00+08:00 | 2027-08-14T06:00:00+08:00 |  |  |  |  | 120.00 | 06H851 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H851 | [{"equipmentGUID": "6f13f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H851", "name": "06H851 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83338 | 2026-07-02T05:06:19.560562+00:00 | 2026-07-02T13:06:19.560562+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:45:18.7309096+00:00 | 2026-07-29T10:45:18.7309096+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330510 | TRUE | TRUE | 2026-07-29T02:45:18.7309096+00:00 | 2026-07-29T10:45:18.7309096+08:00 | #83338 - WAN: 120hrs - 06R270 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-07-04T22:00:00+00:00 | 2027-07-09T22:00:00+00:00 | 2027-07-05T06:00:00+08:00 | 2027-07-10T06:00:00+08:00 |  |  |  |  | 120.00 | 06R270 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R270 | [{"equipmentGUID": "232cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R270", "name": "06R270 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83339 | 2026-07-02T05:06:19.5607774+00:00 | 2026-07-02T13:06:19.5607774+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:46:13.2584181+00:00 | 2026-07-29T10:46:13.2584181+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330511 | TRUE | TRUE | 2026-07-29T02:46:13.2584181+00:00 | 2026-07-29T10:46:13.2584181+08:00 | #83339 - WAN: 120hrs - 06R642 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-09-19T22:00:00+00:00 | 2027-09-24T22:00:00+00:00 | 2027-09-20T06:00:00+08:00 | 2027-09-25T06:00:00+08:00 |  |  |  |  | 120.00 | 06R642 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R642 | [{"equipmentGUID": "7343f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R642", "name": "06R642 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83333 | 2026-07-02T05:06:19.5600646+00:00 | 2026-07-02T13:06:19.5600646+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:52:36.3176713+00:00 | 2026-07-29T10:52:36.3176713+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330512 | TRUE | TRUE | 2026-07-29T02:52:36.3176713+00:00 | 2026-07-29T10:52:36.3176713+08:00 | #83333 - WAN: 120hrs - 06R660 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-03-07T22:00:00+00:00 | 2027-03-12T22:00:00+00:00 | 2027-03-08T06:00:00+08:00 | 2027-03-13T06:00:00+08:00 |  |  |  |  | 120.00 | 06R660 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R660 | [{"equipmentGUID": "482af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R660", "name": "06R660 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83337 | 2026-07-02T05:06:19.5604624+00:00 | 2026-07-02T13:06:19.5604624+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:55:19.1428628+00:00 | 2026-07-29T10:55:19.1428628+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330515 | TRUE | TRUE | 2026-07-29T02:55:19.1428628+00:00 | 2026-07-29T10:55:19.1428628+08:00 | #83337 - YAN: 120hrs - 06H784 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-12-12T22:00:00+00:00 | 2027-12-17T22:00:00+00:00 | 2027-12-13T06:00:00+08:00 | 2027-12-18T06:00:00+08:00 |  |  |  |  | 120.00 | 06H784 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H784 | [{"equipmentGUID": "6b41f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H784", "name": "06H784 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83346 | 2026-07-02T05:06:19.5616798+00:00 | 2026-07-02T13:06:19.5616798+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T02:56:36.1990029+00:00 | 2026-07-29T10:56:36.1990029+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330516 | TRUE | TRUE | 2026-07-29T02:56:36.1990029+00:00 | 2026-07-29T10:56:36.1990029+08:00 | #83346 - RVJ: 120hrs - 06R607 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-09-19T22:00:00+00:00 | 2027-09-24T22:00:00+00:00 | 2027-09-20T06:00:00+08:00 | 2027-09-25T06:00:00+08:00 |  |  |  |  | 120.00 | 06R607 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R607 | [{"equipmentGUID": "78efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R607", "name": "06R607 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
83357 | 2026-07-02T05:06:19.5628566+00:00 | 2026-07-02T13:06:19.5628566+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:00:27.4104726+00:00 | 2026-07-29T11:00:27.4104726+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330517 | TRUE | TRUE | 2026-07-29T03:00:27.4104726+00:00 | 2026-07-29T11:00:27.4104726+08:00 | #83357 - NBWT: 120hrs - 06H483 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-24T22:00:00+00:00 | 2027-10-29T22:00:00+00:00 | 2027-10-25T06:00:00+08:00 | 2027-10-30T06:00:00+08:00 |  |  |  |  | 120.00 | 06H483 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H483 | [{"equipmentGUID": "26e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H483", "name": "06H483 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | NBWT | Australia/Perth |  | Site Team
83354 | 2026-07-02T05:06:19.5625608+00:00 | 2026-07-02T13:06:19.5625608+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:01:43.9052865+00:00 | 2026-07-29T11:01:43.9052865+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330518 | TRUE | TRUE | 2026-07-29T03:01:43.9052865+00:00 | 2026-07-29T11:01:43.9052865+08:00 | #83354 - BM4: 120hrs - 06H436 KOMATSU 830E-5AT HAUL TRUCK | 2.0 | FALSE |  | 2027-11-28T22:00:00+00:00 | 2027-12-03T22:00:00+00:00 | 2027-11-29T06:00:00+08:00 | 2027-12-04T06:00:00+08:00 |  |  |  |  | 120.00 | 06H436 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H436 | [{"equipmentGUID": "dd32f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H436", "name": "06H436 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM4 | Australia/Perth |  | Site Team
83352 | 2026-07-02T05:06:19.5623653+00:00 | 2026-07-02T13:06:19.5623653+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:03:20.7241649+00:00 | 2026-07-29T11:03:20.7241649+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330519 | TRUE | TRUE | 2026-07-29T03:03:20.7241649+00:00 | 2026-07-29T11:03:20.7241649+08:00 | #83352 - BM4: 120hrs - 06H437 KOMATSU 830E-5AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-31T22:00:00+00:00 | 2027-11-05T22:00:00+00:00 | 2027-11-01T06:00:00+08:00 | 2027-11-06T06:00:00+08:00 |  |  |  |  | 120.00 | 06H437 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H437 | [{"equipmentGUID": "ba0bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H437", "name": "06H437 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM4 | Australia/Perth |  | Site Team
83351 | 2026-07-02T05:06:19.5622614+00:00 | 2026-07-02T13:06:19.5622614+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:04:18.8912813+00:00 | 2026-07-29T11:04:18.8912813+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330520 | TRUE | TRUE | 2026-07-29T03:04:18.8912813+00:00 | 2026-07-29T11:04:18.8912813+08:00 | #83351 - BM4: 120hrs - 06H993 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-24T22:00:00+00:00 | 2027-10-29T22:00:00+00:00 | 2027-10-25T06:00:00+08:00 | 2027-10-30T06:00:00+08:00 |  |  |  |  | 120.00 | 06H993 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H993 | [{"equipmentGUID": "3237f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H993", "name": "06H993 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | BM4 | Australia/Perth |  | Site Team
83345 | 2026-07-02T05:06:19.5615803+00:00 | 2026-07-02T13:06:19.5615803+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:05:50.0157445+00:00 | 2026-07-29T11:05:50.0157445+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330521 | TRUE | TRUE | 2026-07-29T03:05:50.0157445+00:00 | 2026-07-29T11:05:50.0157445+08:00 | #83345 - WAN: 120hrs - 06R728 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-09-12T22:00:00+00:00 | 2027-09-17T22:00:00+00:00 | 2027-09-13T06:00:00+08:00 | 2027-09-18T06:00:00+08:00 |  |  |  |  | 120.00 | 06R728 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R728 | [{"equipmentGUID": "bc70fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R728", "name": "06R728 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83350 | 2026-07-02T05:06:19.5621333+00:00 | 2026-07-02T13:06:19.5621333+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:06:52.0235573+00:00 | 2026-07-29T11:06:52.0235573+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330522 | TRUE | TRUE | 2026-07-29T03:06:52.0235573+00:00 | 2026-07-29T11:06:52.0235573+08:00 | #83350 - WAN: 120hrs - 06R895 KOMATSU 930E-4AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-17T22:00:00+00:00 | 2027-10-22T22:00:00+00:00 | 2027-10-18T06:00:00+08:00 | 2027-10-23T06:00:00+08:00 |  |  |  |  | 120.00 | 06R895 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06R895 | [{"equipmentGUID": "0219f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R895", "name": "06R895 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83344 | 2026-07-02T05:06:19.5614793+00:00 | 2026-07-02T13:06:19.5614793+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:08:09.4829745+00:00 | 2026-07-29T11:08:09.4829745+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330523 | TRUE | TRUE | 2026-07-29T03:08:09.4829745+00:00 | 2026-07-29T11:08:09.4829745+08:00 | #83344 - HD4: 120hrs - 06H156 KOMATSU 830E-1AT HAUL TRUCK | 2.0 | FALSE |  | 2027-10-24T22:00:00+00:00 | 2027-10-29T22:00:00+00:00 | 2027-10-25T06:00:00+08:00 | 2027-10-30T06:00:00+08:00 |  |  |  |  | 120.00 | 06H156 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H156 | [{"equipmentGUID": "9152fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H156", "name": "06H156 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83349 | 2026-07-02T05:06:19.5619718+00:00 | 2026-07-02T13:06:19.5619718+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:09:34.1913466+00:00 | 2026-07-29T11:09:34.1913466+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330524 | TRUE | TRUE | 2026-07-29T03:09:34.1913466+00:00 | 2026-07-29T11:09:34.1913466+08:00 | #83349 - HD4: 120hrs - 06H277 KOMATSU 830E-1AC HAUL TRUCK | 2.0 | FALSE |  | 2027-11-07T22:00:00+00:00 | 2027-11-12T22:00:00+00:00 | 2027-11-08T06:00:00+08:00 | 2027-11-13T06:00:00+08:00 |  |  |  |  | 120.00 | 06H277 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H277 | [{"equipmentGUID": "b5dae8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H277", "name": "06H277 Komatsu 830E-1AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
83347 | 2026-07-02T05:06:19.5617766+00:00 | 2026-07-02T13:06:19.5617766+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-29T03:10:54.5099324+00:00 | 2026-07-29T11:10:54.5099324+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | {"name": "HME"} | 330525 | TRUE | TRUE | 2026-07-29T03:10:54.5099324+00:00 | 2026-07-29T11:10:54.5099324+08:00 | #83347 - HD4: 120hrs - 06H722 KOMATSU 830E-1AC HAUL TRUCK | 2.0 | FALSE |  | 2027-05-30T22:00:00+00:00 | 2027-06-04T22:00:00+00:00 | 2027-05-31T06:00:00+08:00 | 2027-06-05T06:00:00+08:00 |  |  |  |  | 120.00 | 06H722 C/O Engine Module | Date change as requested by Neil McIlhatton 29/07/26 | S06H722 | [{"equipmentGUID": "d017f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H722", "name": "06H722 Komatsu 830E-1AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Update | f1658d5a-306e-4ca3-b60a-20b36f47a157 | Solomon, Dale (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
68048 | 2025-06-30T01:08:21.5162255+00:00 | 2025-06-30T09:08:21.5162255+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2025-10-28T06:27:20.7483498+00:00 | 2025-10-28T14:27:20.7483498+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 265249 | TRUE | TRUE | 2025-10-28T06:27:20.7483498+00:00 | 2025-10-28T14:27:20.7483498+08:00 | #68048 - BM2: 120hrs - 06H818 KOMATSU 930E-4AT HAUL TRUCK | 1.1 | FALSE |  | 2026-12-13T22:00:00+00:00 | 2026-12-18T22:00:00+00:00 | 2026-12-14T06:00:00+08:00 | 2026-12-19T06:00:00+08:00 |  |  |  |  | 120.00 | C/O Engine Module |  |  | [{"equipmentGUID": "4a68fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H818", "name": "06H818 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "emailAddress": "Rogelio.Manlod@riotinto.com", "displayName": "Manlod, Rogelio (RTIO)"}}] | [] | [] | [{"name": "Engine Module Changeout"}] | [] | [] | Approved | Update | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
68046 | 2025-06-30T01:08:21.261767+00:00 | 2025-06-30T09:08:21.261767+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2025-10-28T06:27:21.142944+00:00 | 2025-10-28T14:27:21.142944+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 265250 | TRUE | TRUE | 2025-10-28T06:27:21.142944+00:00 | 2025-10-28T14:27:21.142944+08:00 | #68046 - BM2: 120hrs - 06H328 KOMATSU 930E-4AT HAUL TRUCK | 1.1 | FALSE |  | 2026-12-06T22:00:00+00:00 | 2026-12-11T22:00:00+00:00 | 2026-12-07T06:00:00+08:00 | 2026-12-12T06:00:00+08:00 |  |  |  |  | 120.00 | C/O Engine Module |  |  | [{"equipmentGUID": "3eece8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H328", "name": "06H328 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "emailAddress": "Rogelio.Manlod@riotinto.com", "displayName": "Manlod, Rogelio (RTIO)"}}] | [] | [] | [{"name": "Engine Module Changeout"}] | [] | [] | Approved | Update | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
68045 | 2025-06-30T01:08:21.1378118+00:00 | 2025-06-30T09:08:21.1378118+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2025-10-28T06:27:21.2095359+00:00 | 2025-10-28T14:27:21.2095359+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 265251 | TRUE | TRUE | 2025-10-28T06:27:21.2095359+00:00 | 2025-10-28T14:27:21.2095359+08:00 | #68045 - BM2: 120hrs - 06H826 KOMATSU 930E-4AT HAUL TRUCK | 1.1 | FALSE |  | 2026-11-29T22:00:00+00:00 | 2026-12-04T22:00:00+00:00 | 2026-11-30T06:00:00+08:00 | 2026-12-05T06:00:00+08:00 |  |  |  |  | 120.00 | C/O Engine Module |  |  | [{"equipmentGUID": "ac40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H826", "name": "06H826 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "emailAddress": "Rogelio.Manlod@riotinto.com", "displayName": "Manlod, Rogelio (RTIO)"}}] | [] | [] | [{"name": "Engine Module Changeout"}] | [] | [] | Approved | Update | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83693 | 2026-08-14T04:24:24.2652143+00:00 | 2026-08-14T12:24:24.2652143+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-08-14T04:24:24.2652143+00:00 | 2026-08-14T12:24:24.2652143+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 331270 | TRUE | TRUE | 2026-08-14T04:24:24.2652143+00:00 | 2026-08-14T12:24:24.2652143+08:00 | #83693 - MDO: 427hrs - 06H673 CAT 777 WATER TRUCK | 1.0 | FALSE |  | 2027-06-14T16:00:00+00:00 | 2027-07-02T11:00:00+00:00 | 2027-06-15T00:00:00+08:00 | 2027-07-02T19:00:00+08:00 | 2027-06-12T16:00:00+00:00 | 2027-07-04T11:00:00+00:00 | 2027-06-13T00:00:00+08:00 | 2027-07-04T19:00:00+08:00 | 427.00 | 18,000 hrs Shut |  |  | [{"equipmentGUID": "1c08f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H673", "name": "06H673 CAT 777 Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83412 | 2026-07-02T10:30:03.987446+00:00 | 2026-07-02T18:30:03.987446+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T10:30:03.987446+00:00 | 2026-07-02T18:30:03.987446+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329244 | TRUE | TRUE | 2026-07-02T10:30:03.987446+00:00 | 2026-07-02T18:30:03.987446+08:00 | #83412 - HD1: 1464hrs - 06D11 CAT 777F WATER TRUCK | 1.0 | FALSE |  | 2027-05-02T16:00:00+00:00 | 2027-07-02T16:00:00+00:00 | 2027-05-03T00:00:00+08:00 | 2027-07-03T00:00:00+08:00 |  |  |  |  | 1464.00 | Engine & Major Components |  |  | [{"equipmentGUID": "b213f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D11", "name": "06D11 CAT 777F Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | HD1 | Australia/Perth |  | OSR
83416 | 2026-07-02T11:04:30.6628319+00:00 | 2026-07-02T19:04:30.6628319+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:04:30.6628319+00:00 | 2026-07-02T19:04:30.6628319+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329248 | TRUE | TRUE | 2026-07-02T11:04:30.6628319+00:00 | 2026-07-02T19:04:30.6628319+08:00 | #83416 - PDO: 1288hrs - 06H162 CAT 785C WATER TRUCK | 1.0 | FALSE |  | 2027-05-02T16:00:00+00:00 | 2027-06-25T08:00:00+00:00 | 2027-05-03T00:00:00+08:00 | 2027-06-25T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Halflife |  |  | [{"equipmentGUID": "9573fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H162", "name": "06H162 CAT 785C Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Water Tank Overhaul"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | PDO | Australia/Perth |  | OSR
83417 | 2026-07-02T11:12:27.1698519+00:00 | 2026-07-02T19:12:27.1698519+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:12:27.1698519+00:00 | 2026-07-02T19:12:27.1698519+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329249 | TRUE | TRUE | 2026-07-02T11:12:27.1698519+00:00 | 2026-07-02T19:12:27.1698519+08:00 | #83417 - PDO: 1288hrs - 06H595 CAT 777G WATER TRUCK | 1.0 | FALSE |  | 2027-09-12T16:00:00+00:00 | 2027-11-05T08:00:00+00:00 | 2027-09-13T00:00:00+08:00 | 2027-11-05T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Water Truck Half-life |  |  | [{"equipmentGUID": "dcda00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H595", "name": "06H595 CAT 777G Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Water Tank Overhaul"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | PDO | Australia/Perth |  | OSR
83418 | 2026-07-02T11:21:01.3122953+00:00 | 2026-07-02T19:21:01.3122953+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:21:01.3122953+00:00 | 2026-07-02T19:21:01.3122953+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329250 | TRUE | TRUE | 2026-07-02T11:21:01.3122953+00:00 | 2026-07-02T19:21:01.3122953+08:00 | #83418 - MTP: 1288hrs - 06H55 CAT 777F WATER TRUCK | 1.0 | FALSE |  | 2027-01-10T16:00:00+00:00 | 2027-03-05T08:00:00+00:00 | 2027-01-11T00:00:00+08:00 | 2027-03-05T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "f1e000c0-7c7b-ee11-a846-000d3acacefd", "code": "06H55", "name": "06H55 CAT 777F Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | MTP | Australia/Perth |  | Site Team
83419 | 2026-07-02T11:27:58.8395984+00:00 | 2026-07-02T19:27:58.8395984+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:27:58.8395984+00:00 | 2026-07-02T19:27:58.8395984+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329251 | TRUE | TRUE | 2026-07-02T11:27:58.8395984+00:00 | 2026-07-02T19:27:58.8395984+08:00 | #83419 - MTP: 1288hrs - 06H721 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-07-14T16:00:00+00:00 | 2027-09-06T08:00:00+00:00 | 2027-07-15T00:00:00+08:00 | 2027-09-06T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Water Truck Half-life |  |  | [{"equipmentGUID": "5411f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H721", "name": "06H721 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | MTP | Australia/Perth |  | OSR
83420 | 2026-07-02T11:32:41.6921407+00:00 | 2026-07-02T19:32:41.6921407+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:32:41.6921407+00:00 | 2026-07-02T19:32:41.6921407+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329252 | TRUE | TRUE | 2026-07-02T11:32:41.6921407+00:00 | 2026-07-02T19:32:41.6921407+08:00 | #83420 - MTP: 1288hrs - 06H729 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-11-14T16:00:00+00:00 | 2028-01-07T08:00:00+00:00 | 2027-11-15T00:00:00+08:00 | 2028-01-07T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Water Truck Half-life |  |  | [{"equipmentGUID": "36d900c0-7c7b-ee11-a846-000d3acacefd", "code": "06H729", "name": "06H729 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | MTP | Australia/Perth |  | OSR
83421 | 2026-07-02T11:39:32.0529398+00:00 | 2026-07-02T19:39:32.0529398+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:39:32.0529398+00:00 | 2026-07-02T19:39:32.0529398+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329253 | TRUE | TRUE | 2026-07-02T11:39:32.0529398+00:00 | 2026-07-02T19:39:32.0529398+08:00 | #83421 - HD4: 400hrs - 06H217 CAT 777D WATER TRUCK | 1.0 | FALSE |  | 2027-09-12T16:00:00+00:00 | 2027-09-29T08:00:00+00:00 | 2027-09-13T00:00:00+08:00 | 2027-09-29T16:00:00+08:00 |  |  |  |  | 400.00 | Engine & Major components |  |  | [{"equipmentGUID": "b121f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H217", "name": "06H217 CAT 777D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | HD4 | Australia/Perth |  | Site Team
83422 | 2026-07-02T11:55:43.0037992+00:00 | 2026-07-02T19:55:43.0037992+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T11:55:43.0037992+00:00 | 2026-07-02T19:55:43.0037992+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329254 | TRUE | TRUE | 2026-07-02T11:55:43.0037992+00:00 | 2026-07-02T19:55:43.0037992+08:00 | #83422 - WAN: 1288hrs - 06H109 CAT 785C WATER TRUCK | 1.0 | FALSE |  | 2027-02-14T16:00:00+00:00 | 2027-04-09T08:00:00+00:00 | 2027-02-15T00:00:00+08:00 | 2027-04-09T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "90e0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H109", "name": "06H109 CAT 785C Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | WAN | Australia/Perth |  | OSR
83424 | 2026-07-02T12:09:25.0814745+00:00 | 2026-07-02T20:09:25.0814745+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:09:25.0814745+00:00 | 2026-07-02T20:09:25.0814745+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329256 | TRUE | TRUE | 2026-07-02T12:09:25.0814745+00:00 | 2026-07-02T20:09:25.0814745+08:00 | #83424 - WAN: 1288hrs - 06R915 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-08-08T16:00:00+00:00 | 2027-10-01T08:00:00+00:00 | 2027-08-09T00:00:00+08:00 | 2027-10-01T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "6f50fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R915", "name": "06R915 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | WAN | Australia/Perth |  | OSR
83425 | 2026-07-02T12:15:08.8049925+00:00 | 2026-07-02T20:15:08.8049925+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:15:08.8049925+00:00 | 2026-07-02T20:15:08.8049925+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329257 | TRUE | TRUE | 2026-07-02T12:15:08.8049925+00:00 | 2026-07-02T20:15:08.8049925+08:00 | #83425 - WAN: 1288hrs - 06R600 CAT 777G WATER TRUCK | 1.0 | FALSE |  | 2027-10-10T16:00:00+00:00 | 2027-12-03T08:00:00+00:00 | 2027-10-11T00:00:00+08:00 | 2027-12-03T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "7df4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R600", "name": "06R600 CAT 777G Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | WAN | Australia/Perth |  | OSR
83426 | 2026-07-02T12:21:00.3793193+00:00 | 2026-07-02T20:21:00.3793193+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:21:00.3793193+00:00 | 2026-07-02T20:21:00.3793193+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329258 | TRUE | TRUE | 2026-07-02T12:21:00.3793193+00:00 | 2026-07-02T20:21:00.3793193+08:00 | #83426 - YAN: 1288hrs - 06H110 CAT 777D WATER TRUCK | 1.0 | FALSE |  | 2027-04-04T16:00:00+00:00 | 2027-05-28T08:00:00+00:00 | 2027-04-05T00:00:00+08:00 | 2027-05-28T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Water Truck Half Life |  |  | [{"equipmentGUID": "4320f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H110", "name": "06H110 CAT 777D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | YAN | Australia/Perth |  | OSR
83427 | 2026-07-02T12:29:17.3359796+00:00 | 2026-07-02T20:29:17.3359796+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:29:17.3359796+00:00 | 2026-07-02T20:29:17.3359796+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329259 | TRUE | TRUE | 2026-07-02T12:29:17.3359796+00:00 | 2026-07-02T20:29:17.3359796+08:00 | #83427 - YAN: 1288hrs - 06H836 CAT 777G WATER TRUCK | 1.0 | FALSE |  | 2027-09-12T16:00:00+00:00 | 2027-11-05T08:00:00+00:00 | 2027-09-13T00:00:00+08:00 | 2027-11-05T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "516afbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H836", "name": "06H836 CAT 777G Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | YAN | Australia/Perth |  | OSR
83428 | 2026-07-02T12:35:15.929137+00:00 | 2026-07-02T20:35:15.929137+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:35:15.929137+00:00 | 2026-07-02T20:35:15.929137+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329260 | TRUE | TRUE | 2026-07-02T12:35:15.929137+00:00 | 2026-07-02T20:35:15.929137+08:00 | #83428 - YAN: 1288hrs - 06H599 CAT 777G WATER TRUCK | 1.0 | FALSE |  | 2027-02-02T16:00:00+00:00 | 2027-03-28T08:00:00+00:00 | 2027-02-03T00:00:00+08:00 | 2027-03-28T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "a62df6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H599", "name": "06H599 CAT 777G Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | YAN | Australia/Perth |  | OSR
83429 | 2026-07-02T12:39:37.8055332+00:00 | 2026-07-02T20:39:37.8055332+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:39:37.8055332+00:00 | 2026-07-02T20:39:37.8055332+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329261 | TRUE | TRUE | 2026-07-02T12:39:37.8055332+00:00 | 2026-07-02T20:39:37.8055332+08:00 | #83429 - BM4: 1288hrs - 06H637 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-03-01T16:00:00+00:00 | 2027-04-24T08:00:00+00:00 | 2027-03-02T00:00:00+08:00 | 2027-04-24T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major components - Water Truck Half-life |  |  | [{"equipmentGUID": "9b3df6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H637", "name": "06H637 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Water Tank Overhaul"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | BM4 | Australia/Perth |  | OSR
83430 | 2026-07-02T12:43:12.8848403+00:00 | 2026-07-02T20:43:12.8848403+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:43:12.8848403+00:00 | 2026-07-02T20:43:12.8848403+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329262 | TRUE | TRUE | 2026-07-02T12:43:12.8848403+00:00 | 2026-07-02T20:43:12.8848403+08:00 | #83430 - BM4: 1288hrs - 06H678 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-11-12T16:00:00+00:00 | 2028-01-05T08:00:00+00:00 | 2027-11-13T00:00:00+08:00 | 2028-01-05T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "ded9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H678", "name": "06H678 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | BM4 | Australia/Perth |  | OSR
83431 | 2026-07-02T12:49:26.5040394+00:00 | 2026-07-02T20:49:26.5040394+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:49:26.5040394+00:00 | 2026-07-02T20:49:26.5040394+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329263 | TRUE | TRUE | 2026-07-02T12:49:26.5040394+00:00 | 2026-07-02T20:49:26.5040394+08:00 | #83431 - BM4: 1288hrs - 06H679 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-07-04T16:00:00+00:00 | 2027-08-27T08:00:00+00:00 | 2027-07-05T00:00:00+08:00 | 2027-08-27T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "bfe8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H679", "name": "06H679 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | BM4 | Australia/Perth |  | OSR
83432 | 2026-07-02T12:54:01.6631394+00:00 | 2026-07-02T20:54:01.6631394+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T12:54:01.6631394+00:00 | 2026-07-02T20:54:01.6631394+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329264 | TRUE | TRUE | 2026-07-02T12:54:01.6631394+00:00 | 2026-07-02T20:54:01.6631394+08:00 | #83432 - BM4: 1288hrs - 06H657 CAT 785D WATER TRUCK | 1.0 | FALSE |  | 2027-09-01T16:00:00+00:00 | 2027-10-25T08:00:00+00:00 | 2027-09-02T00:00:00+08:00 | 2027-10-25T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components |  |  | [{"equipmentGUID": "725ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H657", "name": "06H657 CAT 785D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | BM4 | Australia/Perth |  | OSR
83433 | 2026-07-02T13:05:31.8561701+00:00 | 2026-07-02T21:05:31.8561701+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T13:05:31.8561701+00:00 | 2026-07-02T21:05:31.8561701+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329265 | TRUE | TRUE | 2026-07-02T13:05:31.8561701+00:00 | 2026-07-02T21:05:31.8561701+08:00 | #83433 - RVA: 1288hrs - 06R0070 CAT 785C WATER TRUCK | 1.0 | FALSE |  | 2027-06-14T16:00:00+00:00 | 2027-08-07T08:00:00+00:00 | 2027-06-15T00:00:00+08:00 | 2027-08-07T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Shut cancelled in 2026 |  |  | [{"equipmentGUID": "66e9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R0070", "name": "06R0070 CAT 785C Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Water Tank Overhaul"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | RVA | Australia/Perth |  | OSR
83434 | 2026-07-02T13:08:59.9642155+00:00 | 2026-07-02T21:08:59.9642155+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T13:08:59.9642155+00:00 | 2026-07-02T21:08:59.9642155+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329266 | TRUE | TRUE | 2026-07-02T13:08:59.9642155+00:00 | 2026-07-02T21:08:59.9642155+08:00 | #83434 - RVA: 380hrs - 06R34 CAT 777F WATER TRUCK | 1.0 | FALSE |  | 2027-03-01T16:00:00+00:00 | 2027-03-17T12:00:00+00:00 | 2027-03-02T00:00:00+08:00 | 2027-03-17T20:00:00+08:00 |  |  |  |  | 380.00 | Engine Change out |  |  | [{"equipmentGUID": "046cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R34", "name": "06R34 CAT 777F Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | RVA | Australia/Perth |  | Site Team
83435 | 2026-07-02T13:13:48.6134055+00:00 | 2026-07-02T21:13:48.6134055+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-02T13:13:48.6134055+00:00 | 2026-07-02T21:13:48.6134055+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329267 | TRUE | TRUE | 2026-07-02T13:13:48.6134055+00:00 | 2026-07-02T21:13:48.6134055+08:00 | #83435 - GDI: 1288hrs - 06B234 CAT 789D WATER TRUCK | 1.0 | FALSE |  | 2027-09-05T16:00:00+00:00 | 2027-10-29T08:00:00+00:00 | 2027-09-06T00:00:00+08:00 | 2027-10-29T16:00:00+08:00 |  |  |  |  | 1288.00 | Engine & Major Components - Tank Assessment |  |  | [{"equipmentGUID": "fcece8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B234", "name": "06B234 CAT 789D Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | GDI | Australia/Perth |  | OSR
83483 | 2026-07-09T00:33:21.1282932+00:00 | 2026-07-09T08:33:21.1282932+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-07-09T00:33:21.1282932+00:00 | 2026-07-09T08:33:21.1282932+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | {"name": "HME"} | 329725 | TRUE | TRUE | 2026-07-09T00:33:21.1282932+00:00 | 2026-07-09T08:33:21.1282932+08:00 | #83483 - NBWT: 488hrs - 06H072 KOMATSU HD785-7AT WATER TRUCK | 1.0 | FALSE |  | 2027-02-08T16:00:00+00:00 | 2027-03-01T00:00:00+00:00 | 2027-02-09T00:00:00+08:00 | 2027-03-01T08:00:00+08:00 |  |  |  |  | 488.00 | Engine & Major Components |  |  | [{"equipmentGUID": "616bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H072", "name": "06H072 Komatsu HD785-7AT Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | d02f8c57-5dce-4935-bccb-22784ffc8eea | Bellman, Tammera (RTIO) | Placeholder | NBWT | Australia/Perth |  | OSR
74443 | 2025-12-04T09:04:46.9786959+00:00 | 2025-12-04T17:04:46.9786959+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-17T04:51:54.5548249+00:00 | 2025-12-17T12:51:54.5548249+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281662 | TRUE | TRUE | 2025-12-17T04:51:54.5548249+00:00 | 2025-12-17T12:51:54.5548249+08:00 | #74443 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2026-12-26T22:00:00+00:00 | 2026-12-27T10:00:00+00:00 | 2026-12-27T06:00:00+08:00 | 2026-12-27T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
70826 | 2025-10-16T07:27:07.848321+00:00 | 2025-10-16T15:27:07.848321+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-19T05:28:31.2558452+00:00 | 2025-12-19T13:28:31.2558452+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282587 | TRUE | TRUE | 2025-12-19T05:28:31.2558452+00:00 | 2025-12-19T13:28:31.2558452+08:00 | #70826 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2026-12-13T23:00:00+00:00 | 2026-12-14T03:00:00+00:00 | 2026-12-14T07:00:00+08:00 | 2026-12-14T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70827 | 2025-10-16T07:27:08.4760712+00:00 | 2025-10-16T15:27:08.4760712+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-19T05:28:32.1561012+00:00 | 2025-12-19T13:28:32.1561012+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282589 | TRUE | TRUE | 2025-12-19T05:28:32.1561012+00:00 | 2025-12-19T13:28:32.1561012+08:00 | #70827 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2026-12-20T23:00:00+00:00 | 2026-12-21T03:00:00+00:00 | 2026-12-21T07:00:00+08:00 | 2026-12-21T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70828 | 2025-10-16T07:27:09.1636269+00:00 | 2025-10-16T15:27:09.1636269+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-19T05:28:33.0051672+00:00 | 2025-12-19T13:28:33.0051672+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282592 | TRUE | TRUE | 2025-12-19T05:28:33.0051672+00:00 | 2025-12-19T13:28:33.0051672+08:00 | #70828 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2026-12-27T23:00:00+00:00 | 2026-12-28T03:00:00+00:00 | 2026-12-28T07:00:00+08:00 | 2026-12-28T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
73745 | 2025-11-28T01:56:14.1262601+00:00 | 2025-11-28T09:56:14.1262601+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:53:50.8068366+00:00 | 2025-12-10T14:53:50.8068366+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281309 | TRUE | TRUE | 2025-12-10T06:53:50.8068366+00:00 | 2025-12-10T14:53:50.8068366+08:00 | #73745 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2028-01-29T22:00:00+00:00 | 2028-01-30T10:00:00+00:00 | 2028-01-30T06:00:00+08:00 | 2028-01-30T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73738 | 2025-11-28T01:56:11.7058089+00:00 | 2025-11-28T09:56:11.7058089+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:00.2817798+00:00 | 2025-12-10T14:54:00.2817798+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281316 | TRUE | TRUE | 2025-12-10T06:54:00.2817798+00:00 | 2025-12-10T14:54:00.2817798+08:00 | #73738 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-12-11T22:00:00+00:00 | 2027-12-12T10:00:00+00:00 | 2027-12-12T06:00:00+08:00 | 2027-12-12T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73734 | 2025-11-28T01:56:10.4628874+00:00 | 2025-11-28T09:56:10.4628874+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:05.9153996+00:00 | 2025-12-10T14:54:05.9153996+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281320 | TRUE | TRUE | 2025-12-10T06:54:05.9153996+00:00 | 2025-12-10T14:54:05.9153996+08:00 | #73734 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-11-13T22:00:00+00:00 | 2027-11-14T10:00:00+00:00 | 2027-11-14T06:00:00+08:00 | 2027-11-14T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73730 | 2025-11-28T01:56:09.3335337+00:00 | 2025-11-28T09:56:09.3335337+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:11.4188822+00:00 | 2025-12-10T14:54:11.4188822+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281324 | TRUE | TRUE | 2025-12-10T06:54:11.4188822+00:00 | 2025-12-10T14:54:11.4188822+08:00 | #73730 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-10-16T22:00:00+00:00 | 2027-10-17T10:00:00+00:00 | 2027-10-17T06:00:00+08:00 | 2027-10-17T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73725 | 2025-11-28T01:56:07.9363644+00:00 | 2025-11-28T09:56:07.9363644+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:18.4944774+00:00 | 2025-12-10T14:54:18.4944774+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281329 | TRUE | TRUE | 2025-12-10T06:54:18.4944774+00:00 | 2025-12-10T14:54:18.4944774+08:00 | #73725 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-09-11T22:00:00+00:00 | 2027-09-12T10:00:00+00:00 | 2027-09-12T06:00:00+08:00 | 2027-09-12T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73721 | 2025-11-28T01:56:06.7912544+00:00 | 2025-11-28T09:56:06.7912544+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:24.2402969+00:00 | 2025-12-10T14:54:24.2402969+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281333 | TRUE | TRUE | 2025-12-10T06:54:24.2402969+00:00 | 2025-12-10T14:54:24.2402969+08:00 | #73721 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-08-14T22:00:00+00:00 | 2027-08-15T10:00:00+00:00 | 2027-08-15T06:00:00+08:00 | 2027-08-15T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73717 | 2025-11-28T01:56:05.7305222+00:00 | 2025-11-28T09:56:05.7305222+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:29.5677291+00:00 | 2025-12-10T14:54:29.5677291+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281337 | TRUE | TRUE | 2025-12-10T06:54:29.5677291+00:00 | 2025-12-10T14:54:29.5677291+08:00 | #73717 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-07-17T22:00:00+00:00 | 2027-07-18T10:00:00+00:00 | 2027-07-18T06:00:00+08:00 | 2027-07-18T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73711 | 2025-11-28T01:56:04.1709854+00:00 | 2025-11-28T09:56:04.1709854+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:37.9294493+00:00 | 2025-12-10T14:54:37.9294493+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281343 | TRUE | TRUE | 2025-12-10T06:54:37.9294493+00:00 | 2025-12-10T14:54:37.9294493+08:00 | #73711 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-06-05T22:00:00+00:00 | 2027-06-06T10:00:00+00:00 | 2027-06-06T06:00:00+08:00 | 2027-06-06T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73708 | 2025-11-28T01:56:03.423931+00:00 | 2025-11-28T09:56:03.423931+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:42.437876+00:00 | 2025-12-10T14:54:42.437876+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281346 | TRUE | TRUE | 2025-12-10T06:54:42.437876+00:00 | 2025-12-10T14:54:42.437876+08:00 | #73708 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-05-15T22:00:00+00:00 | 2027-05-16T10:00:00+00:00 | 2027-05-16T06:00:00+08:00 | 2027-05-16T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73704 | 2025-11-28T01:56:02.5015516+00:00 | 2025-11-28T09:56:02.5015516+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:48.2096163+00:00 | 2025-12-10T14:54:48.2096163+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281350 | TRUE | TRUE | 2025-12-10T06:54:48.2096163+00:00 | 2025-12-10T14:54:48.2096163+08:00 | #73704 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-04-17T22:00:00+00:00 | 2027-04-18T10:00:00+00:00 | 2027-04-18T06:00:00+08:00 | 2027-04-18T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73699 | 2025-11-28T01:56:01.3561947+00:00 | 2025-11-28T09:56:01.3561947+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:54:56.1354003+00:00 | 2025-12-10T14:54:56.1354003+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281359 | TRUE | TRUE | 2025-12-10T06:54:56.1354003+00:00 | 2025-12-10T14:54:56.1354003+08:00 | #73699 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-03-13T22:00:00+00:00 | 2027-03-14T10:00:00+00:00 | 2027-03-14T06:00:00+08:00 | 2027-03-14T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73696 | 2025-11-28T01:56:00.713713+00:00 | 2025-11-28T09:56:00.713713+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:55:00.6891616+00:00 | 2025-12-10T14:55:00.6891616+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281365 | TRUE | TRUE | 2025-12-10T06:55:00.6891616+00:00 | 2025-12-10T14:55:00.6891616+08:00 | #73696 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-02-20T22:00:00+00:00 | 2027-02-21T10:00:00+00:00 | 2027-02-21T06:00:00+08:00 | 2027-02-21T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73692 | 2025-11-28T01:55:59.8775198+00:00 | 2025-11-28T09:55:59.8775198+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2025-12-10T06:55:07.7572932+00:00 | 2025-12-10T14:55:07.7572932+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 281373 | TRUE | TRUE | 2025-12-10T06:55:07.7572932+00:00 | 2025-12-10T14:55:07.7572932+08:00 | #73692 - HD4: 12hrs - BOO PLANT | 1.0 | TRUE |  | 2027-01-23T22:00:00+00:00 | 2027-01-24T10:00:00+00:00 | 2027-01-24T06:00:00+08:00 | 2027-01-24T18:00:00+08:00 |  |  |  |  | 12.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
70885 | 2025-10-16T08:28:23.733542+00:00 | 2025-10-16T16:28:23.733542+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:08.6067538+00:00 | 2026-01-22T11:54:08.6067538+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284950 | TRUE | TRUE | 2026-01-22T03:54:08.6067538+00:00 | 2026-01-22T11:54:08.6067538+08:00 | #70885 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2028-01-23T23:00:00+00:00 | 2028-01-24T03:00:00+00:00 | 2028-01-24T07:00:00+08:00 | 2028-01-24T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70884 | 2025-10-16T08:28:23.5771575+00:00 | 2025-10-16T16:28:23.5771575+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:10.7468447+00:00 | 2026-01-22T11:54:10.7468447+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284951 | TRUE | TRUE | 2026-01-22T03:54:10.7468447+00:00 | 2026-01-22T11:54:10.7468447+08:00 | #70884 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2028-01-16T23:00:00+00:00 | 2028-01-17T03:00:00+00:00 | 2028-01-17T07:00:00+08:00 | 2028-01-17T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70883 | 2025-10-16T08:28:23.4028754+00:00 | 2025-10-16T16:28:23.4028754+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:12.7529348+00:00 | 2026-01-22T11:54:12.7529348+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284952 | TRUE | TRUE | 2026-01-22T03:54:12.7529348+00:00 | 2026-01-22T11:54:12.7529348+08:00 | #70883 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2028-01-09T23:00:00+00:00 | 2028-01-10T03:00:00+00:00 | 2028-01-10T07:00:00+08:00 | 2028-01-10T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70882 | 2025-10-16T08:28:23.2284963+00:00 | 2025-10-16T16:28:23.2284963+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:14.7983328+00:00 | 2026-01-22T11:54:14.7983328+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284953 | TRUE | TRUE | 2026-01-22T03:54:14.7983328+00:00 | 2026-01-22T11:54:14.7983328+08:00 | #70882 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2028-01-02T23:00:00+00:00 | 2028-01-03T03:00:00+00:00 | 2028-01-03T07:00:00+08:00 | 2028-01-03T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70881 | 2025-10-16T08:28:23.0703155+00:00 | 2025-10-16T16:28:23.0703155+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:18.0338462+00:00 | 2026-01-22T11:54:18.0338462+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284955 | TRUE | TRUE | 2026-01-22T03:54:18.0338462+00:00 | 2026-01-22T11:54:18.0338462+08:00 | #70881 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-12-19T23:00:00+00:00 | 2027-12-20T03:00:00+00:00 | 2027-12-20T07:00:00+08:00 | 2027-12-20T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70880 | 2025-10-16T08:28:22.9215153+00:00 | 2025-10-16T16:28:22.9215153+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:22.2042724+00:00 | 2026-01-22T11:54:22.2042724+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284957 | TRUE | TRUE | 2026-01-22T03:54:22.2042724+00:00 | 2026-01-22T11:54:22.2042724+08:00 | #70880 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-12-05T23:00:00+00:00 | 2027-12-06T03:00:00+00:00 | 2027-12-06T07:00:00+08:00 | 2027-12-06T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70879 | 2025-10-16T08:28:22.7228794+00:00 | 2025-10-16T16:28:22.7228794+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:25.9935511+00:00 | 2026-01-22T11:54:25.9935511+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284959 | TRUE | TRUE | 2026-01-22T03:54:25.9935511+00:00 | 2026-01-22T11:54:25.9935511+08:00 | #70879 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-11-21T23:00:00+00:00 | 2027-11-22T03:00:00+00:00 | 2027-11-22T07:00:00+08:00 | 2027-11-22T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70878 | 2025-10-16T08:28:22.5294156+00:00 | 2025-10-16T16:28:22.5294156+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:29.8218363+00:00 | 2026-01-22T11:54:29.8218363+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284961 | TRUE | TRUE | 2026-01-22T03:54:29.8218363+00:00 | 2026-01-22T11:54:29.8218363+08:00 | #70878 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-11-07T23:00:00+00:00 | 2027-11-08T03:00:00+00:00 | 2027-11-08T07:00:00+08:00 | 2027-11-08T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70877 | 2025-10-16T08:28:22.3376655+00:00 | 2025-10-16T16:28:22.3376655+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:33.9264396+00:00 | 2026-01-22T11:54:33.9264396+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284963 | TRUE | TRUE | 2026-01-22T03:54:33.9264396+00:00 | 2026-01-22T11:54:33.9264396+08:00 | #70877 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-10-24T23:00:00+00:00 | 2027-10-25T03:00:00+00:00 | 2027-10-25T07:00:00+08:00 | 2027-10-25T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70876 | 2025-10-16T08:28:22.1341724+00:00 | 2025-10-16T16:28:22.1341724+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:37.7591286+00:00 | 2026-01-22T11:54:37.7591286+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284965 | TRUE | TRUE | 2026-01-22T03:54:37.7591286+00:00 | 2026-01-22T11:54:37.7591286+08:00 | #70876 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-10-10T23:00:00+00:00 | 2027-10-11T03:00:00+00:00 | 2027-10-11T07:00:00+08:00 | 2027-10-11T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70875 | 2025-10-16T08:28:21.9740565+00:00 | 2025-10-16T16:28:21.9740565+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:41.5231954+00:00 | 2026-01-22T11:54:41.5231954+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284967 | TRUE | TRUE | 2026-01-22T03:54:41.5231954+00:00 | 2026-01-22T11:54:41.5231954+08:00 | #70875 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-09-26T23:00:00+00:00 | 2027-09-27T03:00:00+00:00 | 2027-09-27T07:00:00+08:00 | 2027-09-27T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70874 | 2025-10-16T08:28:21.8068939+00:00 | 2025-10-16T16:28:21.8068939+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:45.0980107+00:00 | 2026-01-22T11:54:45.0980107+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284969 | TRUE | TRUE | 2026-01-22T03:54:45.0980107+00:00 | 2026-01-22T11:54:45.0980107+08:00 | #70874 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-09-12T23:00:00+00:00 | 2027-09-13T03:00:00+00:00 | 2027-09-13T07:00:00+08:00 | 2027-09-13T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70873 | 2025-10-16T08:28:21.6258545+00:00 | 2025-10-16T16:28:21.6258545+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:49.8866042+00:00 | 2026-01-22T11:54:49.8866042+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284971 | TRUE | TRUE | 2026-01-22T03:54:49.8866042+00:00 | 2026-01-22T11:54:49.8866042+08:00 | #70873 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-08-29T23:00:00+00:00 | 2027-08-30T03:00:00+00:00 | 2027-08-30T07:00:00+08:00 | 2027-08-30T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70857 | 2025-10-16T07:27:30.6676537+00:00 | 2025-10-16T15:27:30.6676537+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:53.358601+00:00 | 2026-01-22T11:54:53.358601+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284972 | TRUE | TRUE | 2026-01-22T03:54:53.358601+00:00 | 2026-01-22T11:54:53.358601+08:00 | #70857 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-08-22T23:00:00+00:00 | 2027-08-23T03:00:00+00:00 | 2027-08-23T07:00:00+08:00 | 2027-08-23T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70872 | 2025-10-16T08:28:21.4716188+00:00 | 2025-10-16T16:28:21.4716188+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:54:55.8602309+00:00 | 2026-01-22T11:54:55.8602309+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284973 | TRUE | TRUE | 2026-01-22T03:54:55.8602309+00:00 | 2026-01-22T11:54:55.8602309+08:00 | #70872 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-08-15T23:00:00+00:00 | 2027-08-16T03:00:00+00:00 | 2027-08-16T07:00:00+08:00 | 2027-08-16T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70871 | 2025-10-16T08:28:21.3232954+00:00 | 2025-10-16T16:28:21.3232954+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:00.7515087+00:00 | 2026-01-22T11:55:00.7515087+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284975 | TRUE | TRUE | 2026-01-22T03:55:00.7515087+00:00 | 2026-01-22T11:55:00.7515087+08:00 | #70871 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-08-01T23:00:00+00:00 | 2027-08-02T03:00:00+00:00 | 2027-08-02T07:00:00+08:00 | 2027-08-02T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70870 | 2025-10-16T08:28:21.1762926+00:00 | 2025-10-16T16:28:21.1762926+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:05.5893763+00:00 | 2026-01-22T11:55:05.5893763+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284977 | TRUE | TRUE | 2026-01-22T03:55:05.5893763+00:00 | 2026-01-22T11:55:05.5893763+08:00 | #70870 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-07-18T23:00:00+00:00 | 2027-07-19T03:00:00+00:00 | 2027-07-19T07:00:00+08:00 | 2027-07-19T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70869 | 2025-10-16T08:28:21.011963+00:00 | 2025-10-16T16:28:21.011963+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:10.4363377+00:00 | 2026-01-22T11:55:10.4363377+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284979 | TRUE | TRUE | 2026-01-22T03:55:10.4363377+00:00 | 2026-01-22T11:55:10.4363377+08:00 | #70869 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-07-04T23:00:00+00:00 | 2027-07-05T03:00:00+00:00 | 2027-07-05T07:00:00+08:00 | 2027-07-05T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70868 | 2025-10-16T08:28:20.6074163+00:00 | 2025-10-16T16:28:20.6074163+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:15.3691529+00:00 | 2026-01-22T11:55:15.3691529+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284981 | TRUE | TRUE | 2026-01-22T03:55:15.3691529+00:00 | 2026-01-22T11:55:15.3691529+08:00 | #70868 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-06-20T23:00:00+00:00 | 2027-06-21T03:00:00+00:00 | 2027-06-21T07:00:00+08:00 | 2027-06-21T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70851 | 2025-10-16T07:27:26.5213667+00:00 | 2025-10-16T15:27:26.5213667+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:20.3977324+00:00 | 2026-01-22T11:55:20.3977324+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284983 | TRUE | TRUE | 2026-01-22T03:55:20.3977324+00:00 | 2026-01-22T11:55:20.3977324+08:00 | #70851 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-06-06T23:00:00+00:00 | 2027-06-07T03:00:00+00:00 | 2027-06-07T07:00:00+08:00 | 2027-06-07T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70849 | 2025-10-16T07:27:25.2072826+00:00 | 2025-10-16T15:27:25.2072826+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:25.3407364+00:00 | 2026-01-22T11:55:25.3407364+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284985 | TRUE | TRUE | 2026-01-22T03:55:25.3407364+00:00 | 2026-01-22T11:55:25.3407364+08:00 | #70849 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-05-23T23:00:00+00:00 | 2027-05-24T03:00:00+00:00 | 2027-05-24T07:00:00+08:00 | 2027-05-24T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70847 | 2025-10-16T07:27:23.8519267+00:00 | 2025-10-16T15:27:23.8519267+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:30.2930165+00:00 | 2026-01-22T11:55:30.2930165+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284987 | TRUE | TRUE | 2026-01-22T03:55:30.2930165+00:00 | 2026-01-22T11:55:30.2930165+08:00 | #70847 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-05-09T23:00:00+00:00 | 2027-05-10T03:00:00+00:00 | 2027-05-10T07:00:00+08:00 | 2027-05-10T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70845 | 2025-10-16T07:27:22.3836613+00:00 | 2025-10-16T15:27:22.3836613+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:35.3608353+00:00 | 2026-01-22T11:55:35.3608353+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284989 | TRUE | TRUE | 2026-01-22T03:55:35.3608353+00:00 | 2026-01-22T11:55:35.3608353+08:00 | #70845 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-04-25T23:00:00+00:00 | 2027-04-26T03:00:00+00:00 | 2027-04-26T07:00:00+08:00 | 2027-04-26T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70843 | 2025-10-16T07:27:21.1511129+00:00 | 2025-10-16T15:27:21.1511129+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:40.3309617+00:00 | 2026-01-22T11:55:40.3309617+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284991 | TRUE | TRUE | 2026-01-22T03:55:40.3309617+00:00 | 2026-01-22T11:55:40.3309617+08:00 | #70843 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-04-11T23:00:00+00:00 | 2027-04-12T03:00:00+00:00 | 2027-04-12T07:00:00+08:00 | 2027-04-12T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70841 | 2025-10-16T07:27:19.8484764+00:00 | 2025-10-16T15:27:19.8484764+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:45.2965109+00:00 | 2026-01-22T11:55:45.2965109+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284993 | TRUE | TRUE | 2026-01-22T03:55:45.2965109+00:00 | 2026-01-22T11:55:45.2965109+08:00 | #70841 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-03-28T23:00:00+00:00 | 2027-03-29T03:00:00+00:00 | 2027-03-29T07:00:00+08:00 | 2027-03-29T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70839 | 2025-10-16T07:27:18.4264934+00:00 | 2025-10-16T15:27:18.4264934+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:50.2111491+00:00 | 2026-01-22T11:55:50.2111491+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284995 | TRUE | TRUE | 2026-01-22T03:55:50.2111491+00:00 | 2026-01-22T11:55:50.2111491+08:00 | #70839 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-03-14T23:00:00+00:00 | 2027-03-15T03:00:00+00:00 | 2027-03-15T07:00:00+08:00 | 2027-03-15T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70837 | 2025-10-16T07:27:16.9381388+00:00 | 2025-10-16T15:27:16.9381388+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:55.2070492+00:00 | 2026-01-22T11:55:55.2070492+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284997 | TRUE | TRUE | 2026-01-22T03:55:55.2070492+00:00 | 2026-01-22T11:55:55.2070492+08:00 | #70837 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-02-28T23:00:00+00:00 | 2027-03-01T03:00:00+00:00 | 2027-03-01T07:00:00+08:00 | 2027-03-01T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70836 | 2025-10-16T07:27:16.283399+00:00 | 2025-10-16T15:27:16.283399+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:55:57.6964078+00:00 | 2026-01-22T11:55:57.6964078+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284998 | TRUE | TRUE | 2026-01-22T03:55:57.6964078+00:00 | 2026-01-22T11:55:57.6964078+08:00 | #70836 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-02-21T23:00:00+00:00 | 2027-02-22T03:00:00+00:00 | 2027-02-22T07:00:00+08:00 | 2027-02-22T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70835 | 2025-10-16T07:27:15.3518425+00:00 | 2025-10-16T15:27:15.3518425+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:56:00.0680997+00:00 | 2026-01-22T11:56:00.0680997+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 284999 | TRUE | TRUE | 2026-01-22T03:56:00.0680997+00:00 | 2026-01-22T11:56:00.0680997+08:00 | #70835 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-02-14T23:00:00+00:00 | 2027-02-15T03:00:00+00:00 | 2027-02-15T07:00:00+08:00 | 2027-02-15T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70833 | 2025-10-16T07:27:13.5406224+00:00 | 2025-10-16T15:27:13.5406224+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:56:05.2746839+00:00 | 2026-01-22T11:56:05.2746839+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 285001 | TRUE | TRUE | 2026-01-22T03:56:05.2746839+00:00 | 2026-01-22T11:56:05.2746839+08:00 | #70833 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-01-31T23:00:00+00:00 | 2027-02-01T03:00:00+00:00 | 2027-02-01T07:00:00+08:00 | 2027-02-01T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70831 | 2025-10-16T07:27:11.8480856+00:00 | 2025-10-16T15:27:11.8480856+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:56:10.5180354+00:00 | 2026-01-22T11:56:10.5180354+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 285003 | TRUE | TRUE | 2026-01-22T03:56:10.5180354+00:00 | 2026-01-22T11:56:10.5180354+08:00 | #70831 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-01-17T23:00:00+00:00 | 2027-01-18T03:00:00+00:00 | 2027-01-18T07:00:00+08:00 | 2027-01-18T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
70829 | 2025-10-16T07:27:10.1121347+00:00 | 2025-10-16T15:27:10.1121347+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-01-22T03:56:15.4123077+00:00 | 2026-01-22T11:56:15.4123077+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 285006 | TRUE | TRUE | 2026-01-22T03:56:15.4123077+00:00 | 2026-01-22T11:56:15.4123077+08:00 | #70829 - RVA: 4hrs - DP CHANGEOVER | 3.0 | TRUE |  | 2027-01-03T23:00:00+00:00 | 2027-01-04T03:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-04T11:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Incorrect start and finish time, also required is 4 hours |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2d31d92d-6540-4a15-b1fc-fd291a3e5acb", "emailAddress": "Ashika.LaldaParsad@riotinto.com", "displayName": "Lalda-Parsad, Ashika (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
83858 | 2026-08-28T05:25:32.47116+00:00 | 2026-08-28T13:25:32.47116+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-09-01T01:21:06.8203576+00:00 | 2026-09-01T09:21:06.8203576+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 332381 | TRUE | TRUE | 2026-09-01T01:21:06.8203576+00:00 | 2026-09-01T09:21:06.8203576+08:00 | #83858 - HD1: 214hrs - SOUTH PLANT - C/O APRON FEEDER COMPONENTS AF51 | 1.0 | TRUE |  | 2027-03-10T10:00:00+00:00 | 2027-03-19T08:00:00+00:00 | 2027-03-10T18:00:00+08:00 | 2027-03-19T16:00:00+08:00 |  |  |  |  | 214.00 | AF51 C/O Outage |  |  | [{"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 41468, "shutVersionId": 334170, "title": "#41468 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH", "startDatetimeUTC": "2027-03-11T10:00:00+00:00", "endDatetimeUTC": "2027-03-16T10:00:00+00:00"}}] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83652 | 2026-08-05T23:23:49.5608768+00:00 | 2026-08-06T07:23:49.5608768+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-09-16T08:39:23.0018444+00:00 | 2026-09-16T16:39:23.0018444+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 333457 | TRUE | TRUE | 2026-09-16T08:39:23.0018444+00:00 | 2026-09-16T16:39:23.0018444+08:00 | #83652 - HD4: 60hrs - HD4 PLT - SPRINT SHUT | 2.0 | TRUE |  | 2027-02-16T22:00:00+00:00 | 2027-02-19T10:00:00+00:00 | 2027-02-17T06:00:00+08:00 | 2027-02-19T18:00:00+08:00 |  |  |  |  | 60.00 | HD4 Plant Sprint Shut - due to 53 week year. | taken hours from week 2 and added to week 07 as per direction from F Afifa |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73690 | 2025-11-28T01:55:59.4742938+00:00 | 2025-11-28T09:55:59.4742938+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:03.5570954+00:00 | 2026-08-05T14:21:03.5570954+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330864 | TRUE | TRUE | 2026-08-05T06:21:03.5570954+00:00 | 2026-08-05T14:21:03.5570954+08:00 | #73690 - HD4: 54hrs - BOO PLANT | 2.0 | TRUE |  | 2027-01-07T22:00:00+00:00 | 2027-01-10T04:00:00+00:00 | 2027-01-08T06:00:00+08:00 | 2027-01-10T12:00:00+08:00 |  |  |  |  | 54.00 | BOO Plant Maintenance for CSI | Shut schedule change request by G Kite |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73694 | 2025-11-28T01:56:00.2892978+00:00 | 2025-11-28T09:56:00.2892978+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:03.7426498+00:00 | 2026-08-05T14:21:03.7426498+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330865 | TRUE | TRUE | 2026-08-05T06:21:03.7426498+00:00 | 2026-08-05T14:21:03.7426498+08:00 | #73694 - HD4: 60hrs - BOO PLANT | 2.0 | TRUE |  | 2027-02-04T22:00:00+00:00 | 2027-02-07T10:00:00+00:00 | 2027-02-05T06:00:00+08:00 | 2027-02-07T18:00:00+08:00 |  |  |  |  | 60.00 | BOO Plant Maintenance for CSI | updating as per request from BOO team. |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73702 | 2025-11-28T01:56:02.0318317+00:00 | 2025-11-28T09:56:02.0318317+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:04.1107333+00:00 | 2026-08-05T14:21:04.1107333+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330867 | TRUE | TRUE | 2026-08-05T06:21:04.1107333+00:00 | 2026-08-05T14:21:04.1107333+08:00 | #73702 - HD4: 96hrs - BOO PLANT | 2.0 | TRUE |  | 2027-04-01T22:00:00+00:00 | 2027-04-05T22:00:00+00:00 | 2027-04-02T06:00:00+08:00 | 2027-04-06T06:00:00+08:00 |  |  |  |  | 96.00 | BOO Plant Maintenance for CSI | updating as per request from BOO team |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73715 | 2025-11-28T01:56:05.1910751+00:00 | 2025-11-28T09:56:05.1910751+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:04.7206246+00:00 | 2026-08-05T14:21:04.7206246+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330870 | TRUE | TRUE | 2026-08-05T06:21:04.7206246+00:00 | 2026-08-05T14:21:04.7206246+08:00 | #73715 - HD4: 96hrs - BOO PLANT | 2.0 | TRUE |  | 2027-07-01T22:00:00+00:00 | 2027-07-05T22:00:00+00:00 | 2027-07-02T06:00:00+08:00 | 2027-07-06T06:00:00+08:00 |  |  |  |  | 96.00 | BOO Plant Maintenance for CSI | updated as per request from BOO team |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73728 | 2025-11-28T01:56:08.7956439+00:00 | 2025-11-28T09:56:08.7956439+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:05.3237003+00:00 | 2026-08-05T14:21:05.3237003+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330873 | TRUE | TRUE | 2026-08-05T06:21:05.3237003+00:00 | 2026-08-05T14:21:05.3237003+08:00 | #73728 - HD4: 96hrs - BOO PLANT | 2.0 | TRUE |  | 2027-09-30T22:00:00+00:00 | 2027-10-04T22:00:00+00:00 | 2027-10-01T06:00:00+08:00 | 2027-10-05T06:00:00+08:00 |  |  |  |  | 96.00 | BOO Plant Maintenance for CSI | Shut schedule change request by G Kite |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73741 | 2025-11-28T01:56:12.6162927+00:00 | 2025-11-28T09:56:12.6162927+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-08-05T06:21:05.9462637+00:00 | 2026-08-05T14:21:05.9462637+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 330876 | TRUE | TRUE | 2026-08-05T06:21:05.9462637+00:00 | 2026-08-05T14:21:05.9462637+08:00 | #73741 - HD4: 96hrs - BOO PLANT | 2.0 | TRUE |  | 2027-12-30T22:00:00+00:00 | 2028-01-03T22:00:00+00:00 | 2027-12-31T06:00:00+08:00 | 2028-01-04T06:00:00+08:00 |  |  |  |  | 96.00 | BOO Plant Maintenance for CSI | Shut schedule change request by G Kite |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73736 | 2025-11-28T01:56:11.1208828+00:00 | 2025-11-28T09:56:11.1208828+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:21.0869779+00:00 | 2026-10-05T15:38:21.0869779+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335291 | TRUE | TRUE | 2026-10-05T07:38:21.0869779+00:00 | 2026-10-05T15:38:21.0869779+08:00 | #73736 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-11-27T10:00:00+00:00 | 2027-11-28T16:00:00+00:00 | 2027-11-27T18:00:00+08:00 | 2027-11-29T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73732 | 2025-11-28T01:56:09.9025692+00:00 | 2025-11-28T09:56:09.9025692+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:21.4195957+00:00 | 2026-10-05T15:38:21.4195957+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335292 | TRUE | TRUE | 2026-10-05T07:38:21.4195957+00:00 | 2026-10-05T15:38:21.4195957+08:00 | #73732 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-10-30T10:00:00+00:00 | 2027-10-31T16:00:00+00:00 | 2027-10-30T18:00:00+08:00 | 2027-11-01T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
82979 | 2026-06-24T23:17:37.9839876+00:00 | 2026-06-25T07:17:37.9839876+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-06-29T03:20:18.9080243+00:00 | 2026-06-29T11:20:18.9080243+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 328595 | TRUE | TRUE | 2026-06-29T03:20:18.9080243+00:00 | 2026-06-29T11:20:18.9080243+08:00 | #82979 - HD4: 84hrs - BOO PROCESSING PLANT | 1.0 | TRUE |  | 2026-12-11T10:00:00+00:00 | 2026-12-14T22:00:00+00:00 | 2026-12-11T18:00:00+08:00 | 2026-12-15T06:00:00+08:00 |  |  |  |  | 84.00 | BOO Plant Maintenance for CSI |  |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73723 | 2025-11-28T01:56:07.3590764+00:00 | 2025-11-28T09:56:07.3590764+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:21.5938157+00:00 | 2026-10-05T15:38:21.5938157+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335293 | TRUE | TRUE | 2026-10-05T07:38:21.5938157+00:00 | 2026-10-05T15:38:21.5938157+08:00 | #73723 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-08-28T10:00:00+00:00 | 2027-08-29T16:00:00+00:00 | 2027-08-28T18:00:00+08:00 | 2027-08-30T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73719 | 2025-11-28T01:56:06.2579518+00:00 | 2025-11-28T09:56:06.2579518+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:21.7684788+00:00 | 2026-10-05T15:38:21.7684788+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335294 | TRUE | TRUE | 2026-10-05T07:38:21.7684788+00:00 | 2026-10-05T15:38:21.7684788+08:00 | #73719 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-07-31T10:00:00+00:00 | 2027-08-01T16:00:00+00:00 | 2027-07-31T18:00:00+08:00 | 2027-08-02T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73710 | 2025-11-28T01:56:03.891138+00:00 | 2025-11-28T09:56:03.891138+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:21.9429144+00:00 | 2026-10-05T15:38:21.9429144+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335295 | TRUE | TRUE | 2026-10-05T07:38:21.9429144+00:00 | 2026-10-05T15:38:21.9429144+08:00 | #73710 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-05-29T10:00:00+00:00 | 2027-05-30T16:00:00+00:00 | 2027-05-29T18:00:00+08:00 | 2027-05-31T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73706 | 2025-11-28T01:56:02.9680017+00:00 | 2025-11-28T09:56:02.9680017+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:22.1299309+00:00 | 2026-10-05T15:38:22.1299309+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335296 | TRUE | TRUE | 2026-10-05T07:38:22.1299309+00:00 | 2026-10-05T15:38:22.1299309+08:00 | #73706 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-05-01T10:00:00+00:00 | 2027-05-02T16:00:00+00:00 | 2027-05-01T18:00:00+08:00 | 2027-05-03T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
73698 | 2025-11-28T01:56:01.1267337+00:00 | 2025-11-28T09:56:01.1267337+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-05T07:38:22.3111126+00:00 | 2026-10-05T15:38:22.3111126+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 335297 | TRUE | TRUE | 2026-10-05T07:38:22.3111126+00:00 | 2026-10-05T15:38:22.3111126+08:00 | #73698 - HD4: 30hrs - BOO PLANT | 3.0 | TRUE |  | 2027-03-06T10:00:00+00:00 | 2027-03-07T16:00:00+00:00 | 2027-03-06T18:00:00+08:00 | 2027-03-08T00:00:00+08:00 |  |  |  |  | 30.00 | BOO Plant Maintenance for CSI | Fixing starting times |  | [{"equipmentGUID": "1114b296-1f82-ef11-a853-000d3acacefd", "code": "HD4PLTBOO", "name": "Plant: HD4 Build-Own-Operate", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b247d0da-8528-4ca1-a39b-8dabdf81d89a", "emailAddress": "Georgina.Kite@riotinto.com", "displayName": "Kite, Georgina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
74767 | 2026-01-18T22:59:16.8118651+00:00 | 2026-01-19T06:59:16.8118651+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-02-05T07:54:22.6273458+00:00 | 2026-02-05T15:54:22.6273458+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 286161 | TRUE | TRUE | 2026-02-05T07:54:22.6273458+00:00 | 2026-02-05T15:54:22.6273458+08:00 | #74767 - HD1: 168hrs - NORTH PLANT ROCK BREAKER UPGRADE | 1.0 | TRUE |  | 2027-01-26T22:00:00+00:00 | 2027-02-02T22:00:00+00:00 | 2027-01-27T06:00:00+08:00 | 2027-02-03T06:00:00+08:00 |  |  |  |  | 168.00 | P-0701016 HD1 Rock Breaker Upgrades |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d60a8541-ee56-4a42-b135-8b265ed73497", "emailAddress": "Stephen.Camm@riotinto.com", "displayName": "Camm, Stephen (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 54890, "shutVersionId": 331883, "title": "#54890 - HD1: 96hrs - HD1 NTH & CS02 MODULAR SHUT", "startDatetimeUTC": "2027-01-26T22:00:00+00:00", "endDatetimeUTC": "2027-01-30T22:00:00+00:00"}}] | [{"name": "Project Interactions"}] | [{"code": "P-0701016", "name": "HD1 Rock Breaker Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
81570 | 2026-03-06T04:06:38.6053042+00:00 | 2026-03-06T12:06:38.6053042+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-03-20T05:10:39.5541813+00:00 | 2026-03-20T13:10:39.5541813+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 322598 | TRUE | TRUE | 2026-03-20T05:10:39.5541813+00:00 | 2026-03-20T13:10:39.5541813+08:00 | #81570 - HD1: 144hrs - TLO - C/O CONVEYOR BELT HDCV15 | 1.0 | TRUE |  | 2027-09-14T16:00:00+00:00 | 2027-09-20T16:00:00+00:00 | 2027-09-15T00:00:00+08:00 | 2027-09-21T00:00:00+08:00 |  |  |  |  | 144.00 | C/O Conveyor Belt HDCV15 |  |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
81623 | 2026-03-10T00:16:13.3741265+00:00 | 2026-03-10T08:16:13.3741265+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-03-20T05:10:39.8513193+00:00 | 2026-03-20T13:10:39.8513193+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 322599 | TRUE | TRUE | 2026-03-20T05:10:39.8513193+00:00 | 2026-03-20T13:10:39.8513193+08:00 | #81623 - HD1: 240hrs - PLANT - C/O CRUSHER MAINFRAME CS03 | 1.0 | FALSE |  | 2027-09-08T10:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-08T18:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 240.00 | North Plant - C/O Crusher Mainframe CS03 major task standalone outage |  |  | [{"equipmentGUID": "0ef4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS03NTH", "name": "Crusher - Secondary: HD1 03 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
81622 | 2026-03-10T00:11:15.1894891+00:00 | 2026-03-10T08:11:15.1894891+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-03-20T05:10:40.4648837+00:00 | 2026-03-20T13:10:40.4648837+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 322601 | TRUE | TRUE | 2026-03-20T05:10:40.4648837+00:00 | 2026-03-20T13:10:40.4648837+08:00 | #81622 - HD1: 240hrs - PLANT - C/O CRUSHER MAINFRAME CS02 | 1.0 | FALSE |  | 2027-03-10T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-10T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 240.00 | North Plant - C/O Crusher Mainframe CS02 |  |  | [{"equipmentGUID": "87f1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS02NTH", "name": "Crusher - Secondary: HD1 02 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
75141 | 2026-02-10T00:03:42.4021396+00:00 | 2026-02-10T08:03:42.4021396+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-09-29T00:04:01.9887838+00:00 | 2026-09-29T08:04:01.9887838+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 334171 | TRUE | TRUE | 2026-09-29T00:04:01.9887838+00:00 | 2026-09-29T08:04:01.9887838+08:00 | #75141 - HD1: 336hrs - HDBN00 REPAIR ROM WALL | 1.1 | TRUE |  | 2027-12-08T10:00:00+00:00 | 2027-12-22T10:00:00+00:00 | 2027-12-08T18:00:00+08:00 | 2027-12-22T18:00:00+08:00 |  |  |  |  | 336.00 | Description of work – Repair/replace the North ROM bin upper rear wall Install concrete/grout to back-prop damaged rear wall on North ROM Bin |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "15220f78-8a39-4007-ab42-dc8fc51c2972", "emailAddress": "Chee.Yong@riotinto.com", "displayName": "Yong, Chee Leong (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44418, "shutVersionId": 329405, "title": "#44418 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH", "startDatetimeUTC": "2027-12-09T10:00:00+00:00", "endDatetimeUTC": "2027-12-14T10:00:00+00:00"}}] | [{"name": "Project Interactions"}] | [{"code": "P-0701999", "name": "HD1 ROM Bins Rear wall strengthening Phase 2", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
81571 | 2026-03-06T04:09:58.5119575+00:00 | 2026-03-06T12:09:58.5119575+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-03-10T02:33:22.9267256+00:00 | 2026-03-10T10:33:22.9267256+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 320898 | TRUE | TRUE | 2026-03-10T02:33:22.9267256+00:00 | 2026-03-10T10:33:22.9267256+08:00 | #81571 - HD1: 108hrs - TLO - C/O RECL CONV BELT HDRC01/HDCV14 | 1.0 | TRUE |  | 2027-12-14T16:00:00+00:00 | 2027-12-19T04:00:00+00:00 | 2027-12-15T00:00:00+08:00 | 2027-12-19T12:00:00+08:00 |  |  |  |  | 108.00 | C/O Recl Conv Belt HDRC01/HDCV14 |  |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "f6f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1RC01", "name": "Reclaimer: HD1 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
81572 | 2026-03-06T04:26:46.3694927+00:00 | 2026-03-06T12:26:46.3694927+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-03-10T02:33:23.0863966+00:00 | 2026-03-10T10:33:23.0863966+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 320899 | TRUE | TRUE | 2026-03-10T02:33:23.0863966+00:00 | 2026-03-10T10:33:23.0863966+08:00 | #81572 - HD1: 108hrs - TLO - C/O RECL CONV BELT HDRC01/HDCV14 | 1.0 | TRUE |  | 2027-03-16T16:00:00+00:00 | 2027-03-21T04:00:00+00:00 | 2027-03-17T00:00:00+08:00 | 2027-03-21T12:00:00+08:00 |  |  |  |  | 108.00 | C/O Recl Conv Belt HDRC01/HDCV14 |  |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "f6f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1RC01", "name": "Reclaimer: HD1 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Create | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
41468 | 2021-05-24T09:29:47+00:00 | 2021-05-24T17:29:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T00:00:15.4081409+00:00 | 2026-09-29T08:00:15.4081409+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 334170 | TRUE | TRUE | 2026-09-29T00:00:15.4081409+00:00 | 2026-09-29T08:00:15.4081409+08:00 | #41468 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH | 12.1 | TRUE |  | 2027-03-11T10:00:00+00:00 | 2027-03-16T10:00:00+00:00 | 2027-03-11T18:00:00+08:00 | 2027-03-16T18:00:00+08:00 |  |  |  |  | 120.00 | HD1 NTH Plant Shut - 120Hrs |  |  | [{"equipmentGUID": "6717ee47-4b9a-ee11-a847-000d3acacefd", "code": "HD1PLTNTH", "name": "Plant: HD1 North", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "e4497c23-757f-4930-9277-51217d6dd18a", "emailAddress": "andrew.tubb@riotinto.com", "displayName": "Andrew Tubb"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "323ea2ce-7f41-4049-9c74-6b962d31ba41", "emailAddress": "Sarah.Maimoun@riotinto.com", "displayName": "Maimoun, Sarah (RTIO-GUIDANTGLOBAL)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83858, "shutVersionId": 332381, "title": "#83858 - HD1: 214hrs - SOUTH PLANT - C/O APRON FEEDER COMPONENTS AF51", "startDatetimeUTC": "2027-03-10T10:00:00+00:00", "endDatetimeUTC": "2027-03-19T08:00:00+00:00"}}] | [{"name": "Project Interactions"}] | [{"code": "P-0701011", "name": "P-0701011-HD1 Screen House Dust Collector Upgrade", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}, {"code": "P-0701016", "name": "P-0701016-HD1 Rockbreaker Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
44344 | 2021-11-24T07:44:54+00:00 | 2021-11-24T15:44:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:29.3978273+00:00 | 2025-12-24T07:12:29.3978273+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282816 | TRUE | TRUE | 2025-12-23T23:12:29.3978273+00:00 | 2025-12-24T07:12:29.3978273+08:00 | #44344 - HD4: 228hrs - PLANT: HD4 | 8.1 | TRUE |  | 2027-03-23T22:00:00+00:00 | 2027-04-02T10:00:00+00:00 | 2027-03-24T06:00:00+08:00 | 2027-04-02T18:00:00+08:00 |  |  |  |  | 228.00 | HD4 Plant Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44348 | 2021-11-24T07:44:58+00:00 | 2021-11-24T15:44:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:29.6535206+00:00 | 2025-12-24T07:12:29.6535206+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282819 | TRUE | TRUE | 2025-12-23T23:12:29.6535206+00:00 | 2025-12-24T07:12:29.6535206+08:00 | #44348 - HD4: 228hrs - PLANT: HD4 | 8.1 | TRUE |  | 2027-06-22T22:00:00+00:00 | 2027-07-02T10:00:00+00:00 | 2027-06-23T06:00:00+08:00 | 2027-07-02T18:00:00+08:00 |  |  |  |  | 228.00 | HD4 Plant Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
47680 | 2022-08-19T01:49:23+00:00 | 2022-08-19T09:49:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:29.8339399+00:00 | 2025-12-24T07:12:29.8339399+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282821 | TRUE | TRUE | 2025-12-23T23:12:29.8339399+00:00 | 2025-12-24T07:12:29.8339399+08:00 | #47680 - HD4: 96hrs - TRAIN LOADOUT: HD4 | 8.1 | TRUE |  | 2027-07-02T22:00:00+00:00 | 2027-07-06T22:00:00+00:00 | 2027-07-03T06:00:00+08:00 | 2027-07-07T06:00:00+08:00 |  |  |  |  | 96.00 | HD4 TLO Shut |  |  | [{"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44350 | 2021-11-24T07:45:03+00:00 | 2021-11-24T15:45:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:30.0188251+00:00 | 2025-12-24T07:12:30.0188251+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282823 | TRUE | TRUE | 2025-12-23T23:12:30.0188251+00:00 | 2025-12-24T07:12:30.0188251+08:00 | #44350 - HD4: 228hrs - PLANT: HD4 | 7.1 | TRUE |  | 2027-09-21T22:00:00+00:00 | 2027-10-01T10:00:00+00:00 | 2027-09-22T06:00:00+08:00 | 2027-10-01T18:00:00+08:00 |  |  |  |  | 228.00 | HD4 Plant Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44357 | 2021-11-24T08:06:42+00:00 | 2021-11-24T16:06:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:30.1097005+00:00 | 2025-12-24T07:12:30.1097005+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282824 | TRUE | TRUE | 2025-12-23T23:12:30.1097005+00:00 | 2025-12-24T07:12:30.1097005+08:00 | #44357 - HD4: 96hrs - TRAIN LOADOUT: HD4 | 8.1 | TRUE |  | 2027-10-01T22:00:00+00:00 | 2027-10-05T22:00:00+00:00 | 2027-10-02T06:00:00+08:00 | 2027-10-06T06:00:00+08:00 |  |  |  |  | 96.00 | HD4 TLO Shut |  |  | [{"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44353 | 2021-11-24T07:45:08+00:00 | 2021-11-24T15:45:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:30.2683757+00:00 | 2025-12-24T07:12:30.2683757+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282826 | TRUE | TRUE | 2025-12-23T23:12:30.2683757+00:00 | 2025-12-24T07:12:30.2683757+08:00 | #44353 - HD4: 228hrs - PLANT: HD4 | 8.1 | TRUE |  | 2027-12-21T22:00:00+00:00 | 2027-12-31T10:00:00+00:00 | 2027-12-22T06:00:00+08:00 | 2027-12-31T18:00:00+08:00 |  |  |  |  | 228.00 | HD4 Plant Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
47692 | 2022-08-19T08:35:20+00:00 | 2022-08-19T16:35:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:12:30.3720579+00:00 | 2025-12-24T07:12:30.3720579+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282827 | TRUE | TRUE | 2025-12-23T23:12:30.3720579+00:00 | 2025-12-24T07:12:30.3720579+08:00 | #47692 - HD4: 96hrs - TRAIN LOADOUT: HD4 | 8.1 | TRUE |  | 2027-12-31T22:00:00+00:00 | 2028-01-04T22:00:00+00:00 | 2028-01-01T06:00:00+08:00 | 2028-01-05T06:00:00+08:00 |  |  |  |  | 96.00 | HD4 TLO Shut |  |  | [{"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44721 | 2021-11-26T04:26:46+00:00 | 2021-11-26T12:26:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:19:00.6370909+00:00 | 2025-12-24T07:19:00.6370909+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282958 | TRUE | TRUE | 2025-12-23T23:19:00.6370909+00:00 | 2025-12-24T07:19:00.6370909+08:00 | #44721 - RVA: 144hrs - PLANT: RVA WET | 8.1 | TRUE |  | 2027-02-20T03:00:00+00:00 | 2027-02-26T03:00:00+00:00 | 2027-02-20T11:00:00+08:00 | 2027-02-26T11:00:00+08:00 |  |  |  |  | 144.00 | RVA WET PLANT SHUT |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
44724 | 2021-11-26T04:26:51+00:00 | 2021-11-26T12:26:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:19:01.3256394+00:00 | 2025-12-24T07:19:01.3256394+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 282967 | TRUE | TRUE | 2025-12-23T23:19:01.3256394+00:00 | 2025-12-24T07:19:01.3256394+08:00 | #44724 - RVA: 144hrs - PLANT: RVA WET | 9.1 | TRUE |  | 2027-11-20T03:00:00+00:00 | 2027-11-26T03:00:00+00:00 | 2027-11-20T11:00:00+08:00 | 2027-11-26T11:00:00+08:00 |  |  |  |  | 144.00 | RVA WET PLANT SHUT - required for trunnion alignments |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVA | Australia/Perth
44665 | 2021-11-26T04:24:06+00:00 | 2021-11-26T12:24:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:34:59.9352174+00:00 | 2025-12-24T07:34:59.9352174+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 283101 | TRUE | TRUE | 2025-12-23T23:34:59.9352174+00:00 | 2025-12-24T07:34:59.9352174+08:00 | #44665 - RVJ: 120hrs - PLANT: RVJ 01 | 5.1 | TRUE |  | 2027-01-05T21:00:00+00:00 | 2027-01-10T21:00:00+00:00 | 2027-01-06T05:00:00+08:00 | 2027-01-11T05:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 82178, "shutVersionId": 330560, "title": "#82178 - RVJ: 462hrs - PP1 SIZER PROJECT", "startDatetimeUTC": "2027-01-05T21:00:00+00:00", "endDatetimeUTC": "2027-01-25T03:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVJ | Australia/Perth
44747 | 2021-11-26T11:04:22+00:00 | 2021-11-26T19:04:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-23T23:35:00.1590317+00:00 | 2025-12-24T07:35:00.1590317+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 283104 | TRUE | TRUE | 2025-12-23T23:35:00.1590317+00:00 | 2025-12-24T07:35:00.1590317+08:00 | #44747 - RVJ: 120hrs - PLANT: RVJ 03 | 9.1 | TRUE |  | 2027-02-21T03:00:00+00:00 | 2027-02-26T03:00:00+00:00 | 2027-02-21T11:00:00+08:00 | 2027-02-26T11:00:00+08:00 |  |  |  |  | 120.00 | PP3 SHUT |  |  | [{"equipmentGUID": "7217ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT03", "name": "Plant: RVJ 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | RVJ | Australia/Perth
44354 | 2021-11-24T07:45:08+00:00 | 2021-11-24T15:45:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-16T08:39:22.525519+00:00 | 2026-09-16T16:39:22.525519+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 333455 | TRUE | TRUE | 2026-09-16T08:39:22.525519+00:00 | 2026-09-16T16:39:22.525519+08:00 | #44354 - HD4: 60hrs - HD4 PLT - SPRINT SHUT | 9.0 | TRUE |  | 2027-11-10T22:00:00+00:00 | 2027-11-13T10:00:00+00:00 | 2027-11-11T06:00:00+08:00 | 2027-11-13T18:00:00+08:00 |  |  |  |  | 60.00 | HD4 Plant Sprint Shut | updated as per request from Fatima Afifa |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44352 | 2021-11-24T07:45:04+00:00 | 2021-11-24T15:45:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-16T08:39:22.7653772+00:00 | 2026-09-16T16:39:22.7653772+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 333456 | TRUE | TRUE | 2026-09-16T08:39:22.7653772+00:00 | 2026-09-16T16:39:22.7653772+08:00 | #44352 - HD4: 60hrs - HD4 PLT - SPRINT SHUT | 11.0 | TRUE |  | 2027-08-11T22:00:00+00:00 | 2027-08-14T10:00:00+00:00 | 2027-08-12T06:00:00+08:00 | 2027-08-14T18:00:00+08:00 |  |  |  |  | 60.00 | HD4 Plant Sprint Shut | extended as per direction from Fatima Afifa |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
44376 | 2021-11-25T01:02:16+00:00 | 2021-11-25T09:02:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-20T05:10:38.4285307+00:00 | 2026-03-20T13:10:38.4285307+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 322595 | TRUE | TRUE | 2026-03-20T05:10:38.4285307+00:00 | 2026-03-20T13:10:38.4285307+08:00 | #44376 - HD1: 84hrs - TRAIN LOADOUT: HD1 | 10.0 | TRUE |  | 2027-12-14T16:00:00+00:00 | 2027-12-18T04:00:00+00:00 | 2027-12-15T00:00:00+08:00 | 2027-12-18T12:00:00+08:00 |  |  |  |  | 84.00 | HD1 TLO Shut | belt no longer being changed here |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
44375 | 2021-11-25T01:02:13+00:00 | 2021-11-25T09:02:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-20T05:10:39.2784239+00:00 | 2026-03-20T13:10:39.2784239+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 322597 | TRUE | TRUE | 2026-03-20T05:10:39.2784239+00:00 | 2026-03-20T13:10:39.2784239+08:00 | #44375 - HD1: 84hrs - TRAIN LOADOUT: HD1 | 12.0 | TRUE |  | 2027-09-14T16:00:00+00:00 | 2027-09-18T04:00:00+00:00 | 2027-09-15T00:00:00+08:00 | 2027-09-18T12:00:00+08:00 |  |  |  |  | 84.00 | HD1 TLO Shut. | belt no longer in this outage |  | [{"equipmentGUID": "132af6bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1TLO", "name": "Train Loadout: HD1", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
44349 | 2021-11-24T07:44:59+00:00 | 2021-11-24T15:44:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-23T00:13:06.4144816+00:00 | 2026-03-23T08:13:06.4144816+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 323693 | TRUE | TRUE | 2026-03-23T00:13:06.4144816+00:00 | 2026-03-23T08:13:06.4144816+08:00 | #44349 - HD4: 60hrs - HD4 PLT - SPRINT SHUT | 8.2 | TRUE |  | 2027-05-11T22:00:00+00:00 | 2027-05-14T10:00:00+00:00 | 2027-05-12T06:00:00+08:00 | 2027-05-14T18:00:00+08:00 |  |  |  |  | 60.00 | HD4 Plant Sprint Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
41410 | 2021-05-20T04:25:29+00:00 | 2021-05-20T12:25:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-12T05:08:17.608289+00:00 | 2026-08-12T13:08:17.608289+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331127 | TRUE | TRUE | 2026-08-12T05:08:17.608289+00:00 | 2026-08-12T13:08:17.608289+08:00 | #41410 - HD4: 168hrs - TRAIN LOADOUT: HD4 | 12.0 | TRUE |  | 2027-03-30T22:00:00+00:00 | 2027-04-06T22:00:00+00:00 | 2027-03-31T06:00:00+08:00 | 2027-04-07T06:00:00+08:00 |  |  |  |  | 168.00 | HD4 TLO Shut Ring chute change out. | Requested by F Afifa |  | [{"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [{"name": "Bucket Wheel Maintenance Major"}] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD4 | Australia/Perth
54890 | 2023-04-17T02:12:55+00:00 | 2023-04-17T10:12:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-27T03:03:05.6301307+00:00 | 2026-08-27T11:03:05.6301307+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331883 | TRUE | TRUE | 2026-08-27T03:03:05.6301307+00:00 | 2026-08-27T11:03:05.6301307+08:00 | #54890 - HD1: 96hrs - HD1 NTH & CS02 MODULAR SHUT | 9.1 | TRUE |  | 2027-01-26T22:00:00+00:00 | 2027-01-30T22:00:00+00:00 | 2027-01-27T06:00:00+08:00 | 2027-01-31T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 NTH Crusher Shut - Modular Shut |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "87f1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS02NTH", "name": "Crusher - Secondary: HD1 02 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8442b14-8ab7-41ed-954e-96c982f3754b", "emailAddress": "John.Marevich@riotinto.com", "displayName": "Marevich, John (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 74767, "shutVersionId": 286161, "title": "#74767 - HD1: 168hrs - NORTH PLANT ROCK BREAKER UPGRADE", "startDatetimeUTC": "2027-01-26T22:00:00+00:00", "endDatetimeUTC": "2027-02-02T22:00:00+00:00"}}] | [] | [{"code": "P-0701016", "name": "HD1 Rockbreaker Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "72"}] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
54891 | 2023-04-17T02:13:42+00:00 | 2023-04-17T10:13:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-27T03:03:05.6303846+00:00 | 2026-08-27T11:03:05.6303846+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331884 | TRUE | TRUE | 2026-08-27T03:03:05.6303846+00:00 | 2026-08-27T11:03:05.6303846+08:00 | #54891 - HD1: 96hrs - HD1 NTH & CS02 MODULAR SHUT | 9.1 | TRUE |  | 2027-04-27T22:00:00+00:00 | 2027-05-01T22:00:00+00:00 | 2027-04-28T06:00:00+08:00 | 2027-05-02T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 NTH Crusher Shut - Modular shut |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "87f1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS02NTH", "name": "Crusher - Secondary: HD1 02 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
54892 | 2023-04-17T02:14:31+00:00 | 2023-04-17T10:14:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-27T03:03:05.6304525+00:00 | 2026-08-27T11:03:05.6304525+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331885 | TRUE | TRUE | 2026-08-27T03:03:05.6304525+00:00 | 2026-08-27T11:03:05.6304525+08:00 | #54892 - HD1: 96hrs - HD1 NTH & CS02 MODULAR SHUT | 9.1 | TRUE |  | 2027-07-27T22:00:00+00:00 | 2027-07-31T22:00:00+00:00 | 2027-07-28T06:00:00+08:00 | 2027-08-01T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 NTH Crusher Shut - Modular Shut |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "87f1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS02NTH", "name": "Crusher - Secondary: HD1 02 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
54893 | 2023-04-17T02:15:25+00:00 | 2023-04-17T10:15:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-27T03:03:05.6304638+00:00 | 2026-08-27T11:03:05.6304638+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331886 | TRUE | TRUE | 2026-08-27T03:03:05.6304638+00:00 | 2026-08-27T11:03:05.6304638+08:00 | #54893 - HD1: 96hrs - HD1 NTH & CS02 MODULAR SHUT | 9.1 | TRUE |  | 2027-10-26T22:00:00+00:00 | 2027-10-30T22:00:00+00:00 | 2027-10-27T06:00:00+08:00 | 2027-10-31T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 NTH Crusher Shut - Modular shut |  |  | [{"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "87f1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS02NTH", "name": "Crusher - Secondary: HD1 02 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83448 | 2026-07-03T06:40:46.6085316+00:00 | 2026-07-03T14:40:46.6085316+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | 2026-08-27T03:10:28.604067+00:00 | 2026-08-27T11:10:28.604067+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331887 | TRUE | TRUE | 2026-08-27T03:10:28.604067+00:00 | 2026-08-27T11:10:28.604067+08:00 | #83448 - HD1: 96hrs - HD1 STH & CS03 MODULAR | 1.1 | TRUE |  | 2027-01-21T22:00:00+00:00 | 2027-01-25T22:00:00+00:00 | 2027-01-22T06:00:00+08:00 | 2027-01-26T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 South Crusher Modular Shut (MoC 136554) |  |  | [{"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0ef4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS03NTH", "name": "Crusher - Secondary: HD1 03 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83449 | 2026-07-03T06:59:14.8833028+00:00 | 2026-07-03T14:59:14.8833028+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | 2026-08-27T03:10:28.6043156+00:00 | 2026-08-27T11:10:28.6043156+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331888 | TRUE | TRUE | 2026-08-27T03:10:28.6043156+00:00 | 2026-08-27T11:10:28.6043156+08:00 | #83449 - HD1: 96hrs - HD1 STH & CS03 MODULAR | 1.1 | TRUE |  | 2027-04-22T22:00:00+00:00 | 2027-04-26T22:00:00+00:00 | 2027-04-23T06:00:00+08:00 | 2027-04-27T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 South Crusher Modular Shut (MoC 136554) |  |  | [{"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0ef4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS03NTH", "name": "Crusher - Secondary: HD1 03 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83450 | 2026-07-03T07:07:25.5317246+00:00 | 2026-07-03T15:07:25.5317246+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | 2026-08-27T03:10:28.6043794+00:00 | 2026-08-27T11:10:28.6043794+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331889 | TRUE | TRUE | 2026-08-27T03:10:28.6043794+00:00 | 2026-08-27T11:10:28.6043794+08:00 | #83450 - HD1: 96hrs - HD1 STH & CS03 MODULAR | 1.1 | TRUE |  | 2027-07-22T22:00:00+00:00 | 2027-07-26T22:00:00+00:00 | 2027-07-23T06:00:00+08:00 | 2027-07-27T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 South Crusher Modular Shut (MoC 136554) |  |  | [{"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0ef4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS03NTH", "name": "Crusher - Secondary: HD1 03 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83451 | 2026-07-03T07:24:49.2369778+00:00 | 2026-07-03T15:24:49.2369778+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | 2026-08-27T03:10:28.6043939+00:00 | 2026-08-27T11:10:28.6043939+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | {"name": "Fixed Plant"} | 331890 | TRUE | TRUE | 2026-08-27T03:10:28.6043939+00:00 | 2026-08-27T11:10:28.6043939+08:00 | #83451 - HD1: 96hrs - HD1 STH & CS03 MODULAR | 1.1 | TRUE |  | 2027-10-21T22:00:00+00:00 | 2027-10-25T22:00:00+00:00 | 2027-10-22T06:00:00+08:00 | 2027-10-26T06:00:00+08:00 |  |  |  |  | 96.00 | HD1 South Crusher Modular Shut (MoC 136554) |  |  | [{"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0ef4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1SCS03NTH", "name": "Crusher - Secondary: HD1 03 North", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "601d7f3f-0b8f-4c69-9824-6683af2a82f0", "emailAddress": "Croydon.Pukepuke1@riotinto.com", "displayName": "Pukepuke, Croydon (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2ac89c59-444d-4f1a-8210-22c8b8cbcb01 | Corfield, Nick (RTIO) | Scheduled | HD1 | Australia/Perth
83494 | 2026-07-09T04:38:30.0814781+00:00 | 2026-07-09T12:38:30.0814781+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-02T05:15:14.8558491+00:00 | 2026-10-02T13:15:14.8558491+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334985 | TRUE | TRUE | 2026-10-02T05:15:14.8558491+00:00 | 2026-10-02T13:15:14.8558491+08:00 | #83494 - EII: 76hrs - STACKER: EII 1EN | 3.0 | FALSE |  | 2027-02-25T23:00:00+00:00 | 2027-03-01T03:00:00+00:00 | 2027-02-26T07:00:00+08:00 | 2027-03-01T11:00:00+08:00 |  |  |  |  | 76.00 | RMP defects - blast and paint | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
82489 | 2026-05-12T05:37:24.495293+00:00 | 2026-05-12T13:37:24.495293+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-09-17T23:37:18.4343315+00:00 | 2026-09-18T07:37:18.4343315+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333531 | TRUE | TRUE | 2026-09-17T23:37:18.4343315+00:00 | 2026-09-18T07:37:18.4343315+08:00 | #82489 - EII: 72hrs - CONVEYOR: EII 8E | 2.0 | FALSE |  | 2027-01-27T23:00:00+00:00 | 2027-01-30T23:00:00+00:00 | 2027-01-28T07:00:00+08:00 | 2027-01-31T07:00:00+08:00 |  |  |  |  | 72.00 | IAM Conveyor: EII 8E | Outage times updated - Requested by the Dampier planning team. |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83496 | 2026-07-09T04:42:25.9729572+00:00 | 2026-07-09T12:42:25.9729572+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-07T06:23:19.4133725+00:00 | 2026-10-07T14:23:19.4133725+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335415 | TRUE | TRUE | 2026-10-07T06:23:19.4133725+00:00 | 2026-10-07T14:23:19.4133725+08:00 | #83496 - EII: 76hrs - EIIST3EN - RMP | 2.0 | FALSE |  | 2027-04-08T23:00:00+00:00 | 2027-04-12T03:00:00+00:00 | 2027-04-09T07:00:00+08:00 | 2027-04-12T11:00:00+08:00 |  |  |  |  | 76.00 | RMP defects - blast and paint | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84002 | 2026-09-28T04:41:23.3576966+00:00 | 2026-09-28T12:41:23.3576966+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | 2026-10-01T00:54:43.0324449+00:00 | 2026-10-01T08:54:43.0324449+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334766 | TRUE | TRUE | 2026-10-01T00:54:43.0324449+00:00 | 2026-10-01T08:54:43.0324449+08:00 | #84002 - EII: 72hrs - CONVEYOR: EII 11E | 1.0 | FALSE |  | 2027-01-10T11:00:00+00:00 | 2027-01-13T11:00:00+00:00 | 2027-01-10T19:00:00+08:00 | 2027-01-13T19:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Shut |  |  | [{"equipmentGUID": "4375fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV11E", "name": "Conveyor: EII 11E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "emailAddress": "Kate.Wilson2@riotinto.com", "displayName": "Wilson, Kate (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45676 | 2022-01-20T08:38:39+00:00 | 2022-01-20T16:38:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:03:34.2040877+00:00 | 2026-10-08T08:03:34.2040877+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335448 | TRUE | TRUE | 2026-10-08T00:03:34.2040877+00:00 | 2026-10-08T08:03:34.2040877+08:00 | #45676 - EII: 96hrs - RECLAIMER: EII 3E | 7.0 | FALSE |  | 2027-10-25T11:00:00+00:00 | 2027-10-29T11:00:00+00:00 | 2027-10-25T19:00:00+08:00 | 2027-10-29T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45656 | 2022-01-20T08:06:33+00:00 | 2022-01-20T16:06:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:04:06.2244625+00:00 | 2026-10-08T08:04:06.2244625+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335449 | TRUE | TRUE | 2026-10-08T00:04:06.2244625+00:00 | 2026-10-08T08:04:06.2244625+08:00 | #45656 - EII: 108hrs - STACKER: EII 1EN | 5.0 | FALSE |  | 2027-11-21T23:00:00+00:00 | 2027-11-26T11:00:00+00:00 | 2027-11-22T07:00:00+08:00 | 2027-11-26T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed Off' time |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45669 | 2022-01-20T08:29:06+00:00 | 2022-01-20T16:29:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:04:06.4107117+00:00 | 2026-10-08T08:04:06.4107117+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335450 | TRUE | TRUE | 2026-10-08T00:04:06.4107117+00:00 | 2026-10-08T08:04:06.4107117+08:00 | #45669 - EII: 96hrs - RECLAIMER: EII 1E | 5.0 | FALSE |  | 2027-11-22T11:00:00+00:00 | 2027-11-26T11:00:00+00:00 | 2027-11-22T19:00:00+08:00 | 2027-11-26T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45675 | 2022-01-20T08:37:20+00:00 | 2022-01-20T16:37:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:27:53.0237576+00:00 | 2026-10-07T15:27:53.0237576+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335435 | TRUE | TRUE | 2026-10-07T07:27:53.0237576+00:00 | 2026-10-07T15:27:53.0237576+08:00 | #45675 - EII: 96hrs - RECLAIMER: EII 3E | 7.0 | FALSE |  | 2027-07-26T11:00:00+00:00 | 2027-07-30T11:00:00+00:00 | 2027-07-26T19:00:00+08:00 | 2027-07-30T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45673 | 2022-01-20T08:33:40+00:00 | 2022-01-20T16:33:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:05:46.099137+00:00 | 2026-10-08T08:05:46.099137+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335453 | TRUE | TRUE | 2026-10-08T00:05:46.099137+00:00 | 2026-10-08T08:05:46.099137+08:00 | #45673 - EII: 96hrs - RECLAIMER: EII 2E | 5.0 | FALSE |  | 2027-12-13T11:00:00+00:00 | 2027-12-17T11:00:00+00:00 | 2027-12-13T19:00:00+08:00 | 2027-12-17T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45663 | 2022-01-20T08:15:05+00:00 | 2022-01-20T16:15:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T12:00:01.1439514+00:00 | 2026-10-05T20:00:01.1439514+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335324 | TRUE | TRUE | 2026-10-05T12:00:01.1439514+00:00 | 2026-10-05T20:00:01.1439514+08:00 | #45663 - EII: 108hrs - STACKER: EII 2EN | 6.0 | FALSE |  | 2027-07-25T23:00:00+00:00 | 2027-07-30T11:00:00+00:00 | 2027-07-26T07:00:00+08:00 | 2027-07-30T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45661 | 2022-01-20T08:12:23+00:00 | 2022-01-20T16:12:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T12:00:01.3631155+00:00 | 2026-10-05T20:00:01.3631155+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335325 | TRUE | TRUE | 2026-10-05T12:00:01.3631155+00:00 | 2026-10-05T20:00:01.3631155+08:00 | #45661 - EII: 108hrs - STACKER: EII 3EN | 5.0 | FALSE |  | 2027-10-03T23:00:00+00:00 | 2027-10-08T11:00:00+00:00 | 2027-10-04T07:00:00+08:00 | 2027-10-08T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45664 | 2022-01-20T08:16:09+00:00 | 2022-01-20T16:16:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T12:00:02.1345751+00:00 | 2026-10-05T20:00:02.1345751+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335328 | TRUE | TRUE | 2026-10-05T12:00:02.1345751+00:00 | 2026-10-05T20:00:02.1345751+08:00 | #45664 - EII: 108hrs - STACKER: EII 2EN | 6.0 | FALSE |  | 2027-10-24T23:00:00+00:00 | 2027-10-29T11:00:00+00:00 | 2027-10-25T07:00:00+08:00 | 2027-10-29T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
59946 | 2023-12-11T01:37:03+00:00 | 2023-12-11T09:37:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T06:41:33.9471257+00:00 | 2026-10-07T14:41:33.9471257+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335422 | TRUE | TRUE | 2026-10-07T06:41:33.9471257+00:00 | 2026-10-07T14:41:33.9471257+08:00 | #59946 - PPT: 396hrs - BERTH 4 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 11.0 | FALSE |  | 2027-05-09T22:00:00+00:00 | 2027-05-26T10:00:00+00:00 | 2027-05-10T06:00:00+08:00 | 2027-05-26T18:00:00+08:00 |  |  |  |  | 396.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works - Extended to align with Ship Loader SDN outage. | PPT B:4 Outage time updated - Requested by the Sus Cap Project Team. |  | [{"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "bc521488-59eb-4d88-8834-d789fcc969eb", "emailAddress": "Lewis.Buckland@riotinto.com", "displayName": "Buckland, Lewis (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | PPT | Australia/Perth
45654 | 2022-01-20T08:03:10+00:00 | 2022-01-20T16:03:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T06:42:43.3893849+00:00 | 2026-10-07T14:42:43.3893849+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335423 | TRUE | TRUE | 2026-10-07T06:42:43.3893849+00:00 | 2026-10-07T14:42:43.3893849+08:00 | #45654 - EII: 108hrs - STACKER: EII 1EN | 7.0 | FALSE |  | 2027-05-23T23:00:00+00:00 | 2027-05-28T11:00:00+00:00 | 2027-05-24T07:00:00+08:00 | 2027-05-28T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance. | Outage changed to be only a standard IAM outage. Functional Safety to be completed in a new standalone outage. Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45671 | 2022-01-20T08:31:17+00:00 | 2022-01-20T16:31:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:15:49.1703033+00:00 | 2026-10-07T15:15:49.1703033+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335429 | TRUE | TRUE | 2026-10-07T07:15:49.1703033+00:00 | 2026-10-07T15:15:49.1703033+08:00 | #45671 - EII: 96hrs - RECLAIMER: EII 2E | 5.0 | FALSE |  | 2027-06-14T11:00:00+00:00 | 2027-06-18T11:00:00+00:00 | 2027-06-14T19:00:00+08:00 | 2027-06-18T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45660 | 2022-01-20T08:11:24+00:00 | 2022-01-20T16:11:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:19:15.1813491+00:00 | 2026-10-07T15:19:15.1813491+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335432 | TRUE | TRUE | 2026-10-07T07:19:15.1813491+00:00 | 2026-10-07T15:19:15.1813491+08:00 | #45660 - EII: 108hrs - STACKER: EII 3EN | 5.0 | FALSE |  | 2027-07-04T23:00:00+00:00 | 2027-07-09T11:00:00+00:00 | 2027-07-05T07:00:00+08:00 | 2027-07-09T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45655 | 2022-01-20T08:04:52+00:00 | 2022-01-20T16:04:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:43:05.9569856+00:00 | 2026-10-07T15:43:05.9569856+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335438 | TRUE | TRUE | 2026-10-07T07:43:05.9569856+00:00 | 2026-10-07T15:43:05.9569856+08:00 | #45655 - EII: 108hrs - STACKER: EII 1EN | 5.0 | FALSE |  | 2027-08-22T23:00:00+00:00 | 2027-08-27T11:00:00+00:00 | 2027-08-23T07:00:00+08:00 | 2027-08-27T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "75bc9cce-242f-44ec-8ed3-7158f993005f", "emailAddress": "Jesse.Cunningham@riotinto.com", "displayName": "Cunningham, Jesse (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45668 | 2022-01-20T08:28:02+00:00 | 2022-01-20T16:28:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:43:06.1511349+00:00 | 2026-10-07T15:43:06.1511349+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335439 | TRUE | TRUE | 2026-10-07T07:43:06.1511349+00:00 | 2026-10-07T15:43:06.1511349+08:00 | #45668 - EII: 96hrs - RECLAIMER: EII 1E | 5.0 | FALSE |  | 2027-08-23T11:00:00+00:00 | 2027-08-27T11:00:00+00:00 | 2027-08-23T19:00:00+08:00 | 2027-08-27T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45672 | 2022-01-20T08:32:20+00:00 | 2022-01-20T16:32:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:00:59.0289868+00:00 | 2026-10-08T08:00:59.0289868+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335446 | TRUE | TRUE | 2026-10-08T00:00:59.0289868+00:00 | 2026-10-08T08:00:59.0289868+08:00 | #45672 - EII: 96hrs - RECLAIMER: EII 2E | 5.0 | FALSE |  | 2027-09-13T11:00:00+00:00 | 2027-09-17T11:00:00+00:00 | 2027-09-13T19:00:00+08:00 | 2027-09-17T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45662 | 2022-01-20T08:13:46+00:00 | 2022-01-20T16:13:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T04:19:56.3598923+00:00 | 2026-10-02T12:19:56.3598923+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334968 | TRUE | TRUE | 2026-10-02T04:19:56.3598923+00:00 | 2026-10-02T12:19:56.3598923+08:00 | #45662 - EII: 108hrs - STACKER: EII 2EN | 8.0 | FALSE |  | 2027-04-25T23:00:00+00:00 | 2027-04-30T11:00:00+00:00 | 2027-04-26T07:00:00+08:00 | 2027-04-30T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance Additional Info: 48 HR PITSTOP | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45674 | 2022-01-20T08:35:42+00:00 | 2022-01-20T16:35:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T04:55:36.2551449+00:00 | 2026-10-05T12:55:36.2551449+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335242 | TRUE | TRUE | 2026-10-05T04:55:36.2551449+00:00 | 2026-10-05T12:55:36.2551449+08:00 | #45674 - EII: 108hrs - RECLAIMER: EII 3E | 8.0 | FALSE |  | 2027-01-26T23:00:00+00:00 | 2027-01-31T11:00:00+00:00 | 2027-01-27T07:00:00+08:00 | 2027-01-31T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45670 | 2022-01-20T08:30:16+00:00 | 2022-01-20T16:30:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-18T00:14:40.1671238+00:00 | 2026-09-18T08:14:40.1671238+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333547 | TRUE | TRUE | 2026-09-18T00:14:40.1671238+00:00 | 2026-09-18T08:14:40.1671238+08:00 | #45670 - EII: 96hrs - RECLAIMER: EII 2E | 5.0 | FALSE |  | 2027-03-15T11:00:00+00:00 | 2027-03-19T11:00:00+00:00 | 2027-03-15T19:00:00+08:00 | 2027-03-19T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Outage time updated - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
64425 | 2024-09-25T07:52:01+00:00 | 2024-09-25T15:52:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T03:11:34.6854455+00:00 | 2026-06-15T11:11:34.6854455+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 327915 | TRUE | TRUE | 2026-06-15T03:11:34.6854455+00:00 | 2026-06-15T11:11:34.6854455+08:00 | #64425 - PPT: 984hrs - PPSS REC1P REPLACEMENT - INSTALLATION RCL4P - LOAD COMMISSIONING | 7.0 | FALSE |  | 2027-10-23T16:00:00+00:00 | 2027-12-03T16:00:00+00:00 | 2027-10-24T00:00:00+08:00 | 2027-12-04T00:00:00+08:00 |  |  |  |  | 984.00 | Ramp up duration is 41 days equates to ~16 days of production loss. | Project timing and duration adjustments ref Alan Mercer. |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [] | [] | [{"code": "X", "name": "PPSS PPT RECLAIMER REPLACEMENT", "projectTeam": {"name": "D&T"}, "totalProjectTime": "984"}] | [{"name": "Reduced Rates"}] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Site Constraint | PPT | Australia/Perth
50545 | 2022-11-03T07:02:08+00:00 | 2022-11-03T15:02:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T03:11:34.8161899+00:00 | 2026-06-15T11:11:34.8161899+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 327916 | TRUE | TRUE | 2026-06-15T03:11:34.8161899+00:00 | 2026-06-15T11:11:34.8161899+08:00 | #50545 - PPT: 2016hrs - PPSS RCL1P REPLACEMENT PROJECT - INSTALLATION RCL4P | 14.0 | FALSE |  | 2027-07-31T16:00:00+00:00 | 2027-10-23T16:00:00+00:00 | 2027-08-01T00:00:00+08:00 | 2027-10-24T00:00:00+08:00 |  |  |  |  | 2016.00 | PPSS Placeholder for RCL1P replacement project | Project timing and duration adjustments ref Alan Mercer. |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84077, "shutVersionId": 334953, "title": "#84077 - PPT: 1519hrs - PPSS RCL1P REPLACEMENT PROJECT - INSTALLATION RCL4P", "startDatetimeUTC": "2027-07-31T16:00:00+00:00", "endDatetimeUTC": "2027-10-02T23:00:00+00:00"}}] | [{"name": "Reclaimer Replacement"}] | [{"code": "X", "name": "PPSS PPT RECLAIMER REPLACEMENT", "projectTeam": {"name": "D&T"}, "totalProjectTime": "2208"}] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | PPT | Australia/Perth
50440 | 2022-11-03T06:48:59+00:00 | 2022-11-03T14:48:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T03:11:34.9680107+00:00 | 2026-06-15T11:11:34.9680107+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 327917 | TRUE | TRUE | 2026-06-15T03:11:34.9680107+00:00 | 2026-06-15T11:11:34.9680107+08:00 | #50440 - PPT: 2016hrs - PPSS RCL3P REPLACEMENT PROJECT - INSTALLATION RCL6P | 14.0 | FALSE |  | 2027-03-07T16:00:00+00:00 | 2027-05-30T16:00:00+00:00 | 2027-03-08T00:00:00+08:00 | 2027-05-31T00:00:00+08:00 |  |  |  |  | 2016.00 | PPSS Placeholder for RCL3P replacement project Installation of RCL6P | Project timing and duration adjustments ref Alan Mercer. |  | [{"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84075, "shutVersionId": 334995, "title": "#84075 - PPT: 1350hrs - PPSS RCL3P REPLACEMENT PROJECT - INSTALLATION RCL6P", "startDatetimeUTC": "2027-03-07T16:00:00+00:00", "endDatetimeUTC": "2027-05-02T22:00:00+00:00"}}] | [{"name": "Reclaimer Replacement"}] | [{"code": "X", "name": "PPSS PPT RECLAIMER REPLACEMENT", "projectTeam": {"name": "D&T"}, "totalProjectTime": "2520"}] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | PPT | Australia/Perth
45677 | 2022-01-20T08:39:44+00:00 | 2022-01-20T16:39:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-05-07T08:03:07.4504132+00:00 | 2026-05-07T16:03:07.4504132+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 326172 | TRUE | TRUE | 2026-05-07T08:03:07.4504132+00:00 | 2026-05-07T16:03:07.4504132+08:00 | #45677 - EII: 108hrs - RECLAIMER: EII 3E | 6.0 | FALSE |  | 2028-01-23T22:00:00+00:00 | 2028-01-28T10:00:00+00:00 | 2028-01-24T06:00:00+08:00 | 2028-01-28T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Approved IAM Outage Week Change. |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
45666 | 2022-01-20T08:25:44+00:00 | 2022-01-20T16:25:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-01T00:56:08.4078421+00:00 | 2026-10-01T08:56:08.4078421+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334768 | TRUE | TRUE | 2026-10-01T00:56:08.4078421+00:00 | 2026-10-01T08:56:08.4078421+08:00 | #45666 - EII: 96hrs - RECLAIMER: EII 1E | 6.0 | FALSE |  | 2027-02-21T11:00:00+00:00 | 2027-02-25T11:00:00+00:00 | 2027-02-21T19:00:00+08:00 | 2027-02-25T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Outage Feed Off Time Updated - 19:00 |  | [{"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
65250 | 2024-10-11T03:16:23+00:00 | 2024-10-11T11:16:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T23:37:18.1971103+00:00 | 2026-09-18T07:37:18.1971103+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333530 | TRUE | TRUE | 2026-09-17T23:37:18.1971103+00:00 | 2026-09-18T07:37:18.1971103+08:00 | #65250 - EII: 96hrs - STACKER: EII 2EN | 5.0 | FALSE |  | 2027-01-27T23:00:00+00:00 | 2027-01-31T23:00:00+00:00 | 2027-01-28T07:00:00+08:00 | 2027-02-01T07:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Outage date time updates - requested by the Dampier planning team. |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
65261 | 2024-10-11T03:35:43+00:00 | 2024-10-11T11:35:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T05:16:19.60702+00:00 | 2026-09-17T13:16:19.60702+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333482 | TRUE | TRUE | 2026-09-17T05:16:19.60702+00:00 | 2026-09-17T13:16:19.60702+08:00 | #65261 - EII: 96hrs - STACKER: EII 3EN | 4.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-07T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-08T07:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Outage start time moved to 07:00 - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
64206 | 2024-09-16T04:28:38+00:00 | 2024-09-16T12:28:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T05:41:32.8211054+00:00 | 2026-09-17T13:41:32.8211054+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333495 | TRUE | TRUE | 2026-09-17T05:41:32.8211054+00:00 | 2026-09-17T13:41:32.8211054+08:00 | #64206 - EII: 130hrs - SCREENHOUSE: EII 1E | 5.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage start time moved to 19:00 - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49029 | 2022-11-01T06:36:00+00:00 | 2022-11-01T14:36:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T05:41:33.0054628+00:00 | 2026-09-17T13:41:33.0054628+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333496 | TRUE | TRUE | 2026-09-17T05:41:33.0054628+00:00 | 2026-09-17T13:41:33.0054628+08:00 | #49029 - EII: 130hrs - BERTH: EII | 7.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage start time moved to 19:00 - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "", "code": "EIIBTH", "name": "Berth: EII", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49168 | 2022-11-01T22:33:10+00:00 | 2022-11-02T06:33:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T05:41:33.2366243+00:00 | 2026-09-17T13:41:33.2366243+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333497 | TRUE | TRUE | 2026-09-17T05:41:33.2366243+00:00 | 2026-09-17T13:41:33.2366243+08:00 | #49168 - EII: 130hrs - BERTH: EII LAYBY | 7.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage start time moved to 19:00 - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "", "code": "EIIBTHLAYBY", "name": "Berth: EII Layby", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
64957 | 2024-10-04T02:59:43+00:00 | 2024-10-04T10:59:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-17T23:59:20.8367276+00:00 | 2026-09-18T07:59:20.8367276+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333542 | TRUE | TRUE | 2026-09-17T23:59:20.8367276+00:00 | 2026-09-18T07:59:20.8367276+08:00 | #64957 - EII: 72hrs - SCREENHOUSE: EII 1E | 5.0 | FALSE |  | 2027-02-25T11:00:00+00:00 | 2027-02-28T11:00:00+00:00 | 2027-02-25T19:00:00+08:00 | 2027-02-28T19:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | Outage time updated - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
65239 | 2024-10-11T03:04:38+00:00 | 2024-10-11T11:04:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-18T00:02:18.068643+00:00 | 2026-09-18T08:02:18.068643+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333543 | TRUE | TRUE | 2026-09-18T00:02:18.068643+00:00 | 2026-09-18T08:02:18.068643+08:00 | #65239 - EII: 96hrs - STACKER: EII 1EN | 4.0 | FALSE |  | 2027-02-24T11:00:00+00:00 | 2027-02-28T11:00:00+00:00 | 2027-02-24T19:00:00+08:00 | 2027-02-28T19:00:00+08:00 |  |  |  |  | 96.00 | Stacker: EII 1EN | Outage time updates - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
54806 | 2023-04-04T23:27:43+00:00 | 2023-04-05T07:27:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-26T05:14:38.4570164+00:00 | 2025-11-26T13:14:38.4570164+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 277805 | TRUE | TRUE | 2025-11-26T05:14:38.4570164+00:00 | 2025-11-26T13:14:38.4570164+08:00 | #54806 - CLA: 336hrs - BERTH 3 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 6.0 | FALSE |  | 2027-05-02T16:00:00+00:00 | 2027-05-16T16:00:00+00:00 | 2027-05-03T00:00:00+08:00 | 2027-05-17T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 2 Marine Structural Life Extension Berth Works | Outage Duration Change. |  | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
54808 | 2023-04-05T01:08:28+00:00 | 2023-04-05T09:08:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2025-11-26T05:14:39.104558+00:00 | 2025-11-26T13:14:39.104558+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 277806 | TRUE | TRUE | 2025-11-26T05:14:39.104558+00:00 | 2025-11-26T13:14:39.104558+08:00 | #54808 - CLA: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 7.0 | FALSE |  | 2027-05-25T16:00:00+00:00 | 2027-06-08T16:00:00+00:00 | 2027-05-26T00:00:00+08:00 | 2027-06-09T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works | Outage Duration Change. |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
54805 | 2023-04-04T23:11:12+00:00 | 2023-04-05T07:11:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-01T07:49:39.3101138+00:00 | 2026-10-01T15:49:39.3101138+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334917 | TRUE | TRUE | 2026-10-01T07:49:39.3101138+00:00 | 2026-10-01T15:49:39.3101138+08:00 | #54805 - CLA: 672hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 11.0 | FALSE |  | 2027-01-19T22:00:00+00:00 | 2027-02-16T22:00:00+00:00 | 2027-01-20T06:00:00+08:00 | 2027-02-17T06:00:00+08:00 |  |  |  |  | 672.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works | Outage updated to match: #53161 - CLA: 672hrs - CLAHDO SL2C BM WORKS & SAMPLE STATION CUT OVER |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000001763", "emailAddress": "Alex.TengHuiChung@riotinto.com", "displayName": "Alex Teng"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
65095 | 2024-10-08T05:48:17+00:00 | 2024-10-08T13:48:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-02T04:18:20.7753431+00:00 | 2026-10-02T12:18:20.7753431+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334964 | TRUE | TRUE | 2026-10-02T04:18:20.7753431+00:00 | 2026-10-02T12:18:20.7753431+08:00 | #65095 - EII: 108hrs - STACKER: EII 3EN | 5.0 | FALSE |  | 2027-04-04T23:00:00+00:00 | 2027-04-09T11:00:00+00:00 | 2027-04-05T07:00:00+08:00 | 2027-04-09T19:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance Additional Info: 48 HR PITSTOP | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49030 | 2022-11-01T06:36:01+00:00 | 2022-11-01T14:36:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T06:04:49.5071768+00:00 | 2026-10-05T14:04:49.5071768+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335253 | TRUE | TRUE | 2026-10-05T06:04:49.5071768+00:00 | 2026-10-05T14:04:49.5071768+08:00 | #49030 - EII: 130hrs - BERTH: EII | 7.0 | FALSE |  | 2027-04-22T11:00:00+00:00 | 2027-04-27T21:00:00+00:00 | 2027-04-22T19:00:00+08:00 | 2027-04-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTH", "name": "Berth: EII", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49169 | 2022-11-01T22:33:11+00:00 | 2022-11-02T06:33:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T06:04:49.7050051+00:00 | 2026-10-05T14:04:49.7050051+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335254 | TRUE | TRUE | 2026-10-05T06:04:49.7050051+00:00 | 2026-10-05T14:04:49.7050051+08:00 | #49169 - EII: 130hrs - BERTH: EII LAYBY | 7.0 | FALSE |  | 2027-04-22T11:00:00+00:00 | 2027-04-27T21:00:00+00:00 | 2027-04-22T19:00:00+08:00 | 2027-04-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTHLAYBY", "name": "Berth: EII Layby", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44377 | 2021-11-25T01:53:28+00:00 | 2021-11-25T09:53:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T04:24:23.0823191+00:00 | 2026-10-01T12:24:23.0823191+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334811 | TRUE | TRUE | 2026-10-01T04:24:23.0823191+00:00 | 2026-10-01T12:24:23.0823191+08:00 | #44377 - EII: 106hrs - CAR DUMPER: EII 2E | 9.0 | TRUE |  | 2027-01-18T11:00:00+00:00 | 2027-01-22T21:00:00+00:00 | 2027-01-18T19:00:00+08:00 | 2027-01-23T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Outage Updated - Feed off time 19:00 Requested by IS&P |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
39877 | 2021-01-21T00:07:08+00:00 | 2021-01-21T08:07:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T00:54:42.8513832+00:00 | 2026-10-01T08:54:42.8513832+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334765 | TRUE | TRUE | 2026-10-01T00:54:42.8513832+00:00 | 2026-10-01T08:54:42.8513832+08:00 | #39877 - EII: 72hrs - CONVEYOR: EII 9E | 3.0 | FALSE |  | 2027-01-07T11:00:00+00:00 | 2027-01-10T11:00:00+00:00 | 2027-01-07T19:00:00+08:00 | 2027-01-10T19:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | Outage Time Updated. |  | [{"equipmentGUID": "5361fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV9E", "name": "Conveyor: EII 9E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "75bc9cce-242f-44ec-8ed3-7158f993005f", "emailAddress": "Jesse.Cunningham@riotinto.com", "displayName": "Cunningham, Jesse (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49171 | 2022-11-01T22:33:13+00:00 | 2022-11-02T06:33:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T12:00:01.570968+00:00 | 2026-10-05T20:00:01.570968+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335326 | TRUE | TRUE | 2026-10-05T12:00:01.570968+00:00 | 2026-10-05T20:00:01.570968+08:00 | #49171 - EII: 130hrs - BERTH: EII LAYBY | 7.0 | FALSE |  | 2027-10-21T11:00:00+00:00 | 2027-10-26T21:00:00+00:00 | 2027-10-21T19:00:00+08:00 | 2027-10-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTHLAYBY", "name": "Berth: EII Layby", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49032 | 2022-11-01T06:36:03+00:00 | 2022-11-01T14:36:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T12:00:01.8147463+00:00 | 2026-10-05T20:00:01.8147463+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335327 | TRUE | TRUE | 2026-10-05T12:00:01.8147463+00:00 | 2026-10-05T20:00:01.8147463+08:00 | #49032 - EII: 130hrs - BERTH: EII | 7.0 | FALSE |  | 2027-10-21T11:00:00+00:00 | 2027-10-26T21:00:00+00:00 | 2027-10-21T19:00:00+08:00 | 2027-10-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTH", "name": "Berth: EII", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49031 | 2022-11-01T06:36:01+00:00 | 2022-11-01T14:36:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T12:00:00.7702154+00:00 | 2026-10-05T20:00:00.7702154+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335322 | TRUE | TRUE | 2026-10-05T12:00:00.7702154+00:00 | 2026-10-05T20:00:00.7702154+08:00 | #49031 - EII: 130hrs - BERTH: EII | 7.0 | FALSE |  | 2027-07-22T11:00:00+00:00 | 2027-07-27T21:00:00+00:00 | 2027-07-22T19:00:00+08:00 | 2027-07-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTH", "name": "Berth: EII", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49170 | 2022-11-01T22:33:12+00:00 | 2022-11-02T06:33:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-05T12:00:00.9572148+00:00 | 2026-10-05T20:00:00.9572148+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335323 | TRUE | TRUE | 2026-10-05T12:00:00.9572148+00:00 | 2026-10-05T20:00:00.9572148+08:00 | #49170 - EII: 130hrs - BERTH: EII LAYBY | 7.0 | FALSE |  | 2027-07-22T11:00:00+00:00 | 2027-07-27T21:00:00+00:00 | 2027-07-22T19:00:00+08:00 | 2027-07-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "EIIBTHLAYBY", "name": "Berth: EII Layby", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
39790 | 2021-01-20T03:13:18+00:00 | 2021-01-20T11:13:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-07T06:39:49.0471885+00:00 | 2026-10-07T14:39:49.0471885+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335420 | TRUE | TRUE | 2026-10-07T06:39:49.0471885+00:00 | 2026-10-07T14:39:49.0471885+08:00 | #39790 - EII: 96hrs - RECLAIMER: EII 3E | 7.0 | FALSE |  | 2027-04-26T11:00:00+00:00 | 2027-04-30T11:00:00+00:00 | 2027-04-26T19:00:00+08:00 | 2027-04-30T19:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44380 | 2021-11-25T01:53:31+00:00 | 2021-11-25T09:53:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T11:46:19.3610589+00:00 | 2026-10-05T19:46:19.3610589+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335320 | TRUE | TRUE | 2026-10-05T11:46:19.3610589+00:00 | 2026-10-05T19:46:19.3610589+08:00 | #44380 - EII: 106hrs - CAR DUMPER: EII 2E | 8.0 | TRUE |  | 2027-10-18T11:00:00+00:00 | 2027-10-22T21:00:00+00:00 | 2027-10-18T19:00:00+08:00 | 2027-10-23T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cf432606-a42e-449b-b28a-08e3cff7b5e4", "emailAddress": "Trevor.Fawcett@riotinto.com", "displayName": "Trevor Fawcett"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44379 | 2021-11-25T01:53:29+00:00 | 2021-11-25T09:53:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T11:46:19.5364383+00:00 | 2026-10-05T19:46:19.5364383+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335321 | TRUE | TRUE | 2026-10-05T11:46:19.5364383+00:00 | 2026-10-05T19:46:19.5364383+08:00 | #44379 - EII: 106hrs - CAR DUMPER: EII 2E | 8.0 | TRUE |  | 2027-07-19T11:00:00+00:00 | 2027-07-23T21:00:00+00:00 | 2027-07-19T19:00:00+08:00 | 2027-07-24T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Feed Off 19:00 |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cf432606-a42e-449b-b28a-08e3cff7b5e4", "emailAddress": "Trevor.Fawcett@riotinto.com", "displayName": "Trevor Fawcett"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44378 | 2021-11-25T01:53:28+00:00 | 2021-11-25T09:53:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-02T04:19:18.8633632+00:00 | 2026-10-02T12:19:18.8633632+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334966 | TRUE | TRUE | 2026-10-02T04:19:18.8633632+00:00 | 2026-10-02T12:19:18.8633632+08:00 | #44378 - EII: 106hrs - CAR DUMPER: EII 2E | 10.0 | TRUE |  | 2027-04-19T11:00:00+00:00 | 2027-04-23T21:00:00+00:00 | 2027-04-19T19:00:00+08:00 | 2027-04-24T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Feed Off 19:00 |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cf432606-a42e-449b-b28a-08e3cff7b5e4", "emailAddress": "Trevor.Fawcett@riotinto.com", "displayName": "Trevor Fawcett"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44396 | 2021-11-25T02:01:11+00:00 | 2021-11-25T10:01:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T23:50:29.3768727+00:00 | 2026-10-02T07:50:29.3768727+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334943 | TRUE | TRUE | 2026-10-01T23:50:29.3768727+00:00 | 2026-10-02T07:50:29.3768727+08:00 | #44396 - EII: 130hrs - SHIPLOADER: EII 1E | 7.0 | TRUE |  | 2027-10-21T11:00:00+00:00 | 2027-10-26T21:00:00+00:00 | 2027-10-21T19:00:00+08:00 | 2027-10-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44394 | 2021-11-25T02:01:09+00:00 | 2021-11-25T10:01:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T23:50:28.3929787+00:00 | 2026-10-02T07:50:28.3929787+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334938 | TRUE | TRUE | 2026-10-01T23:50:28.3929787+00:00 | 2026-10-02T07:50:28.3929787+08:00 | #44394 - EII: 130hrs - SHIPLOADER: EII 1E | 9.0 | TRUE |  | 2027-04-22T11:00:00+00:00 | 2027-04-27T21:00:00+00:00 | 2027-04-22T19:00:00+08:00 | 2027-04-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Start time updated to 19:00 |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44395 | 2021-11-25T02:01:09+00:00 | 2021-11-25T10:01:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T23:50:28.7693115+00:00 | 2026-10-02T07:50:28.7693115+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334940 | TRUE | TRUE | 2026-10-01T23:50:28.7693115+00:00 | 2026-10-02T07:50:28.7693115+08:00 | #44395 - EII: 130hrs - SHIPLOADER: EII 1E | 7.0 | TRUE |  | 2027-07-22T11:00:00+00:00 | 2027-07-27T21:00:00+00:00 | 2027-07-22T19:00:00+08:00 | 2027-07-28T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Feed Off 19:00 |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
44393 | 2021-11-25T02:01:08+00:00 | 2021-11-25T10:01:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-09-17T05:40:31.8730606+00:00 | 2026-09-17T13:40:31.8730606+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333493 | TRUE | TRUE | 2026-09-17T05:40:31.8730606+00:00 | 2026-09-17T13:40:31.8730606+08:00 | #44393 - EII: 130hrs - SHIPLOADER: EII 1E | 7.0 | TRUE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage start time moved to 19:00 - Requested by the Dampier site planning team. |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
49135 | 2022-11-01T07:10:08+00:00 | 2022-11-01T15:10:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-02T05:27:31.037124+00:00 | 2026-10-02T13:27:31.037124+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334992 | TRUE | TRUE | 2026-10-02T05:27:31.037124+00:00 | 2026-10-02T13:27:31.037124+08:00 | #49135 - PPT: 130hrs - BERTH: PPT 03 | 5.0 | FALSE |  | 2027-03-28T11:00:00+00:00 | 2027-04-02T21:00:00+00:00 | 2027-03-28T19:00:00+08:00 | 2027-04-03T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage Feed Off Time Amended - 19:00 |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | PPT | Australia/Perth
49119 | 2022-11-01T07:09:42+00:00 | 2022-11-01T15:09:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-02T05:27:31.2021293+00:00 | 2026-10-02T13:27:31.2021293+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334993 | TRUE | TRUE | 2026-10-02T05:27:31.2021293+00:00 | 2026-10-02T13:27:31.2021293+08:00 | #49119 - PPT: 130hrs - BERTH: PPT 02 | 5.0 | FALSE |  | 2027-03-28T11:00:00+00:00 | 2027-04-02T21:00:00+00:00 | 2027-03-28T19:00:00+08:00 | 2027-04-03T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Outage Feed Off Time Amended - 19:00 |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | PPT | Australia/Perth
84072 | 2026-10-01T01:46:54.1700435+00:00 | 2026-10-01T09:46:54.1700435+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T01:46:54.6605136+00:00 | 2026-10-01T09:46:54.6605136+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334791 | TRUE | TRUE | 2026-10-01T01:46:54.6605136+00:00 | 2026-10-01T09:46:54.6605136+08:00 | #84072 - EII: 48hrs - BAY: EII RECLAIMER MAINTENANCE | 1.0 | FALSE |  | 2027-02-28T16:00:00+00:00 | 2027-03-02T16:00:00+00:00 | 2027-03-01T00:00:00+08:00 | 2027-03-03T00:00:00+08:00 |  |  |  |  | 48.00 | EII Stockyard Isolator Project |  |  | [{"equipmentGUID": "cb20f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIBAYS01", "name": "Bay: EII Reclaimer Maintenance ", "assetClass": {"name": "Bay"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b9ec4e2a-3784-4d87-9441-b26e047c5279", "emailAddress": "Chris.Burg@riotinto.com", "displayName": "Burg, Christopher (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84073 | 2026-10-01T01:48:25.6542797+00:00 | 2026-10-01T09:48:25.6542797+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T01:48:26.1874914+00:00 | 2026-10-01T09:48:26.1874914+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334793 | TRUE | TRUE | 2026-10-01T01:48:26.1874914+00:00 | 2026-10-01T09:48:26.1874914+08:00 | #84073 - EII: 48hrs - BAY: EII STACKER MAINTENANCE | 1.0 | FALSE |  | 2027-02-28T16:00:00+00:00 | 2027-03-02T16:00:00+00:00 | 2027-03-01T00:00:00+08:00 | 2027-03-03T00:00:00+08:00 |  |  |  |  | 48.00 | EII Stockyard Isolator Project |  |  | [{"equipmentGUID": "0e09f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIBAYS02", "name": "Bay: EII Stacker Maintenance ", "assetClass": {"name": "Bay"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b9ec4e2a-3784-4d87-9441-b26e047c5279", "emailAddress": "Chris.Burg@riotinto.com", "displayName": "Burg, Christopher (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84061 | 2026-09-30T07:28:49.0784069+00:00 | 2026-09-30T15:28:49.0784069+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-01T04:22:32.4260794+00:00 | 2026-10-01T12:22:32.4260794+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334810 | TRUE | TRUE | 2026-10-01T04:22:32.4260794+00:00 | 2026-10-01T12:22:32.4260794+08:00 | #84061 - EII: 72hrs - CONVEYOR: EII 31E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 31E - IAM |  |  | [{"equipmentGUID": "c719f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV31E", "name": "Conveyor: EII 31E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83963 | 2026-09-22T06:37:49.0349379+00:00 | 2026-09-22T14:37:49.0349379+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-21T01:10:03.5005103+00:00 | 2026-10-21T09:10:03.5005103+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336244 | TRUE | TRUE | 2026-10-21T01:10:03.5005103+00:00 | 2026-10-21T09:10:03.5005103+08:00 | #83963 - EII: 36hrs - FUNCTIONAL SAFETY TP12EN - STANDALONE OUTAGE | 2.0 | FALSE |  | 2027-05-30T23:00:00+00:00 | 2027-06-01T11:00:00+00:00 | 2027-05-31T07:00:00+08:00 | 2027-06-01T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP12EN - Standalone Outage | Feed Off changed to 07:00 / Duration 36Hr |  | [{"equipmentGUID": "d627f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV12E", "name": "Conveyor: EII 12E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "14a81ce8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP12E", "name": "Tripper: EII 12E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83475 | 2026-07-08T03:41:17.8138752+00:00 | 2026-07-08T11:41:17.8138752+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-21T01:11:07.2878594+00:00 | 2026-10-21T09:11:07.2878594+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336246 | TRUE | TRUE | 2026-10-21T01:11:07.2878594+00:00 | 2026-10-21T09:11:07.2878594+08:00 | #83475 - EII: 300hrs - CONVEYOR: EII 10E | 2.0 | FALSE |  | 2027-07-22T10:00:00+00:00 | 2027-08-03T22:00:00+00:00 | 2027-07-22T18:00:00+08:00 | 2027-08-04T06:00:00+08:00 |  |  |  |  | 300.00 | 10E Drive Platform Upgrades. | 10E Drive Platform works to align to10E / 13E Chute projects works - Action from the PACE workshop. |  | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83962 | 2026-09-22T06:30:12.0793989+00:00 | 2026-09-22T14:30:12.0793989+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-21T01:12:29.68472+00:00 | 2026-10-21T09:12:29.68472+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336247 | TRUE | TRUE | 2026-10-21T01:12:29.68472+00:00 | 2026-10-21T09:12:29.68472+08:00 | #83962 - EII: 12hrs - FUNCTIONAL SAFETY TP19E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-05-30T11:00:00+00:00 | 2027-05-30T23:00:00+00:00 | 2027-05-30T19:00:00+08:00 | 2027-05-31T07:00:00+08:00 |  |  |  |  | 12.00 | FUNCTIONAL SAFETY TP19E - Standalone Outage |  |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "d75ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV19E", "name": "Conveyor: EII 19E ", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "17504be8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP19E", "name": "Tripper: EII 19E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83465 | 2026-07-08T02:03:32.6030349+00:00 | 2026-07-08T10:03:32.6030349+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-21T01:14:01.1600702+00:00 | 2026-10-21T09:14:01.1600702+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336248 | TRUE | TRUE | 2026-10-21T01:14:01.1600702+00:00 | 2026-10-21T09:14:01.1600702+08:00 | #83465 - EII: 203hrs - 9E/13E TRANSFER CHUTE REPLACEMENT | 3.0 | TRUE |  | 2027-04-22T11:00:00+00:00 | 2027-04-30T22:00:00+00:00 | 2027-04-22T19:00:00+08:00 | 2027-05-01T06:00:00+08:00 |  |  |  |  | 203.00 | 13E Chute Project Works. | 9E & 13E Chute Project Works. |  | [{"equipmentGUID": "7effe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV13E", "name": "Conveyor: EII 13E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83966 | 2026-09-22T07:29:32.2249059+00:00 | 2026-09-22T15:29:32.2249059+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-21T02:58:51.9959212+00:00 | 2026-10-21T10:58:51.9959212+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336258 | TRUE | TRUE | 2026-10-21T02:58:51.9959212+00:00 | 2026-10-21T10:58:51.9959212+08:00 | #83966 - EII: 12hrs - FUNCTIONAL SAFETY 6E - STANDALONE OUTAGE | 1.0 | TRUE |  | 2027-07-23T09:00:00+00:00 | 2027-07-23T21:00:00+00:00 | 2027-07-23T17:00:00+08:00 | 2027-07-24T05:00:00+08:00 |  |  |  |  | 12.00 | FUNCTIONAL SAFETY 6E - Standalone Outage Outage moved to 23rd July / Duration reduced to 12HR |  |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "ba41f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV6E", "name": "Conveyor: EII 6E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "cd9501e8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP6E", "name": "Tripper: EII 6E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
76488 | 2026-02-26T08:45:43.0731624+00:00 | 2026-02-26T16:45:43.0731624+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-09-18T05:32:25.6415993+00:00 | 2026-09-18T13:32:25.6415993+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333588 | TRUE | TRUE | 2026-09-18T05:32:25.6415993+00:00 | 2026-09-18T13:32:25.6415993+08:00 | #76488 - PPT: 130hrs - SL2P CORROSION CONTROL | 2.0 | TRUE |  | 2027-09-21T00:00:00+00:00 | 2027-09-26T10:00:00+00:00 | 2027-09-21T08:00:00+08:00 | 2027-09-26T18:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control | Berth Function Location's Added. |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}, {"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | PPT | Australia/Perth
73663 | 2025-11-26T04:29:22.8713768+00:00 | 2025-11-26T12:29:22.8713768+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2025-11-26T05:14:37.8267578+00:00 | 2025-11-26T13:14:37.8267578+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 277804 | TRUE | TRUE | 2025-11-26T05:14:37.8267578+00:00 | 2025-11-26T13:14:37.8267578+08:00 | #73663 - CLA: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-04-04T16:00:00+00:00 | 2027-04-18T16:00:00+00:00 | 2027-04-05T00:00:00+08:00 | 2027-04-19T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works. |  |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
73665 | 2025-11-26T05:20:02.0931405+00:00 | 2025-11-26T13:20:02.0931405+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2025-11-27T00:40:30.4923069+00:00 | 2025-11-27T08:40:30.4923069+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 277858 | TRUE | TRUE | 2025-11-27T00:40:30.4923069+00:00 | 2025-11-27T08:40:30.4923069+08:00 | #73665 - CLA: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-07-04T16:00:00+00:00 | 2027-07-18T16:00:00+00:00 | 2027-07-05T00:00:00+08:00 | 2027-07-19T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works. |  |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
73667 | 2025-11-26T05:26:18.1678367+00:00 | 2025-11-26T13:26:18.1678367+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2025-11-27T00:40:31.9117179+00:00 | 2025-11-27T08:40:31.9117179+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 277860 | TRUE | TRUE | 2025-11-27T00:40:31.9117179+00:00 | 2025-11-27T08:40:31.9117179+08:00 | #73667 - CLA: 336hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 1.0 | FALSE |  | 2027-10-03T16:00:00+00:00 | 2027-10-17T16:00:00+00:00 | 2027-10-04T00:00:00+08:00 | 2027-10-18T00:00:00+08:00 |  |  |  |  | 336.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works. |  |  | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1cc5c737-3628-4537-b89f-d7231b10129f", "emailAddress": "Jason.Wheeler2@riotinto.com", "displayName": "Wheeler, Jason (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Major Projects | CLA | Australia/Perth
84052 | 2026-09-30T06:54:02.4882736+00:00 | 2026-09-30T14:54:02.4882736+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-30T07:11:33.4177352+00:00 | 2026-09-30T15:11:33.4177352+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334670 | TRUE | TRUE | 2026-09-30T07:11:33.4177352+00:00 | 2026-09-30T15:11:33.4177352+08:00 | #84052 - EII: 106hrs - CONVEYOR: EII 6E | 1.0 | FALSE |  | 2027-01-17T23:00:00+00:00 | 2027-01-22T09:00:00+00:00 | 2027-01-18T07:00:00+08:00 | 2027-01-22T17:00:00+08:00 |  |  |  |  | 106.00 | Conveyor: EII 6E - IAM |  |  | [{"equipmentGUID": "ba41f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV6E", "name": "Conveyor: EII 6E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84062 | 2026-09-30T07:29:47.8416499+00:00 | 2026-09-30T15:29:47.8416499+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-30T07:29:47.8416499+00:00 | 2026-09-30T15:29:47.8416499+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334692 | TRUE | TRUE | 2026-09-30T07:29:47.8416499+00:00 | 2026-09-30T15:29:47.8416499+08:00 | #84062 - EII: 72hrs - CONVEYOR: EII 33E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 33E - IAM |  |  | [{"equipmentGUID": "11e8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV33E", "name": "Conveyor: EII 33E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84063 | 2026-09-30T07:31:03.4190839+00:00 | 2026-09-30T15:31:03.4190839+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-30T07:31:03.4190839+00:00 | 2026-09-30T15:31:03.4190839+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334694 | TRUE | TRUE | 2026-09-30T07:31:03.4190839+00:00 | 2026-09-30T15:31:03.4190839+08:00 | #84063 - EII: 72hrs - CONVEYOR: EII 34E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 34E - IAM |  |  | [{"equipmentGUID": "0e21f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV34E", "name": "Conveyor: EII 34E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84064 | 2026-09-30T07:33:30.5566303+00:00 | 2026-09-30T15:33:30.5566303+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-30T07:33:30.5566303+00:00 | 2026-09-30T15:33:30.5566303+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334699 | TRUE | TRUE | 2026-09-30T07:33:30.5566303+00:00 | 2026-09-30T15:33:30.5566303+08:00 | #84064 - EII: 72hrs - CONVEYOR: EII 35E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 35E - IAM |  |  | [{"equipmentGUID": "4cfce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV35E", "name": "Conveyor: EII 35E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83956 | 2026-09-22T03:24:45.1251834+00:00 | 2026-09-22T11:24:45.1251834+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-22T23:55:27.9619098+00:00 | 2026-09-23T07:55:27.9619098+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333718 | TRUE | TRUE | 2026-09-22T23:55:27.9619098+00:00 | 2026-09-23T07:55:27.9619098+08:00 | #83956 - EII: 60hrs - FUNCTIONAL SAFETY TP8EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-03-04T23:00:00+00:00 | 2027-03-07T11:00:00+00:00 | 2027-03-05T07:00:00+08:00 | 2027-03-07T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY TP8EN - Standalone Outage |  |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "853a63e8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP8E", "name": "Tripper: EII 8E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84049, "shutVersionId": 334986, "title": "#84049 - EII: 60hrs - FUNCTIONAL SAFETY ST2EN - STANDALONE OUTAGE", "startDatetimeUTC": "2027-03-04T23:00:00+00:00", "endDatetimeUTC": "2027-03-07T11:00:00+00:00"}}] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83960 | 2026-09-22T06:24:26.6271696+00:00 | 2026-09-22T14:24:26.6271696+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-23T00:00:29.0294315+00:00 | 2026-09-23T08:00:29.0294315+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333719 | TRUE | TRUE | 2026-09-23T00:00:29.0294315+00:00 | 2026-09-23T08:00:29.0294315+08:00 | #83960 - EII: 60hrs - FUNCTIONAL SAFETY TP9EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-04-14T23:00:00+00:00 | 2027-04-17T11:00:00+00:00 | 2027-04-15T07:00:00+08:00 | 2027-04-17T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY TP9EN - Standalone Outage |  |  | [{"equipmentGUID": "5361fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV9E", "name": "Conveyor: EII 9E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "958f1ce8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP9E", "name": "Tripper: EII 9E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83958, "shutVersionId": 335417, "title": "#83958 - EII: 60hrs - FUNCTIONAL SAFETY ST1EN - STANDALONE OUTAGE", "startDatetimeUTC": "2027-04-14T23:00:00+00:00", "endDatetimeUTC": "2027-04-17T11:00:00+00:00"}}] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83953 | 2026-09-22T02:24:08.2103468+00:00 | 2026-09-22T10:24:08.2103468+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-23T00:33:29.7004534+00:00 | 2026-09-23T08:33:29.7004534+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333722 | TRUE | TRUE | 2026-09-23T00:33:29.7004534+00:00 | 2026-09-23T08:33:29.7004534+08:00 | #83953 - EII: 60hrs - FUNCTIONAL SAFETY ST3EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-12-05T23:00:00+00:00 | 2027-12-08T11:00:00+00:00 | 2027-12-06T07:00:00+08:00 | 2027-12-08T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY ST3EN - Standalone Outage |  |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83932 | 2026-09-17T07:20:25.5280039+00:00 | 2026-09-17T15:20:25.5280039+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-18T05:28:17.0806098+00:00 | 2026-09-18T13:28:17.0806098+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333586 | TRUE | TRUE | 2026-09-18T05:28:17.0806098+00:00 | 2026-09-18T13:28:17.0806098+08:00 | #83932 - EII: 72hrs - CONVEYOR: EII 7E | 1.0 | FALSE |  | 2027-12-10T11:00:00+00:00 | 2027-12-13T11:00:00+00:00 | 2027-12-10T19:00:00+08:00 | 2027-12-13T19:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 7E |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83931 | 2026-09-17T07:13:47.0961484+00:00 | 2026-09-17T15:13:47.0961484+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-18T05:29:58.1774248+00:00 | 2026-09-18T13:29:58.1774248+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333587 | TRUE | TRUE | 2026-09-18T05:29:58.1774248+00:00 | 2026-09-18T13:29:58.1774248+08:00 | #83931 - EII: 72hrs - CONVEYOR: EII 7E | 1.0 | FALSE |  | 2027-09-10T11:00:00+00:00 | 2027-09-13T11:00:00+00:00 | 2027-09-10T19:00:00+08:00 | 2027-09-13T19:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 7E |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83930 | 2026-09-17T07:09:26.4490741+00:00 | 2026-09-17T15:09:26.4490741+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-18T04:37:25.3540501+00:00 | 2026-09-18T12:37:25.3540501+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333572 | TRUE | TRUE | 2026-09-18T04:37:25.3540501+00:00 | 2026-09-18T12:37:25.3540501+08:00 | #83930 - EII: 72hrs - CONVEYOR: EII 7E | 1.0 | FALSE |  | 2027-06-11T11:00:00+00:00 | 2027-06-14T11:00:00+00:00 | 2027-06-11T19:00:00+08:00 | 2027-06-14T19:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 7E |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83498 | 2026-07-10T00:48:21.3420338+00:00 | 2026-07-10T08:48:21.3420338+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-09-18T00:14:40.3513365+00:00 | 2026-09-18T08:14:40.3513365+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 333548 | TRUE | TRUE | 2026-09-18T00:14:40.3513365+00:00 | 2026-09-18T08:14:40.3513365+08:00 | #83498 - EII: 120hrs - RECLAIMER: EII 2E | 2.0 | FALSE |  | 2027-03-19T10:00:00+00:00 | 2027-03-24T10:00:00+00:00 | 2027-03-19T18:00:00+08:00 | 2027-03-24T18:00:00+08:00 |  |  |  |  | 120.00 | RMP Project Works. | WK06 RMP Project Works Outage moved to the back of the WK11 REC2E IAM Outage. Action from the site PACE workshop. |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83970 | 2026-09-22T07:42:29.2113759+00:00 | 2026-09-22T15:42:29.2113759+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T06:12:15.064393+00:00 | 2026-10-07T14:12:15.064393+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335412 | TRUE | TRUE | 2026-10-07T06:12:15.064393+00:00 | 2026-10-07T14:12:15.064393+08:00 | #83970 - EII: 12hrs - CAPD - REC3E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-01-31T23:00:00+00:00 | 2027-02-01T11:00:00+00:00 | 2027-02-01T07:00:00+08:00 | 2027-02-01T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD - REC3E - Standalone Outage |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
81673 | 2026-03-13T09:01:53.0064667+00:00 | 2026-03-13T17:01:53.0064667+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T06:39:49.2802783+00:00 | 2026-10-07T14:39:49.2802783+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335421 | TRUE | TRUE | 2026-10-07T06:39:49.2802783+00:00 | 2026-10-07T14:39:49.2802783+08:00 | #81673 - EII: 340hrs - REC3E BUCKET WHEEL CHANGE OUT | 3.0 | FALSE |  | 2027-04-30T10:00:00+00:00 | 2027-05-14T14:00:00+00:00 | 2027-04-30T18:00:00+08:00 | 2027-05-14T22:00:00+08:00 |  |  |  |  | 340.00 | REC3E Bucket Wheel Change Out. | Outage moved to the back of the REC3E IAM outage. PACE Workshop action - Approved by the site MWP team. |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2cb93764-e84c-426e-842a-2e8dff5b3945", "emailAddress": "Marc.Hodges@riotinto.com", "displayName": "Hodges, Marc (RTIO)"}}] | [] | [] | [{"name": "Bucket Wheel Changeout"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83958 | 2026-09-22T06:20:20.0471475+00:00 | 2026-09-22T14:20:20.0471475+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T06:26:36.1974207+00:00 | 2026-10-07T14:26:36.1974207+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335417 | TRUE | TRUE | 2026-10-07T06:26:36.1974207+00:00 | 2026-10-07T14:26:36.1974207+08:00 | #83958 - EII: 60hrs - FUNCTIONAL SAFETY ST1EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-04-14T23:00:00+00:00 | 2027-04-17T11:00:00+00:00 | 2027-04-15T07:00:00+08:00 | 2027-04-17T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY ST1EN - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83960, "shutVersionId": 333719, "title": "#83960 - EII: 60hrs - FUNCTIONAL SAFETY TP9EN - STANDALONE OUTAGE", "startDatetimeUTC": "2027-04-14T23:00:00+00:00", "endDatetimeUTC": "2027-04-17T11:00:00+00:00"}}] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83965 | 2026-09-22T07:21:57.9702784+00:00 | 2026-09-22T15:21:57.9702784+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T06:30:31.4247696+00:00 | 2026-10-07T14:30:31.4247696+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335418 | TRUE | TRUE | 2026-10-07T06:30:31.4247696+00:00 | 2026-10-07T14:30:31.4247696+08:00 | #83965 - EII: 6hrs - FUNCTIONAL SAFETY 5E | 1.0 | TRUE |  | 2027-04-19T23:00:00+00:00 | 2027-04-20T05:00:00+00:00 | 2027-04-20T07:00:00+08:00 | 2027-04-20T13:00:00+08:00 |  |  |  |  | 6.00 | FUNCTIONAL SAFETY 5E |  |  | [{"equipmentGUID": "9e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICD2E", "name": "Car Dumper: EII 2E", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "fa18f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV5E", "name": "Conveyor: EII 5E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83499 | 2026-07-10T00:51:50.6529374+00:00 | 2026-07-10T08:51:50.6529374+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T06:22:45.6041001+00:00 | 2026-10-07T14:22:45.6041001+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335414 | TRUE | TRUE | 2026-10-07T06:22:45.6041001+00:00 | 2026-10-07T14:22:45.6041001+08:00 | #83499 - EII: 120hrs - EIIRC3E - RMP | 2.0 | FALSE |  | 2027-04-07T11:00:00+00:00 | 2027-04-12T11:00:00+00:00 | 2027-04-07T19:00:00+08:00 | 2027-04-12T19:00:00+08:00 |  |  |  |  | 120.00 | RMP Project Works - Project Contact: Neen Barry (RTIO) | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "3fdce8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC3E", "name": "Reclaimer: EII 3E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83954 | 2026-09-22T03:00:52.8903123+00:00 | 2026-09-22T11:00:52.8903123+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-08T00:05:18.7792939+00:00 | 2026-10-08T08:05:18.7792939+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335452 | TRUE | TRUE | 2026-10-08T00:05:18.7792939+00:00 | 2026-10-08T08:05:18.7792939+08:00 | #83954 - EII: 60hrs - FUNCTIONAL SAFETY TP32EN - STANDALONE OUTAGE | 3.0 | FALSE |  | 2027-12-05T23:00:00+00:00 | 2027-12-08T11:00:00+00:00 | 2027-12-06T07:00:00+08:00 | 2027-12-08T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY TR32EN - Standalone Outage | Start date moved to the 6th to align with ST3EN |  | [{"equipmentGUID": "16d200c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV32E", "name": "Conveyor: EII 32E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "7108e9e7-4a8c-ee11-a847-000d3acacefd", "code": "EIITP32E", "name": "Tripper: EII 32E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84059 | 2026-09-30T07:24:22.7389998+00:00 | 2026-09-30T15:24:22.7389998+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:04:45.1227644+00:00 | 2026-10-02T14:04:45.1227644+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334998 | TRUE | TRUE | 2026-10-02T06:04:45.1227644+00:00 | 2026-10-02T14:04:45.1227644+08:00 | #84059 - EII: 130hrs - CONVEYOR: EII 20E | 2.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 20E - IAM | Outage date change to align with SL1E - IAM. |  | [{"equipmentGUID": "4546f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV20E", "name": "Conveyor: EII 20E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84060 | 2026-09-30T07:25:52.1137102+00:00 | 2026-09-30T15:25:52.1137102+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:09:54.0892411+00:00 | 2026-10-02T14:09:54.0892411+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334999 | TRUE | TRUE | 2026-10-02T06:09:54.0892411+00:00 | 2026-10-02T14:09:54.0892411+08:00 | #84060 - EII: 130hrs - CONVEYOR: EII 21E | 2.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 21E - IAM | Outage date change to align with SL1E - IAM. |  | [{"equipmentGUID": "5663fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV21E", "name": "Conveyor: EII 21E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84055 | 2026-09-30T07:01:53.0930712+00:00 | 2026-09-30T15:01:53.0930712+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:12:50.2368375+00:00 | 2026-10-02T14:12:50.2368375+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335001 | TRUE | TRUE | 2026-10-02T06:12:50.2368375+00:00 | 2026-10-02T14:12:50.2368375+08:00 | #84055 - EII: 130hrs - CONVEYOR: EII 14E | 2.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 14E - IAM | Outage date change to align with SL1E - IAM. |  | [{"equipmentGUID": "0fce00c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV14E", "name": "Conveyor: EII 14E ", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84056 | 2026-09-30T07:08:45.1885957+00:00 | 2026-09-30T15:08:45.1885957+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:14:21.8674626+00:00 | 2026-10-02T14:14:21.8674626+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335002 | TRUE | TRUE | 2026-10-02T06:14:21.8674626+00:00 | 2026-10-02T14:14:21.8674626+08:00 | #84056 - EII: 130hrs - CONVEYOR: EII 17E | 2.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 17E - IAM | Outage date change to align with SL1E - IAM. |  | [{"equipmentGUID": "1061fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV17E", "name": "Conveyor: EII 17E ", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84054 | 2026-09-30T06:59:48.1367835+00:00 | 2026-09-30T14:59:48.1367835+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:16:24.7682567+00:00 | 2026-10-02T14:16:24.7682567+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335003 | TRUE | TRUE | 2026-10-02T06:16:24.7682567+00:00 | 2026-10-02T14:16:24.7682567+08:00 | #84054 - EII: 130hrs - CONVEYOR: EII 13E | 2.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 13E - IAM | Outage date change to align with SL1E - IAM. |  | [{"equipmentGUID": "7effe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV13E", "name": "Conveyor: EII 13E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83967 | 2026-09-22T07:33:51.8673052+00:00 | 2026-09-22T15:33:51.8673052+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-22T00:54:29.2540012+00:00 | 2026-10-22T08:54:29.2540012+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336280 | TRUE | TRUE | 2026-10-22T00:54:29.2540012+00:00 | 2026-10-22T08:54:29.2540012+08:00 | #83967 - EII: 12hrs - CAPD SL1E - STANDALONE OUTAGE | 2.0 | TRUE |  | 2027-01-21T11:00:00+00:00 | 2027-01-21T23:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-22T07:00:00+08:00 |  |  |  |  | 12.00 | CAPD SL1E - Standalone Outage | CAPD SL1E - Standalone Outage / To be completed in the footprint of the SL1E WK3 outage. |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83469 | 2026-07-08T02:18:26.0333969+00:00 | 2026-07-08T10:18:26.0333969+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-22T03:34:42.501577+00:00 | 2026-10-22T11:34:42.501577+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 336291 | TRUE | TRUE | 2026-10-22T03:34:42.501577+00:00 | 2026-10-22T11:34:42.501577+08:00 | #83469 - EII: 203hrs - 10E/13E TRANSFER CHUTE REPLACEMENT | 3.0 | TRUE |  | 2027-07-22T11:00:00+00:00 | 2027-07-30T22:00:00+00:00 | 2027-07-22T19:00:00+08:00 | 2027-07-31T06:00:00+08:00 |  |  |  |  | 203.00 | 13E Chute Projects Works. | 10E & 13E Chute Project Works Outage increased to 203HR requested by the Dampier Major Works Planning Team. |  | [{"equipmentGUID": "7effe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV13E", "name": "Conveyor: EII 13E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84058 | 2026-09-30T07:21:20.5686274+00:00 | 2026-09-30T15:21:20.5686274+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-05T01:14:16.2224886+00:00 | 2026-10-05T09:14:16.2224886+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335225 | TRUE | TRUE | 2026-10-05T01:14:16.2224886+00:00 | 2026-10-05T09:14:16.2224886+08:00 | #84058 - EII: 130hrs - CONVEYOR: EII 19E | 1.0 | FALSE |  | 2027-01-21T11:00:00+00:00 | 2027-01-26T21:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T05:00:00+08:00 |  |  |  |  | 130.00 | Conveyor: EII 19E - IAM |  |  | [{"equipmentGUID": "d75ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV19E", "name": "Conveyor: EII 19E ", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83497 | 2026-07-10T00:45:52.6315706+00:00 | 2026-07-10T08:45:52.6315706+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-05T06:04:49.8909344+00:00 | 2026-10-05T14:04:49.8909344+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335255 | TRUE | TRUE | 2026-10-05T06:04:49.8909344+00:00 | 2026-10-05T14:04:49.8909344+08:00 | #83497 - EII: 120hrs - EIIRC1E - RMP | 2.0 | FALSE |  | 2027-05-18T23:00:00+00:00 | 2027-05-23T23:00:00+00:00 | 2027-05-19T07:00:00+08:00 | 2027-05-24T07:00:00+08:00 |  |  |  |  | 120.00 | RMP Project Works. | Aligning to new IAM standard 'Feed off' time |  | [{"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84071 | 2026-10-01T01:38:56.8422016+00:00 | 2026-10-01T09:38:56.8422016+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T05:12:52.71005+00:00 | 2026-10-02T13:12:52.71005+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334984 | TRUE | TRUE | 2026-10-02T05:12:52.71005+00:00 | 2026-10-02T13:12:52.71005+08:00 | #84071 - EII: 156hrs - CONVEYOR: EII 32E | 1.0 | FALSE |  | 2027-02-21T23:00:00+00:00 | 2027-02-28T11:00:00+00:00 | 2027-02-22T07:00:00+08:00 | 2027-02-28T19:00:00+08:00 |  |  |  |  | 156.00 | EII Stockyard Isolator Project |  |  | [{"equipmentGUID": "16d200c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV32E", "name": "Conveyor: EII 32E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b9ec4e2a-3784-4d87-9441-b26e047c5279", "emailAddress": "Chris.Burg@riotinto.com", "displayName": "Burg, Christopher (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83864 | 2026-08-31T01:54:25.7939795+00:00 | 2026-08-31T09:54:25.7939795+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T05:16:37.7338076+00:00 | 2026-10-02T13:16:37.7338076+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334987 | TRUE | TRUE | 2026-10-02T05:16:37.7338076+00:00 | 2026-10-02T13:16:37.7338076+08:00 | #83864 - EII: 72hrs - CONVEYOR: EII 7E | 1.0 | FALSE |  | 2027-03-12T11:00:00+00:00 | 2027-03-15T11:00:00+00:00 | 2027-03-12T19:00:00+08:00 | 2027-03-15T19:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 7E - Outage. |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83961 | 2026-09-22T06:27:56.2299093+00:00 | 2026-09-22T14:27:56.2299093+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T05:18:16.5284331+00:00 | 2026-10-02T13:18:16.5284331+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334988 | TRUE | TRUE | 2026-10-02T05:18:16.5284331+00:00 | 2026-10-02T13:18:16.5284331+08:00 | #83961 - EII: 36hrs - FUNCTIONAL SAFETY TP10EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-03-16T23:00:00+00:00 | 2027-03-18T11:00:00+00:00 | 2027-03-17T07:00:00+08:00 | 2027-03-18T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP10EN - Standalone Outage |  |  | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "5fa801e8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP10E", "name": "Tripper: EII 10E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
84053 | 2026-09-30T06:55:54.8337209+00:00 | 2026-09-30T14:55:54.8337209+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T05:18:16.8870466+00:00 | 2026-10-02T13:18:16.8870466+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334990 | TRUE | TRUE | 2026-10-02T05:18:16.8870466+00:00 | 2026-10-02T13:18:16.8870466+08:00 | #84053 - EII: 72hrs - CONVEYOR: EII 10E | 1.0 | FALSE |  | 2027-03-18T11:00:00+00:00 | 2027-03-21T11:00:00+00:00 | 2027-03-18T19:00:00+08:00 | 2027-03-21T19:00:00+08:00 |  |  |  |  | 72.00 | Conveyor: EII 10E - IAM |  |  | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad561fd7-221c-46d7-82b0-9513ad5cfbc7", "emailAddress": "Paul.Munro@riotinto.com", "displayName": "Munro, Paul (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83957 | 2026-09-22T06:13:51.8548194+00:00 | 2026-09-22T14:13:51.8548194+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-08T00:10:54.1254572+00:00 | 2026-10-08T08:10:54.1254572+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335454 | TRUE | TRUE | 2026-10-08T00:10:54.1254572+00:00 | 2026-10-08T08:10:54.1254572+08:00 | #83957 - EII: 36hrs - FUNCTIONAL SAFETY TP11EN - STANDALONE OUTAGE | 2.0 | FALSE |  | 2027-12-16T23:00:00+00:00 | 2027-12-18T11:00:00+00:00 | 2027-12-17T07:00:00+08:00 | 2027-12-18T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP11EN - Standalone Outage | Outage duration change - 36HR |  | [{"equipmentGUID": "4375fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV11E", "name": "Conveyor: EII 11E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "055bd3e7-4a8c-ee11-a847-000d3acacefd", "code": "EIITP11E", "name": "Tripper: EII 11E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83964 | 2026-09-22T07:05:46.4772327+00:00 | 2026-09-22T15:05:46.4772327+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T07:29:24.2317256+00:00 | 2026-10-07T15:29:24.2317256+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335437 | TRUE | TRUE | 2026-10-07T07:29:24.2317256+00:00 | 2026-10-07T15:29:24.2317256+08:00 | #83964 - EII: 36hrs - FUNCTIONAL SAFETY TP7EN - STANDALONE OUTAGE | 2.0 | FALSE |  | 2027-08-01T23:00:00+00:00 | 2027-08-03T11:00:00+00:00 | 2027-08-02T07:00:00+08:00 | 2027-08-03T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP7EN - Standalone Outage | Duration change to 36HR |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "609e1ce8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP7E", "name": "Tripper: EII 7E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
83474 | 2026-07-08T03:36:16.6391981+00:00 | 2026-07-08T11:36:16.6391981+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-08-11T07:16:48.0501145+00:00 | 2026-08-11T15:16:48.0501145+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 331067 | TRUE | TRUE | 2026-08-11T07:16:48.0501145+00:00 | 2026-08-11T15:16:48.0501145+08:00 | #83474 - EII: 299hrs - CONVEYOR: EII 12E | 1.0 | FALSE |  | 2027-03-28T23:00:00+00:00 | 2027-04-10T10:00:00+00:00 | 2027-03-29T07:00:00+08:00 | 2027-04-10T18:00:00+08:00 |  |  |  |  | 299.00 | 12E Drive Platform Project Works. |  |  | [{"equipmentGUID": "d627f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV12E", "name": "Conveyor: EII 12E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
81640 | 2026-03-11T05:19:06.273414+00:00 | 2026-03-11T13:19:06.273414+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-01T23:50:29.149968+00:00 | 2026-10-02T07:50:29.149968+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 334942 | TRUE | TRUE | 2026-10-01T23:50:29.149968+00:00 | 2026-10-02T07:50:29.149968+08:00 | #81640 - EII: 130hrs - SL1E CORROSION CONTROL | 2.0 | TRUE |  | 2027-07-28T11:00:00+00:00 | 2027-08-02T21:00:00+00:00 | 2027-07-28T19:00:00+08:00 | 2027-08-03T05:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
76476 | 2026-02-26T00:48:54.3781893+00:00 | 2026-02-26T08:48:54.3781893+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-07T06:34:25.3679869+00:00 | 2026-10-07T14:34:25.3679869+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | {"name": "Fixed Plant"} | 335419 | TRUE | TRUE | 2026-10-07T06:34:25.3679869+00:00 | 2026-10-07T14:34:25.3679869+08:00 | #76476 - EII: 130hrs - SL1E CORROSION CONTROL | 2.0 | TRUE |  | 2027-04-27T21:00:00+00:00 | 2027-05-03T07:00:00+00:00 | 2027-04-28T05:00:00+08:00 | 2027-05-03T15:00:00+08:00 |  |  |  |  | 130.00 | RMP Corrosion Control | RMP Corrosion Control Outage Time Updated - To Align with SL1E IAM Outage. |  | [{"equipmentGUID": "3c27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISLD1E", "name": "Shiploader: EII 1E", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | df667c75-45d9-4943-a1a3-282393b957c2 | Drewett, Troy (RTIO) | Scheduled | EII | Australia/Perth
69215 | 2025-10-07T05:39:58.0660728+00:00 | 2025-10-07T13:39:58.0660728+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-29T07:07:02.3928804+00:00 | 2026-09-29T15:07:02.3928804+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334270 | TRUE | TRUE | 2026-09-29T07:07:02.3928804+00:00 | 2026-09-29T15:07:02.3928804+08:00 | #69215 - GDI: 133hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-02-04T23:00:00+00:00 | 2027-02-10T12:00:00+00:00 | 2027-02-05T07:00:00+08:00 | 2027-02-10T20:00:00+08:00 |  |  |  |  | 133.00 | Major Lab Shut PM for: CV01, Dust Extraction System Works, Pit Cell, Production Cell, Archive Cell, Vial Conveyors | Updated timing |  | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
69216 | 2025-10-07T05:39:58.1769878+00:00 | 2025-10-07T13:39:58.1769878+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-29T07:07:02.3930837+00:00 | 2026-09-29T15:07:02.3930837+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334271 | TRUE | TRUE | 2026-09-29T07:07:02.3930837+00:00 | 2026-09-29T15:07:02.3930837+08:00 | #69216 - GDI: 133hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-05-06T23:00:00+00:00 | 2027-05-12T12:00:00+00:00 | 2027-05-07T07:00:00+08:00 | 2027-05-12T20:00:00+08:00 |  |  |  |  | 133.00 | Major Lab Shut PM for: CV01, Dust Extraction System Works, Pit Cell, Production Cell, Archive Cell, Vial Conveyors | Updated timing |  | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
69217 | 2025-10-07T05:39:58.274127+00:00 | 2025-10-07T13:39:58.274127+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-29T07:07:02.3931495+00:00 | 2026-09-29T15:07:02.3931495+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334272 | TRUE | TRUE | 2026-09-29T07:07:02.3931495+00:00 | 2026-09-29T15:07:02.3931495+08:00 | #69217 - GDI: 133hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-08-05T23:00:00+00:00 | 2027-08-11T12:00:00+00:00 | 2027-08-06T07:00:00+08:00 | 2027-08-11T20:00:00+08:00 |  |  |  |  | 133.00 | Major Lab Shut PM for: CV01, Dust Extraction System Works, Pit Cell, Production Cell, Archive Cell, Vial Conveyors | Updated timing |  | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
69218 | 2025-10-07T05:39:58.3705031+00:00 | 2025-10-07T13:39:58.3705031+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-29T07:07:02.3931557+00:00 | 2026-09-29T15:07:02.3931557+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334273 | TRUE | TRUE | 2026-09-29T07:07:02.3931557+00:00 | 2026-09-29T15:07:02.3931557+08:00 | #69218 - GDI: 133hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-11-04T23:00:00+00:00 | 2027-11-10T12:00:00+00:00 | 2027-11-05T07:00:00+08:00 | 2027-11-10T20:00:00+08:00 |  |  |  |  | 133.00 | Major Lab Shut PM for: CV01, Dust Extraction System Works, Pit Cell, Production Cell, Archive Cell, Vial Conveyors | Updated timing |  | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67247 | 2025-05-06T05:54:17.7877361+00:00 | 2025-05-06T13:54:17.7877361+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-25T04:15:41.7051848+00:00 | 2026-09-25T12:15:41.7051848+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334122 | TRUE | TRUE | 2026-09-25T04:15:41.7051848+00:00 | 2026-09-25T12:15:41.7051848+08:00 | #67247 - GDI: 48hrs - VIBRATING FEEDER: GDI 0305 | 4.0 | FALSE |  | 2027-01-12T22:00:00+00:00 | 2027-01-14T22:00:00+00:00 | 2027-01-13T06:00:00+08:00 | 2027-01-15T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0305 | To algin with mod shut |  | [{"equipmentGUID": "b70af0bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0305", "name": "Vibrating Feeder: GDI 0305", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67301 | 2025-05-09T03:05:52.4223476+00:00 | 2025-05-09T11:05:52.4223476+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-23T03:52:47.7030741+00:00 | 2026-09-23T11:52:47.7030741+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 333942 | TRUE | TRUE | 2026-09-23T03:52:47.7030741+00:00 | 2026-09-23T11:52:47.7030741+08:00 | #67301 - GDI: 134hrs - SCREEN: GDI 03 MODULE 02 | 3.0 | FALSE |  | 2028-01-11T23:00:00+00:00 | 2028-01-17T13:00:00+00:00 | 2028-01-12T07:00:00+08:00 | 2028-01-17T21:00:00+08:00 |  |  |  |  | 134.00 | MOD2 - Screens 5-7 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates |  | [{"equipmentGUID": "7617ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD02", "name": "Screen: GDI 03 Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
71490 | 2025-10-27T03:49:52.9022913+00:00 | 2025-10-27T11:49:52.9022913+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-23T03:52:47.7030863+00:00 | 2026-09-23T11:52:47.7030863+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 333943 | TRUE | TRUE | 2026-09-23T03:52:47.7030863+00:00 | 2026-09-23T11:52:47.7030863+08:00 | #71490 - GDI: 60hrs - SCREEN: GDI 0306 VIBRATING | 6.0 | FALSE |  | 2028-01-14T16:00:00+00:00 | 2028-01-17T04:00:00+00:00 | 2028-01-15T00:00:00+08:00 | 2028-01-17T12:00:00+08:00 |  |  |  |  | 60.00 | C/O SC0306 Screen | Align with Plant down time start dates |  | [{"equipmentGUID": "90d500c0-7c7b-ee11-a846-000d3acacefd", "code": "GDISC0306", "name": "Screen: GDI 0306 Vibrating", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67300 | 2025-05-09T03:04:59.1485505+00:00 | 2025-05-09T11:04:59.1485505+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:10:45.5983103+00:00 | 2026-09-30T16:10:45.5983103+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334737 | TRUE | TRUE | 2026-09-30T08:10:45.5983103+00:00 | 2026-09-30T16:10:45.5983103+08:00 | #67300 - GDI: 134hrs - SCREEN: GDI 03 MODULE 02 | 4.0 | FALSE |  | 2027-10-12T23:00:00+00:00 | 2027-10-18T13:00:00+00:00 | 2027-10-13T07:00:00+08:00 | 2027-10-18T21:00:00+08:00 |  |  |  |  | 134.00 | MOD2 - Screens 5-7 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2740 | [{"equipmentGUID": "7617ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD02", "name": "Screen: GDI 03 Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67299 | 2025-05-09T03:04:12.4011358+00:00 | 2025-05-09T11:04:12.4011358+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:39.4160481+00:00 | 2026-09-30T16:06:39.4160481+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334722 | TRUE | TRUE | 2026-09-30T08:06:39.4160481+00:00 | 2026-09-30T16:06:39.4160481+08:00 | #67299 - GDI: 134hrs - SCREEN: GDI 03 MODULE 02 | 4.0 | FALSE |  | 2027-07-13T23:00:00+00:00 | 2027-07-19T13:00:00+00:00 | 2027-07-14T07:00:00+08:00 | 2027-07-19T21:00:00+08:00 |  |  |  |  | 134.00 | MOD2 - Screens 5-7 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2727 | [{"equipmentGUID": "7617ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD02", "name": "Screen: GDI 03 Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67298 | 2025-05-09T03:03:16.9046142+00:00 | 2025-05-09T11:03:16.9046142+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:39.6090227+00:00 | 2026-09-30T16:06:39.6090227+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334723 | TRUE | TRUE | 2026-09-30T08:06:39.6090227+00:00 | 2026-09-30T16:06:39.6090227+08:00 | #67298 - GDI: 134hrs - SCREEN: GDI 03 MODULE 02 | 4.0 | FALSE |  | 2027-04-13T23:00:00+00:00 | 2027-04-19T13:00:00+00:00 | 2027-04-14T07:00:00+08:00 | 2027-04-19T21:00:00+08:00 |  |  |  |  | 134.00 | MOD2 - Screens 5-7 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2714 | [{"equipmentGUID": "7617ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD02", "name": "Screen: GDI 03 Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67305 | 2025-05-09T03:11:53.764297+00:00 | 2025-05-09T11:11:53.764297+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:39.8007934+00:00 | 2026-09-30T16:06:39.8007934+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334724 | TRUE | TRUE | 2026-09-30T08:06:39.8007934+00:00 | 2026-09-30T16:06:39.8007934+08:00 | #67305 - GDI: 170hrs - SCREEN: GDI 03 MODULE 01 | 6.0 | FALSE |  | 2027-03-01T23:00:00+00:00 | 2027-03-09T01:00:00+00:00 | 2027-03-02T07:00:00+08:00 | 2027-03-09T09:00:00+08:00 |  |  |  |  | 170.00 | MOD1 - Screens 1-4 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2708 | [{"equipmentGUID": "7817ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD01", "name": "Screen: GDI 03 Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67306 | 2025-05-09T03:12:40.7264499+00:00 | 2025-05-09T11:12:40.7264499+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:39.9797879+00:00 | 2026-09-30T16:06:39.9797879+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334725 | TRUE | TRUE | 2026-09-30T08:06:39.9797879+00:00 | 2026-09-30T16:06:39.9797879+08:00 | #67306 - GDI: 170hrs - SCREEN: GDI 03 MODULE 01 | 6.0 | FALSE |  | 2027-05-31T23:00:00+00:00 | 2027-06-08T01:00:00+00:00 | 2027-06-01T07:00:00+08:00 | 2027-06-08T09:00:00+08:00 |  |  |  |  | 170.00 | MOD1 - Screens 1-4 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2721 | [{"equipmentGUID": "7817ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD01", "name": "Screen: GDI 03 Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67307 | 2025-05-09T03:13:24.8219347+00:00 | 2025-05-09T11:13:24.8219347+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:40.1727154+00:00 | 2026-09-30T16:06:40.1727154+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334726 | TRUE | TRUE | 2026-09-30T08:06:40.1727154+00:00 | 2026-09-30T16:06:40.1727154+08:00 | #67307 - GDI: 170hrs - SCREEN: GDI 03 MODULE 01 | 7.0 | FALSE |  | 2027-08-30T23:00:00+00:00 | 2027-09-07T01:00:00+00:00 | 2027-08-31T07:00:00+08:00 | 2027-09-07T09:00:00+08:00 |  |  |  |  | 170.00 | MOD1 - Screens 1-4 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2734 | [{"equipmentGUID": "7817ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD01", "name": "Screen: GDI 03 Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67308 | 2025-05-09T03:14:02.4734644+00:00 | 2025-05-09T11:14:02.4734644+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:40.3687786+00:00 | 2026-09-30T16:06:40.3687786+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334727 | TRUE | TRUE | 2026-09-30T08:06:40.3687786+00:00 | 2026-09-30T16:06:40.3687786+08:00 | #67308 - GDI: 170hrs - SCREEN: GDI 03 MODULE 01 | 6.0 | FALSE |  | 2027-11-29T23:00:00+00:00 | 2027-12-07T01:00:00+00:00 | 2027-11-30T07:00:00+08:00 | 2027-12-07T09:00:00+08:00 |  |  |  |  | 170.00 | MOD1 - Screens 1-4 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Align with Plant down time start dates | SGDM2747 | [{"equipmentGUID": "7817ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD01", "name": "Screen: GDI 03 Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
71488 | 2025-10-27T03:49:52.4834133+00:00 | 2025-10-27T11:49:52.4834133+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:37.8610986+00:00 | 2026-09-30T16:06:37.8610986+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334713 | TRUE | TRUE | 2026-09-30T08:06:37.8610986+00:00 | 2026-09-30T16:06:37.8610986+08:00 | #71488 - GDI: 60hrs - SCREEN: GDI 0304 VIBRATING | 4.0 | FALSE |  | 2027-03-05T16:00:00+00:00 | 2027-03-08T04:00:00+00:00 | 2027-03-06T00:00:00+08:00 | 2027-03-08T12:00:00+08:00 |  |  |  |  | 60.00 | C/O SC0304 Screen | Align with Plant down time start dates |  | [{"equipmentGUID": "a023f0bf-7c7b-ee11-a846-000d3acacefd", "code": "GDISC0304", "name": "Screen: GDI 0304 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
71487 | 2025-10-27T03:49:52.279533+00:00 | 2025-10-27T11:49:52.279533+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:38.0237199+00:00 | 2026-09-30T16:06:38.0237199+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334714 | TRUE | TRUE | 2026-09-30T08:06:38.0237199+00:00 | 2026-09-30T16:06:38.0237199+08:00 | #71487 - GDI: 60hrs - SCREEN: GDI 0305 VIBRATING | 4.0 | FALSE |  | 2027-04-16T16:00:00+00:00 | 2027-04-19T04:00:00+00:00 | 2027-04-17T00:00:00+08:00 | 2027-04-19T12:00:00+08:00 |  |  |  |  | 60.00 | C/O SC0305 Screen | Align with Plant down time start dates |  | [{"equipmentGUID": "062ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDISC0305", "name": "Screen: GDI 0305 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
71489 | 2025-10-27T03:49:52.6864863+00:00 | 2025-10-27T11:49:52.6864863+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-30T08:06:38.188318+00:00 | 2026-09-30T16:06:38.188318+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334715 | TRUE | TRUE | 2026-09-30T08:06:38.188318+00:00 | 2026-09-30T16:06:38.188318+08:00 | #71489 - GDI: 60hrs - SCREEN: GDI 0302 VIBRATING | 6.0 | FALSE |  | 2027-12-03T16:00:00+00:00 | 2027-12-06T04:00:00+00:00 | 2027-12-04T00:00:00+08:00 | 2027-12-06T12:00:00+08:00 |  |  |  |  | 60.00 | C/O SC0302 Screen | Align with Plant down time start dates |  | [{"equipmentGUID": "e7d200c0-7c7b-ee11-a846-000d3acacefd", "code": "GDISC0302", "name": "Screen: GDI 0302 Vibrating", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73460 | 2025-11-25T03:31:10.2905049+00:00 | 2025-11-25T11:31:10.2905049+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1692381+00:00 | 2026-09-02T07:47:16.1692381+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332714 | TRUE | TRUE | 2026-09-01T23:47:16.1692381+00:00 | 2026-09-02T07:47:16.1692381+08:00 | #73460 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-12-10T02:00:00+00:00 | 2027-12-10T04:00:00+00:00 | 2027-12-10T10:00:00+08:00 | 2027-12-10T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73461 | 2025-11-25T03:31:10.502876+00:00 | 2025-11-25T11:31:10.502876+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1692448+00:00 | 2026-09-02T07:47:16.1692448+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332715 | TRUE | TRUE | 2026-09-01T23:47:16.1692448+00:00 | 2026-09-02T07:47:16.1692448+08:00 | #73461 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2028-01-07T02:00:00+00:00 | 2028-01-07T04:00:00+00:00 | 2028-01-07T10:00:00+08:00 | 2028-01-07T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67248 | 2025-05-06T05:55:04.7955021+00:00 | 2025-05-06T13:55:04.7955021+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.308722+00:00 | 2026-09-02T08:08:28.308722+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332887 | TRUE | TRUE | 2026-09-02T00:08:28.308722+00:00 | 2026-09-02T08:08:28.308722+08:00 | #67248 - GDI: 48hrs - VIBRATING FEEDER: GDI 0307 | 4.1 | FALSE |  | 2027-02-14T22:00:00+00:00 | 2027-02-16T22:00:00+00:00 | 2027-02-15T06:00:00+08:00 | 2027-02-17T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0307 |  |  | [{"equipmentGUID": "bb19f0bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0307", "name": "Vibrating Feeder: GDI 0307", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67249 | 2025-05-06T05:55:54.4809068+00:00 | 2025-05-06T13:55:54.4809068+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.3087404+00:00 | 2026-09-02T08:08:28.3087404+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332889 | TRUE | TRUE | 2026-09-02T00:08:28.3087404+00:00 | 2026-09-02T08:08:28.3087404+08:00 | #67249 - GDI: 48hrs - VIBRATING FEEDER: GDI 0301 | 3.1 | FALSE |  | 2027-04-18T22:00:00+00:00 | 2027-04-20T22:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-21T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0301 |  |  | [{"equipmentGUID": "0a61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0301", "name": "Vibrating Feeder: GDI 0301", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67250 | 2025-05-06T05:58:34.7503829+00:00 | 2025-05-06T13:58:34.7503829+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.308749+00:00 | 2026-09-02T08:08:28.308749+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332891 | TRUE | TRUE | 2026-09-02T00:08:28.308749+00:00 | 2026-09-02T08:08:28.308749+08:00 | #67250 - GDI: 48hrs - VIBRATING FEEDER: GDI 0304 | 4.1 | FALSE |  | 2027-06-13T22:00:00+00:00 | 2027-06-15T22:00:00+00:00 | 2027-06-14T06:00:00+08:00 | 2027-06-16T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0304 |  |  | [{"equipmentGUID": "8d5cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0304", "name": "Vibrating Feeder: GDI 0304", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67252 | 2025-05-06T05:59:54.902826+00:00 | 2025-05-06T13:59:54.902826+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.3087527+00:00 | 2026-09-02T08:08:28.3087527+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332892 | TRUE | TRUE | 2026-09-02T00:08:28.3087527+00:00 | 2026-09-02T08:08:28.3087527+08:00 | #67252 - GDI: 48hrs - VIBRATING FEEDER: GDI 0303 | 4.1 | FALSE |  | 2027-09-12T22:00:00+00:00 | 2027-09-14T22:00:00+00:00 | 2027-09-13T06:00:00+08:00 | 2027-09-15T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0303 |  |  | [{"equipmentGUID": "9522f0bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0303", "name": "Vibrating Feeder: GDI 0303", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67251 | 2025-05-06T05:59:19.6827124+00:00 | 2025-05-06T13:59:19.6827124+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.3087565+00:00 | 2026-09-02T08:08:28.3087565+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332893 | TRUE | TRUE | 2026-09-02T00:08:28.3087565+00:00 | 2026-09-02T08:08:28.3087565+08:00 | #67251 - GDI: 48hrs - VIBRATING FEEDER: GDI 0302 | 4.1 | FALSE |  | 2027-10-24T22:00:00+00:00 | 2027-10-26T22:00:00+00:00 | 2027-10-25T06:00:00+08:00 | 2027-10-27T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0302 |  |  | [{"equipmentGUID": "0dd300c0-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0302", "name": "Vibrating Feeder: GDI 0302", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
67253 | 2025-05-06T06:02:09.4505995+00:00 | 2025-05-06T14:02:09.4505995+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-02T00:08:28.3087772+00:00 | 2026-09-02T08:08:28.3087772+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332896 | TRUE | TRUE | 2026-09-02T00:08:28.3087772+00:00 | 2026-09-02T08:08:28.3087772+08:00 | #67253 - GDI: 48hrs - VIBRATING FEEDER: GDI 0306 | 3.1 | FALSE |  | 2028-01-23T22:00:00+00:00 | 2028-01-25T22:00:00+00:00 | 2028-01-24T06:00:00+08:00 | 2028-01-26T06:00:00+08:00 |  |  |  |  | 48.00 | C/O Vibration Feeder 65wk VF0306 |  |  | [{"equipmentGUID": "bf2ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIVF0306", "name": "Vibrating Feeder: GDI 0306", "assetClass": {"name": "Vibrating Feeder"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74914 | 2026-01-29T05:08:54.8351784+00:00 | 2026-01-29T13:08:54.8351784+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2276259+00:00 | 2026-09-02T07:45:12.2276259+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332421 | TRUE | TRUE | 2026-09-01T23:45:12.2276259+00:00 | 2026-09-02T07:45:12.2276259+08:00 | #74914 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-01-01T02:00:00+00:00 | 2027-01-01T04:00:00+00:00 | 2027-01-01T10:00:00+08:00 | 2027-01-01T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Site Constraint | GDI | Australia/Perth
74277 | 2025-12-04T03:51:45.6907888+00:00 | 2025-12-04T11:51:45.6907888+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2277749+00:00 | 2026-09-02T07:45:12.2277749+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332422 | TRUE | TRUE | 2026-09-01T23:45:12.2277749+00:00 | 2026-09-02T07:45:12.2277749+08:00 | #74277 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-01-29T02:00:00+00:00 | 2027-01-29T04:00:00+00:00 | 2027-01-29T10:00:00+08:00 | 2027-01-29T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74278 | 2025-12-04T03:51:45.918788+00:00 | 2025-12-04T11:51:45.918788+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278158+00:00 | 2026-09-02T07:45:12.2278158+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332424 | TRUE | TRUE | 2026-09-01T23:45:12.2278158+00:00 | 2026-09-02T07:45:12.2278158+08:00 | #74278 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-02-26T02:00:00+00:00 | 2027-02-26T04:00:00+00:00 | 2027-02-26T10:00:00+08:00 | 2027-02-26T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74279 | 2025-12-04T03:51:46.1444892+00:00 | 2025-12-04T11:51:46.1444892+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278226+00:00 | 2026-09-02T07:45:12.2278226+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332425 | TRUE | TRUE | 2026-09-01T23:45:12.2278226+00:00 | 2026-09-02T07:45:12.2278226+08:00 | #74279 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-03-26T02:00:00+00:00 | 2027-03-26T04:00:00+00:00 | 2027-03-26T10:00:00+08:00 | 2027-03-26T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74280 | 2025-12-04T03:51:46.37066+00:00 | 2025-12-04T11:51:46.37066+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278291+00:00 | 2026-09-02T07:45:12.2278291+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332426 | TRUE | TRUE | 2026-09-01T23:45:12.2278291+00:00 | 2026-09-02T07:45:12.2278291+08:00 | #74280 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-04-23T02:00:00+00:00 | 2027-04-23T04:00:00+00:00 | 2027-04-23T10:00:00+08:00 | 2027-04-23T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74281 | 2025-12-04T03:51:46.6141791+00:00 | 2025-12-04T11:51:46.6141791+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278451+00:00 | 2026-09-02T07:45:12.2278451+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332428 | TRUE | TRUE | 2026-09-01T23:45:12.2278451+00:00 | 2026-09-02T07:45:12.2278451+08:00 | #74281 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-05-21T02:00:00+00:00 | 2027-05-21T04:00:00+00:00 | 2027-05-21T10:00:00+08:00 | 2027-05-21T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74282 | 2025-12-04T03:51:46.8473823+00:00 | 2025-12-04T11:51:46.8473823+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278537+00:00 | 2026-09-02T07:45:12.2278537+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332429 | TRUE | TRUE | 2026-09-01T23:45:12.2278537+00:00 | 2026-09-02T07:45:12.2278537+08:00 | #74282 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-06-18T02:00:00+00:00 | 2027-06-18T04:00:00+00:00 | 2027-06-18T10:00:00+08:00 | 2027-06-18T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74283 | 2025-12-04T03:51:47.0901888+00:00 | 2025-12-04T11:51:47.0901888+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278608+00:00 | 2026-09-02T07:45:12.2278608+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332430 | TRUE | TRUE | 2026-09-01T23:45:12.2278608+00:00 | 2026-09-02T07:45:12.2278608+08:00 | #74283 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-07-16T02:00:00+00:00 | 2027-07-16T04:00:00+00:00 | 2027-07-16T10:00:00+08:00 | 2027-07-16T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74284 | 2025-12-04T03:51:47.3276244+00:00 | 2025-12-04T11:51:47.3276244+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278748+00:00 | 2026-09-02T07:45:12.2278748+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332432 | TRUE | TRUE | 2026-09-01T23:45:12.2278748+00:00 | 2026-09-02T07:45:12.2278748+08:00 | #74284 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-08-13T02:00:00+00:00 | 2027-08-13T04:00:00+00:00 | 2027-08-13T10:00:00+08:00 | 2027-08-13T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74285 | 2025-12-04T03:51:47.567538+00:00 | 2025-12-04T11:51:47.567538+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278847+00:00 | 2026-09-02T07:45:12.2278847+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332433 | TRUE | TRUE | 2026-09-01T23:45:12.2278847+00:00 | 2026-09-02T07:45:12.2278847+08:00 | #74285 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-09-10T02:00:00+00:00 | 2027-09-10T04:00:00+00:00 | 2027-09-10T10:00:00+08:00 | 2027-09-10T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74286 | 2025-12-04T03:51:47.8193538+00:00 | 2025-12-04T11:51:47.8193538+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278911+00:00 | 2026-09-02T07:45:12.2278911+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332434 | TRUE | TRUE | 2026-09-01T23:45:12.2278911+00:00 | 2026-09-02T07:45:12.2278911+08:00 | #74286 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-10-08T02:00:00+00:00 | 2027-10-08T04:00:00+00:00 | 2027-10-08T10:00:00+08:00 | 2027-10-08T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74287 | 2025-12-04T03:51:48.0773769+00:00 | 2025-12-04T11:51:48.0773769+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2278982+00:00 | 2026-09-02T07:45:12.2278982+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332435 | TRUE | TRUE | 2026-09-01T23:45:12.2278982+00:00 | 2026-09-02T07:45:12.2278982+08:00 | #74287 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-11-05T02:00:00+00:00 | 2027-11-05T04:00:00+00:00 | 2027-11-05T10:00:00+08:00 | 2027-11-05T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74288 | 2025-12-04T03:51:48.3333227+00:00 | 2025-12-04T11:51:48.3333227+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2279125+00:00 | 2026-09-02T07:45:12.2279125+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332437 | TRUE | TRUE | 2026-09-01T23:45:12.2279125+00:00 | 2026-09-02T07:45:12.2279125+08:00 | #74288 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-12-03T02:00:00+00:00 | 2027-12-03T04:00:00+00:00 | 2027-12-03T10:00:00+08:00 | 2027-12-03T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74289 | 2025-12-04T03:51:48.585571+00:00 | 2025-12-04T11:51:48.585571+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.2279217+00:00 | 2026-09-02T07:45:12.2279217+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332438 | TRUE | TRUE | 2026-09-01T23:45:12.2279217+00:00 | 2026-09-02T07:45:12.2279217+08:00 | #74289 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2027-12-31T02:00:00+00:00 | 2027-12-31T04:00:00+00:00 | 2027-12-31T10:00:00+08:00 | 2027-12-31T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74928 | 2026-01-29T05:08:57.6986314+00:00 | 2026-01-29T13:08:57.6986314+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:45:12.227938+00:00 | 2026-09-02T07:45:12.227938+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332440 | TRUE | TRUE | 2026-09-01T23:45:12.227938+00:00 | 2026-09-02T07:45:12.227938+08:00 | #74928 - GDI: 2hrs - TRAIN LOADOUT: GDI | 1.1 | TRUE |  | 2028-01-28T02:00:00+00:00 | 2028-01-28T04:00:00+00:00 | 2028-01-28T10:00:00+08:00 | 2028-01-28T12:00:00+08:00 |  |  |  |  | 2.00 | Replenish Reclaimer Lubrication |  |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Site Constraint | GDI | Australia/Perth
73447 | 2025-11-25T03:31:07.810976+00:00 | 2025-11-25T11:31:07.810976+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691407+00:00 | 2026-09-02T07:47:16.1691407+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332693 | TRUE | TRUE | 2026-09-01T23:47:16.1691407+00:00 | 2026-09-02T07:47:16.1691407+08:00 | #73447 - GDI: 2hrs - PLANT: GDI | 1.1 | TRUE |  | 2026-12-11T02:00:00+00:00 | 2026-12-11T04:00:00+00:00 | 2026-12-11T10:00:00+08:00 | 2026-12-11T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Additional Info: Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73448 | 2025-11-25T03:31:07.9869358+00:00 | 2025-11-25T11:31:07.9869358+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691449+00:00 | 2026-09-02T07:47:16.1691449+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332694 | TRUE | TRUE | 2026-09-01T23:47:16.1691449+00:00 | 2026-09-02T07:47:16.1691449+08:00 | #73448 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-01-08T02:00:00+00:00 | 2027-01-08T04:00:00+00:00 | 2027-01-08T10:00:00+08:00 | 2027-01-08T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73449 | 2025-11-25T03:31:08.1720815+00:00 | 2025-11-25T11:31:08.1720815+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691511+00:00 | 2026-09-02T07:47:16.1691511+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332695 | TRUE | TRUE | 2026-09-01T23:47:16.1691511+00:00 | 2026-09-02T07:47:16.1691511+08:00 | #73449 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-02-05T02:00:00+00:00 | 2027-02-05T04:00:00+00:00 | 2027-02-05T10:00:00+08:00 | 2027-02-05T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73450 | 2025-11-25T03:31:08.3559606+00:00 | 2025-11-25T11:31:08.3559606+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691593+00:00 | 2026-09-02T07:47:16.1691593+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332697 | TRUE | TRUE | 2026-09-01T23:47:16.1691593+00:00 | 2026-09-02T07:47:16.1691593+08:00 | #73450 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-03-05T02:00:00+00:00 | 2027-03-05T04:00:00+00:00 | 2027-03-05T10:00:00+08:00 | 2027-03-05T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73451 | 2025-11-25T03:31:08.5347582+00:00 | 2025-11-25T11:31:08.5347582+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691688+00:00 | 2026-09-02T07:47:16.1691688+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332699 | TRUE | TRUE | 2026-09-01T23:47:16.1691688+00:00 | 2026-09-02T07:47:16.1691688+08:00 | #73451 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-04-02T02:00:00+00:00 | 2027-04-02T04:00:00+00:00 | 2027-04-02T10:00:00+08:00 | 2027-04-02T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73452 | 2025-11-25T03:31:08.7367779+00:00 | 2025-11-25T11:31:08.7367779+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691737+00:00 | 2026-09-02T07:47:16.1691737+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332700 | TRUE | TRUE | 2026-09-01T23:47:16.1691737+00:00 | 2026-09-02T07:47:16.1691737+08:00 | #73452 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-04-30T02:00:00+00:00 | 2027-04-30T04:00:00+00:00 | 2027-04-30T10:00:00+08:00 | 2027-04-30T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73453 | 2025-11-25T03:31:08.9226698+00:00 | 2025-11-25T11:31:08.9226698+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691823+00:00 | 2026-09-02T07:47:16.1691823+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332702 | TRUE | TRUE | 2026-09-01T23:47:16.1691823+00:00 | 2026-09-02T07:47:16.1691823+08:00 | #73453 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-05-28T02:00:00+00:00 | 2027-05-28T04:00:00+00:00 | 2027-05-28T10:00:00+08:00 | 2027-05-28T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73454 | 2025-11-25T03:31:09.1128986+00:00 | 2025-11-25T11:31:09.1128986+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691932+00:00 | 2026-09-02T07:47:16.1691932+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332704 | TRUE | TRUE | 2026-09-01T23:47:16.1691932+00:00 | 2026-09-02T07:47:16.1691932+08:00 | #73454 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-06-25T02:00:00+00:00 | 2027-06-25T04:00:00+00:00 | 2027-06-25T10:00:00+08:00 | 2027-06-25T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73455 | 2025-11-25T03:31:09.3025957+00:00 | 2025-11-25T11:31:09.3025957+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1691975+00:00 | 2026-09-02T07:47:16.1691975+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332705 | TRUE | TRUE | 2026-09-01T23:47:16.1691975+00:00 | 2026-09-02T07:47:16.1691975+08:00 | #73455 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-07-23T02:00:00+00:00 | 2027-07-23T04:00:00+00:00 | 2027-07-23T10:00:00+08:00 | 2027-07-23T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73456 | 2025-11-25T03:31:09.5022233+00:00 | 2025-11-25T11:31:09.5022233+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.169206+00:00 | 2026-09-02T07:47:16.169206+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332707 | TRUE | TRUE | 2026-09-01T23:47:16.169206+00:00 | 2026-09-02T07:47:16.169206+08:00 | #73456 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-08-20T02:00:00+00:00 | 2027-08-20T04:00:00+00:00 | 2027-08-20T10:00:00+08:00 | 2027-08-20T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73457 | 2025-11-25T03:31:09.6944882+00:00 | 2025-11-25T11:31:09.6944882+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1692159+00:00 | 2026-09-02T07:47:16.1692159+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332709 | TRUE | TRUE | 2026-09-01T23:47:16.1692159+00:00 | 2026-09-02T07:47:16.1692159+08:00 | #73457 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-09-17T02:00:00+00:00 | 2027-09-17T04:00:00+00:00 | 2027-09-17T10:00:00+08:00 | 2027-09-17T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73458 | 2025-11-25T03:31:09.8840912+00:00 | 2025-11-25T11:31:09.8840912+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1692202+00:00 | 2026-09-02T07:47:16.1692202+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332710 | TRUE | TRUE | 2026-09-01T23:47:16.1692202+00:00 | 2026-09-02T07:47:16.1692202+08:00 | #73458 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-10-15T02:00:00+00:00 | 2027-10-15T04:00:00+00:00 | 2027-10-15T10:00:00+08:00 | 2027-10-15T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
73459 | 2025-11-25T03:31:10.0867401+00:00 | 2025-11-25T11:31:10.0867401+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | 2026-09-01T23:47:16.1692282+00:00 | 2026-09-02T07:47:16.1692282+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332712 | TRUE | TRUE | 2026-09-01T23:47:16.1692282+00:00 | 2026-09-02T07:47:16.1692282+08:00 | #73459 - GDI: 2hrs - PLANT: GDI | 1.2 | TRUE |  | 2027-11-12T02:00:00+00:00 | 2027-11-12T04:00:00+00:00 | 2027-11-12T10:00:00+08:00 | 2027-11-12T12:00:00+08:00 |  |  |  |  | 2.00 | GDI Plant Key Drivers Replenish Stacker Lubrication |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
49765 | 2022-11-03T02:55:41+00:00 | 2022-11-03T10:55:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-10-06T00:29:08.634109+00:00 | 2026-10-06T08:29:08.634109+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335349 | TRUE | TRUE | 2026-10-06T00:29:08.634109+00:00 | 2026-10-06T08:29:08.634109+08:00 | #49765 - GDI: 96hrs - TRAIN LOADOUT: GDI | 11.0 | TRUE |  | 2027-11-07T23:00:00+00:00 | 2027-11-11T23:00:00+00:00 | 2027-11-08T07:00:00+08:00 | 2027-11-12T07:00:00+08:00 |  |  |  |  | 96.00 | GDI TLO Shut Lower back wall | Align with Plant down time start dates |  | [{"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
49764 | 2022-11-03T02:55:40+00:00 | 2022-11-03T10:55:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-10-06T00:29:08.1702775+00:00 | 2026-10-06T08:29:08.1702775+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335347 | TRUE | TRUE | 2026-10-06T00:29:08.1702775+00:00 | 2026-10-06T08:29:08.1702775+08:00 | #49764 - GDI: 108hrs - TRAIN LOADOUT: GDI | 13.0 | TRUE |  | 2027-08-08T23:00:00+00:00 | 2027-08-13T11:00:00+00:00 | 2027-08-09T07:00:00+08:00 | 2027-08-13T19:00:00+08:00 |  |  |  |  | 108.00 | GDI TLO Shut Bucket teeth half life CV21 Belt C/o | Align with Plant down time start dates |  | [{"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Bucket Wheel Maintenance Major"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
56128 | 2023-06-23T00:18:56+00:00 | 2023-06-23T08:18:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-09-30T08:09:02.8540066+00:00 | 2026-09-30T16:09:02.8540066+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334733 | TRUE | TRUE | 2026-09-30T08:09:02.8540066+00:00 | 2026-09-30T16:09:02.8540066+08:00 | #56128 - GDI: 120hrs - CRUSHER - SECONDARY: GDI 0401 | 6.0 | FALSE |  | 2027-08-27T04:00:00+00:00 | 2027-09-01T04:00:00+00:00 | 2027-08-27T12:00:00+08:00 | 2027-09-01T12:00:00+08:00 |  |  |  |  | 120.00 | GDI CS0401/CS0402 - Bowl and mantle change, inspect eccentric both crusher + rebuild CS0401 bowl to install in CS0402. 24hr for dry+wet commissioning CS0401 + rundown and isolation of CS0402. | Align with Plant down time start dates | SGDM2833 | [{"equipmentGUID": "2062fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDISCS0401", "name": "Crusher - Secondary: GDI 0401", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
56131 | 2023-06-23T00:19:01+00:00 | 2023-06-23T08:19:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-09-30T08:09:03.0064505+00:00 | 2026-09-30T16:09:03.0064505+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334734 | TRUE | TRUE | 2026-09-30T08:09:03.0064505+00:00 | 2026-09-30T16:09:03.0064505+08:00 | #56131 - GDI: 120hrs - CRUSHER - SECONDARY: GDI 0401 | 6.0 | FALSE |  | 2027-12-17T04:00:00+00:00 | 2027-12-22T04:00:00+00:00 | 2027-12-17T12:00:00+08:00 | 2027-12-22T12:00:00+08:00 |  |  |  |  | 120.00 | GDI CS0401/CS0402 - Bowl and mantle change, inspect eccentric both crusher + rebuild CS0401 bowl to install in CS0402. 24hr for dry+wet commissioning CS0401 + rundown and isolation of CS0402. | Align with Plant down time start dates | SGDM2750 | [{"equipmentGUID": "2062fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDISCS0401", "name": "Crusher - Secondary: GDI 0401", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
56125 | 2023-06-23T00:18:51+00:00 | 2023-06-23T08:18:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-09-30T08:09:03.1678232+00:00 | 2026-09-30T16:09:03.1678232+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334735 | TRUE | TRUE | 2026-09-30T08:09:03.1678232+00:00 | 2026-09-30T16:09:03.1678232+08:00 | #56125 - GDI: 168hrs - CRUSHER - SECONDARY: GDI 0401 | 6.0 | FALSE |  | 2027-04-16T04:00:00+00:00 | 2027-04-23T04:00:00+00:00 | 2027-04-16T12:00:00+08:00 | 2027-04-23T12:00:00+08:00 |  |  |  |  | 168.00 | GDI CS0401/CS0402 - Bowl and mantle change, inspect eccentric both crusher + rebuild CS0401 bowl to install in CS0402. Includes mainframe liners and arm guard liners (+24hr / crusher). 24hr for dry+wet commissioning CS0401 + rundown and isolation of CS0402. | Align with Plant down time start dates | SGDM2715 | [{"equipmentGUID": "2062fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDISCS0401", "name": "Crusher - Secondary: GDI 0401", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
56147 | 2023-06-23T00:19:27+00:00 | 2023-06-23T08:19:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-09-25T03:30:51.7650495+00:00 | 2026-09-25T11:30:51.7650495+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 334117 | TRUE | TRUE | 2026-09-25T03:30:51.7650495+00:00 | 2026-09-25T11:30:51.7650495+08:00 | #56147 - GDI: 134hrs - SCREEN: GDI 03 MODULE 02 | 9.0 | FALSE |  | 2027-01-12T23:00:00+00:00 | 2027-01-18T13:00:00+00:00 | 2027-01-13T07:00:00+08:00 | 2027-01-18T21:00:00+08:00 |  |  |  |  | 134.00 | "MOD2 - Screens 5-7 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact" | Improved and adjusted the dates and start times to suit mobilisation and predicted duration | SGDM2701 | [{"equipmentGUID": "7617ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD02", "name": "Screen: GDI 03 Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
56123 | 2023-06-23T00:18:47+00:00 | 2023-06-23T08:18:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-09-20T23:27:42.3223478+00:00 | 2026-09-21T07:27:42.3223478+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 333625 | TRUE | TRUE | 2026-09-20T23:27:42.3223478+00:00 | 2026-09-21T07:27:42.3223478+08:00 | #56123 - GDI: 167hrs - SCREEN: GDI 03 MODULE 01 | 13.0 | FALSE |  | 2026-11-24T23:00:00+00:00 | 2026-12-01T22:00:00+00:00 | 2026-11-25T07:00:00+08:00 | 2026-12-02T06:00:00+08:00 |  |  |  |  | 167.00 | MOD1 - Screens 1-4 top and bottom screen panel replacements, screen and vibe feeder inspections and lube replacements Additional Info: Screens will be run off, isolated and permitted one at a time to eliminate production impact | Changes were made to both the start times and also duration of work to better align with labour mobilisation and efficiency gains from the new platform | SGDM2648 | [{"equipmentGUID": "7817ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDISC03MOD01", "name": "Screen: GDI 03 Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
44109 | 2021-11-19T05:08:31+00:00 | 2021-11-19T13:08:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:08.3947716+00:00 | 2026-10-06T08:29:08.3947716+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335348 | TRUE | TRUE | 2026-10-06T00:29:08.3947716+00:00 | 2026-10-06T08:29:08.3947716+08:00 | #44109 - GDI: 144hrs - PLANT: GDI | 11.0 | TRUE |  | 2027-11-04T23:00:00+00:00 | 2027-11-10T23:00:00+00:00 | 2027-11-05T07:00:00+08:00 | 2027-11-11T07:00:00+08:00 |  |  |  |  | 144.00 | GDI Plant Shut CS0101 C/o OS Mainshaft 52wk CV0101 C/o Belt 78wk | Align with Plant down time start dates and updated with project work |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "8cebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIPCS01", "name": "Crusher - Primary: GDI 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "efdfcad9-301b-46dc-8d2c-9622d129af1b", "emailAddress": "Edward.Moala@riotinto.com", "displayName": "Moala, Edward (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Crusher Overhaul"}] | [{"code": "P-0800159", "name": "SR0902 Pond Switch Room Tie-in - Contingency Shut", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "144"}] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
41149 | 2021-05-14T04:45:26+00:00 | 2021-05-14T12:45:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:06.8945472+00:00 | 2026-10-06T08:29:06.8945472+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335342 | TRUE | TRUE | 2026-10-06T00:29:06.8945472+00:00 | 2026-10-06T08:29:06.8945472+08:00 | #41149 - GDI: 144hrs - PLANT: GDI | 13.0 | TRUE |  | 2027-02-04T23:00:00+00:00 | 2027-02-10T23:00:00+00:00 | 2027-02-05T07:00:00+08:00 | 2027-02-11T07:00:00+08:00 |  |  |  |  | 144.00 | GDI Plant Shut BN0102 works - Ceramic back wall & rails CV0514 C/o Belt 104wk | Align with Plant down time start dates |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
44104 | 2021-11-19T04:39:40+00:00 | 2021-11-19T12:39:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:07.1152974+00:00 | 2026-10-06T08:29:07.1152974+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335343 | TRUE | TRUE | 2026-10-06T00:29:07.1152974+00:00 | 2026-10-06T08:29:07.1152974+08:00 | #44104 - GDI: 132hrs - TRAIN LOADOUT: GDI | 17.0 | TRUE |  | 2027-02-07T23:00:00+00:00 | 2027-02-13T11:00:00+00:00 | 2027-02-08T07:00:00+08:00 | 2027-02-13T19:00:00+08:00 |  |  |  |  | 132.00 | GDI TLO Shut RC0601 Bucket Wheel C/O 52wk CV21 Belt C/o 13wk | Align with Plant down time start dates |  | [{"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Bucket Wheel Changeout"}, {"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
44107 | 2021-11-19T05:07:18+00:00 | 2021-11-19T13:07:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:07.343154+00:00 | 2026-10-06T08:29:07.343154+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335344 | TRUE | TRUE | 2026-10-06T00:29:07.343154+00:00 | 2026-10-06T08:29:07.343154+08:00 | #44107 - GDI: 168hrs - PLANT: GDI | 15.0 | TRUE |  | 2027-05-06T23:00:00+00:00 | 2027-05-13T23:00:00+00:00 | 2027-05-07T07:00:00+08:00 | 2027-05-14T07:00:00+08:00 |  |  |  |  | 168.00 | GDI Plant Shut CS0101 C/o Mainshaft & concave liners 52wks CV0312 C/o Belt 104wk CH0201 & CH0202 C/o Chute and throat side liners 104Wk | Align with Plant down time start dates |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "8cebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIPCS01", "name": "Crusher - Primary: GDI 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Crusher Overhaul"}, {"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
44105 | 2021-11-19T04:40:24+00:00 | 2021-11-19T12:40:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:07.7219868+00:00 | 2026-10-06T08:29:07.7219868+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335345 | TRUE | TRUE | 2026-10-06T00:29:07.7219868+00:00 | 2026-10-06T08:29:07.7219868+08:00 | #44105 - GDI: 144hrs - TRAIN LOADOUT: GDI | 14.0 | TRUE |  | 2027-05-09T23:00:00+00:00 | 2027-05-15T23:00:00+00:00 | 2027-05-10T07:00:00+08:00 | 2027-05-16T07:00:00+08:00 |  |  |  |  | 144.00 | GDI TLO Shut CV622 Belt C/o 260wk RC0601 Luff Cylinder C/o 364Wk | Align with Plant down time start dates |  | [{"equipmentGUID": "27ffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "GDIRC601", "name": "Reclaimer: GDI 601", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4167fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDITLO", "name": "Train Loadout: GDI", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
44108 | 2021-11-19T05:07:53+00:00 | 2021-11-19T13:07:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-06T00:29:07.9432059+00:00 | 2026-10-06T08:29:07.9432059+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 335346 | TRUE | TRUE | 2026-10-06T00:29:07.9432059+00:00 | 2026-10-06T08:29:07.9432059+08:00 | #44108 - GDI: 144hrs - PLANT: GDI | 10.0 | TRUE |  | 2027-08-05T23:00:00+00:00 | 2027-08-11T23:00:00+00:00 | 2027-08-06T07:00:00+08:00 | 2027-08-12T07:00:00+08:00 |  |  |  |  | 144.00 | GDI Plant Shut BN0102 works - Ceramic back wall & rails CV0211 C/o Belt 130wks | Align with Plant down time start dates, update with project outage |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "efdfcad9-301b-46dc-8d2c-9622d129af1b", "emailAddress": "Edward.Moala@riotinto.com", "displayName": "Moala, Edward (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Major Liner Changeout"}] | [{"code": "P-0800159", "name": "SR0902 Pond Switch Room Tie-in - targeted for SGDP2731 shut", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "144"}] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74753 | 2026-01-15T04:20:34.6009708+00:00 | 2026-01-15T12:20:34.6009708+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-09-01T23:47:16.169234+00:00 | 2026-09-02T07:47:16.169234+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332713 | TRUE | TRUE | 2026-09-01T23:47:16.169234+00:00 | 2026-09-02T07:47:16.169234+08:00 | #74753 - GDI: 12hrs - PLANT: GDI | 2.1 | TRUE |  | 2027-11-22T22:00:00+00:00 | 2027-11-23T10:00:00+00:00 | 2027-11-23T06:00:00+08:00 | 2027-11-23T18:00:00+08:00 |  |  |  |  | 12.00 | 12h maintenance shut to complete maintenance activity between major shuts. |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74748 | 2026-01-15T04:16:38.8996809+00:00 | 2026-01-15T12:16:38.8996809+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-09-01T23:47:16.1692101+00:00 | 2026-09-02T07:47:16.1692101+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332708 | TRUE | TRUE | 2026-09-01T23:47:16.1692101+00:00 | 2026-09-02T07:47:16.1692101+08:00 | #74748 - GDI: 12hrs - PLANT: GDI | 2.1 | TRUE |  | 2027-08-30T22:00:00+00:00 | 2027-08-31T10:00:00+00:00 | 2027-08-31T06:00:00+08:00 | 2027-08-31T18:00:00+08:00 |  |  |  |  | 12.00 | 12h maintenance shut to complete maintenance activity between major shuts. |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74743 | 2026-01-15T04:14:35.8087284+00:00 | 2026-01-15T12:14:35.8087284+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-09-01T23:47:16.1691874+00:00 | 2026-09-02T07:47:16.1691874+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332703 | TRUE | TRUE | 2026-09-01T23:47:16.1691874+00:00 | 2026-09-02T07:47:16.1691874+08:00 | #74743 - GDI: 12hrs - PLANT: GDI | 1.1 | TRUE |  | 2027-06-07T22:00:00+00:00 | 2027-06-08T10:00:00+00:00 | 2027-06-08T06:00:00+08:00 | 2027-06-08T18:00:00+08:00 |  |  |  |  | 12.00 | 12h maintenance shut to complete maintenance activity between major shuts. |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
74738 | 2026-01-15T04:10:17.5359819+00:00 | 2026-01-15T12:10:17.5359819+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-09-01T23:47:16.1691631+00:00 | 2026-09-02T07:47:16.1691631+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 332698 | TRUE | TRUE | 2026-09-01T23:47:16.1691631+00:00 | 2026-09-02T07:47:16.1691631+08:00 | #74738 - GDI: 12hrs - PLANT: GDI | 1.1 | TRUE |  | 2027-03-15T22:00:00+00:00 | 2027-03-16T10:00:00+00:00 | 2027-03-16T06:00:00+08:00 | 2027-03-16T18:00:00+08:00 |  |  |  |  | 12.00 | 52wk Functional Safety Testing of SK0501 and SK0502 |  |  | [{"equipmentGUID": "7717ee47-4b9a-ee11-a847-000d3acacefd", "code": "GDIPLT", "name": "Plant: GDI", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "59750e6f-1ee0-472c-a842-c68d2cf093b2", "emailAddress": "Paul.Davies@riotinto.com", "displayName": "Davies, Paul (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
82331 | 2026-04-15T08:41:44.1189805+00:00 | 2026-04-15T16:41:44.1189805+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-10-15T03:36:18.6517337+00:00 | 2026-10-15T11:36:18.6517337+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 336042 | TRUE | TRUE | 2026-10-15T03:36:18.6517337+00:00 | 2026-10-15T11:36:18.6517337+08:00 | #82331 - GDI: 150.5hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-01-13T23:00:00+00:00 | 2027-01-20T05:30:00+00:00 | 2027-01-14T07:00:00+08:00 | 2027-01-20T13:30:00+08:00 |  |  |  |  | 150.50 | Minor Lab Shut - Pit Cell - Analytical Cell - Archive Cell Vendors: ROCKLABS (SCOTTS AUTOMATION) ROCKLABS (SCOTTS AUTOMATION) - source ABB METTLER TOLEDO KARDEX MALVERN PANALYTICAL LECO SMART SOLUTIONS | Reason for reduction is efficiencies in labour and we we’re unsure of how long a Dayshift only minor lab shut would take originally | SGDL | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
82332 | 2026-04-15T08:41:44.2348029+00:00 | 2026-04-15T16:41:44.2348029+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-10-15T03:36:18.6519911+00:00 | 2026-10-15T11:36:18.6519911+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 336043 | TRUE | TRUE | 2026-10-15T03:36:18.6519911+00:00 | 2026-10-15T11:36:18.6519911+08:00 | #82332 - GDI: 150.5hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-04-14T23:00:00+00:00 | 2027-04-21T05:30:00+00:00 | 2027-04-15T07:00:00+08:00 | 2027-04-21T13:30:00+08:00 |  |  |  |  | 150.50 | Minor Lab Shut - Pit Cell - Analytical Cell - Archive Cell Vendors: ROCKLABS (SCOTTS AUTOMATION) ROCKLABS (SCOTTS AUTOMATION) - source ABB METTLER TOLEDO KARDEX MALVERN PANALYTICAL LECO SMART SOLUTIONS | Reason for reduction is efficiencies in labour and we we’re unsure of how long a Dayshift only minor lab shut would take originally | SGDL2715 | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
82333 | 2026-04-15T08:41:44.3548728+00:00 | 2026-04-15T16:41:44.3548728+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-10-15T03:36:18.6520554+00:00 | 2026-10-15T11:36:18.6520554+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 336044 | TRUE | TRUE | 2026-10-15T03:36:18.6520554+00:00 | 2026-10-15T11:36:18.6520554+08:00 | #82333 - GDI: 150.5hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-07-14T23:00:00+00:00 | 2027-07-21T05:30:00+00:00 | 2027-07-15T07:00:00+08:00 | 2027-07-21T13:30:00+08:00 |  |  |  |  | 150.50 | Minor Lab Shut - Pit Cell - Analytical Cell - Archive Cell Vendors: ROCKLABS (SCOTTS AUTOMATION) ROCKLABS (SCOTTS AUTOMATION) - source ABB METTLER TOLEDO KARDEX MALVERN PANALYTICAL LECO SMART SOLUTIONS | Reason for reduction is efficiencies in labour and we we’re unsure of how long a Dayshift only minor lab shut would take originally | SGDL2728 | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
82334 | 2026-04-15T08:41:44.4751796+00:00 | 2026-04-15T16:41:44.4751796+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-10-15T03:36:18.6520621+00:00 | 2026-10-15T11:36:18.6520621+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 336045 | TRUE | TRUE | 2026-10-15T03:36:18.6520621+00:00 | 2026-10-15T11:36:18.6520621+08:00 | #82334 - GDI: 150.5hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2027-10-13T23:00:00+00:00 | 2027-10-20T05:30:00+00:00 | 2027-10-14T07:00:00+08:00 | 2027-10-20T13:30:00+08:00 |  |  |  |  | 150.50 | Minor Lab Shut - Pit Cell - Analytical Cell - Archive Cell Vendors: ROCKLABS (SCOTTS AUTOMATION) ROCKLABS (SCOTTS AUTOMATION) - source ABB METTLER TOLEDO KARDEX MALVERN PANALYTICAL LECO SMART SOLUTIONS | Reason for reduction is efficiencies in labour and we we’re unsure of how long a Dayshift only minor lab shut would take originally | SGDL2741 | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
82335 | 2026-04-15T08:41:44.6121214+00:00 | 2026-04-15T16:41:44.6121214+08:00 | {"principalGUID": "cf002530-5d04-4a0a-be34-f2becb0ded29", "displayName": "Averhaus, Jan (RTIO)"} | 2026-10-15T03:36:18.652067+00:00 | 2026-10-15T11:36:18.652067+08:00 | {"principalGUID": "1aeb6932-afbf-4957-b96a-2a0d54ea1f25", "displayName": "Dodd, Bronwyn (RTIO)"} | {"name": "Fixed Plant"} | 336046 | TRUE | TRUE | 2026-10-15T03:36:18.652067+00:00 | 2026-10-15T11:36:18.652067+08:00 | #82335 - GDI: 150.5hrs - LABORATORY: GDI | 4.0 | FALSE |  | 2028-01-12T23:00:00+00:00 | 2028-01-19T05:30:00+00:00 | 2028-01-13T07:00:00+08:00 | 2028-01-19T13:30:00+08:00 |  |  |  |  | 150.50 | Minor Lab Shut - Pit Cell - Analytical Cell - Archive Cell Vendors: ROCKLABS (SCOTTS AUTOMATION) ROCKLABS (SCOTTS AUTOMATION) - source ABB METTLER TOLEDO KARDEX MALVERN PANALYTICAL LECO SMART SOLUTIONS | Reason for reduction is efficiencies in labour and we we’re unsure of how long a Dayshift only minor lab shut would take originally | SGDL2802 | [{"equipmentGUID": "4129f6bf-7c7b-ee11-a846-000d3acacefd", "code": "GDILAB", "name": "Laboratory: GDI", "assetClass": {"name": "Laboratory"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5bed8c3f-686b-4af1-be27-c4defbd42eba", "emailAddress": "Jae.Tan@riotinto.com", "displayName": "Tan, Jae (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1aeb6932-afbf-4957-b96a-2a0d54ea1f25 | Dodd, Bronwyn (RTIO) | Scheduled | GDI | Australia/Perth
83890 | 2026-09-08T00:39:26.2181368+00:00 | 2026-09-08T08:39:26.2181368+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-09-08T06:09:52.0327043+00:00 | 2026-09-08T14:09:52.0327043+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 333225 | TRUE | TRUE | 2026-09-08T06:09:52.0327043+00:00 | 2026-09-08T14:09:52.0327043+08:00 | #83890 - YAN: 1.5hrs - BYPASS YCV215 ONTO YCV38 | 1.0 | TRUE |  | 2026-12-10T11:00:00+00:00 | 2026-12-10T12:30:00+00:00 | 2026-12-10T19:00:00+08:00 | 2026-12-10T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
83891 | 2026-09-08T00:41:51.7534431+00:00 | 2026-09-08T08:41:51.7534431+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-09-08T06:09:52.2219758+00:00 | 2026-09-08T14:09:52.2219758+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 333226 | TRUE | TRUE | 2026-09-08T06:09:52.2219758+00:00 | 2026-09-08T14:09:52.2219758+08:00 | #83891 - YAN: 1.5hrs - END BYPASS BACK ON YCV215 | 1.0 | TRUE |  | 2026-12-16T11:00:00+00:00 | 2026-12-16T12:30:00+00:00 | 2026-12-16T19:00:00+08:00 | 2026-12-16T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
83507 | 2026-07-14T05:12:19.9179418+00:00 | 2026-07-14T13:12:19.9179418+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-09-01T03:02:16.4429888+00:00 | 2026-09-01T11:02:16.4429888+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 332389 | TRUE | TRUE | 2026-09-01T03:02:16.4429888+00:00 | 2026-09-01T11:02:16.4429888+08:00 | #83507 - YAN: 85hrs - YFV01 | 2.0 | TRUE |  | 2026-12-06T22:00:00+00:00 | 2026-12-10T11:00:00+00:00 | 2026-12-07T06:00:00+08:00 | 2026-12-10T19:00:00+08:00 |  |  |  |  | 85.00 | Attached is the SIAF for YVF01 which has 0 SOP Impact as YFV01 is an end module in the dry plant, there is no impact to SOP 115436575 C/O 39Wk Feeder FV01 Complete Unit Reason required to be complete Pre shut and needs to be rebuilt before to change out YFV03 in the same week. | Deferred to WK50 |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82638 | 2026-05-29T00:20:23.456583+00:00 | 2026-05-29T08:20:23.456583+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-06-29T02:44:50.6659643+00:00 | 2026-06-29T10:44:50.6659643+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 328587 | TRUE | TRUE | 2026-06-29T02:44:50.6659643+00:00 | 2026-06-29T10:44:50.6659643+08:00 | #82638 - YAN: 144hrs - RECLAIMER: YAN 02 | 2.0 | FALSE |  | 2027-03-05T11:00:00+00:00 | 2027-03-11T11:00:00+00:00 | 2027-03-05T19:00:00+08:00 | 2027-03-11T19:00:00+08:00 |  |  |  |  | 144.00 | Reclaimer 2 Shut - YRC02 Luff Cylinder C/O | Moving to align with STK2 headend c/o shut |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57742 | 2023-08-17T06:27:53+00:00 | 2023-08-17T14:27:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T05:29:41.610721+00:00 | 2026-06-15T13:29:41.610721+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327986 | TRUE | TRUE | 2026-06-15T05:29:41.610721+00:00 | 2026-06-15T13:29:41.610721+08:00 | #57742 - YAN: 48hrs - DRY PLANT SCREEN OUTAGE | 3.0 | TRUE |  | 2027-01-07T22:00:00+00:00 | 2027-01-09T22:00:00+00:00 | 2027-01-08T06:00:00+08:00 | 2027-01-10T06:00:00+08:00 |  |  |  |  | 48.00 | 48hr - Dry Plant Screen Outage - 2 Run PC1 t at 50% for screen panel C/O. Screen to be worked on; YSC07, YSC03 & YSC04 | Updated from 24 to 48 hours (same as 2026) Identified in 2027 MSF review |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [{"name": "Reduced Rates"}] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Site Constraint | YAN | Australia/Perth
57743 | 2023-08-17T06:28:22+00:00 | 2023-08-17T14:28:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T05:29:41.7345093+00:00 | 2026-06-15T13:29:41.7345093+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327987 | TRUE | TRUE | 2026-06-15T05:29:41.7345093+00:00 | 2026-06-15T13:29:41.7345093+08:00 | #57743 - YAN: 48hrs - DRY PLANT SCREEN OUTAGE | 3.0 | TRUE |  | 2027-04-08T22:00:00+00:00 | 2027-04-10T22:00:00+00:00 | 2027-04-09T06:00:00+08:00 | 2027-04-11T06:00:00+08:00 |  |  |  |  | 48.00 | 48hr - Dry Plant Screen Outage - 2 Run PC1 t at 50% for screen panel C/O. Screen to be worked on; YSC07, YSC03 & YSC04 | Updated from 24 to 48 hours (same as 2026) Identified in 2027 MSF review |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [{"name": "Reduced Rates"}] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Site Constraint | YAN | Australia/Perth
57744 | 2023-08-17T06:29:01+00:00 | 2023-08-17T14:29:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T05:29:41.8696508+00:00 | 2026-06-15T13:29:41.8696508+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327988 | TRUE | TRUE | 2026-06-15T05:29:41.8696508+00:00 | 2026-06-15T13:29:41.8696508+08:00 | #57744 - YAN: 48hrs - DRY PLANT SCREEN OUTAGE | 3.0 | TRUE |  | 2027-07-08T22:00:00+00:00 | 2027-07-10T22:00:00+00:00 | 2027-07-09T06:00:00+08:00 | 2027-07-11T06:00:00+08:00 |  |  |  |  | 48.00 | 48hr - Dry Plant Screen Outage - 2 Run PC1 t at 50% for screen panel C/O. Screen to be worked on;YSC07, YSC03 & YSC04 | Updated from 24 to 48 hours (same as 2026) Identified in 2027 MSF review |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [{"name": "Reduced Rates"}] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Site Constraint | YAN | Australia/Perth
57614 | 2023-08-16T08:31:53+00:00 | 2023-08-16T16:31:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-23T04:53:42.46016+00:00 | 2026-07-23T12:53:42.46016+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 330328 | TRUE | TRUE | 2026-07-23T04:53:42.46016+00:00 | 2026-07-23T12:53:42.46016+08:00 | #57614 - YAN: 192hrs - STACKER: YAN 03 | 7.0 | FALSE |  | 2027-09-16T11:00:00+00:00 | 2027-09-24T11:00:00+00:00 | 2027-09-16T19:00:00+08:00 | 2027-09-24T19:00:00+08:00 |  |  |  |  | 192.00 | Stacker 3 shut - YFA32 Apron Feeder Overhaul - 10Yr plan shut extension | Stacker 3 shuts now aligned with Dry Shuts |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57697 | 2023-08-17T04:05:21+00:00 | 2023-08-17T12:05:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-23T04:54:32.9848162+00:00 | 2026-07-23T12:54:32.9848162+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 330330 | TRUE | TRUE | 2026-07-23T04:54:32.9848162+00:00 | 2026-07-23T12:54:32.9848162+08:00 | #57697 - YAN: 321hrs - PC2 SHUT | 7.0 | TRUE |  | 2027-02-11T11:00:00+00:00 | 2027-02-24T20:00:00+00:00 | 2027-02-11T19:00:00+08:00 | 2027-02-25T04:00:00+08:00 |  |  |  |  | 321.00 | PC2 Wet Plant Shut - YFA201 Apron Feeder Overhaul | This particular apron feeder requires 321 hours | SPC22707 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57612 | 2023-08-16T08:31:08+00:00 | 2023-08-16T16:31:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-23T01:55:44.040294+00:00 | 2026-07-23T09:55:44.040294+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 330289 | TRUE | TRUE | 2026-07-23T01:55:44.040294+00:00 | 2026-07-23T09:55:44.040294+08:00 | #57612 - YAN: 108hrs - STACKER: YAN 03 | 6.0 | FALSE |  | 2027-12-16T11:00:00+00:00 | 2027-12-20T23:00:00+00:00 | 2027-12-16T19:00:00+08:00 | 2027-12-21T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 3 shut | Stacker 3 shuts now aligned with Dry shuts |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57608 | 2023-08-16T08:29:41+00:00 | 2023-08-16T16:29:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-23T01:55:44.3813636+00:00 | 2026-07-23T09:55:44.3813636+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 330290 | TRUE | TRUE | 2026-07-23T01:55:44.3813636+00:00 | 2026-07-23T09:55:44.3813636+08:00 | #57608 - YAN: 108hrs - STACKER: YAN 03 | 6.0 | FALSE |  | 2027-03-18T11:00:00+00:00 | 2027-03-22T23:00:00+00:00 | 2027-03-18T19:00:00+08:00 | 2027-03-23T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 3 shut | Stacker 3 shuts have been moved to align with Dry Shuts |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
45060 | 2021-12-01T03:05:18+00:00 | 2021-12-01T11:05:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:09:38.3475549+00:00 | 2026-06-03T12:09:38.3475549+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327149 | TRUE | TRUE | 2026-06-03T04:09:38.3475549+00:00 | 2026-06-03T12:09:38.3475549+08:00 | #45060 - YAN: 144hrs - LOOP SHUT | 9.1 | TRUE |  | 2027-10-21T11:00:00+00:00 | 2027-10-27T11:00:00+00:00 | 2027-10-21T19:00:00+08:00 | 2027-10-27T19:00:00+08:00 |  |  |  |  | 144.00 | LOOP PLANT SHUT |  | SLOO2742 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
45045 | 2021-12-01T03:04:53+00:00 | 2021-12-01T11:04:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:10:14.3605222+00:00 | 2026-06-03T12:10:14.3605222+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327150 | TRUE | TRUE | 2026-06-03T04:10:14.3605222+00:00 | 2026-06-03T12:10:14.3605222+08:00 | #45045 - YAN: 144hrs - LOOP SHUT | 6.2 | TRUE |  | 2027-01-21T11:00:00+00:00 | 2027-01-27T11:00:00+00:00 | 2027-01-21T19:00:00+08:00 | 2027-01-27T19:00:00+08:00 |  |  |  |  | 144.00 | Loop Shut |  | SLOO2703 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
44867 | 2021-11-30T04:09:11+00:00 | 2021-11-30T12:09:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:11:59.4026682+00:00 | 2026-06-03T12:11:59.4026682+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327153 | TRUE | TRUE | 2026-06-03T04:11:59.4026682+00:00 | 2026-06-03T12:11:59.4026682+08:00 | #44867 - YAN: 144hrs - DRY SHUT | 7.1 | TRUE |  | 2027-03-18T11:00:00+00:00 | 2027-03-24T11:00:00+00:00 | 2027-03-18T19:00:00+08:00 | 2027-03-24T19:00:00+08:00 |  |  |  |  | 144.00 | Dry Plant & JSW Shut |  | SDRY2711 | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
44882 | 2021-11-30T04:09:36+00:00 | 2021-11-30T12:09:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:20:33.9057052+00:00 | 2026-06-03T12:20:33.9057052+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327157 | TRUE | TRUE | 2026-06-03T04:20:33.9057052+00:00 | 2026-06-03T12:20:33.9057052+08:00 | #44882 - YAN: 144hrs - DRY SHUT | 7.2 | TRUE |  | 2027-12-16T11:00:00+00:00 | 2027-12-22T11:00:00+00:00 | 2027-12-16T19:00:00+08:00 | 2027-12-22T19:00:00+08:00 |  |  |  |  | 144.00 | Dry Plant Shut |  | SDRY2750 | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57698 | 2023-08-17T04:05:56+00:00 | 2023-08-17T12:05:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:25:47.3549474+00:00 | 2026-06-03T12:25:47.3549474+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327161 | TRUE | TRUE | 2026-06-03T04:25:47.3549474+00:00 | 2026-06-03T12:25:47.3549474+08:00 | #57698 - YAN: 120hrs - PC2 SHUT | 3.2 | TRUE |  | 2027-05-20T11:00:00+00:00 | 2027-05-25T11:00:00+00:00 | 2027-05-20T19:00:00+08:00 | 2027-05-25T19:00:00+08:00 |  |  |  |  | 120.00 | PC2 Wet Plant Shut |  | SPC22720 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57699 | 2023-08-17T04:06:34+00:00 | 2023-08-17T12:06:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:26:55.2594355+00:00 | 2026-06-03T12:26:55.2594355+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327162 | TRUE | TRUE | 2026-06-03T04:26:55.2594355+00:00 | 2026-06-03T12:26:55.2594355+08:00 | #57699 - YAN: 120hrs - PC2 SHUT | 3.1 | TRUE |  | 2027-08-19T11:00:00+00:00 | 2027-08-24T11:00:00+00:00 | 2027-08-19T19:00:00+08:00 | 2027-08-24T19:00:00+08:00 |  |  |  |  | 120.00 | PC2 Wet Plant Shut |  | SPC22733 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57700 | 2023-08-17T04:07:04+00:00 | 2023-08-17T12:07:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-03T04:29:58.8730286+00:00 | 2026-06-03T12:29:58.8730286+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327163 | TRUE | TRUE | 2026-06-03T04:29:58.8730286+00:00 | 2026-06-03T12:29:58.8730286+08:00 | #57700 - YAN: 120hrs - PC2 SHUT | 3.1 | TRUE |  | 2027-11-18T11:00:00+00:00 | 2027-11-23T11:00:00+00:00 | 2027-11-18T19:00:00+08:00 | 2027-11-23T19:00:00+08:00 |  |  |  |  | 120.00 | PC2 Wet Plant Shut |  | SPC22746 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
45108 | 2021-12-01T04:39:36+00:00 | 2021-12-01T12:39:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T04:13:28.017+00:00 | 2026-06-15T12:13:28.017+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327925 | TRUE | TRUE | 2026-06-15T04:13:28.017+00:00 | 2026-06-15T12:13:28.017+08:00 | #45108 - YAN: 24hrs - LOOP PREP - JSE NOT IN BYPASS | 4.0 | TRUE |  | 2027-07-21T15:00:00+00:00 | 2027-07-22T15:00:00+00:00 | 2027-07-21T23:00:00+08:00 | 2027-07-22T23:00:00+08:00 |  |  |  |  | 24.00 | 24hr - Loop Shut Preps | Correction - MSF 2027 |  | [{"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
45103 | 2021-12-01T04:39:26+00:00 | 2021-12-01T12:39:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T04:13:28.1611603+00:00 | 2026-06-15T12:13:28.1611603+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327926 | TRUE | TRUE | 2026-06-15T04:13:28.1611603+00:00 | 2026-06-15T12:13:28.1611603+08:00 | #45103 - YAN: 24hrs - LOOP PREP - JSE NOT IN BYPASS | 4.0 | TRUE |  | 2027-04-21T11:00:00+00:00 | 2027-04-22T11:00:00+00:00 | 2027-04-21T19:00:00+08:00 | 2027-04-22T19:00:00+08:00 |  |  |  |  | 24.00 | 24hr - Loop Shut Preps | Correction MSF review 2027 |  | [{"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
41759 | 2021-05-25T09:23:44+00:00 | 2021-05-25T17:23:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-09T00:53:36.940969+00:00 | 2026-06-09T08:53:36.940969+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327473 | TRUE | TRUE | 2026-06-09T00:53:36.940969+00:00 | 2026-06-09T08:53:36.940969+08:00 | #41759 - YAN: 120hrs - TRAIN LOADOUT: YAN 01 | 10.2 | TRUE |  | 2027-01-29T11:00:00+00:00 | 2027-02-03T11:00:00+00:00 | 2027-01-29T19:00:00+08:00 | 2027-02-03T19:00:00+08:00 |  |  |  |  | 120.00 | TLO1 and Reclaimer 1 Shut |  | STLO2704 | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
57745 | 2023-08-17T06:29:30+00:00 | 2023-08-17T14:29:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T05:29:41.4771826+00:00 | 2026-06-15T13:29:41.4771826+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327985 | TRUE | TRUE | 2026-06-15T05:29:41.4771826+00:00 | 2026-06-15T13:29:41.4771826+08:00 | #57745 - YAN: 48hrs - DRY PLANT SCREEN OUTAGE | 3.0 | TRUE |  | 2027-10-07T22:00:00+00:00 | 2027-10-09T22:00:00+00:00 | 2027-10-08T06:00:00+08:00 | 2027-10-10T06:00:00+08:00 |  |  |  |  | 48.00 | 48hr - Dry Plant Screen Outage - 2 Run PC1 t at 50% for screen panel C/O. Screen to be worked on; YSC07, YSC03 & YSC04 | Updated from 24 to 48 hours (same as 2026) Identified in 2027 MSF review |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [{"name": "Reduced Rates"}] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Site Constraint | YAN | Australia/Perth
82844 | 2026-06-04T06:26:30.0569041+00:00 | 2026-06-04T14:26:30.0569041+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-07-09T05:51:50.6483925+00:00 | 2026-07-09T13:51:50.6483925+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 329757 | TRUE | TRUE | 2026-07-09T05:51:50.6483925+00:00 | 2026-07-09T13:51:50.6483925+08:00 | #82844 - YAN: 156hrs - JSE FULL BYPASS SHUT | 1.0 | TRUE |  | 2027-09-09T11:00:00+00:00 | 2027-09-15T23:00:00+00:00 | 2027-09-09T19:00:00+08:00 | 2027-09-16T07:00:00+08:00 |  |  |  |  | 156.00 | JSE Bypass Shut |  | SJSE2736 | [{"equipmentGUID": "", "code": "YANPLT03BYPASS", "name": "Plant: Yandi Plant 3 (JSE) in Bypass", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82843 | 2026-06-04T06:22:35.8196569+00:00 | 2026-06-04T14:22:35.8196569+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-07-09T05:51:50.8266179+00:00 | 2026-07-09T13:51:50.8266179+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 329758 | TRUE | TRUE | 2026-07-09T05:51:50.8266179+00:00 | 2026-07-09T13:51:50.8266179+08:00 | #82843 - YAN: 156hrs - JSE FULL BYPASS SHUT | 1.0 | TRUE |  | 2027-02-25T11:00:00+00:00 | 2027-03-03T23:00:00+00:00 | 2027-02-25T19:00:00+08:00 | 2027-03-04T07:00:00+08:00 |  |  |  |  | 156.00 | JSE Bypass Shut |  | SJSE2708 | [{"equipmentGUID": "", "code": "YANPLT03BYPASS", "name": "Plant: Yandi Plant 3 (JSE) in Bypass", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
83765 | 2026-08-25T23:18:27.5405581+00:00 | 2026-08-26T07:18:27.5405581+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-08-27T07:18:01.5600943+00:00 | 2026-08-27T15:18:01.5600943+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 332026 | TRUE | TRUE | 2026-08-27T07:18:01.5600943+00:00 | 2026-08-27T15:18:01.5600943+08:00 | #83765 - YAN: 12hrs - PLANT: YAN 01 (DRY) | 1.0 | TRUE |  | 2026-12-05T22:00:00+00:00 | 2026-12-06T10:00:00+00:00 | 2026-12-06T06:00:00+08:00 | 2026-12-06T18:00:00+08:00 |  |  |  |  | 12.00 | Work in Substation 2718 will affect YCV11, YCV38, YFA31 & STK2 |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "e515d223-c54d-4f21-a5bf-1b24853b4e2a", "emailAddress": "Sophie.Wills@riotinto.com", "displayName": "Wills, Sophie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
83510 | 2026-07-15T02:37:53.3710348+00:00 | 2026-07-15T10:37:53.3710348+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-07-23T01:55:44.5386184+00:00 | 2026-07-23T09:55:44.5386184+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 330291 | TRUE | TRUE | 2026-07-23T01:55:44.5386184+00:00 | 2026-07-23T09:55:44.5386184+08:00 | #83510 - YAN: 108hrs - STACKER: YAN 03 | 1.0 | FALSE |  | 2026-12-10T11:00:00+00:00 | 2026-12-14T23:00:00+00:00 | 2026-12-10T19:00:00+08:00 | 2026-12-15T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 3 Shut now with aligned with Dry Shuts |  |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82918 | 2026-06-17T00:08:44.2820713+00:00 | 2026-06-17T08:08:44.2820713+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-06-29T02:44:51.7536447+00:00 | 2026-06-29T10:44:51.7536447+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 328591 | TRUE | TRUE | 2026-06-29T02:44:51.7536447+00:00 | 2026-06-29T10:44:51.7536447+08:00 | #82918 - YAN: 10hrs - STK03 CAPD TESTING | 1.0 | FALSE |  | 2027-09-08T22:00:00+00:00 | 2027-09-09T08:00:00+00:00 | 2027-09-09T06:00:00+08:00 | 2027-09-09T16:00:00+08:00 |  |  |  |  | 10.00 | STK03 CAPD Testing |  |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82917 | 2026-06-17T00:07:59.4925259+00:00 | 2026-06-17T08:07:59.4925259+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-06-29T02:44:51.9641785+00:00 | 2026-06-29T10:44:51.9641785+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 328592 | TRUE | TRUE | 2026-06-29T02:44:51.9641785+00:00 | 2026-06-29T10:44:51.9641785+08:00 | #82917 - YAN: 10hrs - STK02 CAPD TESTING | 1.0 | FALSE |  | 2027-09-07T22:00:00+00:00 | 2027-09-08T08:00:00+00:00 | 2027-09-08T06:00:00+08:00 | 2027-09-08T16:00:00+08:00 |  |  |  |  | 10.00 | STK02 CAPD Testing |  |  | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82916 | 2026-06-17T00:07:14.7199957+00:00 | 2026-06-17T08:07:14.7199957+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-06-29T02:44:52.1502004+00:00 | 2026-06-29T10:44:52.1502004+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 328593 | TRUE | TRUE | 2026-06-29T02:44:52.1502004+00:00 | 2026-06-29T10:44:52.1502004+08:00 | #82916 - YAN: 10hrs - YRC02 CAPD TESTING | 1.0 | FALSE |  | 2027-09-06T22:00:00+00:00 | 2027-09-07T08:00:00+00:00 | 2027-09-07T06:00:00+08:00 | 2027-09-07T16:00:00+08:00 |  |  |  |  | 10.00 | YRC02 CAPD Testing |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82915 | 2026-06-17T00:05:48.1204409+00:00 | 2026-06-17T08:05:48.1204409+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-06-29T02:44:52.3424628+00:00 | 2026-06-29T10:44:52.3424628+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 328594 | TRUE | TRUE | 2026-06-29T02:44:52.3424628+00:00 | 2026-06-29T10:44:52.3424628+08:00 | #82915 - YAN: 10hrs - YRC01 CAPD TESTING | 1.0 | FALSE |  | 2027-09-05T22:00:00+00:00 | 2027-09-06T08:00:00+00:00 | 2027-09-06T06:00:00+08:00 | 2027-09-06T16:00:00+08:00 |  |  |  |  | 10.00 | YRC01 CAPD TESTING |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Create | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
82457 | 2026-05-05T00:10:32.4156439+00:00 | 2026-05-05T08:10:32.4156439+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | 2026-06-09T08:41:42.484706+00:00 | 2026-06-09T16:41:42.484706+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327517 | TRUE | TRUE | 2026-06-09T08:41:42.484706+00:00 | 2026-06-09T16:41:42.484706+08:00 | #82457 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 1.3 | TRUE |  | 2026-11-26T23:00:00+00:00 | 2026-11-30T23:00:00+00:00 | 2026-11-27T07:00:00+08:00 | 2026-12-01T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
73233 | 2025-11-12T03:23:16.6409645+00:00 | 2025-11-12T11:23:16.6409645+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-08-26T23:25:13.6125376+00:00 | 2026-08-27T07:25:13.6125376+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 331865 | TRUE | TRUE | 2026-08-26T23:25:13.6125376+00:00 | 2026-08-27T07:25:13.6125376+08:00 | #73233 - YAN: 120hrs - SCRUBBER: YAN 301 | 2.0 | FALSE |  | 2027-11-25T11:00:00+00:00 | 2027-11-30T11:00:00+00:00 | 2027-11-25T19:00:00+08:00 | 2027-11-30T19:00:00+08:00 |  |  |  |  | 120.00 | JSE Modular 301 - extended 24 hours for YSR301 Scrubber Shell Liners | Requesting extension for YSR301 Scrubber Shell Liners C/O WO116064136 |  | [{"equipmentGUID": "2622f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB301", "name": "Scrubber: YAN 301", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
67876 | 2025-06-19T13:28:58.3344245+00:00 | 2025-06-19T21:28:58.3344245+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-06-04T03:00:52.6567227+00:00 | 2026-06-04T11:00:52.6567227+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327202 | TRUE | TRUE | 2026-06-04T03:00:52.6567227+00:00 | 2026-06-04T11:00:52.6567227+08:00 | #67876 - YAN: 12hrs - RECLAIMER: YAN 02 | 3.0 | FALSE |  | 2027-01-03T16:00:00+00:00 | 2027-01-04T04:00:00+00:00 | 2027-01-04T00:00:00+08:00 | 2027-01-04T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection | Incorrectly moved with IAM refresh |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
67886 | 2025-06-23T08:22:00.7313946+00:00 | 2025-06-23T16:22:00.7313946+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-04-20T02:59:52.9335783+00:00 | 2026-04-20T10:59:52.9335783+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 325535 | TRUE | TRUE | 2026-04-20T02:59:52.9335783+00:00 | 2026-04-20T10:59:52.9335783+08:00 | #67886 - YAN: 12hrs - YAN LOOP PLANT | 6.0 | TRUE |  | 2026-11-30T22:00:00+00:00 | 2026-12-01T10:00:00+00:00 | 2026-12-01T06:00:00+08:00 | 2026-12-01T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's | Moving to align to Tuesday to Thursday |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Site Constraint | YAN | Australia/Perth
82828 | 2026-06-04T03:08:16.7619544+00:00 | 2026-06-04T11:08:16.7619544+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-06-09T08:42:10.9236041+00:00 | 2026-06-09T16:42:10.9236041+08:00 | {"principalGUID": "948a9bbf-139e-44ad-bd5e-35e6f461c379", "displayName": "Chandler, Georgia (RTIO)"} | {"name": "Fixed Plant"} | 327518 | TRUE | TRUE | 2026-06-09T08:42:10.9236041+00:00 | 2026-06-09T16:42:10.9236041+08:00 | #82828 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 1.1 | TRUE |  | 2026-12-24T23:00:00+00:00 | 2026-12-28T23:00:00+00:00 | 2026-12-25T07:00:00+08:00 | 2026-12-29T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | 948a9bbf-139e-44ad-bd5e-35e6f461c379 | Chandler, Georgia (RTIO) | Scheduled | YAN | Australia/Perth
68888 | 2025-09-05T03:30:20.2002187+00:00 | 2025-09-05T11:30:20.2002187+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:28.8892595+00:00 | 2025-10-17T06:56:28.8892595+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259782 | TRUE | TRUE | 2025-10-16T22:56:28.8892595+00:00 | 2025-10-17T06:56:28.8892595+08:00 | #68888 - MTP: 44hrs - CONVEYOR: MTP 72C | 4.0 | FALSE |  | 2026-12-20T16:00:00+00:00 | 2026-12-22T12:00:00+00:00 | 2026-12-21T00:00:00+08:00 | 2026-12-22T20:00:00+08:00 |  |  |  |  | 44.00 | 72C Module Maintenance | Aliging our Local Shutdowns |  | [{"equipmentGUID": "0e27f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV72C", "name": "Conveyor: MTP 72C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68835 | 2025-09-05T02:35:01.7130468+00:00 | 2025-09-05T10:35:01.7130468+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:30.8421915+00:00 | 2025-10-17T06:56:30.8421915+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259784 | TRUE | TRUE | 2025-10-16T22:56:30.8421915+00:00 | 2025-10-17T06:56:30.8421915+08:00 | #68835 - MTP: 68hrs - CRUSHER - TERTIARY: MTP 08 LOW GRADE | 4.0 | FALSE |  | 2026-11-28T16:00:00+00:00 | 2026-12-01T12:00:00+00:00 | 2026-11-29T00:00:00+08:00 | 2026-12-01T20:00:00+08:00 |  |  |  |  | 68.00 | C8 Module Maintenance | Aligning Local Modules |  | [{"equipmentGUID": "c632f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS08", "name": "Crusher - Tertiary: MTP 08 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68892 | 2025-09-05T03:30:20.8634803+00:00 | 2025-09-05T11:30:20.8634803+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:31.913102+00:00 | 2025-10-17T06:56:31.913102+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259785 | TRUE | TRUE | 2025-10-16T22:56:31.913102+00:00 | 2025-10-17T06:56:31.913102+08:00 | #68892 - MTP: 124hrs - DRUM: MTP MODULE 01 | 4.0 | FALSE |  | 2026-12-08T11:00:00+00:00 | 2026-12-13T15:00:00+00:00 | 2026-12-08T19:00:00+08:00 | 2026-12-13T23:00:00+08:00 |  |  |  |  | 124.00 | Drum 1 Module Maintenance | Aligning our Local Mod |  | [{"equipmentGUID": "8f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM01", "name": "Drum: MTP Module 01", "assetClass": {"name": "Drum"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68943 | 2025-09-05T05:11:41.0958552+00:00 | 2025-09-05T13:11:41.0958552+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:34.8888951+00:00 | 2025-10-17T06:56:34.8888951+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259788 | TRUE | TRUE | 2025-10-16T22:56:34.8888951+00:00 | 2025-10-17T06:56:34.8888951+08:00 | #68943 - MTP: 39hrs - SCREEN: MTP FINAL PRODUCT NO. 13 | 4.0 | FALSE |  | 2026-12-22T20:00:00+00:00 | 2026-12-24T11:00:00+00:00 | 2026-12-23T04:00:00+08:00 | 2026-12-24T19:00:00+08:00 |  |  |  |  | 39.00 | 13FPS Module Maintenance | Aligning Local Mod |  | [{"equipmentGUID": "8856fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC13FPS", "name": "Screen: MTP Final Product No. 13", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68911 | 2025-09-05T05:11:34.6182494+00:00 | 2025-09-05T13:11:34.6182494+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:36.9071685+00:00 | 2025-10-17T06:56:36.9071685+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259790 | TRUE | TRUE | 2025-10-16T22:56:36.9071685+00:00 | 2025-10-17T06:56:36.9071685+08:00 | #68911 - MTP: 39hrs - SCREEN: MTP FINAL PRODUCT NO. 5 | 4.0 | FALSE |  | 2026-12-16T20:00:00+00:00 | 2026-12-18T11:00:00+00:00 | 2026-12-17T04:00:00+08:00 | 2026-12-18T19:00:00+08:00 |  |  |  |  | 39.00 | 5FPS Module Maintenance | Aligning Local mod |  | [{"equipmentGUID": "3636f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC5FPS", "name": "Screen: MTP Final Product No. 5 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68927 | 2025-09-05T05:11:37.6788287+00:00 | 2025-09-05T13:11:37.6788287+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:37.9737257+00:00 | 2025-10-17T06:56:37.9737257+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259791 | TRUE | TRUE | 2025-10-16T22:56:37.9737257+00:00 | 2025-10-17T06:56:37.9737257+08:00 | #68927 - MTP: 39hrs - SCREEN: MTP FINAL PRODUCT NO. 9 | 4.0 | FALSE |  | 2026-12-19T20:00:00+00:00 | 2026-12-21T11:00:00+00:00 | 2026-12-20T04:00:00+08:00 | 2026-12-21T19:00:00+08:00 |  |  |  |  | 39.00 | 9FPS Module Maintenance | Aligning Local mod |  | [{"equipmentGUID": "4bdd00c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC9FPS", "name": "Screen: MTP Final Product No. 9 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68855 | 2025-09-05T02:35:04.996755+00:00 | 2025-09-05T10:35:04.996755+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:40.0837852+00:00 | 2025-10-17T06:56:40.0837852+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259793 | TRUE | TRUE | 2025-10-16T22:56:40.0837852+00:00 | 2025-10-17T06:56:40.0837852+08:00 | #68855 - MTP: 92hrs - SCREEN: MTP WASH & SCREEN MODULE 02 | 4.0 | FALSE |  | 2026-12-01T16:00:00+00:00 | 2026-12-05T12:00:00+00:00 | 2026-12-02T00:00:00+08:00 | 2026-12-05T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 2 Maintenance | Aligning Local Mod |  | [{"equipmentGUID": "83318e78-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD02", "name": "Screen: MTP Wash & Screen Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68849 | 2025-09-05T02:35:03.9618298+00:00 | 2025-09-05T10:35:03.9618298+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:41.0758339+00:00 | 2025-10-17T06:56:41.0758339+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259794 | TRUE | TRUE | 2025-10-16T22:56:41.0758339+00:00 | 2025-10-17T06:56:41.0758339+08:00 | #68849 - MTP: 14hrs - SCREEN: MTP WASH & SCREEN MODULE 05 | 4.0 | FALSE |  | 2026-12-05T20:00:00+00:00 | 2026-12-06T10:00:00+00:00 | 2026-12-06T04:00:00+08:00 | 2026-12-06T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 5 Pitstop | Aligning Local Mod |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
68851 | 2025-09-05T02:35:04.2605312+00:00 | 2025-09-05T10:35:04.2605312+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-16T22:56:42.0924813+00:00 | 2025-10-17T06:56:42.0924813+08:00 | {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "displayName": "Sturzaker, David (RTIO)"} | {"name": "Fixed Plant"} | 259795 | TRUE | TRUE | 2025-10-16T22:56:42.0924813+00:00 | 2025-10-17T06:56:42.0924813+08:00 | #68851 - MTP: 14hrs - SCREEN: MTP WASH & SCREEN MODULE 06 | 4.0 | FALSE |  | 2026-12-18T20:00:00+00:00 | 2026-12-19T10:00:00+00:00 | 2026-12-19T04:00:00+08:00 | 2026-12-19T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 6 Pitstop | Aligning Local Mod |  | [{"equipmentGUID": "7571e0a4-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD06", "name": "Screen: MTP Wash & Screen Module 06", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a | Sturzaker, David (RTIO) | Scheduled | MTP | Australia/Perth
83997 | 2026-09-25T07:47:29.1949679+00:00 | 2026-09-25T15:47:29.1949679+08:00 | {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"} | 2026-09-25T08:30:51.2074276+00:00 | 2026-09-25T16:30:51.2074276+08:00 | {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"} | {"name": "Utilities"} | 334128 | TRUE | TRUE | 2026-09-25T08:30:51.2074276+00:00 | 2026-09-25T16:30:51.2074276+08:00 | #83997 - UTL: 276hrs - GENERATION: YMPS GTG4 | 1.0 | FALSE |  | 2027-01-31T22:00:00+00:00 | 2027-02-12T10:00:00+00:00 | 2027-02-01T06:00:00+08:00 | 2027-02-12T18:00:00+08:00 |  |  |  |  | 276.00 | GTG4 BN3500 Vibration System Upgrade Refer WO# 990133947 Mobilisation of Baker Hughes, IHI and Tasman for shift and upgrade of vibration protection system |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG4 YMPS", "name": "Generation: YMPS GTG4", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "emailAddress": "michael.talikowski@riotinto.com", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 147115a4-d37b-437f-b48a-40fda09faac9 | Talikowski, Michael (RTIO-WORKPAC) | Placeholder |  | Australia/Perth
83998 | 2026-09-25T07:54:33.023846+00:00 | 2026-09-25T15:54:33.023846+08:00 | {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"} | 2026-09-25T08:31:50.8939607+00:00 | 2026-09-25T16:31:50.8939607+08:00 | {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"} | {"name": "Utilities"} | 334129 | TRUE | TRUE | 2026-09-25T08:31:50.8939607+00:00 | 2026-09-25T16:31:50.8939607+08:00 | #83998 - UTL: 276hrs - GENERATION: YMPS GTG8 | 1.0 | FALSE |  | 2027-04-18T22:00:00+00:00 | 2027-04-30T10:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-30T18:00:00+08:00 |  |  |  |  | 276.00 | GTG8 BN3500 Vibration System Upgrade Refer WO# 990144614 Mobilisation of Baker Hughes, IHI and Tasman for shift and upgrade of vibration protection system |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG8 YMPS", "name": "Generation: YMPS GTG8", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "147115a4-d37b-437f-b48a-40fda09faac9", "emailAddress": "michael.talikowski@riotinto.com", "displayName": "Talikowski, Michael (RTIO-WORKPAC)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 147115a4-d37b-437f-b48a-40fda09faac9 | Talikowski, Michael (RTIO-WORKPAC) | Placeholder |  | Australia/Perth
83415 | 2026-07-02T10:58:52.5459923+00:00 | 2026-07-02T18:58:52.5459923+08:00 | {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "displayName": "Bellman, Tammera (RTIO)"} | 2026-08-12T05:35:04.8194255+00:00 | 2026-08-12T13:35:04.8194255+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 331137 | TRUE | TRUE | 2026-08-12T05:35:04.8194255+00:00 | 2026-08-12T13:35:04.8194255+08:00 | #83415 - RVJ: 1992hrs - 06R33 CAT 777F WATER TRUCK | 1.2 | FALSE |  | 2027-10-10T16:00:00+00:00 | 2028-01-01T16:00:00+00:00 | 2027-10-11T00:00:00+08:00 | 2028-01-02T00:00:00+08:00 |  |  |  |  | 1992.00 | Engine & WDS Change to ADE |  | S06R33 | [{"equipmentGUID": "63e7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R33", "name": "06R33 CAT 777F Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Water Tank Overhaul"}, {"name": "Off Site Repair"}] | [] | [] | Approved | Update | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Scheduled | RVJ | Australia/Perth |  | OSR
83520 | 2026-07-17T02:59:25.3378599+00:00 | 2026-07-17T10:59:25.3378599+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-07-17T02:59:25.3378599+00:00 | 2026-07-17T10:59:25.3378599+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 330085 | TRUE | TRUE | 2026-07-17T02:59:25.3378599+00:00 | 2026-07-17T10:59:25.3378599+08:00 | #83520 - RVA: 120hrs - 15R381 HITACHI EX3600-7BH EXCAVATOR | 1.0 | FALSE |  | 2026-12-07T16:00:00+00:00 | 2026-12-12T16:00:00+00:00 | 2026-12-08T00:00:00+08:00 | 2026-12-13T00:00:00+08:00 |  |  |  |  | 120.00 | 302215R381 Bucket C/O |  |  | [{"equipmentGUID": "6019f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15R381", "name": "15R381 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "5468c11a-9697-49ea-a19e-dfd3b0d50724", "emailAddress": "TRAVIS.OCONNELL@RIOTINTO.COM", "displayName": "O'Connell, Travis (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Unscheduled | RVA | Australia/Perth |  | Site Team
83402 | 2026-07-02T05:55:49.5857744+00:00 | 2026-07-02T13:55:49.5857744+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-12T05:35:31.1332612+00:00 | 2026-08-12T13:35:31.1332612+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 331138 | TRUE | TRUE | 2026-08-12T05:35:31.1332612+00:00 | 2026-08-12T13:35:31.1332612+08:00 | #83402 - RVJ: 48hrs - 07R192 CAT 980H WHEEL LOADER | 1.3 | FALSE |  | 2027-11-15T22:00:00+00:00 | 2027-11-17T22:00:00+00:00 | 2027-11-16T06:00:00+08:00 | 2027-11-18T06:00:00+08:00 |  |  |  |  | 48.00 | Eng |  | S07R192 | [{"equipmentGUID": "896cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "07R192", "name": "07R192 CAT 980H Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "4b27a261-5347-4d6e-96ad-75f170353b6b", "emailAddress": "Terrence.Hunter@riotinto.com", "displayName": "Hunter, Terrence (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
83436 | 2026-07-02T22:19:00.0598782+00:00 | 2026-07-03T06:19:00.0598782+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-12T05:37:32.5664779+00:00 | 2026-08-12T13:37:32.5664779+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 331141 | TRUE | TRUE | 2026-08-12T05:37:32.5664779+00:00 | 2026-08-12T13:37:32.5664779+08:00 | #83436 - RVJ: 72hrs - 07R553 CAT 992 WHEEL LOADER | 1.1 | FALSE |  | 2027-05-20T16:00:00+00:00 | 2027-05-23T16:00:00+00:00 | 2027-05-21T00:00:00+08:00 | 2027-05-24T00:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife |  | S07R553 | [{"equipmentGUID": "40ce477d-5d7d-f011-a802-002248933a47", "code": "07R553", "name": "07R553 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "4b27a261-5347-4d6e-96ad-75f170353b6b", "emailAddress": "Terrence.Hunter@riotinto.com", "displayName": "Hunter, Terrence (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
83411 | 2026-07-02T06:30:22.653584+00:00 | 2026-07-02T14:30:22.653584+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-12T05:38:04.4818284+00:00 | 2026-08-12T13:38:04.4818284+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 331142 | TRUE | TRUE | 2026-08-12T05:38:04.4818284+00:00 | 2026-08-12T13:38:04.4818284+08:00 | #83411 - RVJ: 72hrs - 07R554 CAT 992 WHEEL LOADER | 1.1 | FALSE |  | 2027-05-14T16:00:00+00:00 | 2027-05-17T16:00:00+00:00 | 2027-05-15T00:00:00+08:00 | 2027-05-18T00:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife |  | S07R554 | [{"equipmentGUID": "6e655d70-5d7d-f011-a802-002248933a47", "code": "07R554", "name": "07R554 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "4b27a261-5347-4d6e-96ad-75f170353b6b", "emailAddress": "Terrence.Hunter@riotinto.com", "displayName": "Hunter, Terrence (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
83397 | 2026-07-02T05:55:49.5851792+00:00 | 2026-07-02T13:55:49.5851792+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-12T05:42:08.9809712+00:00 | 2026-08-12T13:42:08.9809712+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | {"name": "HME"} | 331146 | TRUE | TRUE | 2026-08-12T05:42:08.9809712+00:00 | 2026-08-12T13:42:08.9809712+08:00 | #83397 - RVA: 192hrs - 07R210 KOMATSU WA1200-6 WHEEL LOADER | 1.2 | FALSE |  | 2027-07-16T04:00:00+00:00 | 2027-07-24T04:00:00+00:00 | 2027-07-16T12:00:00+08:00 | 2027-07-24T12:00:00+08:00 |  |  |  |  | 192.00 | MCV, Hosing, Rr Axle Trunnions Rr&Fr |  | S07R210 | [{"equipmentGUID": "5c20f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07R210", "name": "07R210 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6896f18b-2b9c-4b19-abf9-10160a435472", "emailAddress": "Michael.Dyt@riotinto.com", "displayName": "Michael Dyt"}}] | [] | [] | [] | [] | [] | Approved | Update | b00e8cc6-e6d3-4f82-ac49-49651caa42f7 | Macchia, Stephen (RTIO) | Scheduled | RVA | Australia/Perth |  | Site Team
84081 | 2026-10-01T23:40:47.9419842+00:00 | 2026-10-02T07:40:47.9419842+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:56.6817527+00:00 | 2026-10-02T14:38:56.6817527+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335035 | TRUE | TRUE | 2026-10-02T06:38:56.6817527+00:00 | 2026-10-02T14:38:56.6817527+08:00 | #84081 - YAN: 1.5hrs - BYPASS YCV215 ONTO YCV38 | 1.0 | TRUE |  | 2027-03-18T11:00:00+00:00 | 2027-03-18T12:30:00+00:00 | 2027-03-18T19:00:00+08:00 | 2027-03-18T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84085 | 2026-10-01T23:46:14.5631934+00:00 | 2026-10-02T07:46:14.5631934+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:56.8091284+00:00 | 2026-10-02T14:38:56.8091284+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335036 | TRUE | TRUE | 2026-10-02T06:38:56.8091284+00:00 | 2026-10-02T14:38:56.8091284+08:00 | #84085 - YAN: 1.5hrs - END BYPASS BACK ON YCV215 | 1.0 | TRUE |  | 2027-03-24T09:30:00+00:00 | 2027-03-24T11:00:00+00:00 | 2027-03-24T17:30:00+08:00 | 2027-03-24T19:00:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84082 | 2026-10-01T23:40:48.3853492+00:00 | 2026-10-02T07:40:48.3853492+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:56.9426838+00:00 | 2026-10-02T14:38:56.9426838+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335037 | TRUE | TRUE | 2026-10-02T06:38:56.9426838+00:00 | 2026-10-02T14:38:56.9426838+08:00 | #84082 - YAN: 1.5hrs - BYPASS YCV215 ONTO YCV38 | 1.0 | TRUE |  | 2027-06-17T11:00:00+00:00 | 2027-06-17T12:30:00+00:00 | 2027-06-17T19:00:00+08:00 | 2027-06-17T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84086 | 2026-10-01T23:46:15.0473002+00:00 | 2026-10-02T07:46:15.0473002+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:57.0801276+00:00 | 2026-10-02T14:38:57.0801276+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335038 | TRUE | TRUE | 2026-10-02T06:38:57.0801276+00:00 | 2026-10-02T14:38:57.0801276+08:00 | #84086 - YAN: 1.5hrs - END BYPASS BACK ON YCV215 | 1.0 | TRUE |  | 2027-06-23T09:30:00+00:00 | 2027-06-23T11:00:00+00:00 | 2027-06-23T17:30:00+08:00 | 2027-06-23T19:00:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84083 | 2026-10-01T23:40:48.557054+00:00 | 2026-10-02T07:40:48.557054+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:57.233788+00:00 | 2026-10-02T14:38:57.233788+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335039 | TRUE | TRUE | 2026-10-02T06:38:57.233788+00:00 | 2026-10-02T14:38:57.233788+08:00 | #84083 - YAN: 1.5hrs - BYPASS YCV215 ONTO YCV38 | 1.0 | TRUE |  | 2027-09-16T11:00:00+00:00 | 2027-09-16T12:30:00+00:00 | 2027-09-16T19:00:00+08:00 | 2027-09-16T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84087 | 2026-10-01T23:46:15.2280349+00:00 | 2026-10-02T07:46:15.2280349+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:57.3762034+00:00 | 2026-10-02T14:38:57.3762034+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335040 | TRUE | TRUE | 2026-10-02T06:38:57.3762034+00:00 | 2026-10-02T14:38:57.3762034+08:00 | #84087 - YAN: 1.5hrs - END BYPASS BACK ON YCV215 | 1.0 | TRUE |  | 2027-09-24T09:30:00+00:00 | 2027-09-24T11:00:00+00:00 | 2027-09-24T17:30:00+08:00 | 2027-09-24T19:00:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84084 | 2026-10-01T23:40:48.7277212+00:00 | 2026-10-02T07:40:48.7277212+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:57.5158212+00:00 | 2026-10-02T14:38:57.5158212+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335041 | TRUE | TRUE | 2026-10-02T06:38:57.5158212+00:00 | 2026-10-02T14:38:57.5158212+08:00 | #84084 - YAN: 1.5hrs - BYPASS YCV215 ONTO YCV38 | 1.0 | TRUE |  | 2027-12-16T11:00:00+00:00 | 2027-12-16T12:30:00+00:00 | 2027-12-16T19:00:00+08:00 | 2027-12-16T20:30:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84088 | 2026-10-01T23:46:15.4038213+00:00 | 2026-10-02T07:46:15.4038213+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-02T06:38:57.6490514+00:00 | 2026-10-02T14:38:57.6490514+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335042 | TRUE | TRUE | 2026-10-02T06:38:57.6490514+00:00 | 2026-10-02T14:38:57.6490514+08:00 | #84088 - YAN: 1.5hrs - END BYPASS BACK ON YCV215 | 1.0 | TRUE |  | 2027-12-22T09:30:00+00:00 | 2027-12-22T11:00:00+00:00 | 2027-12-22T17:30:00+08:00 | 2027-12-22T19:00:00+08:00 |  |  |  |  | 1.50 | YBN31 putting the loop into bypass 3hrs downtime total at the Loop in order to bypass YBN31 – 1.5hrs to open bypass gate & 1.5hrs to shut gate. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82827 | 2026-06-04T03:04:24.5836322+00:00 | 2026-06-04T11:04:24.5836322+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-07-08T02:42:48.4925298+00:00 | 2026-07-08T10:42:48.4925298+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 329662 | TRUE | TRUE | 2026-07-08T02:42:48.4925298+00:00 | 2026-07-08T10:42:48.4925298+08:00 | #82827 - YAN: 72hrs - YCC202 LOOP CRUSHER MODS | 2.0 | FALSE |  | 2028-01-14T10:00:00+00:00 | 2028-01-17T10:00:00+00:00 | 2028-01-14T18:00:00+08:00 | 2028-01-17T18:00:00+08:00 |  |  |  |  | 72.00 | YCC202 Loop Crusher Mods | Drumbeat re alignment |  | [{"equipmentGUID": "e374fbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS202", "name": "Crusher - Tertiary: YAN 202 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82822 | 2026-06-04T02:59:45.2533494+00:00 | 2026-06-04T10:59:45.2533494+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-07-08T02:42:48.4925377+00:00 | 2026-07-08T10:42:48.4925377+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 329663 | TRUE | TRUE | 2026-07-08T02:42:48.4925377+00:00 | 2026-07-08T10:42:48.4925377+08:00 | #82822 - YAN: 72hrs - YCC206 LOOP CRUSHER MODS | 2.0 | FALSE |  | 2028-01-07T10:00:00+00:00 | 2028-01-10T10:00:00+00:00 | 2028-01-07T18:00:00+08:00 | 2028-01-10T18:00:00+08:00 |  |  |  |  | 72.00 | YCC206 Loop Crusher Mods | Drumbeat re alignment |  | [{"equipmentGUID": "f032f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS206", "name": "Crusher - Tertiary: YAN 206 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82823 | 2026-06-04T03:04:23.7034684+00:00 | 2026-06-04T11:04:23.7034684+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-07-08T02:42:48.4925495+00:00 | 2026-07-08T10:42:48.4925495+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 329670 | TRUE | TRUE | 2026-07-08T02:42:48.4925495+00:00 | 2026-07-08T10:42:48.4925495+08:00 | #82823 - YAN: 72hrs - YCC202 LOOP CRUSHER MODS | 2.0 | FALSE |  | 2027-01-15T10:00:00+00:00 | 2027-01-18T10:00:00+00:00 | 2027-01-15T18:00:00+08:00 | 2027-01-18T18:00:00+08:00 |  |  |  |  | 72.00 | YCC202 Loop Crusher Mods | Drumbeat re alignment | SH2702 | [{"equipmentGUID": "e374fbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS202", "name": "Crusher - Tertiary: YAN 202 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82818 | 2026-06-04T02:59:44.424894+00:00 | 2026-06-04T10:59:44.424894+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-07-08T02:42:48.4925503+00:00 | 2026-07-08T10:42:48.4925503+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 329671 | TRUE | TRUE | 2026-07-08T02:42:48.4925503+00:00 | 2026-07-08T10:42:48.4925503+08:00 | #82818 - YAN: 72hrs - YCC206 LOOP CRUSHER MODS | 2.0 | FALSE |  | 2027-01-08T10:00:00+00:00 | 2027-01-11T10:00:00+00:00 | 2027-01-08T18:00:00+08:00 | 2027-01-11T18:00:00+08:00 |  |  |  |  | 72.00 | YCC206 Loop Crusher Mods | Drumbeat re alignment | SH2701 | [{"equipmentGUID": "f032f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS206", "name": "Crusher - Tertiary: YAN 206 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69132 | 2025-09-24T02:24:27.0519532+00:00 | 2025-09-24T10:24:27.0519532+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:29.8573541+00:00 | 2025-11-03T11:29:29.8573541+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270080 | TRUE | TRUE | 2025-11-03T03:29:29.8573541+00:00 | 2025-11-03T11:29:29.8573541+08:00 | #69132 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-01-17T11:00:00+00:00 | 2027-01-17T15:00:00+00:00 | 2027-01-17T19:00:00+08:00 | 2027-01-17T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69133 | 2025-09-24T02:24:27.4769059+00:00 | 2025-09-24T10:24:27.4769059+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:35.2346836+00:00 | 2025-11-03T11:29:35.2346836+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270086 | TRUE | TRUE | 2025-11-03T03:29:35.2346836+00:00 | 2025-11-03T11:29:35.2346836+08:00 | #69133 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-02-28T11:00:00+00:00 | 2027-02-28T15:00:00+00:00 | 2027-02-28T19:00:00+08:00 | 2027-02-28T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69134 | 2025-09-24T02:24:27.9140321+00:00 | 2025-09-24T10:24:27.9140321+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:38.7059657+00:00 | 2025-11-03T11:29:38.7059657+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270090 | TRUE | TRUE | 2025-11-03T03:29:38.7059657+00:00 | 2025-11-03T11:29:38.7059657+08:00 | #69134 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-04-11T11:00:00+00:00 | 2027-04-11T15:00:00+00:00 | 2027-04-11T19:00:00+08:00 | 2027-04-11T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69141 | 2025-09-24T02:24:31.0483689+00:00 | 2025-09-24T10:24:31.0483689+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:30:13.6022269+00:00 | 2025-11-03T11:30:13.6022269+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270124 | TRUE | TRUE | 2025-11-03T03:30:13.6022269+00:00 | 2025-11-03T11:30:13.6022269+08:00 | #69141 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2028-01-30T11:00:00+00:00 | 2028-01-30T15:00:00+00:00 | 2028-01-30T19:00:00+08:00 | 2028-01-30T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82830 | 2026-06-04T03:08:17.3509456+00:00 | 2026-06-04T11:08:17.3509456+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:08.3567729+00:00 | 2026-10-09T14:32:08.3567729+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335777 | TRUE | TRUE | 2026-10-09T06:32:08.3567729+00:00 | 2026-10-09T14:32:08.3567729+08:00 | #82830 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-02-25T23:00:00+00:00 | 2027-03-01T23:00:00+00:00 | 2027-02-26T07:00:00+08:00 | 2027-03-02T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
67887 | 2025-06-23T08:22:01.1703171+00:00 | 2025-06-23T16:22:01.1703171+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1904018+00:00 | 2026-10-12T11:43:01.1904018+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335799 | TRUE | TRUE | 2026-10-12T03:43:01.1904018+00:00 | 2026-10-12T11:43:01.1904018+08:00 | #67887 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-03-08T22:00:00+00:00 | 2027-03-09T10:00:00+00:00 | 2027-03-09T06:00:00+08:00 | 2027-03-09T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67895 | 2025-06-23T08:23:57.4419196+00:00 | 2025-06-23T16:23:57.4419196+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1904843+00:00 | 2026-10-12T11:43:01.1904843+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335800 | TRUE | TRUE | 2026-10-12T03:43:01.1904843+00:00 | 2026-10-12T11:43:01.1904843+08:00 | #67895 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-03-09T22:00:00+00:00 | 2027-03-10T10:00:00+00:00 | 2027-03-10T06:00:00+08:00 | 2027-03-10T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67903 | 2025-06-23T08:25:56.5382047+00:00 | 2025-06-23T16:25:56.5382047+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1904937+00:00 | 2026-10-12T11:43:01.1904937+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335801 | TRUE | TRUE | 2026-10-12T03:43:01.1904937+00:00 | 2026-10-12T11:43:01.1904937+08:00 | #67903 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-03-10T22:00:00+00:00 | 2027-03-11T10:00:00+00:00 | 2027-03-11T06:00:00+08:00 | 2027-03-11T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67888 | 2025-06-23T08:22:01.629388+00:00 | 2025-06-23T16:22:01.629388+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1904992+00:00 | 2026-10-12T11:43:01.1904992+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335802 | TRUE | TRUE | 2026-10-12T03:43:01.1904992+00:00 | 2026-10-12T11:43:01.1904992+08:00 | #67888 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-06-07T22:00:00+00:00 | 2027-06-08T10:00:00+00:00 | 2027-06-08T06:00:00+08:00 | 2027-06-08T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67896 | 2025-06-23T08:23:57.9057991+00:00 | 2025-06-23T16:23:57.9057991+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905047+00:00 | 2026-10-12T11:43:01.1905047+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335803 | TRUE | TRUE | 2026-10-12T03:43:01.1905047+00:00 | 2026-10-12T11:43:01.1905047+08:00 | #67896 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-06-08T22:00:00+00:00 | 2027-06-09T10:00:00+00:00 | 2027-06-09T06:00:00+08:00 | 2027-06-09T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67904 | 2025-06-23T08:25:57.0178393+00:00 | 2025-06-23T16:25:57.0178393+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905114+00:00 | 2026-10-12T11:43:01.1905114+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335804 | TRUE | TRUE | 2026-10-12T03:43:01.1905114+00:00 | 2026-10-12T11:43:01.1905114+08:00 | #67904 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-06-09T22:00:00+00:00 | 2027-06-10T10:00:00+00:00 | 2027-06-10T06:00:00+08:00 | 2027-06-10T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67889 | 2025-06-23T08:22:02.1167503+00:00 | 2025-06-23T16:22:02.1167503+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905199+00:00 | 2026-10-12T11:43:01.1905199+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335805 | TRUE | TRUE | 2026-10-12T03:43:01.1905199+00:00 | 2026-10-12T11:43:01.1905199+08:00 | #67889 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-09-06T22:00:00+00:00 | 2027-09-07T10:00:00+00:00 | 2027-09-07T06:00:00+08:00 | 2027-09-07T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67897 | 2025-06-23T08:23:58.4340101+00:00 | 2025-06-23T16:23:58.4340101+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.190526+00:00 | 2026-10-12T11:43:01.190526+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335806 | TRUE | TRUE | 2026-10-12T03:43:01.190526+00:00 | 2026-10-12T11:43:01.190526+08:00 | #67897 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-09-07T22:00:00+00:00 | 2027-09-08T10:00:00+00:00 | 2027-09-08T06:00:00+08:00 | 2027-09-08T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67905 | 2025-06-23T08:25:57.50796+00:00 | 2025-06-23T16:25:57.50796+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905324+00:00 | 2026-10-12T11:43:01.1905324+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335807 | TRUE | TRUE | 2026-10-12T03:43:01.1905324+00:00 | 2026-10-12T11:43:01.1905324+08:00 | #67905 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-09-08T22:00:00+00:00 | 2027-09-09T10:00:00+00:00 | 2027-09-09T06:00:00+08:00 | 2027-09-09T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67890 | 2025-06-23T08:22:02.5608178+00:00 | 2025-06-23T16:22:02.5608178+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905408+00:00 | 2026-10-12T11:43:01.1905408+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335808 | TRUE | TRUE | 2026-10-12T03:43:01.1905408+00:00 | 2026-10-12T11:43:01.1905408+08:00 | #67890 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-12-06T22:00:00+00:00 | 2027-12-07T10:00:00+00:00 | 2027-12-07T06:00:00+08:00 | 2027-12-07T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67898 | 2025-06-23T08:23:58.921979+00:00 | 2025-06-23T16:23:58.921979+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905492+00:00 | 2026-10-12T11:43:01.1905492+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335809 | TRUE | TRUE | 2026-10-12T03:43:01.1905492+00:00 | 2026-10-12T11:43:01.1905492+08:00 | #67898 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-12-07T22:00:00+00:00 | 2027-12-08T10:00:00+00:00 | 2027-12-08T06:00:00+08:00 | 2027-12-08T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
67906 | 2025-06-23T08:25:57.9827088+00:00 | 2025-06-23T16:25:57.9827088+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-12T03:43:01.1905562+00:00 | 2026-10-12T11:43:01.1905562+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335810 | TRUE | TRUE | 2026-10-12T03:43:01.1905562+00:00 | 2026-10-12T11:43:01.1905562+08:00 | #67906 - YAN: 12hrs - YAN LOOP PLANT | 2.1 | TRUE |  | 2027-12-08T22:00:00+00:00 | 2027-12-09T10:00:00+00:00 | 2027-12-09T06:00:00+08:00 | 2027-12-09T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Site Constraint | YAN | Australia/Perth
69139 | 2025-09-24T02:24:30.1398019+00:00 | 2025-09-24T10:24:30.1398019+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:30:04.9213183+00:00 | 2025-11-03T11:30:04.9213183+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270116 | TRUE | TRUE | 2025-11-03T03:30:04.9213183+00:00 | 2025-11-03T11:30:04.9213183+08:00 | #69139 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-11-07T11:00:00+00:00 | 2027-11-07T15:00:00+00:00 | 2027-11-07T19:00:00+08:00 | 2027-11-07T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69140 | 2025-09-24T02:24:30.5996508+00:00 | 2025-09-24T10:24:30.5996508+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:30:08.8906159+00:00 | 2025-11-03T11:30:08.8906159+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270120 | TRUE | TRUE | 2025-11-03T03:30:08.8906159+00:00 | 2025-11-03T11:30:08.8906159+08:00 | #69140 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-12-19T11:00:00+00:00 | 2027-12-19T15:00:00+00:00 | 2027-12-19T19:00:00+08:00 | 2027-12-19T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69137 | 2025-09-24T02:24:29.2308801+00:00 | 2025-09-24T10:24:29.2308801+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:54.3263707+00:00 | 2025-11-03T11:29:54.3263707+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270106 | TRUE | TRUE | 2025-11-03T03:29:54.3263707+00:00 | 2025-11-03T11:29:54.3263707+08:00 | #69137 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-08-15T11:00:00+00:00 | 2027-08-15T15:00:00+00:00 | 2027-08-15T19:00:00+08:00 | 2027-08-15T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69138 | 2025-09-24T02:24:29.6824181+00:00 | 2025-09-24T10:24:29.6824181+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:58.0408673+00:00 | 2025-11-03T11:29:58.0408673+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270110 | TRUE | TRUE | 2025-11-03T03:29:58.0408673+00:00 | 2025-11-03T11:29:58.0408673+08:00 | #69138 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-09-26T11:00:00+00:00 | 2027-09-26T15:00:00+00:00 | 2027-09-26T19:00:00+08:00 | 2027-09-26T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69135 | 2025-09-24T02:24:28.3310673+00:00 | 2025-09-24T10:24:28.3310673+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:44.5268055+00:00 | 2025-11-03T11:29:44.5268055+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270096 | TRUE | TRUE | 2025-11-03T03:29:44.5268055+00:00 | 2025-11-03T11:29:44.5268055+08:00 | #69135 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-05-23T11:00:00+00:00 | 2027-05-23T15:00:00+00:00 | 2027-05-23T19:00:00+08:00 | 2027-05-23T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69136 | 2025-09-24T02:24:28.7549382+00:00 | 2025-09-24T10:24:28.7549382+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-03T03:29:48.0635556+00:00 | 2025-11-03T11:29:48.0635556+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 270100 | TRUE | TRUE | 2025-11-03T03:29:48.0635556+00:00 | 2025-11-03T11:29:48.0635556+08:00 | #69136 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 1.0 | FALSE |  | 2027-07-04T11:00:00+00:00 | 2027-07-04T15:00:00+00:00 | 2027-07-04T19:00:00+08:00 | 2027-07-04T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. |  |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
69131 | 2025-09-24T02:24:26.629195+00:00 | 2025-09-24T10:24:26.629195+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-10-15T08:23:46.0351888+00:00 | 2025-10-15T16:23:46.0351888+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 257637 | TRUE | TRUE | 2025-10-15T08:23:46.0351888+00:00 | 2025-10-15T16:23:46.0351888+08:00 | #69131 - YAN: 4hrs - YCC201 SPIDER GREASE CHECKS | 2.0 | FALSE |  | 2026-12-06T11:00:00+00:00 | 2026-12-06T15:00:00+00:00 | 2026-12-06T19:00:00+08:00 | 2026-12-06T23:00:00+08:00 |  |  |  |  | 4.00 | 4hrs - YCC201 Spider Grease Check Additional Info: The wet plant will be shut down as we have to isolate the conveyor below to do the grease check on YCC201. The bypass plant will not be ran during this time. | Please remove YANPLTLOOP & YANPLT02 as an equipment item for each of the above shuts in 2026 (and any YCC201 Spider Grease Checks going forward). Jess Stallard |  | [{"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82842 | 2026-06-04T03:08:19.3349758+00:00 | 2026-06-04T11:08:19.3349758+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-06-15T02:35:07.1777549+00:00 | 2026-06-15T10:35:07.1777549+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 327909 | TRUE | TRUE | 2026-06-15T02:35:07.1777549+00:00 | 2026-06-15T10:35:07.1777549+08:00 | #82842 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 1.0 | TRUE |  | 2028-01-20T23:00:00+00:00 | 2028-01-24T23:00:00+00:00 | 2028-01-21T07:00:00+08:00 | 2028-01-25T07:00:00+08:00 |  |  |  |  | 96.00 | 10-4 strategy to run PC1 for 10 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82840 | 2026-06-04T03:08:18.9840278+00:00 | 2026-06-04T11:08:18.9840278+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:06.7585164+00:00 | 2026-10-09T14:32:06.7585164+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335769 | TRUE | TRUE | 2026-10-09T06:32:06.7585164+00:00 | 2026-10-09T14:32:06.7585164+08:00 | #82840 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-12-02T23:00:00+00:00 | 2027-12-06T23:00:00+00:00 | 2027-12-03T07:00:00+08:00 | 2027-12-07T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82839 | 2026-06-04T03:08:18.8148658+00:00 | 2026-06-04T11:08:18.8148658+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:06.9430598+00:00 | 2026-10-09T14:32:06.9430598+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335770 | TRUE | TRUE | 2026-10-09T06:32:06.9430598+00:00 | 2026-10-09T14:32:06.9430598+08:00 | #82839 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-11-04T23:00:00+00:00 | 2027-11-08T23:00:00+00:00 | 2027-11-05T07:00:00+08:00 | 2027-11-09T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82837 | 2026-06-04T03:08:18.4855628+00:00 | 2026-06-04T11:08:18.4855628+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:07.1242963+00:00 | 2026-10-09T14:32:07.1242963+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335771 | TRUE | TRUE | 2026-10-09T06:32:07.1242963+00:00 | 2026-10-09T14:32:07.1242963+08:00 | #82837 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-09-09T23:00:00+00:00 | 2027-09-13T23:00:00+00:00 | 2027-09-10T07:00:00+08:00 | 2027-09-14T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82836 | 2026-06-04T03:08:18.3164953+00:00 | 2026-06-04T11:08:18.3164953+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:07.3093575+00:00 | 2026-10-09T14:32:07.3093575+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335772 | TRUE | TRUE | 2026-10-09T06:32:07.3093575+00:00 | 2026-10-09T14:32:07.3093575+08:00 | #82836 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-08-12T23:00:00+00:00 | 2027-08-16T23:00:00+00:00 | 2027-08-13T07:00:00+08:00 | 2027-08-17T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82835 | 2026-06-04T03:08:18.1476403+00:00 | 2026-06-04T11:08:18.1476403+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:07.5024332+00:00 | 2026-10-09T14:32:07.5024332+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335773 | TRUE | TRUE | 2026-10-09T06:32:07.5024332+00:00 | 2026-10-09T14:32:07.5024332+08:00 | #82835 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-07-15T23:00:00+00:00 | 2027-07-19T23:00:00+00:00 | 2027-07-16T07:00:00+08:00 | 2027-07-20T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82833 | 2026-06-04T03:08:17.83196+00:00 | 2026-06-04T11:08:17.83196+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:07.6923156+00:00 | 2026-10-09T14:32:07.6923156+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335774 | TRUE | TRUE | 2026-10-09T06:32:07.6923156+00:00 | 2026-10-09T14:32:07.6923156+08:00 | #82833 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-05-20T23:00:00+00:00 | 2027-05-24T23:00:00+00:00 | 2027-05-21T07:00:00+08:00 | 2027-05-25T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82832 | 2026-06-04T03:08:17.665569+00:00 | 2026-06-04T11:08:17.665569+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:07.8918463+00:00 | 2026-10-09T14:32:07.8918463+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335775 | TRUE | TRUE | 2026-10-09T06:32:07.8918463+00:00 | 2026-10-09T14:32:07.8918463+08:00 | #82832 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-04-22T23:00:00+00:00 | 2027-04-26T23:00:00+00:00 | 2027-04-23T07:00:00+08:00 | 2027-04-27T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82829 | 2026-06-04T03:08:17.1969688+00:00 | 2026-06-04T11:08:17.1969688+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-09T06:32:08.1304064+00:00 | 2026-10-09T14:32:08.1304064+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335776 | TRUE | TRUE | 2026-10-09T06:32:08.1304064+00:00 | 2026-10-09T14:32:08.1304064+08:00 | #82829 - YAN: 96hrs - PC1 - MONTHLY 96HR OUTAGE | 2.0 | TRUE |  | 2027-01-28T23:00:00+00:00 | 2027-02-01T23:00:00+00:00 | 2027-01-29T07:00:00+08:00 | 2027-02-02T07:00:00+08:00 |  |  |  |  | 96.00 | 26/4 strategy to run PC1 for 26 days and have 4 days down for maintenance. No SOP impact as this will be accounted for in 2-week plan FXP leadership team + MTS are across this strategy. | Realign the outages due to the extra week in 2026. WK3 PC1 outage and move to week 4 away from the loop shut and then continue with the rest for 2027. Darren Bray |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "18ce3fc8-6f66-4105-97f2-3bdf2eee5e31", "emailAddress": "Paul.Jennings2@riotinto.com", "displayName": "Paul Jennings"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84182 | 2026-10-05T04:21:51.2738489+00:00 | 2026-10-05T12:21:51.2738489+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:16.7302881+00:00 | 2026-10-05T19:05:16.7302881+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335312 | TRUE | TRUE | 2026-10-05T11:05:16.7302881+00:00 | 2026-10-05T19:05:16.7302881+08:00 | #84182 - YAN: 1hrs - YBN31 CLOSE KNIFE GATE | 1.0 | TRUE |  | 2027-03-04T11:00:00+00:00 | 2027-03-04T12:00:00+00:00 | 2027-03-04T19:00:00+08:00 | 2027-03-04T20:00:00+08:00 |  |  |  |  | 1.00 | YBN31 CLOSE KNIFE GATE |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84184 | 2026-10-05T04:56:59.8436745+00:00 | 2026-10-05T12:56:59.8436745+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:16.94857+00:00 | 2026-10-05T19:05:16.94857+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335313 | TRUE | TRUE | 2026-10-05T11:05:16.94857+00:00 | 2026-10-05T19:05:16.94857+08:00 | #84184 - YAN: 1hrs - YBN31 OPEN KNIFE GATE | 1.0 | TRUE |  | 2027-03-16T11:00:00+00:00 | 2027-03-16T12:00:00+00:00 | 2027-03-16T19:00:00+08:00 | 2027-03-16T20:00:00+08:00 |  |  |  |  | 1.00 | YBN31 OPEN KNIFE GATE |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
67913 | 2025-06-23T08:33:50.4807167+00:00 | 2025-06-23T16:33:50.4807167+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:17.6147131+00:00 | 2026-10-05T19:05:17.6147131+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335316 | TRUE | TRUE | 2026-10-05T11:05:17.6147131+00:00 | 2026-10-05T19:05:17.6147131+08:00 | #67913 - YAN: 1hrs - YBN31 CLOSE KNIFE GATE | 2.0 | TRUE |  | 2027-08-27T11:00:00+00:00 | 2027-08-27T12:00:00+00:00 | 2027-08-27T19:00:00+08:00 | 2027-08-27T20:00:00+08:00 |  |  |  |  | 1.00 | STK 2 Prep Bin 31 Gate close. | Shut Schedulers requested date amendments |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84186 | 2026-10-05T04:59:42.532483+00:00 | 2026-10-05T12:59:42.532483+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:17.8630232+00:00 | 2026-10-05T19:05:17.8630232+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335317 | TRUE | TRUE | 2026-10-05T11:05:17.8630232+00:00 | 2026-10-05T19:05:17.8630232+08:00 | #84186 - YAN: 1hrs - YBN31 OPEN KNIFE GATE | 1.0 | TRUE |  | 2027-08-31T22:00:00+00:00 | 2027-08-31T23:00:00+00:00 | 2027-09-01T06:00:00+08:00 | 2027-09-01T07:00:00+08:00 |  |  |  |  | 1.00 | YBN31 OPEN KNIFE GATE |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
67914 | 2025-06-23T08:33:50.9103461+00:00 | 2025-06-23T16:33:50.9103461+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:18.1084907+00:00 | 2026-10-05T19:05:18.1084907+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335318 | TRUE | TRUE | 2026-10-05T11:05:18.1084907+00:00 | 2026-10-05T19:05:18.1084907+08:00 | #67914 - YAN: 1hrs - YBN31 CLOSE KNIFE GATE | 2.0 | TRUE |  | 2027-11-26T11:00:00+00:00 | 2027-11-26T12:00:00+00:00 | 2027-11-26T19:00:00+08:00 | 2027-11-26T20:00:00+08:00 |  |  |  |  | 1.00 | STK 2 Prep Bin 31 Gate close. | Amending current shut - updated title |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84187 | 2026-10-05T05:00:27.3248728+00:00 | 2026-10-05T13:00:27.3248728+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-05T11:05:18.3629362+00:00 | 2026-10-05T19:05:18.3629362+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335319 | TRUE | TRUE | 2026-10-05T11:05:18.3629362+00:00 | 2026-10-05T19:05:18.3629362+08:00 | #84187 - YAN: 1hrs - YBN31 OPEN KNIFE GATE | 1.0 | TRUE |  | 2027-11-30T22:00:00+00:00 | 2027-11-30T23:00:00+00:00 | 2027-12-01T06:00:00+08:00 | 2027-12-01T07:00:00+08:00 |  |  |  |  | 1.00 | YBN31 OPEN KNIFE GATE |  |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
67822 | 2025-06-19T13:12:45.0372275+00:00 | 2025-06-19T21:12:45.0372275+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-06-03T02:04:25.051074+00:00 | 2026-06-03T10:04:25.051074+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 327139 | TRUE | TRUE | 2026-06-03T02:04:25.051074+00:00 | 2026-06-03T10:04:25.051074+08:00 | #67822 - YAN: 12hrs - RECLAIMER: YAN 01 | 3.0 | FALSE |  | 2027-01-10T16:00:00+00:00 | 2027-01-11T04:00:00+00:00 | 2027-01-11T00:00:00+08:00 | 2027-01-11T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection | Incorrectly moved with IAM refresh |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75997 | 2026-02-25T03:05:50.2066919+00:00 | 2026-02-25T11:05:50.2066919+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-27T01:23:19.7575907+00:00 | 2026-02-27T09:23:19.7575907+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 289899 | TRUE | TRUE | 2026-02-27T01:23:19.7575907+00:00 | 2026-02-27T09:23:19.7575907+08:00 | #75997 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2028-01-30T02:00:00+00:00 | 2028-01-30T05:00:00+00:00 | 2028-01-30T10:00:00+08:00 | 2028-01-30T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75996 | 2026-02-25T03:05:49.7528638+00:00 | 2026-02-25T11:05:49.7528638+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-27T01:23:20.3620344+00:00 | 2026-02-27T09:23:20.3620344+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 289900 | TRUE | TRUE | 2026-02-27T01:23:20.3620344+00:00 | 2026-02-27T09:23:20.3620344+08:00 | #75996 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2028-01-16T02:00:00+00:00 | 2028-01-16T05:00:00+00:00 | 2028-01-16T10:00:00+08:00 | 2028-01-16T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75995 | 2026-02-25T03:05:48.9319289+00:00 | 2026-02-25T11:05:48.9319289+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-27T01:23:20.953702+00:00 | 2026-02-27T09:23:20.953702+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 289901 | TRUE | TRUE | 2026-02-27T01:23:20.953702+00:00 | 2026-02-27T09:23:20.953702+08:00 | #75995 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2028-01-02T02:00:00+00:00 | 2028-01-02T05:00:00+00:00 | 2028-01-02T10:00:00+08:00 | 2028-01-02T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
73230 | 2025-11-12T03:23:15.6632562+00:00 | 2025-11-12T11:23:15.6632562+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-12T03:23:16.0861876+00:00 | 2025-11-12T11:23:16.0861876+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 274537 | TRUE | TRUE | 2025-11-12T03:23:16.0861876+00:00 | 2025-11-12T11:23:16.0861876+08:00 | #73230 - YAN: 96hrs - SCRUBBER: YAN 301 | 1.0 | FALSE |  | 2027-05-27T11:00:00+00:00 | 2027-05-31T11:00:00+00:00 | 2027-05-27T19:00:00+08:00 | 2027-05-31T19:00:00+08:00 |  |  |  |  | 96.00 | JSE Modular 301 |  |  | [{"equipmentGUID": "2622f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB301", "name": "Scrubber: YAN 301", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
73231 | 2025-11-12T03:23:16.1621916+00:00 | 2025-11-12T11:23:16.1621916+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-12T03:23:16.3216558+00:00 | 2025-11-12T11:23:16.3216558+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 274539 | TRUE | TRUE | 2025-11-12T03:23:16.3216558+00:00 | 2025-11-12T11:23:16.3216558+08:00 | #73231 - YAN: 96hrs - SCRUBBER: YAN 302 | 1.0 | FALSE |  | 2027-06-03T11:00:00+00:00 | 2027-06-07T11:00:00+00:00 | 2027-06-03T19:00:00+08:00 | 2027-06-07T19:00:00+08:00 |  |  |  |  | 96.00 | JSE Modular 302 |  |  | [{"equipmentGUID": "a0d200c0-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB302", "name": "Scrubber: YAN 302", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
73232 | 2025-11-12T03:23:16.3970446+00:00 | 2025-11-12T11:23:16.3970446+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-12T03:23:16.5612912+00:00 | 2025-11-12T11:23:16.5612912+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 274541 | TRUE | TRUE | 2025-11-12T03:23:16.5612912+00:00 | 2025-11-12T11:23:16.5612912+08:00 | #73232 - YAN: 96hrs - SCRUBBER: YAN 303 | 1.0 | FALSE |  | 2027-06-10T11:00:00+00:00 | 2027-06-14T11:00:00+00:00 | 2027-06-10T19:00:00+08:00 | 2027-06-14T19:00:00+08:00 |  |  |  |  | 96.00 | JSE Modular 303 |  |  | [{"equipmentGUID": "7efbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB303", "name": "Scrubber: YAN 303", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
73234 | 2025-11-12T03:23:16.8800934+00:00 | 2025-11-12T11:23:16.8800934+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-12T03:23:17.0510422+00:00 | 2025-11-12T11:23:17.0510422+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 274545 | TRUE | TRUE | 2025-11-12T03:23:17.0510422+00:00 | 2025-11-12T11:23:17.0510422+08:00 | #73234 - YAN: 96hrs - SCRUBBER: YAN 302 | 1.0 | FALSE |  | 2027-12-02T11:00:00+00:00 | 2027-12-06T11:00:00+00:00 | 2027-12-02T19:00:00+08:00 | 2027-12-06T19:00:00+08:00 |  |  |  |  | 96.00 | JSE Modular 302 |  |  | [{"equipmentGUID": "a0d200c0-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB302", "name": "Scrubber: YAN 302", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
73235 | 2025-11-12T03:23:17.1340791+00:00 | 2025-11-12T11:23:17.1340791+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-12T03:23:17.3007642+00:00 | 2025-11-12T11:23:17.3007642+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 274547 | TRUE | TRUE | 2025-11-12T03:23:17.3007642+00:00 | 2025-11-12T11:23:17.3007642+08:00 | #73235 - YAN: 96hrs - SCRUBBER: YAN 303 | 1.0 | FALSE |  | 2027-12-09T11:00:00+00:00 | 2027-12-13T11:00:00+00:00 | 2027-12-09T19:00:00+08:00 | 2027-12-13T19:00:00+08:00 |  |  |  |  | 96.00 | JSE Modular 303 |  |  | [{"equipmentGUID": "7efbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANSCB303", "name": "Scrubber: YAN 303", "assetClass": {"name": "Scrubber"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82826 | 2026-06-04T03:04:24.4270838+00:00 | 2026-06-04T11:04:24.4270838+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:38.3727177+00:00 | 2026-09-30T16:06:38.3727177+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334716 | TRUE | TRUE | 2026-09-30T08:06:38.3727177+00:00 | 2026-09-30T16:06:38.3727177+08:00 | #82826 - YAN: 72hrs - YCC202 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-10-08T10:00:00+00:00 | 2027-10-11T10:00:00+00:00 | 2027-10-08T18:00:00+08:00 | 2027-10-11T18:00:00+08:00 |  |  |  |  | 72.00 | YCC202 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds |  | [{"equipmentGUID": "e374fbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS202", "name": "Crusher - Tertiary: YAN 202 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82821 | 2026-06-04T02:59:45.1247949+00:00 | 2026-06-04T10:59:45.1247949+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:38.5498216+00:00 | 2026-09-30T16:06:38.5498216+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334717 | TRUE | TRUE | 2026-09-30T08:06:38.5498216+00:00 | 2026-09-30T16:06:38.5498216+08:00 | #82821 - YAN: 72hrs - YCC206 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-09-24T10:00:00+00:00 | 2027-09-27T10:00:00+00:00 | 2027-09-24T18:00:00+08:00 | 2027-09-27T18:00:00+08:00 |  |  |  |  | 72.00 | YCC206 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds |  | [{"equipmentGUID": "f032f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS206", "name": "Crusher - Tertiary: YAN 206 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82825 | 2026-06-04T03:04:24.2825415+00:00 | 2026-06-04T11:04:24.2825415+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:38.7150086+00:00 | 2026-09-30T16:06:38.7150086+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334718 | TRUE | TRUE | 2026-09-30T08:06:38.7150086+00:00 | 2026-09-30T16:06:38.7150086+08:00 | #82825 - YAN: 72hrs - YCC202 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-07-09T10:00:00+00:00 | 2027-07-12T10:00:00+00:00 | 2027-07-09T18:00:00+08:00 | 2027-07-12T18:00:00+08:00 |  |  |  |  | 72.00 | YCC202 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds |  | [{"equipmentGUID": "e374fbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS202", "name": "Crusher - Tertiary: YAN 202 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82820 | 2026-06-04T02:59:44.991046+00:00 | 2026-06-04T10:59:44.991046+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:38.8759317+00:00 | 2026-09-30T16:06:38.8759317+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334719 | TRUE | TRUE | 2026-09-30T08:06:38.8759317+00:00 | 2026-09-30T16:06:38.8759317+08:00 | #82820 - YAN: 72hrs - YCC206 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-06-25T10:00:00+00:00 | 2027-06-28T10:00:00+00:00 | 2027-06-25T18:00:00+08:00 | 2027-06-28T18:00:00+08:00 |  |  |  |  | 72.00 | YCC206 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds. |  | [{"equipmentGUID": "f032f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS206", "name": "Crusher - Tertiary: YAN 206 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82824 | 2026-06-04T03:04:24.1443612+00:00 | 2026-06-04T11:04:24.1443612+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:39.0797847+00:00 | 2026-09-30T16:06:39.0797847+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334720 | TRUE | TRUE | 2026-09-30T08:06:39.0797847+00:00 | 2026-09-30T16:06:39.0797847+08:00 | #82824 - YAN: 72hrs - YCC202 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-04-09T10:00:00+00:00 | 2027-04-12T10:00:00+00:00 | 2027-04-09T18:00:00+08:00 | 2027-04-12T18:00:00+08:00 |  |  |  |  | 72.00 | YCC202 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds. |  | [{"equipmentGUID": "e374fbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS202", "name": "Crusher - Tertiary: YAN 202 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
82819 | 2026-06-04T02:59:44.8584741+00:00 | 2026-06-04T10:59:44.8584741+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-09-30T08:06:39.2473284+00:00 | 2026-09-30T16:06:39.2473284+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334721 | TRUE | TRUE | 2026-09-30T08:06:39.2473284+00:00 | 2026-09-30T16:06:39.2473284+08:00 | #82819 - YAN: 72hrs - YCC206 LOOP CRUSHER MODS | 3.0 | FALSE |  | 2027-03-26T10:00:00+00:00 | 2027-03-29T10:00:00+00:00 | 2027-03-26T18:00:00+08:00 | 2027-03-29T18:00:00+08:00 |  |  |  |  | 72.00 | YCC206 Loop Crusher Mods | Typically we will have a crusher shut 2 and 4 weeks prior to Loop this gives adequate time between shuts for head and bowl rebuilds. |  | [{"equipmentGUID": "f032f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS206", "name": "Crusher - Tertiary: YAN 206 Loop Plant", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74493 | 2025-12-09T23:33:37.3555331+00:00 | 2025-12-10T07:33:37.3555331+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:51.6608957+00:00 | 2026-02-02T12:48:51.6608957+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285485 | TRUE | TRUE | 2026-02-02T04:48:51.6608957+00:00 | 2026-02-02T12:48:51.6608957+08:00 | #74493 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-12-19T02:00:00+00:00 | 2027-12-19T05:00:00+00:00 | 2027-12-19T10:00:00+08:00 | 2027-12-19T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74492 | 2025-12-09T23:33:36.8453966+00:00 | 2025-12-10T07:33:36.8453966+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:52.4955727+00:00 | 2026-02-02T12:48:52.4955727+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285486 | TRUE | TRUE | 2026-02-02T04:48:52.4955727+00:00 | 2026-02-02T12:48:52.4955727+08:00 | #74492 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-12-05T02:00:00+00:00 | 2027-12-05T05:00:00+00:00 | 2027-12-05T10:00:00+08:00 | 2027-12-05T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74491 | 2025-12-09T23:33:36.3397733+00:00 | 2025-12-10T07:33:36.3397733+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:53.2736441+00:00 | 2026-02-02T12:48:53.2736441+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285487 | TRUE | TRUE | 2026-02-02T04:48:53.2736441+00:00 | 2026-02-02T12:48:53.2736441+08:00 | #74491 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-11-21T02:00:00+00:00 | 2027-11-21T05:00:00+00:00 | 2027-11-21T10:00:00+08:00 | 2027-11-21T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74490 | 2025-12-09T23:33:35.8393657+00:00 | 2025-12-10T07:33:35.8393657+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:54.0320371+00:00 | 2026-02-02T12:48:54.0320371+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285488 | TRUE | TRUE | 2026-02-02T04:48:54.0320371+00:00 | 2026-02-02T12:48:54.0320371+08:00 | #74490 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-11-07T02:00:00+00:00 | 2027-11-07T05:00:00+00:00 | 2027-11-07T10:00:00+08:00 | 2027-11-07T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74489 | 2025-12-09T23:33:35.3368191+00:00 | 2025-12-10T07:33:35.3368191+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:54.7860876+00:00 | 2026-02-02T12:48:54.7860876+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285489 | TRUE | TRUE | 2026-02-02T04:48:54.7860876+00:00 | 2026-02-02T12:48:54.7860876+08:00 | #74489 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-10-24T02:00:00+00:00 | 2027-10-24T05:00:00+00:00 | 2027-10-24T10:00:00+08:00 | 2027-10-24T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74488 | 2025-12-09T23:33:34.8361249+00:00 | 2025-12-10T07:33:34.8361249+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:55.7679813+00:00 | 2026-02-02T12:48:55.7679813+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285490 | TRUE | TRUE | 2026-02-02T04:48:55.7679813+00:00 | 2026-02-02T12:48:55.7679813+08:00 | #74488 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-10-10T02:00:00+00:00 | 2027-10-10T05:00:00+00:00 | 2027-10-10T10:00:00+08:00 | 2027-10-10T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74487 | 2025-12-09T23:33:34.3171764+00:00 | 2025-12-10T07:33:34.3171764+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:56.5855326+00:00 | 2026-02-02T12:48:56.5855326+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285491 | TRUE | TRUE | 2026-02-02T04:48:56.5855326+00:00 | 2026-02-02T12:48:56.5855326+08:00 | #74487 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-09-26T02:00:00+00:00 | 2027-09-26T05:00:00+00:00 | 2027-09-26T10:00:00+08:00 | 2027-09-26T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74486 | 2025-12-09T23:33:33.8158878+00:00 | 2025-12-10T07:33:33.8158878+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:57.3655229+00:00 | 2026-02-02T12:48:57.3655229+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285492 | TRUE | TRUE | 2026-02-02T04:48:57.3655229+00:00 | 2026-02-02T12:48:57.3655229+08:00 | #74486 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-09-12T02:00:00+00:00 | 2027-09-12T05:00:00+00:00 | 2027-09-12T10:00:00+08:00 | 2027-09-12T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74485 | 2025-12-09T23:33:33.3169142+00:00 | 2025-12-10T07:33:33.3169142+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:58.1732166+00:00 | 2026-02-02T12:48:58.1732166+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285493 | TRUE | TRUE | 2026-02-02T04:48:58.1732166+00:00 | 2026-02-02T12:48:58.1732166+08:00 | #74485 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-08-29T02:00:00+00:00 | 2027-08-29T05:00:00+00:00 | 2027-08-29T10:00:00+08:00 | 2027-08-29T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74484 | 2025-12-09T23:33:32.8210736+00:00 | 2025-12-10T07:33:32.8210736+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:48:59.0338936+00:00 | 2026-02-02T12:48:59.0338936+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285494 | TRUE | TRUE | 2026-02-02T04:48:59.0338936+00:00 | 2026-02-02T12:48:59.0338936+08:00 | #74484 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-08-15T02:00:00+00:00 | 2027-08-15T05:00:00+00:00 | 2027-08-15T10:00:00+08:00 | 2027-08-15T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74483 | 2025-12-09T23:33:32.3129281+00:00 | 2025-12-10T07:33:32.3129281+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:00.884037+00:00 | 2026-02-02T12:49:00.884037+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285495 | TRUE | TRUE | 2026-02-02T04:49:00.884037+00:00 | 2026-02-02T12:49:00.884037+08:00 | #74483 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-08-01T02:00:00+00:00 | 2027-08-01T05:00:00+00:00 | 2027-08-01T10:00:00+08:00 | 2027-08-01T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74482 | 2025-12-09T23:33:31.8102252+00:00 | 2025-12-10T07:33:31.8102252+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:01.6882245+00:00 | 2026-02-02T12:49:01.6882245+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285496 | TRUE | TRUE | 2026-02-02T04:49:01.6882245+00:00 | 2026-02-02T12:49:01.6882245+08:00 | #74482 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-07-18T02:00:00+00:00 | 2027-07-18T05:00:00+00:00 | 2027-07-18T10:00:00+08:00 | 2027-07-18T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74481 | 2025-12-09T23:33:31.3054638+00:00 | 2025-12-10T07:33:31.3054638+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:02.515615+00:00 | 2026-02-02T12:49:02.515615+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285497 | TRUE | TRUE | 2026-02-02T04:49:02.515615+00:00 | 2026-02-02T12:49:02.515615+08:00 | #74481 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-07-04T02:00:00+00:00 | 2027-07-04T05:00:00+00:00 | 2027-07-04T10:00:00+08:00 | 2027-07-04T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74480 | 2025-12-09T23:33:30.8016987+00:00 | 2025-12-10T07:33:30.8016987+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:03.3279749+00:00 | 2026-02-02T12:49:03.3279749+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285498 | TRUE | TRUE | 2026-02-02T04:49:03.3279749+00:00 | 2026-02-02T12:49:03.3279749+08:00 | #74480 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-06-20T02:00:00+00:00 | 2027-06-20T05:00:00+00:00 | 2027-06-20T10:00:00+08:00 | 2027-06-20T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74479 | 2025-12-09T23:33:30.3132912+00:00 | 2025-12-10T07:33:30.3132912+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:04.1468796+00:00 | 2026-02-02T12:49:04.1468796+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285499 | TRUE | TRUE | 2026-02-02T04:49:04.1468796+00:00 | 2026-02-02T12:49:04.1468796+08:00 | #74479 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-06-06T02:00:00+00:00 | 2027-06-06T05:00:00+00:00 | 2027-06-06T10:00:00+08:00 | 2027-06-06T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74478 | 2025-12-09T23:33:29.8241756+00:00 | 2025-12-10T07:33:29.8241756+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:04.9910305+00:00 | 2026-02-02T12:49:04.9910305+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285500 | TRUE | TRUE | 2026-02-02T04:49:04.9910305+00:00 | 2026-02-02T12:49:04.9910305+08:00 | #74478 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-05-23T02:00:00+00:00 | 2027-05-23T05:00:00+00:00 | 2027-05-23T10:00:00+08:00 | 2027-05-23T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74477 | 2025-12-09T23:33:28.8836718+00:00 | 2025-12-10T07:33:28.8836718+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:05.8641463+00:00 | 2026-02-02T12:49:05.8641463+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285501 | TRUE | TRUE | 2026-02-02T04:49:05.8641463+00:00 | 2026-02-02T12:49:05.8641463+08:00 | #74477 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-05-09T02:00:00+00:00 | 2027-05-09T05:00:00+00:00 | 2027-05-09T10:00:00+08:00 | 2027-05-09T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74475 | 2025-12-09T23:33:27.9318976+00:00 | 2025-12-10T07:33:27.9318976+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:07.5134919+00:00 | 2026-02-02T12:49:07.5134919+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285503 | TRUE | TRUE | 2026-02-02T04:49:07.5134919+00:00 | 2026-02-02T12:49:07.5134919+08:00 | #74475 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-04-11T02:00:00+00:00 | 2027-04-11T05:00:00+00:00 | 2027-04-11T10:00:00+08:00 | 2027-04-11T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74474 | 2025-12-09T23:33:27.4581058+00:00 | 2025-12-10T07:33:27.4581058+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:08.3898433+00:00 | 2026-02-02T12:49:08.3898433+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285504 | TRUE | TRUE | 2026-02-02T04:49:08.3898433+00:00 | 2026-02-02T12:49:08.3898433+08:00 | #74474 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-03-28T02:00:00+00:00 | 2027-03-28T05:00:00+00:00 | 2027-03-28T10:00:00+08:00 | 2027-03-28T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74473 | 2025-12-09T23:33:26.9917342+00:00 | 2025-12-10T07:33:26.9917342+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:09.2234835+00:00 | 2026-02-02T12:49:09.2234835+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285505 | TRUE | TRUE | 2026-02-02T04:49:09.2234835+00:00 | 2026-02-02T12:49:09.2234835+08:00 | #74473 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-03-14T02:00:00+00:00 | 2027-03-14T05:00:00+00:00 | 2027-03-14T10:00:00+08:00 | 2027-03-14T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74472 | 2025-12-09T23:33:26.4870135+00:00 | 2025-12-10T07:33:26.4870135+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:10.3633402+00:00 | 2026-02-02T12:49:10.3633402+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285506 | TRUE | TRUE | 2026-02-02T04:49:10.3633402+00:00 | 2026-02-02T12:49:10.3633402+08:00 | #74472 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-02-28T02:00:00+00:00 | 2027-02-28T05:00:00+00:00 | 2027-02-28T10:00:00+08:00 | 2027-02-28T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74471 | 2025-12-09T23:33:26.0079303+00:00 | 2025-12-10T07:33:26.0079303+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:11.438271+00:00 | 2026-02-02T12:49:11.438271+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285507 | TRUE | TRUE | 2026-02-02T04:49:11.438271+00:00 | 2026-02-02T12:49:11.438271+08:00 | #74471 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-02-14T02:00:00+00:00 | 2027-02-14T05:00:00+00:00 | 2027-02-14T10:00:00+08:00 | 2027-02-14T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74470 | 2025-12-09T23:33:25.5259904+00:00 | 2025-12-10T07:33:25.5259904+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:12.3684294+00:00 | 2026-02-02T12:49:12.3684294+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285508 | TRUE | TRUE | 2026-02-02T04:49:12.3684294+00:00 | 2026-02-02T12:49:12.3684294+08:00 | #74470 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-01-31T02:00:00+00:00 | 2027-01-31T05:00:00+00:00 | 2027-01-31T10:00:00+08:00 | 2027-01-31T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74469 | 2025-12-09T23:33:24.7750966+00:00 | 2025-12-10T07:33:24.7750966+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:13.2919349+00:00 | 2026-02-02T12:49:13.2919349+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285509 | TRUE | TRUE | 2026-02-02T04:49:13.2919349+00:00 | 2026-02-02T12:49:13.2919349+08:00 | #74469 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 1.0 | TRUE |  | 2027-01-17T02:00:00+00:00 | 2027-01-17T05:00:00+00:00 | 2027-01-17T10:00:00+08:00 | 2027-01-17T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance |  |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
67849 | 2025-06-19T13:21:47.5356358+00:00 | 2025-06-19T21:21:47.5356358+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:49:14.1636009+00:00 | 2026-02-02T12:49:14.1636009+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285510 | TRUE | TRUE | 2026-02-02T04:49:14.1636009+00:00 | 2026-02-02T12:49:14.1636009+08:00 | #67849 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 4.0 | TRUE |  | 2027-01-03T02:00:00+00:00 | 2027-01-03T05:00:00+00:00 | 2027-01-03T10:00:00+08:00 | 2027-01-03T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop, Additional Info: 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance | Bringing forward due to the Week 53 2026 |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74520 | 2025-12-10T01:09:17.9190173+00:00 | 2025-12-10T09:09:17.9190173+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:08.5260869+00:00 | 2026-02-02T12:50:08.5260869+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285511 | TRUE | TRUE | 2026-02-02T04:50:08.5260869+00:00 | 2026-02-02T12:50:08.5260869+08:00 | #74520 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-12-26T16:00:00+00:00 | 2027-12-27T04:00:00+00:00 | 2027-12-27T00:00:00+08:00 | 2027-12-27T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74545 | 2025-12-10T01:17:20.449987+00:00 | 2025-12-10T09:17:20.449987+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:09.2481481+00:00 | 2026-02-02T12:50:09.2481481+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285512 | TRUE | TRUE | 2026-02-02T04:50:09.2481481+00:00 | 2026-02-02T12:50:09.2481481+08:00 | #74545 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-12-19T16:00:00+00:00 | 2027-12-20T04:00:00+00:00 | 2027-12-20T00:00:00+08:00 | 2027-12-20T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74519 | 2025-12-10T01:09:17.4094526+00:00 | 2025-12-10T09:09:17.4094526+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:09.9473326+00:00 | 2026-02-02T12:50:09.9473326+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285513 | TRUE | TRUE | 2026-02-02T04:50:09.9473326+00:00 | 2026-02-02T12:50:09.9473326+08:00 | #74519 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-12-12T16:00:00+00:00 | 2027-12-13T04:00:00+00:00 | 2027-12-13T00:00:00+08:00 | 2027-12-13T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74544 | 2025-12-10T01:17:19.7757998+00:00 | 2025-12-10T09:17:19.7757998+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:10.6903451+00:00 | 2026-02-02T12:50:10.6903451+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285514 | TRUE | TRUE | 2026-02-02T04:50:10.6903451+00:00 | 2026-02-02T12:50:10.6903451+08:00 | #74544 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-12-05T16:00:00+00:00 | 2027-12-06T04:00:00+00:00 | 2027-12-06T00:00:00+08:00 | 2027-12-06T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74518 | 2025-12-10T01:09:16.9023932+00:00 | 2025-12-10T09:09:16.9023932+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:11.4579956+00:00 | 2026-02-02T12:50:11.4579956+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285515 | TRUE | TRUE | 2026-02-02T04:50:11.4579956+00:00 | 2026-02-02T12:50:11.4579956+08:00 | #74518 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-11-28T16:00:00+00:00 | 2027-11-29T04:00:00+00:00 | 2027-11-29T00:00:00+08:00 | 2027-11-29T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74543 | 2025-12-10T01:17:19.2525066+00:00 | 2025-12-10T09:17:19.2525066+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:12.2856492+00:00 | 2026-02-02T12:50:12.2856492+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285516 | TRUE | TRUE | 2026-02-02T04:50:12.2856492+00:00 | 2026-02-02T12:50:12.2856492+08:00 | #74543 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-11-21T16:00:00+00:00 | 2027-11-22T04:00:00+00:00 | 2027-11-22T00:00:00+08:00 | 2027-11-22T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74517 | 2025-12-10T01:09:16.406844+00:00 | 2025-12-10T09:09:16.406844+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:13.0550499+00:00 | 2026-02-02T12:50:13.0550499+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285517 | TRUE | TRUE | 2026-02-02T04:50:13.0550499+00:00 | 2026-02-02T12:50:13.0550499+08:00 | #74517 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-11-14T16:00:00+00:00 | 2027-11-15T04:00:00+00:00 | 2027-11-15T00:00:00+08:00 | 2027-11-15T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74542 | 2025-12-10T01:17:18.7246277+00:00 | 2025-12-10T09:17:18.7246277+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:13.9199786+00:00 | 2026-02-02T12:50:13.9199786+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285518 | TRUE | TRUE | 2026-02-02T04:50:13.9199786+00:00 | 2026-02-02T12:50:13.9199786+08:00 | #74542 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-11-07T16:00:00+00:00 | 2027-11-08T04:00:00+00:00 | 2027-11-08T00:00:00+08:00 | 2027-11-08T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74516 | 2025-12-10T01:09:15.9079638+00:00 | 2025-12-10T09:09:15.9079638+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:14.7425772+00:00 | 2026-02-02T12:50:14.7425772+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285519 | TRUE | TRUE | 2026-02-02T04:50:14.7425772+00:00 | 2026-02-02T12:50:14.7425772+08:00 | #74516 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-10-31T16:00:00+00:00 | 2027-11-01T04:00:00+00:00 | 2027-11-01T00:00:00+08:00 | 2027-11-01T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74510 | 2025-12-10T01:09:12.9282863+00:00 | 2025-12-10T09:09:12.9282863+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:24.8951021+00:00 | 2026-02-02T12:50:24.8951021+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285531 | TRUE | TRUE | 2026-02-02T04:50:24.8951021+00:00 | 2026-02-02T12:50:24.8951021+08:00 | #74510 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-08-08T16:00:00+00:00 | 2027-08-09T04:00:00+00:00 | 2027-08-09T00:00:00+08:00 | 2027-08-09T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74535 | 2025-12-10T01:17:15.0353889+00:00 | 2025-12-10T09:17:15.0353889+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:25.7601071+00:00 | 2026-02-02T12:50:25.7601071+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285532 | TRUE | TRUE | 2026-02-02T04:50:25.7601071+00:00 | 2026-02-02T12:50:25.7601071+08:00 | #74535 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-08-01T16:00:00+00:00 | 2027-08-02T04:00:00+00:00 | 2027-08-02T00:00:00+08:00 | 2027-08-02T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74509 | 2025-12-10T01:09:12.459403+00:00 | 2025-12-10T09:09:12.459403+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:26.6377435+00:00 | 2026-02-02T12:50:26.6377435+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285533 | TRUE | TRUE | 2026-02-02T04:50:26.6377435+00:00 | 2026-02-02T12:50:26.6377435+08:00 | #74509 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-07-25T16:00:00+00:00 | 2027-07-26T04:00:00+00:00 | 2027-07-26T00:00:00+08:00 | 2027-07-26T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74534 | 2025-12-10T01:17:14.5328058+00:00 | 2025-12-10T09:17:14.5328058+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:27.5501238+00:00 | 2026-02-02T12:50:27.5501238+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285534 | TRUE | TRUE | 2026-02-02T04:50:27.5501238+00:00 | 2026-02-02T12:50:27.5501238+08:00 | #74534 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-07-18T16:00:00+00:00 | 2027-07-19T04:00:00+00:00 | 2027-07-19T00:00:00+08:00 | 2027-07-19T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74508 | 2025-12-10T01:09:11.9976809+00:00 | 2025-12-10T09:09:11.9976809+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:28.4475621+00:00 | 2026-02-02T12:50:28.4475621+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285535 | TRUE | TRUE | 2026-02-02T04:50:28.4475621+00:00 | 2026-02-02T12:50:28.4475621+08:00 | #74508 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-07-11T16:00:00+00:00 | 2027-07-12T04:00:00+00:00 | 2027-07-12T00:00:00+08:00 | 2027-07-12T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74533 | 2025-12-10T01:17:14.0327953+00:00 | 2025-12-10T09:17:14.0327953+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:29.3236128+00:00 | 2026-02-02T12:50:29.3236128+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285536 | TRUE | TRUE | 2026-02-02T04:50:29.3236128+00:00 | 2026-02-02T12:50:29.3236128+08:00 | #74533 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-07-04T16:00:00+00:00 | 2027-07-05T04:00:00+00:00 | 2027-07-05T00:00:00+08:00 | 2027-07-05T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74507 | 2025-12-10T01:09:11.523875+00:00 | 2025-12-10T09:09:11.523875+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:30.2042439+00:00 | 2026-02-02T12:50:30.2042439+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285537 | TRUE | TRUE | 2026-02-02T04:50:30.2042439+00:00 | 2026-02-02T12:50:30.2042439+08:00 | #74507 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-06-27T16:00:00+00:00 | 2027-06-28T04:00:00+00:00 | 2027-06-28T00:00:00+08:00 | 2027-06-28T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74532 | 2025-12-10T01:17:13.528843+00:00 | 2025-12-10T09:17:13.528843+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:31.2245148+00:00 | 2026-02-02T12:50:31.2245148+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285538 | TRUE | TRUE | 2026-02-02T04:50:31.2245148+00:00 | 2026-02-02T12:50:31.2245148+08:00 | #74532 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-06-20T16:00:00+00:00 | 2027-06-21T04:00:00+00:00 | 2027-06-21T00:00:00+08:00 | 2027-06-21T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74506 | 2025-12-10T01:09:11.0299877+00:00 | 2025-12-10T09:09:11.0299877+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:32.0884296+00:00 | 2026-02-02T12:50:32.0884296+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285539 | TRUE | TRUE | 2026-02-02T04:50:32.0884296+00:00 | 2026-02-02T12:50:32.0884296+08:00 | #74506 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-06-13T16:00:00+00:00 | 2027-06-14T04:00:00+00:00 | 2027-06-14T00:00:00+08:00 | 2027-06-14T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74531 | 2025-12-10T01:17:13.0039108+00:00 | 2025-12-10T09:17:13.0039108+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:33.095231+00:00 | 2026-02-02T12:50:33.095231+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285540 | TRUE | TRUE | 2026-02-02T04:50:33.095231+00:00 | 2026-02-02T12:50:33.095231+08:00 | #74531 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-06-06T16:00:00+00:00 | 2027-06-07T04:00:00+00:00 | 2027-06-07T00:00:00+08:00 | 2027-06-07T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74505 | 2025-12-10T01:09:10.5542899+00:00 | 2025-12-10T09:09:10.5542899+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:34.4727161+00:00 | 2026-02-02T12:50:34.4727161+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285541 | TRUE | TRUE | 2026-02-02T04:50:34.4727161+00:00 | 2026-02-02T12:50:34.4727161+08:00 | #74505 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-05-30T16:00:00+00:00 | 2027-05-31T04:00:00+00:00 | 2027-05-31T00:00:00+08:00 | 2027-05-31T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74530 | 2025-12-10T01:17:12.5054561+00:00 | 2025-12-10T09:17:12.5054561+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:35.3562046+00:00 | 2026-02-02T12:50:35.3562046+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285542 | TRUE | TRUE | 2026-02-02T04:50:35.3562046+00:00 | 2026-02-02T12:50:35.3562046+08:00 | #74530 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-05-23T16:00:00+00:00 | 2027-05-24T04:00:00+00:00 | 2027-05-24T00:00:00+08:00 | 2027-05-24T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74504 | 2025-12-10T01:09:10.0908849+00:00 | 2025-12-10T09:09:10.0908849+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:36.2668031+00:00 | 2026-02-02T12:50:36.2668031+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285543 | TRUE | TRUE | 2026-02-02T04:50:36.2668031+00:00 | 2026-02-02T12:50:36.2668031+08:00 | #74504 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-05-16T16:00:00+00:00 | 2027-05-17T04:00:00+00:00 | 2027-05-17T00:00:00+08:00 | 2027-05-17T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74529 | 2025-12-10T01:17:12.0107317+00:00 | 2025-12-10T09:17:12.0107317+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:37.16761+00:00 | 2026-02-02T12:50:37.16761+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285544 | TRUE | TRUE | 2026-02-02T04:50:37.16761+00:00 | 2026-02-02T12:50:37.16761+08:00 | #74529 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-05-09T16:00:00+00:00 | 2027-05-10T04:00:00+00:00 | 2027-05-10T00:00:00+08:00 | 2027-05-10T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74503 | 2025-12-10T01:09:09.6303922+00:00 | 2025-12-10T09:09:09.6303922+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:38.0847624+00:00 | 2026-02-02T12:50:38.0847624+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285545 | TRUE | TRUE | 2026-02-02T04:50:38.0847624+00:00 | 2026-02-02T12:50:38.0847624+08:00 | #74503 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-05-02T16:00:00+00:00 | 2027-05-03T04:00:00+00:00 | 2027-05-03T00:00:00+08:00 | 2027-05-03T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74528 | 2025-12-10T01:17:11.5066185+00:00 | 2025-12-10T09:17:11.5066185+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:39.0274309+00:00 | 2026-02-02T12:50:39.0274309+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285546 | TRUE | TRUE | 2026-02-02T04:50:39.0274309+00:00 | 2026-02-02T12:50:39.0274309+08:00 | #74528 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-04-25T16:00:00+00:00 | 2027-04-26T04:00:00+00:00 | 2027-04-26T00:00:00+08:00 | 2027-04-26T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74502 | 2025-12-10T01:09:09.1387659+00:00 | 2025-12-10T09:09:09.1387659+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:39.9329227+00:00 | 2026-02-02T12:50:39.9329227+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285547 | TRUE | TRUE | 2026-02-02T04:50:39.9329227+00:00 | 2026-02-02T12:50:39.9329227+08:00 | #74502 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-04-18T16:00:00+00:00 | 2027-04-19T04:00:00+00:00 | 2027-04-19T00:00:00+08:00 | 2027-04-19T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74527 | 2025-12-10T01:17:10.9904335+00:00 | 2025-12-10T09:17:10.9904335+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:40.8318047+00:00 | 2026-02-02T12:50:40.8318047+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285548 | TRUE | TRUE | 2026-02-02T04:50:40.8318047+00:00 | 2026-02-02T12:50:40.8318047+08:00 | #74527 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-04-11T16:00:00+00:00 | 2027-04-12T04:00:00+00:00 | 2027-04-12T00:00:00+08:00 | 2027-04-12T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74501 | 2025-12-10T01:09:08.686364+00:00 | 2025-12-10T09:09:08.686364+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:41.7159391+00:00 | 2026-02-02T12:50:41.7159391+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285549 | TRUE | TRUE | 2026-02-02T04:50:41.7159391+00:00 | 2026-02-02T12:50:41.7159391+08:00 | #74501 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-04-04T16:00:00+00:00 | 2027-04-05T04:00:00+00:00 | 2027-04-05T00:00:00+08:00 | 2027-04-05T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74526 | 2025-12-10T01:17:10.5065189+00:00 | 2025-12-10T09:17:10.5065189+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:42.6172977+00:00 | 2026-02-02T12:50:42.6172977+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285550 | TRUE | TRUE | 2026-02-02T04:50:42.6172977+00:00 | 2026-02-02T12:50:42.6172977+08:00 | #74526 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-03-28T16:00:00+00:00 | 2027-03-29T04:00:00+00:00 | 2027-03-29T00:00:00+08:00 | 2027-03-29T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74500 | 2025-12-10T01:09:08.2409387+00:00 | 2025-12-10T09:09:08.2409387+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:43.4971278+00:00 | 2026-02-02T12:50:43.4971278+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285551 | TRUE | TRUE | 2026-02-02T04:50:43.4971278+00:00 | 2026-02-02T12:50:43.4971278+08:00 | #74500 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-03-21T16:00:00+00:00 | 2027-03-22T04:00:00+00:00 | 2027-03-22T00:00:00+08:00 | 2027-03-22T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74525 | 2025-12-10T01:17:09.9880983+00:00 | 2025-12-10T09:17:09.9880983+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:44.4160523+00:00 | 2026-02-02T12:50:44.4160523+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285552 | TRUE | TRUE | 2026-02-02T04:50:44.4160523+00:00 | 2026-02-02T12:50:44.4160523+08:00 | #74525 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-03-14T16:00:00+00:00 | 2027-03-15T04:00:00+00:00 | 2027-03-15T00:00:00+08:00 | 2027-03-15T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74499 | 2025-12-10T01:09:07.7906543+00:00 | 2025-12-10T09:09:07.7906543+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:45.3636726+00:00 | 2026-02-02T12:50:45.3636726+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285553 | TRUE | TRUE | 2026-02-02T04:50:45.3636726+00:00 | 2026-02-02T12:50:45.3636726+08:00 | #74499 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-03-07T16:00:00+00:00 | 2027-03-08T04:00:00+00:00 | 2027-03-08T00:00:00+08:00 | 2027-03-08T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74524 | 2025-12-10T01:17:09.4754387+00:00 | 2025-12-10T09:17:09.4754387+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:46.30443+00:00 | 2026-02-02T12:50:46.30443+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285554 | TRUE | TRUE | 2026-02-02T04:50:46.30443+00:00 | 2026-02-02T12:50:46.30443+08:00 | #74524 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-02-28T16:00:00+00:00 | 2027-03-01T04:00:00+00:00 | 2027-03-01T00:00:00+08:00 | 2027-03-01T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74498 | 2025-12-10T01:09:07.3400539+00:00 | 2025-12-10T09:09:07.3400539+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:47.2496964+00:00 | 2026-02-02T12:50:47.2496964+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285555 | TRUE | TRUE | 2026-02-02T04:50:47.2496964+00:00 | 2026-02-02T12:50:47.2496964+08:00 | #74498 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-02-21T16:00:00+00:00 | 2027-02-22T04:00:00+00:00 | 2027-02-22T00:00:00+08:00 | 2027-02-22T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74523 | 2025-12-10T01:17:08.9804159+00:00 | 2025-12-10T09:17:08.9804159+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:48.1832442+00:00 | 2026-02-02T12:50:48.1832442+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285556 | TRUE | TRUE | 2026-02-02T04:50:48.1832442+00:00 | 2026-02-02T12:50:48.1832442+08:00 | #74523 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-02-14T16:00:00+00:00 | 2027-02-15T04:00:00+00:00 | 2027-02-15T00:00:00+08:00 | 2027-02-15T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74497 | 2025-12-10T01:09:06.8938381+00:00 | 2025-12-10T09:09:06.8938381+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:49.1049582+00:00 | 2026-02-02T12:50:49.1049582+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285557 | TRUE | TRUE | 2026-02-02T04:50:49.1049582+00:00 | 2026-02-02T12:50:49.1049582+08:00 | #74497 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-02-07T16:00:00+00:00 | 2027-02-08T04:00:00+00:00 | 2027-02-08T00:00:00+08:00 | 2027-02-08T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74522 | 2025-12-10T01:17:08.4871362+00:00 | 2025-12-10T09:17:08.4871362+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:50.0561654+00:00 | 2026-02-02T12:50:50.0561654+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285558 | TRUE | TRUE | 2026-02-02T04:50:50.0561654+00:00 | 2026-02-02T12:50:50.0561654+08:00 | #74522 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-01-31T16:00:00+00:00 | 2027-02-01T04:00:00+00:00 | 2027-02-01T00:00:00+08:00 | 2027-02-01T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74496 | 2025-12-10T01:09:06.009464+00:00 | 2025-12-10T09:09:06.009464+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:50.981046+00:00 | 2026-02-02T12:50:50.981046+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285559 | TRUE | TRUE | 2026-02-02T04:50:50.981046+00:00 | 2026-02-02T12:50:50.981046+08:00 | #74496 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-01-24T16:00:00+00:00 | 2027-01-25T04:00:00+00:00 | 2027-01-25T00:00:00+08:00 | 2027-01-25T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74521 | 2025-12-10T01:17:07.6488599+00:00 | 2025-12-10T09:17:07.6488599+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:51.8890059+00:00 | 2026-02-02T12:50:51.8890059+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285560 | TRUE | TRUE | 2026-02-02T04:50:51.8890059+00:00 | 2026-02-02T12:50:51.8890059+08:00 | #74521 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-01-17T16:00:00+00:00 | 2027-01-18T04:00:00+00:00 | 2027-01-18T00:00:00+08:00 | 2027-01-18T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84185 | 2026-10-05T04:58:28.7955012+00:00 | 2026-10-05T12:58:28.7955012+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-19T01:16:28.2304418+00:00 | 2026-10-19T09:16:28.2304418+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 336187 | TRUE | TRUE | 2026-10-19T01:16:28.2304418+00:00 | 2026-10-19T09:16:28.2304418+08:00 | #84185 - YAN: 1hrs - YBN31 OPEN KNIFE GATE | 2.0 | TRUE |  | 2027-06-12T10:00:00+00:00 | 2027-06-12T11:00:00+00:00 | 2027-06-12T18:00:00+08:00 | 2027-06-12T19:00:00+08:00 |  |  |  |  | 1.00 | YBN31 OPEN KNIFE GATE | Offsetting this 24hrs to start 04-Jun 1900 and not at the same time as scrubber 302 shut#73231. To allow adequate resourcing, and streamlined washdown and permitting of the two different areas. Katherine Dilley |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
84183 | 2026-10-05T04:21:51.908998+00:00 | 2026-10-05T12:21:51.908998+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-10-19T01:16:28.3907725+00:00 | 2026-10-19T09:16:28.3907725+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 336188 | TRUE | TRUE | 2026-10-19T01:16:28.3907725+00:00 | 2026-10-19T09:16:28.3907725+08:00 | #84183 - YAN: 1hrs - YBN31 CLOSE KNIFE GATE | 2.0 | TRUE |  | 2027-06-04T11:00:00+00:00 | 2027-06-04T12:00:00+00:00 | 2027-06-04T19:00:00+08:00 | 2027-06-04T20:00:00+08:00 |  |  |  |  | 1.00 | YBN31 CLOSE KNIFE GATE | Offsetting this 24hrs to start 04-Jun 1900 and not at the same time as scrubber 302 shut#73231. To allow adequate resourcing, and streamlined washdown and permitting of the two different areas. Katherine Dilley |  | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75554 | 2026-02-25T00:23:24.0248691+00:00 | 2026-02-25T08:23:24.0248691+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-25T02:07:22.0113661+00:00 | 2026-02-25T10:07:22.0113661+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 288928 | TRUE | TRUE | 2026-02-25T02:07:22.0113661+00:00 | 2026-02-25T10:07:22.0113661+08:00 | #75554 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2028-01-16T16:00:00+00:00 | 2028-01-17T04:00:00+00:00 | 2028-01-17T00:00:00+08:00 | 2028-01-17T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75553 | 2026-02-25T00:23:23.3334505+00:00 | 2026-02-25T08:23:23.3334505+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-25T02:07:47.0582816+00:00 | 2026-02-25T10:07:47.0582816+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 288930 | TRUE | TRUE | 2026-02-25T02:07:47.0582816+00:00 | 2026-02-25T10:07:47.0582816+08:00 | #75553 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2028-01-02T16:00:00+00:00 | 2028-01-03T04:00:00+00:00 | 2028-01-03T00:00:00+08:00 | 2028-01-03T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75476 | 2026-02-25T00:19:48.018127+00:00 | 2026-02-25T08:19:48.018127+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-25T02:08:20.1521912+00:00 | 2026-02-25T10:08:20.1521912+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 288954 | TRUE | TRUE | 2026-02-25T02:08:20.1521912+00:00 | 2026-02-25T10:08:20.1521912+08:00 | #75476 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2028-01-23T16:00:00+00:00 | 2028-01-24T04:00:00+00:00 | 2028-01-24T00:00:00+08:00 | 2028-01-24T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
75475 | 2026-02-25T00:19:47.1757305+00:00 | 2026-02-25T08:19:47.1757305+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-25T02:08:20.7404188+00:00 | 2026-02-25T10:08:20.7404188+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 288955 | TRUE | TRUE | 2026-02-25T02:08:20.7404188+00:00 | 2026-02-25T10:08:20.7404188+08:00 | #75475 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2028-01-09T16:00:00+00:00 | 2028-01-10T04:00:00+00:00 | 2028-01-10T00:00:00+08:00 | 2028-01-10T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74541 | 2025-12-10T01:17:18.1845319+00:00 | 2025-12-10T09:17:18.1845319+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:15.5830703+00:00 | 2026-02-02T12:50:15.5830703+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285520 | TRUE | TRUE | 2026-02-02T04:50:15.5830703+00:00 | 2026-02-02T12:50:15.5830703+08:00 | #74541 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-10-24T16:00:00+00:00 | 2027-10-25T04:00:00+00:00 | 2027-10-25T00:00:00+08:00 | 2027-10-25T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74515 | 2025-12-10T01:09:15.429185+00:00 | 2025-12-10T09:09:15.429185+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:16.365165+00:00 | 2026-02-02T12:50:16.365165+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285521 | TRUE | TRUE | 2026-02-02T04:50:16.365165+00:00 | 2026-02-02T12:50:16.365165+08:00 | #74515 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-10-17T16:00:00+00:00 | 2027-10-18T04:00:00+00:00 | 2027-10-18T00:00:00+08:00 | 2027-10-18T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74540 | 2025-12-10T01:17:17.6639377+00:00 | 2025-12-10T09:17:17.6639377+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:17.1992123+00:00 | 2026-02-02T12:50:17.1992123+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285522 | TRUE | TRUE | 2026-02-02T04:50:17.1992123+00:00 | 2026-02-02T12:50:17.1992123+08:00 | #74540 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-10-10T16:00:00+00:00 | 2027-10-11T04:00:00+00:00 | 2027-10-11T00:00:00+08:00 | 2027-10-11T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74514 | 2025-12-10T01:09:14.9495131+00:00 | 2025-12-10T09:09:14.9495131+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:18.0342294+00:00 | 2026-02-02T12:50:18.0342294+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285523 | TRUE | TRUE | 2026-02-02T04:50:18.0342294+00:00 | 2026-02-02T12:50:18.0342294+08:00 | #74514 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-10-03T16:00:00+00:00 | 2027-10-04T04:00:00+00:00 | 2027-10-04T00:00:00+08:00 | 2027-10-04T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74539 | 2025-12-10T01:17:17.1399271+00:00 | 2025-12-10T09:17:17.1399271+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:18.8589656+00:00 | 2026-02-02T12:50:18.8589656+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285524 | TRUE | TRUE | 2026-02-02T04:50:18.8589656+00:00 | 2026-02-02T12:50:18.8589656+08:00 | #74539 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-09-26T16:00:00+00:00 | 2027-09-27T04:00:00+00:00 | 2027-09-27T00:00:00+08:00 | 2027-09-27T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74513 | 2025-12-10T01:09:14.3932917+00:00 | 2025-12-10T09:09:14.3932917+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:19.6676605+00:00 | 2026-02-02T12:50:19.6676605+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285525 | TRUE | TRUE | 2026-02-02T04:50:19.6676605+00:00 | 2026-02-02T12:50:19.6676605+08:00 | #74513 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-09-19T16:00:00+00:00 | 2027-09-20T04:00:00+00:00 | 2027-09-20T00:00:00+08:00 | 2027-09-20T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74538 | 2025-12-10T01:17:16.6298908+00:00 | 2025-12-10T09:17:16.6298908+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:20.5197381+00:00 | 2026-02-02T12:50:20.5197381+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285526 | TRUE | TRUE | 2026-02-02T04:50:20.5197381+00:00 | 2026-02-02T12:50:20.5197381+08:00 | #74538 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-09-12T16:00:00+00:00 | 2027-09-13T04:00:00+00:00 | 2027-09-13T00:00:00+08:00 | 2027-09-13T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74512 | 2025-12-10T01:09:13.8967533+00:00 | 2025-12-10T09:09:13.8967533+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:21.3672065+00:00 | 2026-02-02T12:50:21.3672065+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285527 | TRUE | TRUE | 2026-02-02T04:50:21.3672065+00:00 | 2026-02-02T12:50:21.3672065+08:00 | #74512 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-09-05T16:00:00+00:00 | 2027-09-06T04:00:00+00:00 | 2027-09-06T00:00:00+08:00 | 2027-09-06T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74537 | 2025-12-10T01:17:16.1187223+00:00 | 2025-12-10T09:17:16.1187223+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:22.2670594+00:00 | 2026-02-02T12:50:22.2670594+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285528 | TRUE | TRUE | 2026-02-02T04:50:22.2670594+00:00 | 2026-02-02T12:50:22.2670594+08:00 | #74537 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-08-29T16:00:00+00:00 | 2027-08-30T04:00:00+00:00 | 2027-08-30T00:00:00+08:00 | 2027-08-30T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74511 | 2025-12-10T01:09:13.4309155+00:00 | 2025-12-10T09:09:13.4309155+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:23.1388596+00:00 | 2026-02-02T12:50:23.1388596+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285529 | TRUE | TRUE | 2026-02-02T04:50:23.1388596+00:00 | 2026-02-02T12:50:23.1388596+08:00 | #74511 - YAN: 12hrs - RECLAIMER: YAN 01 | 1.0 | FALSE |  | 2027-08-22T16:00:00+00:00 | 2027-08-23T04:00:00+00:00 | 2027-08-23T00:00:00+08:00 | 2027-08-23T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
74536 | 2025-12-10T01:17:15.5649812+00:00 | 2025-12-10T09:17:15.5649812+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-02-02T04:50:23.9873022+00:00 | 2026-02-02T12:50:23.9873022+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 285530 | TRUE | TRUE | 2026-02-02T04:50:23.9873022+00:00 | 2026-02-02T12:50:23.9873022+08:00 | #74536 - YAN: 12hrs - RECLAIMER: YAN 02 | 1.0 | FALSE |  | 2027-08-15T16:00:00+00:00 | 2027-08-16T04:00:00+00:00 | 2027-08-16T00:00:00+08:00 | 2027-08-16T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection |  |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Create | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
72723 | 2025-11-03T07:21:28.62242+00:00 | 2025-11-03T15:21:28.62242+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-10T05:39:59.8776624+00:00 | 2026-06-10T13:39:59.8776624+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 327587 | TRUE | TRUE | 2026-06-10T05:39:59.8776624+00:00 | 2026-06-10T13:39:59.8776624+08:00 | #72723 - YAN: 168hrs - LOOP SHUT | 2.3 | TRUE |  | 2027-04-22T11:00:00+00:00 | 2027-04-29T11:00:00+00:00 | 2027-04-22T19:00:00+08:00 | 2027-04-29T19:00:00+08:00 |  |  |  |  | 168.00 | LOOP PLANT SHUT - YFA301 Apron Feeder Overhaul - 10Yr plan shut extension YCV213 Shuttle Rail C/O |  | SLOO2716 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d393f455-6e8c-4840-8cae-22cbd45f17af", "emailAddress": "Liam.Newstead@riotinto.com", "displayName": "Newstead, Liam (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}, {"name": "Other"}] | [{"code": "P-0508955", "name": "YCV213 Shuttle Rail C/O", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "96"}] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
41772 | 2021-05-25T10:09:14+00:00 | 2021-05-25T18:09:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T05:39:15.1337788+00:00 | 2026-06-11T13:39:15.1337788+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 327750 | TRUE | TRUE | 2026-06-11T05:39:15.1337788+00:00 | 2026-06-11T13:39:15.1337788+08:00 | #41772 - YAN: 120hrs - TRAIN LOADOUT: YAN 02 | 10.3 | TRUE |  | 2027-01-28T11:00:00+00:00 | 2027-02-02T11:00:00+00:00 | 2027-01-28T19:00:00+08:00 | 2027-02-02T19:00:00+08:00 |  |  |  |  | 120.00 | TLO2 and Reclaimer 2 Shut |  | STLO2704 | [{"equipmentGUID": "5ae5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO02", "name": "Train Loadout: YAN 02", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8ad99f21-60bb-4331-800b-0650f0042da8", "emailAddress": "Bradley.Davis2@riotinto.com", "displayName": "Davis, Bradley (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0505846", "name": "Yandi GTU Rectification Project - (YCV06/16) - PREPARATORY WORKS YCV16", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "96"}] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
45113 | 2021-12-01T04:39:45+00:00 | 2021-12-01T12:39:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-15T04:13:28.3009595+00:00 | 2026-06-15T12:13:28.3009595+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 327927 | TRUE | TRUE | 2026-06-15T04:13:28.3009595+00:00 | 2026-06-15T12:13:28.3009595+08:00 | #45113 - YAN: 24hrs - LOOP PREP - JSE NOT IN BYPASS | 4.0 | TRUE |  | 2027-10-20T11:00:00+00:00 | 2027-10-21T11:00:00+00:00 | 2027-10-20T19:00:00+08:00 | 2027-10-21T19:00:00+08:00 |  |  |  |  | 24.00 | 24hr - Loop Shut Preps | Correction MSF review 2027 |  | [{"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
45055 | 2021-12-01T03:05:10+00:00 | 2021-12-01T11:05:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-01T01:43:30.1667731+00:00 | 2026-10-01T09:43:30.1667731+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 334789 | TRUE | TRUE | 2026-10-01T01:43:30.1667731+00:00 | 2026-10-01T09:43:30.1667731+08:00 | #45055 - YAN: 144hrs - LOOP SHUT | 8.4 | TRUE |  | 2027-07-22T11:00:00+00:00 | 2027-07-28T11:00:00+00:00 | 2027-07-22T19:00:00+08:00 | 2027-07-28T19:00:00+08:00 |  |  |  |  | 144.00 | LOOP PLANT SHUT - YCV213 Shuttle Rail C/O |  | SLOO2729 | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d393f455-6e8c-4840-8cae-22cbd45f17af", "emailAddress": "Liam.Newstead@riotinto.com", "displayName": "Newstead, Liam (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Project Interactions"}] | [{"code": "P-0508955", "name": "YCV213 Shuttle Rail C/O", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "96"}] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
57610 | 2023-08-16T08:30:21+00:00 | 2023-08-16T16:30:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-21T23:34:48.0646409+00:00 | 2026-09-22T07:34:48.0646409+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 333672 | TRUE | TRUE | 2026-09-21T23:34:48.0646409+00:00 | 2026-09-22T07:34:48.0646409+08:00 | #57610 - YAN: 108hrs - STACKER: YAN 03 | 8.0 | FALSE |  | 2027-06-17T11:00:00+00:00 | 2027-06-21T23:00:00+00:00 | 2027-06-17T19:00:00+08:00 | 2027-06-22T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 3 shut | Luff Cylinder C/O moved to WK08 2028 |  | [{"equipmentGUID": "5829f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST03", "name": "Stacker: YAN 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
57611 | 2023-08-16T08:30:51+00:00 | 2023-08-16T16:30:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-22T05:56:21.3207966+00:00 | 2026-09-22T13:56:21.3207966+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 333688 | TRUE | TRUE | 2026-09-22T05:56:21.3207966+00:00 | 2026-09-22T13:56:21.3207966+08:00 | #57611 - YAN: 108hrs - STACKER: YAN 02 | 7.0 | FALSE |  | 2027-08-27T11:00:00+00:00 | 2027-08-31T23:00:00+00:00 | 2027-08-27T19:00:00+08:00 | 2027-09-01T07:00:00+08:00 |  |  |  |  | 108.00 | Stacker 2 shut | Luff Cylinder C/O moved to WK21 2028 |  | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
57609 | 2023-08-16T08:30:02+00:00 | 2023-08-16T16:30:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-19T03:52:45.5607338+00:00 | 2026-10-19T11:52:45.5607338+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 336199 | TRUE | TRUE | 2026-10-19T03:52:45.5607338+00:00 | 2026-10-19T11:52:45.5607338+08:00 | #57609 - YAN: 192hrs - STACKER: YAN 02 | 8.0 | FALSE |  | 2027-06-04T11:00:00+00:00 | 2027-06-12T11:00:00+00:00 | 2027-06-04T19:00:00+08:00 | 2027-06-12T19:00:00+08:00 |  |  |  |  | 192.00 | Stacker 2 shut - YFA31 Apron Feeder Overhaul - 10Yr plan shut extension | offsetting this 24hrs to start 04-Jun 1900 and not at the same time as scrubber 302 shut#73231. To allow adequate resourcing, and streamlined washdown and permitting of the two different areas. Katherine Dilley |  | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
44877 | 2021-11-30T04:09:27+00:00 | 2021-11-30T12:09:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-13T06:05:13.3389969+00:00 | 2026-10-13T14:05:13.3389969+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335867 | TRUE | TRUE | 2026-10-13T06:05:13.3389969+00:00 | 2026-10-13T14:05:13.3389969+08:00 | #44877 - YAN: 274hrs - DRY SHUT | 11.0 | TRUE |  | 2027-09-16T11:00:00+00:00 | 2027-09-27T21:00:00+00:00 | 2027-09-16T19:00:00+08:00 | 2027-09-28T05:00:00+08:00 |  |  |  |  | 274.00 | Dry Plant & JSW Shut - YCC03 Mainframe C/O, Conveyor YCV06 GTU mass/pulley/winch changeout 240hrs - 10Yr plan shut extension | Brad Davis, Project Lead advises need to make a further change to part of the below request following recent feedback from the potential Contractor | SDRY2737 | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "886afbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANTCS03", "name": "Crusher - Tertiary: YAN 03 Plant 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8ad99f21-60bb-4331-800b-0650f0042da8", "emailAddress": "Bradley.Davis2@riotinto.com", "displayName": "Davis, Bradley (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Crusher Overhaul"}, {"name": "Project Interactions"}] | [{"code": "P-0505846", "name": "Yandi GTU Rectification Project", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "240"}] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
44838 | 2021-11-30T04:02:32+00:00 | 2021-11-30T12:02:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-26T09:17:32.0850914+00:00 | 2026-08-26T17:17:32.0850914+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 331853 | TRUE | TRUE | 2026-08-26T09:17:32.0850914+00:00 | 2026-08-26T17:17:32.0850914+08:00 | #44838 - YAN: 120hrs - TRAIN LOADOUT: YAN 01 | 10.0 | TRUE |  | 2027-04-30T11:00:00+00:00 | 2027-05-05T11:00:00+00:00 | 2027-04-30T19:00:00+08:00 | 2027-05-05T19:00:00+08:00 |  |  |  |  | 120.00 | TLO1 and Reclaimer 1 Shut | Project faced some delays up to this point which have meant we will need to request pushing execution back by one 3-month shut cycle. |  | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
44872 | 2021-11-30T04:09:18+00:00 | 2021-11-30T12:09:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-26T09:17:32.6015819+00:00 | 2026-08-26T17:17:32.6015819+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 331854 | TRUE | TRUE | 2026-08-26T09:17:32.6015819+00:00 | 2026-08-26T17:17:32.6015819+08:00 | #44872 - YAN: 144hrs - DRY SHUT | 8.0 | TRUE |  | 2027-06-17T11:00:00+00:00 | 2027-06-23T11:00:00+00:00 | 2027-06-17T19:00:00+08:00 | 2027-06-23T19:00:00+08:00 |  |  |  |  | 144.00 | Dry Plant & JSW Shut | Project faced some delays up to this point which have meant we will need to request pushing execution back by one 3-month shut cycle | SDRY2724 | [{"equipmentGUID": "6217ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT01", "name": "Plant: YAN 01 (Dry)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "5e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT04", "name": "Plant: YAN 04 (JSW)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
45098 | 2021-12-01T04:39:20+00:00 | 2021-12-01T12:39:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:40:00.3251609+00:00 | 2026-10-02T14:40:00.3251609+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335044 | TRUE | TRUE | 2026-10-02T06:40:00.3251609+00:00 | 2026-10-02T14:40:00.3251609+08:00 | #45098 - YAN: 24hrs - LOOP PREP - JSE NOT IN BYPASS | 5.0 | TRUE |  | 2027-01-20T11:00:00+00:00 | 2027-01-21T11:00:00+00:00 | 2027-01-20T19:00:00+08:00 | 2027-01-21T19:00:00+08:00 |  |  |  |  | 24.00 | 24hr - Loop Shut Preps | Hi Rohan/Mal Just noticed JSE is scheduled to come down at 23:00 on 20/01/2027 can we get this changed to 19:00 please? James Procter |  | [{"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
57607 | 2023-08-16T08:29:24+00:00 | 2023-08-16T16:29:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T03:59:24.839241+00:00 | 2026-10-05T11:59:24.839241+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335231 | TRUE | TRUE | 2026-10-05T03:59:24.839241+00:00 | 2026-10-05T11:59:24.839241+08:00 | #57607 - YAN: 289hrs - STACKER 2 SHUT - HEAD END C/O | 7.1 | FALSE |  | 2027-03-04T11:00:00+00:00 | 2027-03-16T12:00:00+00:00 | 2027-03-04T19:00:00+08:00 | 2027-03-16T20:00:00+08:00 |  |  |  |  | 289.00 | Stacker 2 Shut + Head end C/O (duration 289 hours, 181hr extension for the head end) |  | STK22709 | [{"equipmentGUID": "7544f6bf-7c7b-ee11-a846-000d3acacefd", "code": "YANST02", "name": "Stacker: YAN 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "274da65a-a894-4ff4-b5c0-7b4ac9dfb393", "emailAddress": "Rohan.Stacey@riotinto.com", "displayName": "Rohan Stacey"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
54738 | 2023-03-24T11:14:43+00:00 | 2023-03-24T19:14:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T04:05:02.6019628+00:00 | 2026-10-05T12:05:02.6019628+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | {"name": "Fixed Plant"} | 335232 | TRUE | TRUE | 2026-10-05T04:05:02.6019628+00:00 | 2026-10-05T12:05:02.6019628+08:00 | #54738 - YAN: 288hrs - TRAIN LOADOUT: YAN 01 | 7.3 | TRUE |  | 2027-07-30T11:00:00+00:00 | 2027-08-11T11:00:00+00:00 | 2027-07-30T19:00:00+08:00 | 2027-08-11T19:00:00+08:00 |  |  |  |  | 288.00 | TLO1 and Reclaimer 1 Shut - Conveyor YCV16 GTU mass/pulley/winch changeout 288hrs & Guillotine and VMX chute C/O - 10Yr plan shut extension |  | STL2730 | [{"equipmentGUID": "c4f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANTLO01", "name": "Train Loadout: YAN 01", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8ad99f21-60bb-4331-800b-0650f0042da8", "emailAddress": "Bradley.Davis2@riotinto.com", "displayName": "Davis, Bradley (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Project Interactions"}, {"name": "VMAX Chute Changeout"}] | [{"code": "P-0505846", "name": "Yandi GTU Rectification Project", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "288"}] | [] | Approved | Update | ed8648ca-ebc6-4536-bb85-49ad6324f770 | Boyd, Malcolm (RTIO) | Scheduled | YAN | Australia/Perth
83407 | 2026-07-02T06:20:44.4078266+00:00 | 2026-07-02T14:20:44.4078266+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T06:20:44.4078266+00:00 | 2026-07-02T14:20:44.4078266+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329235 | TRUE | TRUE | 2026-07-02T06:20:44.4078266+00:00 | 2026-07-02T14:20:44.4078266+08:00 | #83407 - YAN: 72hrs - 07H558 CAT 992 WHEEL LOADER | 1.0 | FALSE |  | 2027-12-18T16:00:00+00:00 | 2027-12-21T16:00:00+00:00 | 2027-12-19T00:00:00+08:00 | 2027-12-22T00:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife |  |  | [{"equipmentGUID": "e8591634-8173-f111-a817-002248933a47", "code": "07H558", "name": "07H558 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "17232fd8-3407-40c5-9b2f-a048e7538a2a", "emailAddress": "John.Lachmaniuk@riotinto.com", "displayName": "John Lachmaniuk"}}] | [] | [] | [] | [] | [] | Approved | Create | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83406 | 2026-07-02T06:18:02.9054904+00:00 | 2026-07-02T14:18:02.9054904+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:18:44.9190179+00:00 | 2026-07-03T07:18:44.9190179+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329272 | TRUE | TRUE | 2026-07-02T23:18:44.9190179+00:00 | 2026-07-03T07:18:44.9190179+08:00 | #83406 - YAN: 72hrs - 07H576 CAT 992 WHEEL LOADER | 2.0 | FALSE |  | 2027-12-14T16:00:00+00:00 | 2027-12-17T16:00:00+00:00 | 2027-12-15T00:00:00+08:00 | 2027-12-18T00:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife | Incorrect date was entered, should have been 2027 not 2026 |  | [{"equipmentGUID": "6eda57c7-8073-f111-a817-002248933a47", "code": "07H576", "name": "07H576 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "17232fd8-3407-40c5-9b2f-a048e7538a2a", "emailAddress": "John.Lachmaniuk@riotinto.com", "displayName": "John Lachmaniuk"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83394 | 2026-07-02T05:55:49.5848654+00:00 | 2026-07-02T13:55:49.5848654+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:51:32.9938657+00:00 | 2026-07-03T07:51:32.9938657+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329274 | TRUE | TRUE | 2026-07-02T23:51:32.9938657+00:00 | 2026-07-03T07:51:32.9938657+08:00 | #83394 - MTP: 120hrs - 15H180 KOMATSU PC1250SP-8 EXCAVATOR | 1.1 | FALSE |  | 2027-01-01T04:00:00+00:00 | 2027-01-06T04:00:00+00:00 | 2027-01-01T12:00:00+08:00 | 2027-01-06T12:00:00+08:00 |  |  |  |  | 120.00 | Swing Bearing |  |  | [{"equipmentGUID": "c714f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15H180", "name": "15H180 Komatsu PC1250SP-8 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6896f18b-2b9c-4b19-abf9-10160a435472", "emailAddress": "Michael.Dyt@riotinto.com", "displayName": "Michael Dyt"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | MTP | Australia/Perth |  | Site Team
83395 | 2026-07-02T05:55:49.5849692+00:00 | 2026-07-02T13:55:49.5849692+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:51:59.931819+00:00 | 2026-07-03T07:51:59.931819+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329275 | TRUE | TRUE | 2026-07-02T23:51:59.931819+00:00 | 2026-07-03T07:51:59.931819+08:00 | #83395 - BM4: 144hrs - 07H267 LETOURNEAU L2350 II WHEEL LOADER | 1.1 | FALSE |  | 2027-02-14T04:00:00+00:00 | 2027-02-20T04:00:00+00:00 | 2027-02-14T12:00:00+08:00 | 2027-02-20T12:00:00+08:00 |  |  |  |  | 144.00 | Dr&WM RHR, Lift Cyls, Tilt Cyls RH |  |  | [{"equipmentGUID": "0b19f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H267", "name": "07H267 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | BM4 | Australia/Perth |  | Site Team
83396 | 2026-07-02T05:55:49.585076+00:00 | 2026-07-02T13:55:49.585076+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:53:01.5742449+00:00 | 2026-07-03T07:53:01.5742449+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329277 | TRUE | TRUE | 2026-07-02T23:53:01.5742449+00:00 | 2026-07-03T07:53:01.5742449+08:00 | #83396 - BM2: 72hrs - 07H419 CAT 972M WHEEL LOADER | 1.1 | FALSE |  | 2027-06-13T04:00:00+00:00 | 2027-06-16T04:00:00+00:00 | 2027-06-13T12:00:00+08:00 | 2027-06-16T12:00:00+08:00 |  |  |  |  | 72.00 | Engine & After Cooler |  |  | [{"equipmentGUID": "205bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H419", "name": "07H419 CAT 972M Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "60369043-9d5f-4d1c-ba70-f38cb856f626", "emailAddress": "Kimberley.Turner@riotinto.com", "displayName": "Turner, Kimberley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83398 | 2026-07-02T05:55:49.5852861+00:00 | 2026-07-02T13:55:49.5852861+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:53:54.7861164+00:00 | 2026-07-03T07:53:54.7861164+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329279 | TRUE | TRUE | 2026-07-02T23:53:54.7861164+00:00 | 2026-07-03T07:53:54.7861164+08:00 | #83398 - BM2: 72hrs - 07H426 CAT 992K WHEEL LOADER | 1.1 | FALSE |  | 2027-08-10T22:00:00+00:00 | 2027-08-13T22:00:00+00:00 | 2027-08-11T06:00:00+08:00 | 2027-08-14T06:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife & Ovhl Artic |  |  | [{"equipmentGUID": "f355fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H426", "name": "07H426 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "60369043-9d5f-4d1c-ba70-f38cb856f626", "emailAddress": "Kimberley.Turner@riotinto.com", "displayName": "Turner, Kimberley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | BM2 | Australia/Perth |  | Site Team
83399 | 2026-07-02T05:55:49.5853903+00:00 | 2026-07-02T13:55:49.5853903+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:54:17.6653304+00:00 | 2026-07-03T07:54:17.6653304+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329280 | TRUE | TRUE | 2026-07-02T23:54:17.6653304+00:00 | 2026-07-03T07:54:17.6653304+08:00 | #83399 - PDO: 72hrs - 07H167 CAT 992K WHEEL LOADER | 1.1 | FALSE |  | 2027-09-05T04:00:00+00:00 | 2027-09-08T04:00:00+00:00 | 2027-09-05T12:00:00+08:00 | 2027-09-08T12:00:00+08:00 |  |  |  |  | 72.00 | Ovhl Artic |  |  | [{"equipmentGUID": "cce0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07H167", "name": "07H167 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1b2c82f7-da9b-4800-906e-cd4837987eb8", "emailAddress": "Dane.Parker@riotinto.com", "displayName": "Dane Parker"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | PDO | Australia/Perth |  | Site Team
83400 | 2026-07-02T05:55:49.5854962+00:00 | 2026-07-02T13:55:49.5854962+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:54:35.0270969+00:00 | 2026-07-03T07:54:35.0270969+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329281 | TRUE | TRUE | 2026-07-02T23:54:35.0270969+00:00 | 2026-07-03T07:54:35.0270969+08:00 | #83400 - GDI: 72hrs - 07B408 CAT 992K WHEEL LOADER | 1.1 | FALSE |  | 2027-10-10T22:00:00+00:00 | 2027-10-13T22:00:00+00:00 | 2027-10-11T06:00:00+08:00 | 2027-10-14T06:00:00+08:00 |  |  |  |  | 72.00 | Eng Midlife |  |  | [{"equipmentGUID": "bbe5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07B408", "name": "07B408 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83401 | 2026-07-02T05:55:49.5856146+00:00 | 2026-07-02T13:55:49.5856146+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:54:53.4679292+00:00 | 2026-07-03T07:54:53.4679292+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329282 | TRUE | TRUE | 2026-07-02T23:54:53.4679292+00:00 | 2026-07-03T07:54:53.4679292+08:00 | #83401 - PDO: 96hrs - 07H1486 KOMATSU WA900-3 WHEEL LOADER | 1.1 | FALSE |  | 2027-11-02T04:00:00+00:00 | 2027-11-06T04:00:00+00:00 | 2027-11-02T12:00:00+08:00 | 2027-11-06T12:00:00+08:00 |  |  |  |  | 96.00 | Eng Midlife, Damper |  |  | [{"equipmentGUID": "f8ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "07H1486", "name": "07H1486 Komatsu WA900-3 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d5da4aa0-4cdf-4a4d-8c38-ba48b7666aa1", "emailAddress": "Katrina.Bostock@riotinto.com", "displayName": "Bostock, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | PDO | Australia/Perth |  | Site Team
83403 | 2026-07-02T05:55:49.5858955+00:00 | 2026-07-02T13:55:49.5858955+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-07-02T23:55:31.5315378+00:00 | 2026-07-03T07:55:31.5315378+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | {"name": "HME"} | 329284 | TRUE | TRUE | 2026-07-02T23:55:31.5315378+00:00 | 2026-07-03T07:55:31.5315378+08:00 | #83403 - HD4: 96hrs - 07D275 KOMATSU WA900-3EO WHEEL LOADER | 1.1 | FALSE |  | 2027-11-18T04:00:00+00:00 | 2027-11-22T04:00:00+00:00 | 2027-11-18T12:00:00+08:00 | 2027-11-22T12:00:00+08:00 |  |  |  |  | 96.00 | Eng Midlife, Damper |  |  | [{"equipmentGUID": "9f1ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "07D275", "name": "07D275 Komatsu WA900-3EO Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ae603dad-ec46-43e9-8781-48346138bf52", "emailAddress": "Paul.Alves@riotinto.com", "displayName": "Paul Alves"}}] | [] | [] | [] | [] | [] | Approved | Update | 295b44c4-31e0-4da6-88f8-4a466e0deb1c | Milosevic, Nebojsa (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
84497 | 2026-10-17T05:33:35.4927097+00:00 | 2026-10-17T13:33:35.4927097+08:00 | {"principalGUID": "ad9362cf-64e6-4c53-b904-529b695986ad", "displayName": "George, Blake (RTIO)"} | 2026-10-17T08:03:47.2784822+00:00 | 2026-10-17T16:03:47.2784822+08:00 | {"principalGUID": "ad9362cf-64e6-4c53-b904-529b695986ad", "displayName": "George, Blake (RTIO)"} | {"name": "Utilities"} | 336177 | TRUE | TRUE | 2026-10-17T08:03:47.2784822+00:00 | 2026-10-17T16:03:47.2784822+08:00 | #84497 - UTL: 178hrs - GENERATION: WAPR WAG1 | 1.0 | FALSE |  | 2027-05-18T23:00:00+00:00 | 2027-05-26T09:00:00+00:00 | 2027-05-19T07:00:00+08:00 | 2027-05-26T17:00:00+08:00 |  |  |  |  | 178.00 | Placeholder for WAG1 4k shut |  | WAG1SHUT | [{"equipmentGUID": "", "code": "UTLGENWAG1 WAPR", "name": "Generation: WAPR WAG1", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad9362cf-64e6-4c53-b904-529b695986ad", "emailAddress": "Blake.George@riotinto.com", "displayName": "George, Blake (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "adf3ad49-5e24-4180-8ab5-11188bb64948", "emailAddress": "Jamie.Campbell3@riotinto.com", "displayName": "Campbell, Jamie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ad9362cf-64e6-4c53-b904-529b695986ad | George, Blake (RTIO) | Placeholder |  | Australia/Perth
81901 | 2026-03-20T08:43:55.5242014+00:00 | 2026-03-20T16:43:55.5242014+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-17T01:05:03.395941+00:00 | 2026-06-17T09:05:03.395941+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328193 | TRUE | TRUE | 2026-06-17T01:05:03.395941+00:00 | 2026-06-17T09:05:03.395941+08:00 | #81901 - PDO: 156hrs - TLO UPGRADE PROJECT | 2.1 | TRUE |  | 2027-04-14T22:00:00+00:00 | 2027-04-21T10:00:00+00:00 | 2027-04-15T06:00:00+08:00 | 2027-04-21T18:00:00+08:00 |  |  |  |  | 156.00 | PDO TLO UPGRADE PROJECT contingency shut aligned with standard TLO shut duration |  |  | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "095741eb-1cb0-4b62-b23f-52641c81a2d4", "emailAddress": "LuisitoAcosta.Bulanadi@riotinto.com", "displayName": "Luisito Acosta Bulanadi"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "TLO Major Works"}] | [{"code": "P-0507809", "name": "PDO TLO UPGRADE PROJECT", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "300"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Major Projects | PDO | Australia/Perth
81900 | 2026-03-20T08:41:23.5611646+00:00 | 2026-03-20T16:41:23.5611646+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-06-17T01:07:15.2600869+00:00 | 2026-06-17T09:07:15.2600869+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328194 | TRUE | TRUE | 2026-06-17T01:07:15.2600869+00:00 | 2026-06-17T09:07:15.2600869+08:00 | #81900 - PDO: 336hrs - TLO UPGRADE PROJECT | 1.1 | TRUE |  | 2027-01-06T10:00:00+00:00 | 2027-01-20T10:00:00+00:00 | 2027-01-06T18:00:00+08:00 | 2027-01-20T18:00:00+08:00 |  |  |  |  | 336.00 | PDO TLO Upgrade Project 12.5 DAYS TOOL TIME 14 TOTAL |  |  | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "095741eb-1cb0-4b62-b23f-52641c81a2d4", "emailAddress": "LuisitoAcosta.Bulanadi@riotinto.com", "displayName": "Luisito Acosta Bulanadi"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "TLO Major Works"}] | [{"code": "P-0507809", "name": "PDO TLO UPGRADE", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "300"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Major Projects | PDO | Australia/Perth
48202 | 2022-09-15T07:12:02+00:00 | 2022-09-15T15:12:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T08:46:55.2835463+00:00 | 2026-08-03T16:46:55.2835463+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330732 | TRUE | TRUE | 2026-08-03T08:46:55.2835463+00:00 | 2026-08-03T16:46:55.2835463+08:00 | #48202 - PDO: 180hrs - PLANT: CHR | 12.0 | TRUE |  | 2027-08-16T22:00:00+00:00 | 2027-08-24T10:00:00+00:00 | 2027-08-17T06:00:00+08:00 | 2027-08-24T18:00:00+08:00 |  |  |  |  | 180.00 | Channar Shut CR352 Bowl & Mantle Mainframe Liners Wtr Trgh Refurb Arm Liners | Align all scope for CR352 |  | [{"equipmentGUID": "c0d900c0-7c7b-ee11-a846-000d3acacefd", "code": "CHRSCS352", "name": "Crusher - Secondary: CHR 352", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "8017ee47-4b9a-ee11-a847-000d3acacefd", "code": "CHRPLT", "name": "Plant: CHR", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44819 | 2021-11-30T03:38:20+00:00 | 2021-11-30T11:38:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:01.1263612+00:00 | 2026-08-03T18:08:01.1263612+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330742 | TRUE | TRUE | 2026-08-03T10:08:01.1263612+00:00 | 2026-08-03T18:08:01.1263612+08:00 | #44819 - PDO: 240hrs - FIXED PLANT | 7.0 | TRUE |  | 2027-04-05T22:00:00+00:00 | 2027-04-15T22:00:00+00:00 | 2027-04-06T06:00:00+08:00 | 2027-04-16T06:00:00+08:00 |  |  |  |  | 240.00 | Central Plant Shut (CV8 H&B Frames - awaiting capex, 104W SS02 interaction, w/ Secondaries), Thickener Inspection, Rake, Steel Floor | PC01 Concave change out including Pinion change. Scope moved into 2027 | 44819 | [{"equipmentGUID": "c45a111b-5a28-ef11-a84d-000d3acacefd", "code": "PDOPLT", "name": "Plant: PDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [{"name": "Other"}] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}, {"code": "P-0508537", "name": "PBO COS Ventilation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44823 | 2021-11-30T03:40:58+00:00 | 2021-11-30T11:40:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:01.5875872+00:00 | 2026-08-03T18:08:01.5875872+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330744 | TRUE | TRUE | 2026-08-03T10:08:01.5875872+00:00 | 2026-08-03T18:08:01.5875872+08:00 | #44823 - PDO: 180hrs - FIXED PLANT | 8.0 | TRUE |  | 2027-10-04T22:00:00+00:00 | 2027-10-12T10:00:00+00:00 | 2027-10-05T06:00:00+08:00 | 2027-10-12T18:00:00+08:00 |  |  |  |  | 180.00 | Central Plant Shut CV604, Secondary Crushers) | Concave change out - no longer required as per attached | 44823 | [{"equipmentGUID": "c45a111b-5a28-ef11-a84d-000d3acacefd", "code": "PDOPLT", "name": "Plant: PDO", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48367 | 2022-09-16T05:22:25+00:00 | 2022-09-16T13:22:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:02.4380836+00:00 | 2026-08-03T18:08:02.4380836+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330746 | TRUE | TRUE | 2026-08-03T10:08:02.4380836+00:00 | 2026-08-03T18:08:02.4380836+08:00 | #48367 - PDO: 156hrs - PLANT: WRS | 8.0 | TRUE |  | 2027-10-04T22:00:00+00:00 | 2027-10-11T10:00:00+00:00 | 2027-10-05T06:00:00+08:00 | 2027-10-11T18:00:00+08:00 |  |  |  |  | 156.00 | Western Ranges Shut (CV701 Belt Change) | Change out of AF701 cannot be completed in current shut hours - no longer required as per attached |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48364 | 2022-09-16T05:19:49+00:00 | 2022-09-16T13:19:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:02.6611637+00:00 | 2026-08-03T18:08:02.6611637+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330747 | TRUE | TRUE | 2026-08-03T10:08:02.6611637+00:00 | 2026-08-03T18:08:02.6611637+08:00 | #48364 - PDO: 156hrs - PLANT: WRS | 7.0 | TRUE |  | 2027-01-04T22:00:00+00:00 | 2027-01-11T10:00:00+00:00 | 2027-01-05T06:00:00+08:00 | 2027-01-11T18:00:00+08:00 |  |  |  |  | 156.00 | C/O Crusher Mantle CS701 | CV704 Belt change out hours required to change out belt as there are a few reel changes pulling off a belts 3km – 7km - This belt has now been pushed out of 2027 as per TIntrano |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48366 | 2022-09-16T05:21:34+00:00 | 2022-09-16T13:21:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:02.8832103+00:00 | 2026-08-03T18:08:02.8832103+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330748 | TRUE | TRUE | 2026-08-03T10:08:02.8832103+00:00 | 2026-08-03T18:08:02.8832103+08:00 | #48366 - PDO: 156hrs - PLANT: WRS | 9.0 | TRUE |  | 2027-07-05T22:00:00+00:00 | 2027-07-12T10:00:00+00:00 | 2027-07-06T06:00:00+08:00 | 2027-07-12T18:00:00+08:00 |  |  |  |  | 156.00 | Western Range Shut Mantle, Botom Shell, Arm Liners | CV703 Belt change out - there are a few reel changes pulling off a belts 3km – 7km - Changed as Belt is now in 2028 replaced by Crusher scope and extension no longer required |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48365 | 2022-09-16T05:20:35+00:00 | 2022-09-16T13:20:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-28T01:42:45.440773+00:00 | 2026-07-28T09:42:45.440773+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330425 | TRUE | TRUE | 2026-07-28T01:42:45.440773+00:00 | 2026-07-28T09:42:45.440773+08:00 | #48365 - PDO: 156hrs - PLANT: WRS | 6.3 | TRUE |  | 2027-04-05T22:00:00+00:00 | 2027-04-12T10:00:00+00:00 | 2027-04-06T06:00:00+08:00 | 2027-04-12T18:00:00+08:00 |  |  |  |  | 156.00 | No Key driver |  |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44821 | 2021-11-30T03:39:33+00:00 | 2021-11-30T11:39:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-28T04:55:54.3200233+00:00 | 2026-07-28T12:55:54.3200233+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 330438 | TRUE | TRUE | 2026-07-28T04:55:54.3200233+00:00 | 2026-07-28T12:55:54.3200233+08:00 | #44821 - PDO: 180hrs - FIXED PLANT | 9.4 | TRUE |  | 2027-07-05T22:00:00+00:00 | 2027-07-13T10:00:00+00:00 | 2027-07-06T06:00:00+08:00 | 2027-07-13T18:00:00+08:00 |  |  |  |  | 180.00 | Central Plant Shut (CV6, Bin Works, Secondaries) |  | 44821 | [{"equipmentGUID": "c45a111b-5a28-ef11-a84d-000d3acacefd", "code": "PDOPLT", "name": "Plant: PDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48139 | 2022-09-15T05:44:01+00:00 | 2022-09-15T13:44:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-16T02:04:28.1168523+00:00 | 2026-06-16T10:04:28.1168523+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328057 | TRUE | TRUE | 2026-06-16T02:04:28.1168523+00:00 | 2026-06-16T10:04:28.1168523+08:00 | #48139 - PDO: 156hrs - FIXED PLANT | 7.3 | TRUE |  | 2028-01-12T22:00:00+00:00 | 2028-01-19T10:00:00+00:00 | 2028-01-13T06:00:00+08:00 | 2028-01-19T18:00:00+08:00 |  |  |  |  | 156.00 | TLO Shut |  | 48139 | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "156"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48323 | 2022-09-16T02:27:49+00:00 | 2022-09-16T10:27:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-16T02:04:28.1168597+00:00 | 2026-06-16T10:04:28.1168597+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328058 | TRUE | TRUE | 2026-06-16T02:04:28.1168597+00:00 | 2026-06-16T10:04:28.1168597+08:00 | #48323 - PDO: 180hrs - FIXED PLANT | 8.3 | TRUE |  | 2028-01-03T22:00:00+00:00 | 2028-01-11T10:00:00+00:00 | 2028-01-04T06:00:00+08:00 | 2028-01-11T18:00:00+08:00 |  |  |  |  | 180.00 | Central Plant Shut |  | 48323 | [{"equipmentGUID": "c45a111b-5a28-ef11-a84d-000d3acacefd", "code": "PDOPLT", "name": "Plant: PDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48138 | 2022-09-15T05:43:17+00:00 | 2022-09-15T13:43:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-16T02:04:28.1168655+00:00 | 2026-06-16T10:04:28.1168655+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328059 | TRUE | TRUE | 2026-06-16T02:04:28.1168655+00:00 | 2026-06-16T10:04:28.1168655+08:00 | #48138 - PDO: 156hrs - FIXED PLANT | 7.2 | TRUE |  | 2027-10-13T22:00:00+00:00 | 2027-10-20T10:00:00+00:00 | 2027-10-14T06:00:00+08:00 | 2027-10-20T18:00:00+08:00 |  |  |  |  | 156.00 | TLO Shut |  | 48138 | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "156"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44824 | 2021-11-30T03:41:36+00:00 | 2021-11-30T11:41:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-16T02:04:28.1168765+00:00 | 2026-06-16T10:04:28.1168765+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328061 | TRUE | TRUE | 2026-06-16T02:04:28.1168765+00:00 | 2026-06-16T10:04:28.1168765+08:00 | #44824 - PDO: 156hrs - FIXED PLANT | 8.2 | TRUE |  | 2027-07-14T22:00:00+00:00 | 2027-07-21T10:00:00+00:00 | 2027-07-15T06:00:00+08:00 | 2027-07-21T18:00:00+08:00 |  |  |  |  | 156.00 | TLO Shut |  | 44824 | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "156"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44820 | 2021-11-30T03:38:54+00:00 | 2021-11-30T11:38:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-16T02:04:28.1168997+00:00 | 2026-06-16T10:04:28.1168997+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328065 | TRUE | TRUE | 2026-06-16T02:04:28.1168997+00:00 | 2026-06-16T10:04:28.1168997+08:00 | #44820 - PDO: 156hrs - FIXED PLANT | 8.2 | TRUE |  | 2027-01-13T22:00:00+00:00 | 2027-01-20T10:00:00+00:00 | 2027-01-14T06:00:00+08:00 | 2027-01-20T18:00:00+08:00 |  |  |  |  | 156.00 | TLO Shut |  | 44820 | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "156"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48182 | 2022-09-15T06:42:20+00:00 | 2022-09-15T14:42:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3669995+00:00 | 2026-06-17T09:01:01.3669995+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328134 | TRUE | TRUE | 2026-06-17T01:01:01.3669995+00:00 | 2026-06-17T09:01:01.3669995+08:00 | #48182 - PDO: 156hrs - PLANT: ERS | 8.2 | TRUE |  | 2027-08-30T22:00:00+00:00 | 2027-09-06T10:00:00+00:00 | 2027-08-31T06:00:00+08:00 | 2027-09-06T18:00:00+08:00 |  |  |  |  | 156.00 | ER Shut |  |  | [{"equipmentGUID": "c35a111b-5a28-ef11-a84d-000d3acacefd", "code": "ERSPLT", "name": "Plant: ERS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48225 | 2022-09-15T07:36:06+00:00 | 2022-09-15T15:36:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3670812+00:00 | 2026-06-17T09:01:01.3670812+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328142 | TRUE | TRUE | 2026-06-17T01:01:01.3670812+00:00 | 2026-06-17T09:01:01.3670812+08:00 | #48225 - PDO: 120hrs - RECLAIMER: PDO 02 | 6.1 | FALSE |  | 2027-12-14T22:00:00+00:00 | 2027-12-19T22:00:00+00:00 | 2027-12-15T06:00:00+08:00 | 2027-12-20T06:00:00+08:00 |  |  |  |  | 120.00 | Reclaimer 2 Shut |  |  | [{"equipmentGUID": "1cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC02", "name": "Reclaimer: PDO 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44817 | 2021-11-30T03:36:42+00:00 | 2021-11-30T11:36:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T04:21:57.5358374+00:00 | 2026-10-07T12:21:57.5358374+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 335398 | TRUE | TRUE | 2026-10-07T04:21:57.5358374+00:00 | 2026-10-07T12:21:57.5358374+08:00 | #44817 - PDO: 228hrs - FIXED PLANT | 8.1 | TRUE |  | 2027-01-04T22:00:00+00:00 | 2027-01-14T10:00:00+00:00 | 2027-01-05T06:00:00+08:00 | 2027-01-14T18:00:00+08:00 |  |  |  |  | 228.00 | Central Plant Shut Tertiary Crusher Bin Inspection (SI Works) CV16 & CV14 Conveyor Belt Replacements Screenhouse Bin Structural Repairs |  | STP2701 | [{"equipmentGUID": "c45a111b-5a28-ef11-a84d-000d3acacefd", "code": "PDOPLT", "name": "Plant: PDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}, {"name": "Structural Repairs"}] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}, {"code": "P-0508537", "name": "PBO COS Ventilation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48368 | 2022-09-16T05:23:12+00:00 | 2022-09-16T13:23:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-11-06T02:55:40.9894311+00:00 | 2025-11-06T10:55:40.9894311+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 271972 | TRUE | TRUE | 2025-11-06T02:55:40.9894311+00:00 | 2025-11-06T10:55:40.9894311+08:00 | #48368 - PDO: 156hrs - PLANT: WRS | 7.1 | TRUE |  | 2028-01-03T22:00:00+00:00 | 2028-01-10T10:00:00+00:00 | 2028-01-04T06:00:00+08:00 | 2028-01-10T18:00:00+08:00 |  |  |  |  | 156.00 | C/O Crusher Mantle CS701 |  |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f9e4ea72-2402-4ebc-afb8-09e09e598d8f", "emailAddress": "Frances.Dawson@riotinto.com", "displayName": "Dawson, Jessica (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "24634fbe-9011-478f-b0a2-6a936cd0aafa", "emailAddress": "Toby.Harper@riotinto.com", "displayName": "Harper, Toby (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48162 | 2022-09-15T06:09:02+00:00 | 2022-09-15T14:09:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.367096+00:00 | 2026-06-17T09:01:01.367096+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328144 | TRUE | TRUE | 2026-06-17T01:01:01.367096+00:00 | 2026-06-17T09:01:01.367096+08:00 | #48162 - PDO: 132hrs - RECLAIMER: PDO 01 | 8.1 | FALSE |  | 2027-10-13T22:00:00+00:00 | 2027-10-19T10:00:00+00:00 | 2027-10-14T06:00:00+08:00 | 2027-10-19T18:00:00+08:00 |  |  |  |  | 132.00 | Reclaimer 1 Shut |  |  | [{"equipmentGUID": "fe61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC01", "name": "Reclaimer: PDO 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48224 | 2022-09-15T07:34:40+00:00 | 2022-09-15T15:34:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3671505+00:00 | 2026-06-17T09:01:01.3671505+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328149 | TRUE | TRUE | 2026-06-17T01:01:01.3671505+00:00 | 2026-06-17T09:01:01.3671505+08:00 | #48224 - PDO: 120hrs - RECLAIMER: PDO 02 | 6.1 | FALSE |  | 2027-09-14T22:00:00+00:00 | 2027-09-19T22:00:00+00:00 | 2027-09-15T06:00:00+08:00 | 2027-09-20T06:00:00+08:00 |  |  |  |  | 120.00 | Reclaimer 2 Shut |  |  | [{"equipmentGUID": "1cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC02", "name": "Reclaimer: PDO 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48291 | 2022-09-16T01:26:04+00:00 | 2022-09-16T09:26:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3671619+00:00 | 2026-06-17T09:01:01.3671619+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328150 | TRUE | TRUE | 2026-06-17T01:01:01.3671619+00:00 | 2026-06-17T09:01:01.3671619+08:00 | #48291 - PDO: 180hrs - CRUSHER - PRIMARY: PDO 01 | 8.1 | TRUE |  | 2027-09-13T22:00:00+00:00 | 2027-09-21T10:00:00+00:00 | 2027-09-14T06:00:00+08:00 | 2027-09-21T18:00:00+08:00 |  |  |  |  | 180.00 | C/O 234WK CV01 Belt (Plan 1121488) C/O 208WK Para Prim Crusher PC01 Concave (Plan 1233289) 240 hrs |  |  | [{"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48160 | 2022-09-15T06:04:42+00:00 | 2022-09-15T14:04:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3672061+00:00 | 2026-06-17T09:01:01.3672061+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328151 | TRUE | TRUE | 2026-06-17T01:01:01.3672061+00:00 | 2026-06-17T09:01:01.3672061+08:00 | #48160 - PDO: 132hrs - RECLAIMER: PDO 01 | 6.1 | FALSE |  | 2027-07-14T22:00:00+00:00 | 2027-07-20T10:00:00+00:00 | 2027-07-15T06:00:00+08:00 | 2027-07-20T18:00:00+08:00 |  |  |  |  | 132.00 | Reclaimer 1 Shut |  |  | [{"equipmentGUID": "fe61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC01", "name": "Reclaimer: PDO 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48223 | 2022-09-15T07:33:44+00:00 | 2022-09-15T15:33:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3672566+00:00 | 2026-06-17T09:01:01.3672566+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328156 | TRUE | TRUE | 2026-06-17T01:01:01.3672566+00:00 | 2026-06-17T09:01:01.3672566+08:00 | #48223 - PDO: 120hrs - RECLAIMER: PDO 02 | 6.1 | FALSE |  | 2027-06-15T22:00:00+00:00 | 2027-06-20T22:00:00+00:00 | 2027-06-16T06:00:00+08:00 | 2027-06-21T06:00:00+08:00 |  |  |  |  | 120.00 | Reclaimer 2 Shut |  |  | [{"equipmentGUID": "1cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC02", "name": "Reclaimer: PDO 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48246 | 2022-09-15T09:24:49+00:00 | 2022-09-15T17:24:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3672635+00:00 | 2026-06-17T09:01:01.3672635+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328157 | TRUE | TRUE | 2026-06-17T01:01:01.3672635+00:00 | 2026-06-17T09:01:01.3672635+08:00 | #48246 - PDO: 180hrs - CRUSHER - PRIMARY: PDO 01 | 7.1 | TRUE |  | 2027-06-14T22:00:00+00:00 | 2027-06-22T10:00:00+00:00 | 2027-06-15T06:00:00+08:00 | 2027-06-22T18:00:00+08:00 |  |  |  |  | 180.00 | PLT PC Shut |  |  | [{"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48159 | 2022-09-15T06:03:59+00:00 | 2022-09-15T14:03:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3672708+00:00 | 2026-06-17T09:01:01.3672708+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328158 | TRUE | TRUE | 2026-06-17T01:01:01.3672708+00:00 | 2026-06-17T09:01:01.3672708+08:00 | #48159 - PDO: 132hrs - RECLAIMER: PDO 01 | 6.1 | FALSE |  | 2027-04-14T22:00:00+00:00 | 2027-04-20T10:00:00+00:00 | 2027-04-15T06:00:00+08:00 | 2027-04-20T18:00:00+08:00 |  |  |  |  | 132.00 | Reclaimer 1 Shut |  |  | [{"equipmentGUID": "fe61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC01", "name": "Reclaimer: PDO 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48222 | 2022-09-15T07:33:04+00:00 | 2022-09-15T15:33:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3673287+00:00 | 2026-06-17T09:01:01.3673287+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328163 | TRUE | TRUE | 2026-06-17T01:01:01.3673287+00:00 | 2026-06-17T09:01:01.3673287+08:00 | #48222 - PDO: 120hrs - RECLAIMER: PDO 02 | 7.1 | FALSE |  | 2027-03-16T22:00:00+00:00 | 2027-03-21T22:00:00+00:00 | 2027-03-17T06:00:00+08:00 | 2027-03-22T06:00:00+08:00 |  |  |  |  | 120.00 | Reclaimer 2 Shut |  |  | [{"equipmentGUID": "1cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC02", "name": "Reclaimer: PDO 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48245 | 2022-09-15T09:24:05+00:00 | 2022-09-15T17:24:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3673382+00:00 | 2026-06-17T09:01:01.3673382+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328164 | TRUE | TRUE | 2026-06-17T01:01:01.3673382+00:00 | 2026-06-17T09:01:01.3673382+08:00 | #48245 - PDO: 180hrs - CRUSHER - PRIMARY: PDO 01 | 7.1 | TRUE |  | 2027-03-15T22:00:00+00:00 | 2027-03-23T10:00:00+00:00 | 2027-03-16T06:00:00+08:00 | 2027-03-23T18:00:00+08:00 |  |  |  |  | 180.00 | PLT PC Shut |  |  | [{"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48158 | 2022-09-15T06:03:16+00:00 | 2022-09-15T14:03:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3673463+00:00 | 2026-06-17T09:01:01.3673463+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328165 | TRUE | TRUE | 2026-06-17T01:01:01.3673463+00:00 | 2026-06-17T09:01:01.3673463+08:00 | #48158 - PDO: 132hrs - RECLAIMER: PDO 01 | 7.1 | FALSE |  | 2027-01-13T22:00:00+00:00 | 2027-01-19T10:00:00+00:00 | 2027-01-14T06:00:00+08:00 | 2027-01-19T18:00:00+08:00 |  |  |  |  | 132.00 | Reclaimer 1 Shut |  |  | [{"equipmentGUID": "fe61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC01", "name": "Reclaimer: PDO 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48220 | 2022-09-15T07:28:30+00:00 | 2022-09-15T15:28:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3673817+00:00 | 2026-06-17T09:01:01.3673817+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328170 | TRUE | TRUE | 2026-06-17T01:01:01.3673817+00:00 | 2026-06-17T09:01:01.3673817+08:00 | #48220 - PDO: 120hrs - RECLAIMER: PDO 02 | 4.1 | FALSE |  | 2026-12-08T22:00:00+00:00 | 2026-12-13T22:00:00+00:00 | 2026-12-09T06:00:00+08:00 | 2026-12-14T06:00:00+08:00 |  |  |  |  | 120.00 | Reclaimer 2 Shutdown |  |  | [{"equipmentGUID": "1cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDORC02", "name": "Reclaimer: PDO 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48244 | 2022-09-15T09:23:18+00:00 | 2022-09-15T17:23:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3673895+00:00 | 2026-06-17T09:01:01.3673895+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328171 | TRUE | TRUE | 2026-06-17T01:01:01.3673895+00:00 | 2026-06-17T09:01:01.3673895+08:00 | #48244 - PDO: 180hrs - CRUSHER - PRIMARY: PDO 01 | 7.1 | TRUE |  | 2026-12-07T22:00:00+00:00 | 2026-12-15T10:00:00+00:00 | 2026-12-08T06:00:00+08:00 | 2026-12-15T18:00:00+08:00 |  |  |  |  | 180.00 | PLT PC Shut |  |  | [{"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48184 | 2022-09-15T06:44:57+00:00 | 2022-09-15T14:44:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3674816+00:00 | 2026-06-17T09:01:01.3674816+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328184 | TRUE | TRUE | 2026-06-17T01:01:01.3674816+00:00 | 2026-06-17T09:01:01.3674816+08:00 | #48184 - PDO: 156hrs - PLANT: ERS | 6.1 | TRUE |  | 2027-11-29T22:00:00+00:00 | 2027-12-06T10:00:00+00:00 | 2027-11-30T06:00:00+08:00 | 2027-12-06T18:00:00+08:00 |  |  |  |  | 156.00 | ER plant shut |  |  | [{"equipmentGUID": "c35a111b-5a28-ef11-a84d-000d3acacefd", "code": "ERSPLT", "name": "Plant: ERS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48203 | 2022-09-15T07:12:59+00:00 | 2022-09-15T15:12:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3674886+00:00 | 2026-06-17T09:01:01.3674886+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328185 | TRUE | TRUE | 2026-06-17T01:01:01.3674886+00:00 | 2026-06-17T09:01:01.3674886+08:00 | #48203 - PDO: 156hrs - PLANT: CHR | 8.1 | TRUE |  | 2027-11-15T22:00:00+00:00 | 2027-11-22T10:00:00+00:00 | 2027-11-16T06:00:00+08:00 | 2027-11-22T18:00:00+08:00 |  |  |  |  | 156.00 | Channar Shut |  |  | [{"equipmentGUID": "8017ee47-4b9a-ee11-a847-000d3acacefd", "code": "CHRPLT", "name": "Plant: CHR", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48181 | 2022-09-15T06:41:04+00:00 | 2022-09-15T14:41:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3674958+00:00 | 2026-06-17T09:01:01.3674958+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328186 | TRUE | TRUE | 2026-06-17T01:01:01.3674958+00:00 | 2026-06-17T09:01:01.3674958+08:00 | #48181 - PDO: 156hrs - PLANT: ERS | 8.1 | TRUE |  | 2027-05-31T22:00:00+00:00 | 2027-06-07T10:00:00+00:00 | 2027-06-01T06:00:00+08:00 | 2027-06-07T18:00:00+08:00 |  |  |  |  | 156.00 | ER plant shut |  |  | [{"equipmentGUID": "c35a111b-5a28-ef11-a84d-000d3acacefd", "code": "ERSPLT", "name": "Plant: ERS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48201 | 2022-09-15T07:11:10+00:00 | 2022-09-15T15:11:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.367505+00:00 | 2026-06-17T09:01:01.367505+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328187 | TRUE | TRUE | 2026-06-17T01:01:01.367505+00:00 | 2026-06-17T09:01:01.367505+08:00 | #48201 - PDO: 156hrs - PLANT: CHR | 8.1 | TRUE |  | 2027-05-17T22:00:00+00:00 | 2027-05-24T10:00:00+00:00 | 2027-05-18T06:00:00+08:00 | 2027-05-24T18:00:00+08:00 |  |  |  |  | 156.00 | Channar Shut |  |  | [{"equipmentGUID": "8017ee47-4b9a-ee11-a847-000d3acacefd", "code": "CHRPLT", "name": "Plant: CHR", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48180 | 2022-09-15T06:40:18+00:00 | 2022-09-15T14:40:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3675117+00:00 | 2026-06-17T09:01:01.3675117+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328188 | TRUE | TRUE | 2026-06-17T01:01:01.3675117+00:00 | 2026-06-17T09:01:01.3675117+08:00 | #48180 - PDO: 156hrs - PLANT: ERS | 6.1 | TRUE |  | 2027-03-01T22:00:00+00:00 | 2027-03-08T10:00:00+00:00 | 2027-03-02T06:00:00+08:00 | 2027-03-08T18:00:00+08:00 |  |  |  |  | 156.00 | ER plant shut |  |  | [{"equipmentGUID": "c35a111b-5a28-ef11-a84d-000d3acacefd", "code": "ERSPLT", "name": "Plant: ERS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
48200 | 2022-09-15T07:10:26+00:00 | 2022-09-15T15:10:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-17T01:01:01.3675177+00:00 | 2026-06-17T09:01:01.3675177+08:00 | {"principalGUID": "37671a34-1279-4205-afb5-67566e3347b5", "displayName": "Hempseed, Ola (RTIO)"} | {"name": "Fixed Plant"} | 328189 | TRUE | TRUE | 2026-06-17T01:01:01.3675177+00:00 | 2026-06-17T09:01:01.3675177+08:00 | #48200 - PDO: 156hrs - PLANT: CHR | 8.1 | TRUE |  | 2027-02-15T22:00:00+00:00 | 2027-02-22T10:00:00+00:00 | 2027-02-16T06:00:00+08:00 | 2027-02-22T18:00:00+08:00 |  |  |  |  | 156.00 | C/O 52WK Channar Primary Crush Main Shaft CR151 (Plan 1180721) |  |  | [{"equipmentGUID": "8017ee47-4b9a-ee11-a847-000d3acacefd", "code": "CHRPLT", "name": "Plant: CHR", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 37671a34-1279-4205-afb5-67566e3347b5 | Hempseed, Ola (RTIO) | Scheduled | PDO | Australia/Perth
44418 | 2021-11-25T02:02:52+00:00 | 2021-11-25T10:02:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-06T08:48:52.1152941+00:00 | 2026-07-06T16:48:52.1152941+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | {"name": "Fixed Plant"} | 329405 | TRUE | TRUE | 2026-07-06T08:48:52.1152941+00:00 | 2026-07-06T16:48:52.1152941+08:00 | #44418 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH | 11.0 | TRUE |  | 2027-12-09T10:00:00+00:00 | 2027-12-14T10:00:00+00:00 | 2027-12-09T18:00:00+08:00 | 2027-12-14T18:00:00+08:00 |  |  |  |  | 120.00 | HD1 North Plant Shut | Modular shut change - reduced main shut duration |  | [{"equipmentGUID": "6717ee47-4b9a-ee11-a847-000d3acacefd", "code": "HD1PLTNTH", "name": "Plant: HD1 North", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a7aaecea-901b-42c3-bfe5-631002e540c0", "emailAddress": "Ryan.Smith2@riotinto.com", "displayName": "Ryan Smith"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 75141, "shutVersionId": 334171, "title": "#75141 - HD1: 336hrs - HDBN00 REPAIR ROM WALL", "startDatetimeUTC": "2027-12-08T10:00:00+00:00", "endDatetimeUTC": "2027-12-22T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 9023233d-db3a-4caa-9e22-67fda071261e | O'Toole, Daniel (RTIO) | Scheduled | HD1 | Australia/Perth
44414 | 2021-11-25T02:02:42+00:00 | 2021-11-25T10:02:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-06T08:48:52.3382992+00:00 | 2026-07-06T16:48:52.3382992+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | {"name": "Fixed Plant"} | 329406 | TRUE | TRUE | 2026-07-06T08:48:52.3382992+00:00 | 2026-07-06T16:48:52.3382992+08:00 | #44414 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH | 10.0 | TRUE |  | 2027-09-09T10:00:00+00:00 | 2027-09-14T10:00:00+00:00 | 2027-09-09T18:00:00+08:00 | 2027-09-14T18:00:00+08:00 |  |  |  |  | 120.00 | HD1 North Plant Shut | Modular shut change - reduced main shut duration |  | [{"equipmentGUID": "6717ee47-4b9a-ee11-a847-000d3acacefd", "code": "HD1PLTNTH", "name": "Plant: HD1 North", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a7aaecea-901b-42c3-bfe5-631002e540c0", "emailAddress": "Ryan.Smith2@riotinto.com", "displayName": "Ryan Smith"}}] | [] | [] | [] | [] | [] | Approved | Update | 9023233d-db3a-4caa-9e22-67fda071261e | O'Toole, Daniel (RTIO) | Scheduled | HD1 | Australia/Perth
44412 | 2021-11-25T02:02:41+00:00 | 2021-11-25T10:02:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-06T08:48:52.5452733+00:00 | 2026-07-06T16:48:52.5452733+08:00 | {"principalGUID": "9023233d-db3a-4caa-9e22-67fda071261e", "displayName": "O'Toole, Daniel (RTIO)"} | {"name": "Fixed Plant"} | 329407 | TRUE | TRUE | 2026-07-06T08:48:52.5452733+00:00 | 2026-07-06T16:48:52.5452733+08:00 | #44412 - HD1: 120hrs - CRUSHER - PRIMARY: HD1 01 NORTH & CRUSHER - PRIMARY: HD1 51 SOUTH | 10.0 | TRUE |  | 2027-06-10T10:00:00+00:00 | 2027-06-15T10:00:00+00:00 | 2027-06-10T18:00:00+08:00 | 2027-06-15T18:00:00+08:00 |  |  |  |  | 120.00 | HD1 North Plant Shut | Modular Shut change - reduced Main Shut duration |  | [{"equipmentGUID": "6717ee47-4b9a-ee11-a847-000d3acacefd", "code": "HD1PLTNTH", "name": "Plant: HD1 North", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "a327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS01NTH", "name": "Crusher - Primary: HD1 01 North", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "0dd800c0-7c7b-ee11-a846-000d3acacefd", "code": "HD1PCS51STH", "name": "Crusher - Primary: HD1 51 South", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a7aaecea-901b-42c3-bfe5-631002e540c0", "emailAddress": "Ryan.Smith2@riotinto.com", "displayName": "Ryan Smith"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 74854, "shutVersionId": 285035, "title": "#74854 - HD1: 24hrs - HD1 TOTAL POWER OUTAGE PLT & TLO", "startDatetimeUTC": "2027-06-13T23:00:00+00:00", "endDatetimeUTC": "2027-06-14T23:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 64263, "shutVersionId": 322630, "title": "#64263 - HD4: 24hrs - HD4 TOTAL POWER OUTAGE PLT & TLO", "startDatetimeUTC": "2027-06-13T23:00:00+00:00", "endDatetimeUTC": "2027-06-14T23:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 9023233d-db3a-4caa-9e22-67fda071261e | O'Toole, Daniel (RTIO) | Scheduled | HD1 | Australia/Perth
44181 | 2021-11-23T06:50:11+00:00 | 2021-11-23T14:50:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-09T11:01:28.70363+00:00 | 2026-09-09T19:01:28.70363+08:00 | {"principalGUID": "c97c5fa3-10b1-4c37-be8e-73fd606e5a10", "displayName": "Anderson, Nicholas (RTIO)"} | {"name": "Fixed Plant"} | 333293 | TRUE | TRUE | 2026-09-09T11:01:28.70363+00:00 | 2026-09-09T19:01:28.70363+08:00 | #44181 - BM4: 336hrs - CRUSHER - PRIMARY: BM4 02 | 10.0 | TRUE |  | 2027-03-23T04:00:00+00:00 | 2027-04-06T04:00:00+00:00 | 2027-03-23T12:00:00+08:00 | 2027-04-06T12:00:00+08:00 |  |  |  |  | 336.00 | Per BS1 shutdown #65353 - BM4: 336hrs - BS1 PROJECT - SHUT #9 PC2 | BS1 shutdown extension drive base remediation work |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [{"code": "X", "name": "BS1", "projectTeam": {"name": "D&T"}, "totalProjectTime": "120"}] | [] | Approved | Update | c97c5fa3-10b1-4c37-be8e-73fd606e5a10 | Anderson, Nicholas (RTIO) | Scheduled | BM4 | Australia/Perth
71539 | 2025-10-28T02:08:22.700894+00:00 | 2025-10-28T10:08:22.700894+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-02T06:56:11.1102003+00:00 | 2026-10-02T14:56:11.1102003+08:00 | {"principalGUID": "c97c5fa3-10b1-4c37-be8e-73fd606e5a10", "displayName": "Anderson, Nicholas (RTIO)"} | {"name": "Fixed Plant"} | 335049 | TRUE | TRUE | 2026-10-02T06:56:11.1102003+00:00 | 2026-10-02T14:56:11.1102003+08:00 | #71539 - BM4: 288hrs - PC3 BS1 PROJECT PUNCH LISTING | 4.0 | TRUE |  | 2027-06-29T22:00:00+00:00 | 2027-07-11T22:00:00+00:00 | 2027-06-30T06:00:00+08:00 | 2027-07-12T06:00:00+08:00 |  |  |  |  | 288.00 | BS1 PC3 SHUT FOR PUNCHLISTING | Request from Shutdown team & Project team to allow more time for washdowns and isolations before power outage (see email for context) |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [{"code": "X", "name": "BS1 PROJECT PC3", "projectTeam": {"name": "D&T"}, "totalProjectTime": "288"}] | [] | Approved | Update | c97c5fa3-10b1-4c37-be8e-73fd606e5a10 | Anderson, Nicholas (RTIO) | Major Projects | BM4 | Australia/Perth
74777 | 2026-01-20T01:31:24.0997846+00:00 | 2026-01-20T09:31:24.0997846+08:00 | {"principalGUID": "c97c5fa3-10b1-4c37-be8e-73fd606e5a10", "displayName": "Anderson, Nicholas (RTIO)"} | 2026-02-05T06:32:51.8779965+00:00 | 2026-02-05T14:32:51.8779965+08:00 | {"principalGUID": "c97c5fa3-10b1-4c37-be8e-73fd606e5a10", "displayName": "Anderson, Nicholas (RTIO)"} | {"name": "Fixed Plant"} | 286017 | TRUE | TRUE | 2026-02-05T06:32:51.8779965+00:00 | 2026-02-05T14:32:51.8779965+08:00 | #74777 - BM4: 12hrs - PLANT: BM4 | 1.0 | TRUE |  | 2027-09-17T22:00:00+00:00 | 2027-09-18T10:00:00+00:00 | 2027-09-18T06:00:00+08:00 | 2027-09-18T18:00:00+08:00 |  |  |  |  | 12.00 | BST501/2 annual CAPD (functional safety) testing |  |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | c97c5fa3-10b1-4c37-be8e-73fd606e5a10 | Anderson, Nicholas (RTIO) | Scheduled | BM4 | Australia/Perth
74258 | 2025-12-04T01:06:37.0013454+00:00 | 2025-12-04T09:06:37.0013454+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-02-05T06:45:48.0002214+00:00 | 2026-02-05T14:45:48.0002214+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 286020 | TRUE | TRUE | 2026-02-05T06:45:48.0002214+00:00 | 2026-02-05T14:45:48.0002214+08:00 | #74258 - PDO: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | TRUE |  | 2027-04-05T20:00:00+00:00 | 2027-04-06T18:00:00+00:00 | 2027-04-06T04:00:00+08:00 | 2027-04-07T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons |  |  | [{"equipmentGUID": "3afc42b9-e71b-ef11-a84d-000d3acacefd", "code": "WRSPLT", "name": "Plant: WRS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Create | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | PDO | Australia/Perth
74401 | 2025-12-04T06:09:24.3448797+00:00 | 2025-12-04T14:09:24.3448797+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-02-05T06:46:19.6086792+00:00 | 2026-02-05T14:46:19.6086792+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 286021 | TRUE | TRUE | 2026-02-05T06:46:19.6086792+00:00 | 2026-02-05T14:46:19.6086792+08:00 | #74401 - WTS: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | TRUE |  | 2027-03-08T20:00:00+00:00 | 2027-03-09T18:00:00+00:00 | 2027-03-09T04:00:00+08:00 | 2027-03-10T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons | project team placeholder, align to plant PC shut |  | [{"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WTS | Australia/Perth
74395 | 2025-12-04T04:42:55.2236239+00:00 | 2025-12-04T12:42:55.2236239+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-02-06T06:05:04.470407+00:00 | 2026-02-06T14:05:04.470407+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 286289 | TRUE | TRUE | 2026-02-06T06:05:04.470407+00:00 | 2026-02-06T14:05:04.470407+08:00 | #74395 - WAN: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | TRUE |  | 2027-04-18T20:00:00+00:00 | 2027-04-19T18:00:00+00:00 | 2027-04-19T04:00:00+08:00 | 2027-04-20T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons |  |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6063fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS02", "name": "Crusher - Primary: WAN 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Create | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth
74256 | 2025-12-03T23:26:46.3247165+00:00 | 2025-12-04T07:26:46.3247165+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-02-03T01:58:21.6206513+00:00 | 2026-02-03T09:58:21.6206513+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 285581 | TRUE | TRUE | 2026-02-03T01:58:21.6206513+00:00 | 2026-02-03T09:58:21.6206513+08:00 | #74256 - PDO: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-04-05T20:00:00+00:00 | 2027-04-06T18:00:00+00:00 | 2027-04-06T04:00:00+08:00 | 2027-04-07T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. | ammended to align with plant and WR shut |  | [{"equipmentGUID": "2fe7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06W195", "name": "06W195 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3263fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06W208", "name": "06W208 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6441f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06W211", "name": "06W211 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ae23f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06W249", "name": "06W249 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "c2d100c0-7c7b-ee11-a846-000d3acacefd", "code": "06W250", "name": "06W250 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "da16f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06W248", "name": "06W248 Komatsu 830E-5 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ac689204-59ac-ef11-a857-000d3acacefd", "code": "06W251", "name": "06W251 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "241ee125-59ac-ef11-a857-000d3acacefd", "code": "06W272", "name": "06W272 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0ce5451e-59ac-ef11-a857-000d3acacefd", "code": "06W259", "name": "06W259 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d7e2ac44-59ac-ef11-a857-000d3acacefd", "code": "06W278", "name": "06W278 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d8602e4e-59ac-ef11-a857-000d3acacefd", "code": "06W279", "name": "06W279 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "00377495-c8aa-ef11-a857-000d3acacefd", "code": "06W281", "name": "06W281 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "4c9e6659-59ac-ef11-a857-000d3acacefd", "code": "06W280", "name": "06W280 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "24852cf8-c8aa-ef11-a857-000d3acacefd", "code": "06W282", "name": "06W282 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b5b07a7d-59ac-ef11-a857-000d3acacefd", "code": "06W283", "name": "06W283 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "48183f95-59ac-ef11-a857-000d3acacefd", "code": "06W325", "name": "06W325 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6dec339e-59ac-ef11-a857-000d3acacefd", "code": "06W326", "name": "06W326 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "680911a7-59ac-ef11-a857-000d3acacefd", "code": "06W331", "name": "06W331 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | PDO | Australia/Perth |  | Site Team
83633 | 2026-08-03T01:57:29.4232243+00:00 | 2026-08-03T09:57:29.4232243+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-18T23:17:49.2491887+00:00 | 2026-10-19T07:17:49.2491887+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 336182 | TRUE | TRUE | 2026-10-18T23:17:49.2491887+00:00 | 2026-10-19T07:17:49.2491887+08:00 | #83633 - YAN: 3hrs - HME AHS SERVER CUT OVER | 2.0 | TRUE |  | 2027-03-18T02:00:00+00:00 | 2027-03-18T05:00:00+00:00 | 2027-03-18T10:00:00+08:00 | 2027-03-18T13:00:00+08:00 |  |  |  |  | 3.00 | New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons. | requested 1 extra hour from project delivery team |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | YAN | Australia/Perth
74259 | 2025-12-04T01:27:38.1674292+00:00 | 2025-12-04T09:27:38.1674292+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2025-12-04T01:27:38.1674292+00:00 | 2025-12-04T09:27:38.1674292+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 279011 | TRUE | TRUE | 2025-12-04T01:27:38.1674292+00:00 | 2025-12-04T09:27:38.1674292+08:00 | #74259 - WAN: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | FALSE |  | 2027-04-18T20:00:00+00:00 | 2027-04-19T18:00:00+00:00 | 2027-04-19T04:00:00+08:00 | 2027-04-20T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons |  |  | [{"equipmentGUID": "6808f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R608", "name": "06R608 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "77e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R633", "name": "06R633 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8fede8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R634", "name": "06R634 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b8ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R640", "name": "06R640 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "390bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R644", "name": "06R644 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "301ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H855", "name": "06H855 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b52bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H001", "name": "06H001 Komatsu 830E-17AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "752df6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H199", "name": "06H199 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7a5afbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H146", "name": "06H146 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2ace00c0-7c7b-ee11-a846-000d3acacefd", "code": "06R526", "name": "06R526 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1e50fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R616", "name": "06R616 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7cd200c0-7c7b-ee11-a846-000d3acacefd", "code": "06R617", "name": "06R617 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0b2bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R635", "name": "06R635 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0720f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R650", "name": "06R650 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d116f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R878", "name": "06R878 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a46f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R919", "name": "06R919 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d11ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R921", "name": "06R921 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0233f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R787", "name": "06R787 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6bd800c0-7c7b-ee11-a846-000d3acacefd", "code": "06R788", "name": "06R788 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "51d700c0-7c7b-ee11-a846-000d3acacefd", "code": "06H790", "name": "06H790 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "aefae8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H198", "name": "06H198 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "79dde8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H562", "name": "06H562 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "c911f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R632", "name": "06R632 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7343f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R642", "name": "06R642 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6afee8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H781", "name": "06H781 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "bc70fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R728", "name": "06R728 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "715ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R920", "name": "06R920 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6010f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R766", "name": "06R766 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "a52ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H723", "name": "06H723 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ccd500c0-7c7b-ee11-a846-000d3acacefd", "code": "06H789", "name": "06H789 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7a05f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H205", "name": "06H205 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d521f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R418", "name": "06R418 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a33f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R931", "name": "06R931 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "13d400c0-7c7b-ee11-a846-000d3acacefd", "code": "06R411", "name": "06R411 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "eb5dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R990", "name": "06R990 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6124f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R417", "name": "06R417 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0d6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R413", "name": "06R413 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "e412f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R414", "name": "06R414 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3c38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R415", "name": "06R415 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0219f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R895", "name": "06R895 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0fe1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R914", "name": "06R914 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "580bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R412", "name": "06R412 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6476fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06R416", "name": "06R416 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "9a27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R647", "name": "06R647 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "bee200c0-7c7b-ee11-a846-000d3acacefd", "code": "06R655", "name": "06R655 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "bd13f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R267", "name": "06R267 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5729f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R268", "name": "06R268 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "cc30f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R269", "name": "06R269 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "232cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R270", "name": "06R270 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0915f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R271", "name": "06R271 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "482af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R660", "name": "06R660 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Create | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
74396 | 2025-12-04T05:49:11.4704222+00:00 | 2025-12-04T13:49:11.4704222+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2025-12-04T05:49:11.4704222+00:00 | 2025-12-04T13:49:11.4704222+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 279322 | TRUE | TRUE | 2025-12-04T05:49:11.4704222+00:00 | 2025-12-04T13:49:11.4704222+08:00 | #74396 - RVA: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 1.0 | FALSE |  | 2027-05-17T20:00:00+00:00 | 2027-05-18T18:00:00+00:00 | 2027-05-18T04:00:00+08:00 | 2027-05-19T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons |  |  | [{"equipmentGUID": "a10af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D320", "name": "06D320 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "da2af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R525", "name": "06R525 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fce0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R560", "name": "06R560 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1c31f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R561", "name": "06R561 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1de6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H612", "name": "06H612 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8318f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R464", "name": "06R464 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "cefbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R465", "name": "06R465 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "860df0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H142", "name": "06H142 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ad27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H145", "name": "06H145 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "34f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H143", "name": "06H143 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0f09f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H144", "name": "06H144 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ef6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06D340", "name": "06D340 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0b11f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D36", "name": "06D36 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ec26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R605", "name": "06R605 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Create | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | RVA | Australia/Perth |  | Site Team
74397 | 2025-12-04T05:56:33.9341511+00:00 | 2025-12-04T13:56:33.9341511+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2025-12-04T05:57:25.8889476+00:00 | 2025-12-04T13:57:25.8889476+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 279324 | TRUE | TRUE | 2025-12-04T05:57:25.8889476+00:00 | 2025-12-04T13:57:25.8889476+08:00 | #74397 - RVJ: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-05-17T20:00:00+00:00 | 2027-05-18T18:00:00+00:00 | 2027-05-18T04:00:00+08:00 | 2027-05-19T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons | date error |  | [{"equipmentGUID": "172df6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R31", "name": "06R31 CAT 789C Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3e27f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R39", "name": "06R39 CAT 789C Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "413bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H117", "name": "06H117 CAT 789C Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b922f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H128", "name": "06H128 CAT 789C Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fed600c0-7c7b-ee11-a846-000d3acacefd", "code": "06H140", "name": "06H140 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8ed600c0-7c7b-ee11-a846-000d3acacefd", "code": "06D350", "name": "06D350 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "410ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R606", "name": "06R606 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "78efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R607", "name": "06R607 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5e86bca0-58ac-ef11-a857-000d3acacefd", "code": "06R365", "name": "06R365 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2ba0229a-58ac-ef11-a857-000d3acacefd", "code": "06R364", "name": "06R364 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
74400 | 2025-12-04T06:06:43.7792724+00:00 | 2025-12-04T14:06:43.7792724+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-01-27T08:36:14.9375625+00:00 | 2026-01-27T16:36:14.9375625+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 285189 | TRUE | TRUE | 2026-01-27T08:36:14.9375625+00:00 | 2026-01-27T16:36:14.9375625+08:00 | #74400 - WTS: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-03-08T20:00:00+00:00 | 2027-03-09T18:00:00+00:00 | 2027-03-09T04:00:00+08:00 | 2027-03-10T02:00:00+08:00 |  |  |  |  | 22.00 | SOFTWARE: HME FRONTRUNNER DISPATCH | project team reschedule |  | [{"equipmentGUID": "6416f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H226", "name": "06H226 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2c25f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H230", "name": "06H230 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5938f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H224", "name": "06H224 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "376bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H225", "name": "06H225 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8959fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H227", "name": "06H227 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0672fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H229", "name": "06H229 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0ed200c0-7c7b-ee11-a846-000d3acacefd", "code": "06H231", "name": "06H231 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8c40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H228", "name": "06H228 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "af08f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H121", "name": "06H121 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H153", "name": "06H153 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f3dce8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H154", "name": "06H154 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8271fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H158", "name": "06H158 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "580ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H159", "name": "06H159 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ef5efbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H305", "name": "06H305 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "9441f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H306", "name": "06H306 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "111af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H308", "name": "06H308 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5d53fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H275", "name": "06H275 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "781ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H653", "name": "06H653 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a31f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H307", "name": "06H307 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f71ff0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H309", "name": "06H309 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "282af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H276", "name": "06H276 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6ddc00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H481", "name": "06H481 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "26e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H483", "name": "06H483 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f71ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H482", "name": "06H482 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83631 | 2026-08-03T01:53:55.0143722+00:00 | 2026-08-03T09:53:55.0143722+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-12T07:12:00.9484004+00:00 | 2026-10-12T15:12:00.9484004+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 335853 | TRUE | TRUE | 2026-10-12T07:12:00.9484004+00:00 | 2026-10-12T15:12:00.9484004+08:00 | #83631 - WTS: 2hrs - WTS2 NEW AHS SERVER CUT OVER | 2.0 | TRUE |  | 2027-06-08T02:00:00+00:00 | 2027-06-08T04:00:00+00:00 | 2027-06-08T10:00:00+08:00 | 2027-06-08T12:00:00+08:00 |  |  |  |  | 2.00 | New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons. | project delivery request |  | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WTS | Australia/Perth
83628 | 2026-08-03T01:26:53.1766441+00:00 | 2026-08-03T09:26:53.1766441+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-17T23:24:52.3050069+00:00 | 2026-08-18T07:24:52.3050069+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 331361 | TRUE | TRUE | 2026-08-17T23:24:52.3050069+00:00 | 2026-08-18T07:24:52.3050069+08:00 | #83628 - RVA: 2hrs - AHS SERVER CUT OVER | 2.0 | TRUE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | ALL AT’s will be down however site can still move staffed/manual tons. RV Mesa A and J: New AHS Server Cut Over | vendor feedback and availability |  | [{"equipmentGUID": "7417ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLT", "name": "Plant: RVA Dry", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | RVA | Australia/Perth
83629 | 2026-08-03T01:30:43.0325384+00:00 | 2026-08-03T09:30:43.0325384+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-17T23:25:05.420404+00:00 | 2026-08-18T07:25:05.420404+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "Fixed Plant"} | 331362 | TRUE | TRUE | 2026-08-17T23:25:05.420404+00:00 | 2026-08-18T07:25:05.420404+08:00 | #83629 - RVJ: 2hrs - AHS SERVER CUT OVER | 2.0 | TRUE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | ALL AT’s will be down however site can still move staffed/manual tons. RV Mesa A and J: New AHS Server Cut Over | moved due to vendor feedback and availability |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2123f0bf-7c7b-ee11-a846-000d3acacefd", "code": "RVJPCSSZ03", "name": "Crusher - Primary: RVJ Primary Sizer 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83624, "shutVersionId": 330971, "title": "#83624 - RVJ: 2hrs - AHS SERVER CUT OVER", "startDatetimeUTC": "2027-05-25T02:00:00+00:00", "endDatetimeUTC": "2027-05-25T04:00:00+00:00"}}] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | RVJ | Australia/Perth
83627 | 2026-07-31T06:14:44.1675109+00:00 | 2026-07-31T14:14:44.1675109+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-10T02:53:38.8949164+00:00 | 2026-08-10T10:53:38.8949164+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 330975 | TRUE | TRUE | 2026-08-10T02:53:38.8949164+00:00 | 2026-08-10T10:53:38.8949164+08:00 | #83627 - SYSTEM: 2hrs - AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | RV Mesa A and J: New AHS Server, ALL AT’s will be down however site can still move staffed/manual tons. | moved due to vendor feedback and availability |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "RVA"}] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled |  | Australia/Perth
83630 | 2026-08-03T01:51:52.1960386+00:00 | 2026-08-03T09:51:52.1960386+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-08T00:33:55.8404174+00:00 | 2026-10-08T08:33:55.8404174+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 335456 | TRUE | TRUE | 2026-10-08T00:33:55.8404174+00:00 | 2026-10-08T08:33:55.8404174+08:00 | #83630 - WTS: 2hrs - WTS2 AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-06-08T02:00:00+00:00 | 2027-06-08T04:00:00+00:00 | 2027-06-08T10:00:00+08:00 | 2027-06-08T12:00:00+08:00 |  |  |  |  | 2.00 | ALL AT’s will be down however site can still move staffed/manual tons. | project delivery request |  | [{"equipmentGUID": "6416f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H226", "name": "06H226 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2c25f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H230", "name": "06H230 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5938f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H224", "name": "06H224 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "376bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H225", "name": "06H225 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8959fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H227", "name": "06H227 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0672fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H229", "name": "06H229 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0ed200c0-7c7b-ee11-a846-000d3acacefd", "code": "06H231", "name": "06H231 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8c40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H228", "name": "06H228 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "af08f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H121", "name": "06H121 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H153", "name": "06H153 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f3dce8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H154", "name": "06H154 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "580ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H159", "name": "06H159 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ef5efbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H305", "name": "06H305 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "9441f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H306", "name": "06H306 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "111af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H308", "name": "06H308 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "781ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H653", "name": "06H653 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a31f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H307", "name": "06H307 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f71ff0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H309", "name": "06H309 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6ddc00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H481", "name": "06H481 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "26e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H483", "name": "06H483 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f71ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H482", "name": "06H482 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83632 | 2026-08-03T01:55:32.7754942+00:00 | 2026-08-03T09:55:32.7754942+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-08T00:35:12.0971925+00:00 | 2026-10-08T08:35:12.0971925+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 335458 | TRUE | TRUE | 2026-10-08T00:35:12.0971925+00:00 | 2026-10-08T08:35:12.0971925+08:00 | #83632 - SYSTEM: 2hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-06-08T02:00:00+00:00 | 2027-06-08T04:00:00+00:00 | 2027-06-08T10:00:00+08:00 | 2027-06-08T12:00:00+08:00 |  |  |  |  | 2.00 | New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons. | project delivery request |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "WTS"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint |  | Australia/Perth
83634 | 2026-08-03T02:02:54.4012441+00:00 | 2026-08-03T10:02:54.4012441+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-08T00:37:48.5995839+00:00 | 2026-10-08T08:37:48.5995839+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 335460 | TRUE | TRUE | 2026-10-08T00:37:48.5995839+00:00 | 2026-10-08T08:37:48.5995839+08:00 | #83634 - YAN: 3hrs - AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-03-18T02:00:00+00:00 | 2027-03-18T05:00:00+00:00 | 2027-03-18T10:00:00+08:00 | 2027-03-18T13:00:00+08:00 |  |  |  |  | 3.00 | New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons. | 1 additional hour requested by delivery team |  | [{"equipmentGUID": "ee08f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H537", "name": "06H537 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6607f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H810", "name": "06H810 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3ff4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H831", "name": "06H831 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "a1f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H880", "name": "06H880 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "a70df0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H901", "name": "06H901 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "46dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H203", "name": "06H203 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "91e200c0-7c7b-ee11-a846-000d3acacefd", "code": "06H540", "name": "06H540 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "836dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H573", "name": "06H573 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "e834f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H809", "name": "06H809 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8f60fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H811", "name": "06H811 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ca2bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H812", "name": "06H812 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "553af6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H813", "name": "06H813 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fed800c0-7c7b-ee11-a846-000d3acacefd", "code": "06H814", "name": "06H814 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b626f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H830", "name": "06H830 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ecdb00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H955", "name": "06H955 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0c63fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H900", "name": "06H900 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ec60fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H201", "name": "06H201 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3817f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H533", "name": "06H533 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "a7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H534", "name": "06H534 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "22eae8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H536", "name": "06H536 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a1df0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H535", "name": "06H535 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "450ff0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H564", "name": "06H564 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8320f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H576", "name": "06H576 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1b5ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H815", "name": "06H815 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "68dbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H816", "name": "06H816 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6b68fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H206", "name": "06H206 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1663fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H207", "name": "06H207 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1fffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H953", "name": "06H953 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6b41f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H784", "name": "06H784 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8bd9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H910", "name": "06H910 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "76d400c0-7c7b-ee11-a846-000d3acacefd", "code": "06H911", "name": "06H911 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d226b012-607d-f011-a802-002248933a47", "code": "06H215", "name": "06H215 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "47791821-607d-f011-a802-002248933a47", "code": "06H399", "name": "06H399 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "684a4d03-607d-f011-a802-002248933a47", "code": "06H400", "name": "06H400 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "48791821-607d-f011-a802-002248933a47", "code": "06H401", "name": "06H401 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f8a9b365-607d-f011-a802-002248933a47", "code": "06H402", "name": "06H402 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7368c15c-607d-f011-a802-002248933a47", "code": "06H403", "name": "06H403 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "78ddeeea-5f7d-f011-a802-002248933a47", "code": "06H444", "name": "06H444 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "674a4d03-607d-f011-a802-002248933a47", "code": "06H445", "name": "06H445 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "13cbf839-607d-f011-a802-002248933a47", "code": "06H446", "name": "06H446 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "73f69656-607d-f011-a802-002248933a47", "code": "06H447", "name": "06H447 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "04dc7749-607d-f011-a802-002248933a47", "code": "06H473", "name": "06H473 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f2f933f4-5f7d-f011-a802-002248933a47", "code": "06H474", "name": "06H474 Komatsu 930E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83635 | 2026-08-03T02:06:00.4746599+00:00 | 2026-08-03T10:06:00.4746599+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-10-08T00:38:20.2682501+00:00 | 2026-10-08T08:38:20.2682501+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 335461 | TRUE | TRUE | 2026-10-08T00:38:20.2682501+00:00 | 2026-10-08T08:38:20.2682501+08:00 | #83635 - SYSTEM: 3hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-03-18T02:00:00+00:00 | 2027-03-18T05:00:00+00:00 | 2027-03-18T10:00:00+08:00 | 2027-03-18T13:00:00+08:00 |  |  |  |  | 3.00 | New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons. | 1 extra hour requested by project delivery team |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "YAN"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint |  | Australia/Perth
83623 | 2026-07-31T05:59:49.9433118+00:00 | 2026-07-31T13:59:49.9433118+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-10T02:47:10.2678652+00:00 | 2026-08-10T10:47:10.2678652+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330970 | TRUE | TRUE | 2026-08-10T02:47:10.2678652+00:00 | 2026-08-10T10:47:10.2678652+08:00 | #83623 - RVA: 2hrs - AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | ALL AT’s will be down however site can still move staffed/manual tons. RV Mesa A and J: New AHS Server Cut Over | changed, based on vendor availability and feedback |  | [{"equipmentGUID": "a10af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D320", "name": "06D320 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "da2af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R525", "name": "06R525 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fce0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R560", "name": "06R560 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "1c31f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06R561", "name": "06R561 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8318f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R464", "name": "06R464 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "cefbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R465", "name": "06R465 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "860df0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H142", "name": "06H142 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ad27f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H145", "name": "06H145 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "34f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H143", "name": "06H143 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0f09f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H144", "name": "06H144 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ef6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06D340", "name": "06D340 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0b11f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06D36", "name": "06D36 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ec26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R605", "name": "06R605 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | RVA | Australia/Perth |  | Site Team
83624 | 2026-07-31T06:04:26.7306347+00:00 | 2026-07-31T14:04:26.7306347+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-10T02:48:09.9235854+00:00 | 2026-08-10T10:48:09.9235854+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330971 | TRUE | TRUE | 2026-08-10T02:48:09.9235854+00:00 | 2026-08-10T10:48:09.9235854+08:00 | #83624 - RVJ: 2hrs - AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | RV Mesa A and J: New AHS Server Cut Over, ALL AT’s will be down however site can still move staffed/manual tons | moved, due to vendor feedback and availability |  | [{"equipmentGUID": "89ece8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H141", "name": "06H141 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7a5afbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H146", "name": "06H146 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fed600c0-7c7b-ee11-a846-000d3acacefd", "code": "06H140", "name": "06H140 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "8ed600c0-7c7b-ee11-a846-000d3acacefd", "code": "06D350", "name": "06D350 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "410ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R606", "name": "06R606 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "78efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R607", "name": "06R607 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5e86bca0-58ac-ef11-a857-000d3acacefd", "code": "06R365", "name": "06R365 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2ba0229a-58ac-ef11-a857-000d3acacefd", "code": "06R364", "name": "06R364 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d84a88e7-5d7d-f011-a802-002248933a47", "code": "06R368", "name": "06R368 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "4b941609-5e7d-f011-a802-002248933a47", "code": "06R369", "name": "06R369 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "fac0befe-5d7d-f011-a802-002248933a47", "code": "06R388", "name": "06R388 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "0f546e9a-5d7d-f011-a802-002248933a47", "code": "06R389", "name": "06R389 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "3311ccdd-5d7d-f011-a802-002248933a47", "code": "06R393", "name": "06R393 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6f476215-5e7d-f011-a802-002248933a47", "code": "06R394", "name": "06R394 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "c759e5f4-5d7d-f011-a802-002248933a47", "code": "06R466", "name": "06R466 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "5a1cc7c6-5d7d-f011-a802-002248933a47", "code": "06R467", "name": "06R467 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "dcbc1fd1-5d7d-f011-a802-002248933a47", "code": "06R468", "name": "06R468 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "9e16b5bc-5d7d-f011-a802-002248933a47", "code": "06R469", "name": "06R469 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "2c8a5058-5d7d-f011-a802-002248933a47", "code": "06R470", "name": "06R470 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "65178a63-5d7d-f011-a802-002248933a47", "code": "06R471", "name": "06R471 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83629, "shutVersionId": 331362, "title": "#83629 - RVJ: 2hrs - AHS SERVER CUT OVER", "startDatetimeUTC": "2027-05-25T02:00:00+00:00", "endDatetimeUTC": "2027-05-25T04:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled | RVJ | Australia/Perth |  | Site Team
83626 | 2026-07-31T06:08:35.455165+00:00 | 2026-07-31T14:08:35.455165+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-10T02:48:55.8263842+00:00 | 2026-08-10T10:48:55.8263842+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 330972 | TRUE | TRUE | 2026-08-10T02:48:55.8263842+00:00 | 2026-08-10T10:48:55.8263842+08:00 | #83626 - SYSTEM: 2hrs - AHS SERVER CUT OVER | 2.0 | FALSE |  | 2027-05-25T02:00:00+00:00 | 2027-05-25T04:00:00+00:00 | 2027-05-25T10:00:00+08:00 | 2027-05-25T12:00:00+08:00 |  |  |  |  | 2.00 | RV Mesa A and J: New AHS Server Cut Over | moved due to vendor feedback and availability |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "RVJ"}] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled |  | Australia/Perth
83617 | 2026-07-31T01:53:27.7205026+00:00 | 2026-07-31T09:53:27.7205026+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:03:14.3275671+00:00 | 2026-07-31T10:03:14.3275671+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330661 | TRUE | TRUE | 2026-07-31T02:03:14.3275671+00:00 | 2026-07-31T10:03:14.3275671+08:00 | #83617 - WAN: 12hrs - 06H532 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.1 | FALSE |  | 2027-01-24T22:00:00+00:00 | 2027-01-25T10:00:00+00:00 | 2027-01-25T06:00:00+08:00 | 2027-01-25T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site |  |  | [{"equipmentGUID": "d115f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H532", "name": "06H532 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
83619 | 2026-07-31T01:56:13.0091495+00:00 | 2026-07-31T09:56:13.0091495+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:03:50.1370979+00:00 | 2026-07-31T10:03:50.1370979+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330662 | TRUE | TRUE | 2026-07-31T02:03:50.1370979+00:00 | 2026-07-31T10:03:50.1370979+08:00 | #83619 - WAN: 12hrs - 06H199 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.1 | FALSE |  | 2027-01-26T22:00:00+00:00 | 2027-01-27T10:00:00+00:00 | 2027-01-27T06:00:00+08:00 | 2027-01-27T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site. |  |  | [{"equipmentGUID": "752df6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H199", "name": "06H199 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
83620 | 2026-07-31T01:57:23.2863195+00:00 | 2026-07-31T09:57:23.2863195+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:04:16.2794904+00:00 | 2026-07-31T10:04:16.2794904+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330663 | TRUE | TRUE | 2026-07-31T02:04:16.2794904+00:00 | 2026-07-31T10:04:16.2794904+08:00 | #83620 - WAN: 12hrs - 06R632 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.1 | FALSE |  | 2027-01-27T22:00:00+00:00 | 2027-01-28T10:00:00+00:00 | 2027-01-28T06:00:00+08:00 | 2027-01-28T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site. |  |  | [{"equipmentGUID": "c911f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R632", "name": "06R632 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
83621 | 2026-07-31T01:58:20.4547601+00:00 | 2026-07-31T09:58:20.4547601+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:04:37.9986757+00:00 | 2026-07-31T10:04:37.9986757+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330664 | TRUE | TRUE | 2026-07-31T02:04:37.9986757+00:00 | 2026-07-31T10:04:37.9986757+08:00 | #83621 - WAN: 12hrs - 06R633 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.1 | FALSE |  | 2027-01-28T22:00:00+00:00 | 2027-01-29T10:00:00+00:00 | 2027-01-29T06:00:00+08:00 | 2027-01-29T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site. |  |  | [{"equipmentGUID": "77e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R633", "name": "06R633 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
83622 | 2026-07-31T01:59:14.9461055+00:00 | 2026-07-31T09:59:14.9461055+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:05:00.934576+00:00 | 2026-07-31T10:05:00.934576+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330665 | TRUE | TRUE | 2026-07-31T02:05:00.934576+00:00 | 2026-07-31T10:05:00.934576+08:00 | #83622 - WAN: 12hrs - 06H198 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.1 | FALSE |  | 2027-01-29T22:00:00+00:00 | 2027-01-30T10:00:00+00:00 | 2027-01-30T06:00:00+08:00 | 2027-01-30T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site. |  |  | [{"equipmentGUID": "aefae8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H198", "name": "06H198 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
83618 | 2026-07-31T01:54:49.0459441+00:00 | 2026-07-31T09:54:49.0459441+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-07-31T02:06:20.1684834+00:00 | 2026-07-31T10:06:20.1684834+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "HME"} | 330667 | TRUE | TRUE | 2026-07-31T02:06:20.1684834+00:00 | 2026-07-31T10:06:20.1684834+08:00 | #83618 - WAN: 12hrs - 06R644 AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.3 | FALSE |  | 2027-01-25T22:00:00+00:00 | 2027-01-26T10:00:00+00:00 | 2027-01-26T06:00:00+08:00 | 2027-01-26T18:00:00+08:00 |  |  |  |  | 12.00 | These trucks are now out of AGCCS project scope, as the final commissioning activities could not be completed due to equipment damage or removal. As a result, the remaining work will need to be completed and funded by Site. |  |  | [{"equipmentGUID": "390bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R644", "name": "06R644 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "dfa6ed62-b3da-4008-9b38-b7735795e488", "emailAddress": "Tasha.Chatfield@riotinto.com", "displayName": "Chatfield, Tasha (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Site Constraint | WAN | Australia/Perth |  | Site Team
73405 | 2025-11-24T10:02:49.4562787+00:00 | 2025-11-24T18:02:49.4562787+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | 2026-02-16T06:08:32.08197+00:00 | 2026-02-16T14:08:32.08197+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 287142 | TRUE | TRUE | 2026-02-16T06:08:32.08197+00:00 | 2026-02-16T14:08:32.08197+08:00 | #73405 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 2.0 | FALSE |  | 2027-03-08T20:00:00+00:00 | 2027-03-09T18:00:00+00:00 | 2027-03-09T04:00:00+08:00 | 2027-03-10T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. | moved to align with FP and HME |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "WTS"}] | [{"relationshipType": null, "shut": {"shutId": 69723, "shutVersionId": 257967, "title": "#69723 - WTS: 216hrs - CRUSHER - PRIMARY: WTS2 04", "startDatetimeUTC": "2027-06-05T11:00:00+00:00", "endDatetimeUTC": "2027-06-14T11:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled |  | Australia/Perth
73403 | 2025-11-24T10:00:06.0746277+00:00 | 2025-11-24T18:00:06.0746277+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | 2026-04-02T01:41:12.506731+00:00 | 2026-04-02T09:41:12.506731+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 324552 | TRUE | TRUE | 2026-04-02T01:41:12.506731+00:00 | 2026-04-02T09:41:12.506731+08:00 | #73403 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 4.0 | FALSE |  | 2027-04-05T20:00:00+00:00 | 2027-04-06T18:00:00+00:00 | 2027-04-06T04:00:00+08:00 | 2027-04-07T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. | restored due to error |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "PDO"}] | [] | [] | [] | [] | Approved | Restore | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled |  | Australia/Perth
73404 | 2025-11-24T10:01:28.5604432+00:00 | 2025-11-24T18:01:28.5604432+08:00 | {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "displayName": "Chia, Daniel (RTIO-WORKPAC)"} | 2026-03-26T01:40:10.1366761+00:00 | 2026-03-26T09:40:10.1366761+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | {"name": "System"} | 324275 | TRUE | TRUE | 2026-03-26T01:40:10.1366761+00:00 | 2026-03-26T09:40:10.1366761+08:00 | #73404 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH | 3.0 | FALSE |  | 2027-04-18T20:00:00+00:00 | 2027-04-19T18:00:00+00:00 | 2027-04-19T04:00:00+08:00 | 2027-04-20T02:00:00+08:00 |  |  |  |  | 22.00 | Komatsu Front Runner AHS Upgrade, plant shut window is aligned with this shut, ROM's can be fed from stockpiles with staffed trucks and paper tons. | error |  | [{"equipmentGUID": "", "code": "HME FRONTRUNNER DISPATCH", "name": "Software: HME Frontrunner Dispatch", "assetClass": {"name": "Systems"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "925da579-f1af-4b9c-ba1f-43b4f631a43a", "emailAddress": "Ryan.Beaumont@riotinto.com", "displayName": "Ryan Beaumont"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "e76be1a2-087e-4b54-8c65-7825375ab7d2", "emailAddress": "Daniel.Chia2@riotinto.com", "displayName": "Daniel Chia"}}] | [{"name": "WAN"}] | [{"relationshipType": null, "shut": {"shutId": 44328, "shutVersionId": 330646, "title": "#44328 - WAN: 144hrs - PLANT: WAN", "startDatetimeUTC": "2027-04-15T10:30:00+00:00", "endDatetimeUTC": "2027-04-21T10:30:00+00:00"}}] | [] | [] | [] | Approved | Restore | 19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc | Barlow, Scott A (RTIO) | Scheduled |  | Australia/Perth
84496 | 2026-10-17T05:24:53.8417796+00:00 | 2026-10-17T13:24:53.8417796+08:00 | {"principalGUID": "ad9362cf-64e6-4c53-b904-529b695986ad", "displayName": "George, Blake (RTIO)"} | 2026-10-18T07:56:43.8691666+00:00 | 2026-10-18T15:56:43.8691666+08:00 | {"principalGUID": "69a8451c-6577-42f0-9cea-8150546609fc", "displayName": "Vickery-Howe, Anthony (RTIO)"} | {"name": "Utilities"} | 336181 | TRUE | TRUE | 2026-10-18T07:56:43.8691666+00:00 | 2026-10-18T15:56:43.8691666+08:00 | #84496 - UTL: 209hrs - GENERATION: WAPR WAG2 | 2.0 | FALSE |  | 2027-02-22T23:00:00+00:00 | 2027-03-03T16:00:00+00:00 | 2027-02-23T07:00:00+08:00 | 2027-03-04T00:00:00+08:00 |  |  |  |  | 209.00 | 8K shut placeholder. Dependent on weather. end of wet season. | Correction of asset shut to WAG2 |  | [{"equipmentGUID": "", "code": "UTLGENWAG2 WAPR", "name": "Generation: WAPR WAG2", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "ad9362cf-64e6-4c53-b904-529b695986ad", "emailAddress": "Blake.George@riotinto.com", "displayName": "George, Blake (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "adf3ad49-5e24-4180-8ab5-11188bb64948", "emailAddress": "Jamie.Campbell3@riotinto.com", "displayName": "Campbell, Jamie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 69a8451c-6577-42f0-9cea-8150546609fc | Vickery-Howe, Anthony (RTIO) | Placeholder |  | Australia/Perth
83910 | 2026-09-10T00:53:48.3521643+00:00 | 2026-09-10T08:53:48.3521643+08:00 | {"principalGUID": "57e6f86e-d8e3-42f7-af50-86b69333ab22", "displayName": "Brookes, John (RTIO)"} | 2026-09-10T00:53:48.3521643+00:00 | 2026-09-10T08:53:48.3521643+08:00 | {"principalGUID": "57e6f86e-d8e3-42f7-af50-86b69333ab22", "displayName": "Brookes, John (RTIO)"} | {"name": "HME"} | 333309 | TRUE | TRUE | 2026-09-10T00:53:48.3521643+00:00 | 2026-09-10T08:53:48.3521643+08:00 | #83910 - HD4: 274hrs - 21D13 ATLAS COPCO PV271 DRILL | 1.0 | FALSE |  | 2026-11-23T16:00:00+00:00 | 2026-12-05T02:00:00+00:00 | 2026-11-24T00:00:00+08:00 | 2026-12-05T10:00:00+08:00 |  |  |  |  | 274.00 | RCS5 PV271 Upgrade |  |  | [{"equipmentGUID": "456dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "21D13", "name": "21D13 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "57e6f86e-d8e3-42f7-af50-86b69333ab22", "emailAddress": "John.Brookes@riotinto.com", "displayName": "Brookes, John (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | 57e6f86e-d8e3-42f7-af50-86b69333ab22 | Brookes, John (RTIO) | Unscheduled | HD4 | Australia/Perth |  | Drills
41394 | 2021-05-20T03:43:58+00:00 | 2021-05-20T11:43:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-29T01:42:38.182491+00:00 | 2026-07-29T09:42:38.182491+08:00 | {"principalGUID": "57e6f86e-d8e3-42f7-af50-86b69333ab22", "displayName": "Brookes, John (RTIO)"} | {"name": "Fixed Plant"} | 330481 | TRUE | TRUE | 2026-07-29T01:42:38.182491+00:00 | 2026-07-29T09:42:38.182491+08:00 | #41394 - HD4: 198hrs - PLANT: HD4 | 11.1 | TRUE |  | 2026-12-02T04:00:00+00:00 | 2026-12-10T10:00:00+00:00 | 2026-12-02T12:00:00+08:00 | 2026-12-10T18:00:00+08:00 |  |  |  |  | 198.00 | HD4 Plant Shut |  | SHDP2649 | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 57e6f86e-d8e3-42f7-af50-86b69333ab22 | Brookes, John (RTIO) | Scheduled | HD4 | Australia/Perth
41409 | 2021-05-20T04:24:42+00:00 | 2021-05-20T12:24:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-29T01:43:55.2953232+00:00 | 2026-07-29T09:43:55.2953232+08:00 | {"principalGUID": "57e6f86e-d8e3-42f7-af50-86b69333ab22", "displayName": "Brookes, John (RTIO)"} | {"name": "Fixed Plant"} | 330482 | TRUE | TRUE | 2026-07-29T01:43:55.2953232+00:00 | 2026-07-29T09:43:55.2953232+08:00 | #41409 - HD4: 96hrs - TRAIN LOADOUT: HD4 | 12.1 | TRUE |  | 2026-12-10T22:00:00+00:00 | 2026-12-14T22:00:00+00:00 | 2026-12-11T06:00:00+08:00 | 2026-12-15T06:00:00+08:00 |  |  |  |  | 96.00 | HD4 TLO Shut |  | SHDT2650 | [{"equipmentGUID": "2cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "HD4TLO", "name": "Train Loadout: HD4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 57e6f86e-d8e3-42f7-af50-86b69333ab22 | Brookes, John (RTIO) | Scheduled | HD4 | Australia/Perth
48320 | 2022-09-16T02:14:12+00:00 | 2022-09-16T10:14:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-08-03T10:08:01.39122+00:00 | 2026-08-03T18:08:01.39122+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 330743 | TRUE | TRUE | 2026-08-03T10:08:01.39122+00:00 | 2026-08-03T18:08:01.39122+08:00 | #48320 - PDO: 240hrs - CRUSHER - PRIMARY: PDO 01 | 9.0 | TRUE |  | 2027-12-11T10:00:00+00:00 | 2027-12-21T10:00:00+00:00 | 2027-12-11T18:00:00+08:00 | 2027-12-21T18:00:00+08:00 |  |  |  |  | 240.00 | PLT PC Shut | PC01 Concaves will be required to be changed - this needs to occur prior to 2028. |  | [{"equipmentGUID": "f36afbbf-7c7b-ee11-a846-000d3acacefd", "code": "PDOPCS01", "name": "Crusher - Primary: PDO 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83749 | 2026-08-25T00:09:52.5661198+00:00 | 2026-08-25T08:09:52.5661198+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:46:33.7314523+00:00 | 2026-09-02T11:46:33.7314523+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333090 | TRUE | TRUE | 2026-09-02T03:46:33.7314523+00:00 | 2026-09-02T11:46:33.7314523+08:00 | #83749 - PDO: 80hrs - MODULE - PLANT: PDO FINES D | 1.0 | FALSE |  | 2027-11-15T06:00:00+00:00 | 2027-11-18T14:00:00+00:00 | 2027-11-15T14:00:00+08:00 | 2027-11-18T22:00:00+08:00 |  |  |  |  | 80.00 | MOD D Outage |  |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83748 | 2026-08-25T00:09:52.4495313+00:00 | 2026-08-25T08:09:52.4495313+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:46:52.4393627+00:00 | 2026-09-02T11:46:52.4393627+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333091 | TRUE | TRUE | 2026-09-02T03:46:52.4393627+00:00 | 2026-09-02T11:46:52.4393627+08:00 | #83748 - PDO: 80hrs - MODULE - PLANT: PDO FINES D | 1.0 | FALSE |  | 2027-08-16T06:00:00+00:00 | 2027-08-19T14:00:00+00:00 | 2027-08-16T14:00:00+08:00 | 2027-08-19T22:00:00+08:00 |  |  |  |  | 80.00 | MOD D Outage |  |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83747 | 2026-08-25T00:09:52.3336384+00:00 | 2026-08-25T08:09:52.3336384+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:47:07.8213714+00:00 | 2026-09-02T11:47:07.8213714+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333092 | TRUE | TRUE | 2026-09-02T03:47:07.8213714+00:00 | 2026-09-02T11:47:07.8213714+08:00 | #83747 - PDO: 80hrs - MODULE - PLANT: PDO FINES D | 1.0 | FALSE |  | 2027-05-17T06:00:00+00:00 | 2027-05-20T14:00:00+00:00 | 2027-05-17T14:00:00+08:00 | 2027-05-20T22:00:00+08:00 |  |  |  |  | 80.00 | MOD D Outage |  |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83746 | 2026-08-25T00:09:52.1882047+00:00 | 2026-08-25T08:09:52.1882047+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:47:32.6422684+00:00 | 2026-09-02T11:47:32.6422684+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333093 | TRUE | TRUE | 2026-09-02T03:47:32.6422684+00:00 | 2026-09-02T11:47:32.6422684+08:00 | #83746 - PDO: 80hrs - MODULE - PLANT: PDO FINES D | 1.0 | FALSE |  | 2027-02-15T06:00:00+00:00 | 2027-02-18T14:00:00+00:00 | 2027-02-15T14:00:00+08:00 | 2027-02-18T22:00:00+08:00 |  |  |  |  | 80.00 | MOD D Outage |  |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83744 | 2026-08-25T00:07:44.0185498+00:00 | 2026-08-25T08:07:44.0185498+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:48:08.79176+00:00 | 2026-09-02T11:48:08.79176+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333094 | TRUE | TRUE | 2026-09-02T03:48:08.79176+00:00 | 2026-09-02T11:48:08.79176+08:00 | #83744 - PDO: 80hrs - MODULE - PLANT: PDO FINES C | 1.0 | FALSE |  | 2027-11-11T22:00:00+00:00 | 2027-11-15T06:00:00+00:00 | 2027-11-12T06:00:00+08:00 | 2027-11-15T14:00:00+08:00 |  |  |  |  | 80.00 | MOD C Outage |  |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83743 | 2026-08-25T00:07:43.911608+00:00 | 2026-08-25T08:07:43.911608+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:48:47.9866689+00:00 | 2026-09-02T11:48:47.9866689+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333095 | TRUE | TRUE | 2026-09-02T03:48:47.9866689+00:00 | 2026-09-02T11:48:47.9866689+08:00 | #83743 - PDO: 80hrs - MODULE - PLANT: PDO FINES C | 1.0 | FALSE |  | 2027-08-12T22:00:00+00:00 | 2027-08-16T06:00:00+00:00 | 2027-08-13T06:00:00+08:00 | 2027-08-16T14:00:00+08:00 |  |  |  |  | 80.00 | MOD C Outage |  |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83741 | 2026-08-25T00:07:43.6903629+00:00 | 2026-08-25T08:07:43.6903629+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:49:05.4995573+00:00 | 2026-09-02T11:49:05.4995573+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333096 | TRUE | TRUE | 2026-09-02T03:49:05.4995573+00:00 | 2026-09-02T11:49:05.4995573+08:00 | #83741 - PDO: 80hrs - MODULE - PLANT: PDO FINES C | 1.0 | FALSE |  | 2027-02-11T22:00:00+00:00 | 2027-02-15T06:00:00+00:00 | 2027-02-12T06:00:00+08:00 | 2027-02-15T14:00:00+08:00 |  |  |  |  | 80.00 | MOD C Outage |  |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83742 | 2026-08-25T00:07:43.8070049+00:00 | 2026-08-25T08:07:43.8070049+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:49:20.6466361+00:00 | 2026-09-02T11:49:20.6466361+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333097 | TRUE | TRUE | 2026-09-02T03:49:20.6466361+00:00 | 2026-09-02T11:49:20.6466361+08:00 | #83742 - PDO: 80hrs - MODULE - PLANT: PDO FINES C | 1.0 | FALSE |  | 2027-05-13T22:00:00+00:00 | 2027-05-17T06:00:00+00:00 | 2027-05-14T06:00:00+08:00 | 2027-05-17T14:00:00+08:00 |  |  |  |  | 80.00 | MOD C Outage |  |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83738 | 2026-08-24T04:29:15.1918213+00:00 | 2026-08-24T12:29:15.1918213+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:50:29.9682052+00:00 | 2026-09-02T11:50:29.9682052+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333098 | TRUE | TRUE | 2026-09-02T03:50:29.9682052+00:00 | 2026-09-02T11:50:29.9682052+08:00 | #83738 - PDO: 80hrs - MODULE - PLANT: PDO FINES B | 1.0 | FALSE |  | 2027-11-01T06:00:00+00:00 | 2027-11-04T14:00:00+00:00 | 2027-11-01T14:00:00+08:00 | 2027-11-04T22:00:00+08:00 |  |  |  |  | 80.00 | MOD B Outage |  |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83737 | 2026-08-24T04:29:15.0307876+00:00 | 2026-08-24T12:29:15.0307876+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:50:42.7441583+00:00 | 2026-09-02T11:50:42.7441583+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333099 | TRUE | TRUE | 2026-09-02T03:50:42.7441583+00:00 | 2026-09-02T11:50:42.7441583+08:00 | #83737 - PDO: 80hrs - MODULE - PLANT: PDO FINES B | 1.0 | FALSE |  | 2027-08-02T06:00:00+00:00 | 2027-08-05T14:00:00+00:00 | 2027-08-02T14:00:00+08:00 | 2027-08-05T22:00:00+08:00 |  |  |  |  | 80.00 | MOD B Outage |  |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83736 | 2026-08-24T04:29:14.8703685+00:00 | 2026-08-24T12:29:14.8703685+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:50:53.1903964+00:00 | 2026-09-02T11:50:53.1903964+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333100 | TRUE | TRUE | 2026-09-02T03:50:53.1903964+00:00 | 2026-09-02T11:50:53.1903964+08:00 | #83736 - PDO: 80hrs - MODULE - PLANT: PDO FINES B | 1.0 | FALSE |  | 2027-05-03T06:00:00+00:00 | 2027-05-06T14:00:00+00:00 | 2027-05-03T14:00:00+08:00 | 2027-05-06T22:00:00+08:00 |  |  |  |  | 80.00 | MOD B Outage |  |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83735 | 2026-08-24T04:29:14.7060198+00:00 | 2026-08-24T12:29:14.7060198+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:51:06.7816073+00:00 | 2026-09-02T11:51:06.7816073+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333101 | TRUE | TRUE | 2026-09-02T03:51:06.7816073+00:00 | 2026-09-02T11:51:06.7816073+08:00 | #83735 - PDO: 80hrs - MODULE - PLANT: PDO FINES B | 1.0 | FALSE |  | 2027-02-01T06:00:00+00:00 | 2027-02-04T14:00:00+00:00 | 2027-02-01T14:00:00+08:00 | 2027-02-04T22:00:00+08:00 |  |  |  |  | 80.00 | MOD B Outage |  |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83733 | 2026-08-24T04:24:10.8977008+00:00 | 2026-08-24T12:24:10.8977008+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:51:19.9901385+00:00 | 2026-09-02T11:51:19.9901385+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333102 | TRUE | TRUE | 2026-09-02T03:51:19.9901385+00:00 | 2026-09-02T11:51:19.9901385+08:00 | #83733 - PDO: 80hrs - MODULE - PLANT: PDO FINES A | 1.0 | FALSE |  | 2027-10-28T22:00:00+00:00 | 2027-11-01T06:00:00+00:00 | 2027-10-29T06:00:00+08:00 | 2027-11-01T14:00:00+08:00 |  |  |  |  | 80.00 | MOD A Outage |  |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83732 | 2026-08-24T04:24:10.7351658+00:00 | 2026-08-24T12:24:10.7351658+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:51:33.1308844+00:00 | 2026-09-02T11:51:33.1308844+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333103 | TRUE | TRUE | 2026-09-02T03:51:33.1308844+00:00 | 2026-09-02T11:51:33.1308844+08:00 | #83732 - PDO: 80hrs - MODULE - PLANT: PDO FINES A | 1.0 | FALSE |  | 2027-07-29T22:00:00+00:00 | 2027-08-02T06:00:00+00:00 | 2027-07-30T06:00:00+08:00 | 2027-08-02T14:00:00+08:00 |  |  |  |  | 80.00 | MOD A Outage |  |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83731 | 2026-08-24T04:24:10.5682474+00:00 | 2026-08-24T12:24:10.5682474+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:51:45.4460548+00:00 | 2026-09-02T11:51:45.4460548+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333104 | TRUE | TRUE | 2026-09-02T03:51:45.4460548+00:00 | 2026-09-02T11:51:45.4460548+08:00 | #83731 - PDO: 80hrs - MODULE - PLANT: PDO FINES A | 1.0 | FALSE |  | 2027-04-29T22:00:00+00:00 | 2027-05-03T06:00:00+00:00 | 2027-04-30T06:00:00+08:00 | 2027-05-03T14:00:00+08:00 |  |  |  |  | 80.00 | MOD A Outage |  |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83730 | 2026-08-24T04:24:10.402574+00:00 | 2026-08-24T12:24:10.402574+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-09-02T03:51:58.2782337+00:00 | 2026-09-02T11:51:58.2782337+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | {"name": "Fixed Plant"} | 333105 | TRUE | TRUE | 2026-09-02T03:51:58.2782337+00:00 | 2026-09-02T11:51:58.2782337+08:00 | #83730 - PDO: 80hrs - MODULE - PLANT: PDO FINES A | 1.0 | FALSE |  | 2027-01-28T22:00:00+00:00 | 2027-02-01T06:00:00+00:00 | 2027-01-29T06:00:00+08:00 | 2027-02-01T14:00:00+08:00 |  |  |  |  | 80.00 | MOD A Outage |  |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cac8d5d2-5353-4864-a034-a4ef724a9c6c", "emailAddress": "Josh.Elston@riotinto.com", "displayName": "Elston,Joshua(RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 0157e3f4-358d-4f0a-a40f-919420280981 | Cabassi, Karenza (RTIO) | Scheduled | PDO | Australia/Perth
83675 | 2026-08-11T21:45:16.6972973+00:00 | 2026-08-12T05:45:16.6972973+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-10-15T01:40:42.58025+00:00 | 2026-10-15T09:40:42.58025+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335978 | TRUE | TRUE | 2026-10-15T01:40:42.58025+00:00 | 2026-10-15T09:40:42.58025+08:00 | #83675 - CLA: 108hrs - CO11 BELT C/O | 1.1 | FALSE |  | 2027-03-28T22:00:00+00:00 | 2027-04-02T10:00:00+00:00 | 2027-03-29T06:00:00+08:00 | 2027-04-02T18:00:00+08:00 |  |  |  |  | 108.00 | CO11 Belt C/O |  | SCAL2713 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "6e35f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVCO11", "name": "Conveyor: CLA CO11", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "80b2aed9-1bbb-4760-a197-a338b140a3b5", "emailAddress": "Michael.Stuart@riotinto.com", "displayName": "Stuart, Michael (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
83674 | 2026-08-11T21:41:48.5832726+00:00 | 2026-08-12T05:41:48.5832726+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-10-15T00:31:22.316191+00:00 | 2026-10-15T08:31:22.316191+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335938 | TRUE | TRUE | 2026-10-15T00:31:22.316191+00:00 | 2026-10-15T08:31:22.316191+08:00 | #83674 - CLA: 108hrs - CO13 BELT C/O | 1.1 | FALSE |  | 2027-02-17T05:00:00+00:00 | 2027-02-21T17:00:00+00:00 | 2027-02-17T13:00:00+08:00 | 2027-02-22T01:00:00+08:00 |  |  |  |  | 108.00 | CO13 Belt C/O, duration is greater than standard IAM shut |  | SCAL2707 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "ed22f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVCO13", "name": "Conveyor: CLA CO13", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "80b2aed9-1bbb-4760-a197-a338b140a3b5", "emailAddress": "Michael.Stuart@riotinto.com", "displayName": "Stuart, Michael (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
71530 | 2025-10-27T12:15:46.7338847+00:00 | 2025-10-27T20:15:46.7338847+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2025-10-28T03:03:52.8964877+00:00 | 2025-10-28T11:03:52.8964877+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 265134 | TRUE | TRUE | 2025-10-28T03:03:52.8964877+00:00 | 2025-10-28T11:03:52.8964877+08:00 | #71530 - CLB: 106hrs - CD5 IAM MAINTENANCE | 1.0 | TRUE |  | 2026-12-01T10:00:00+00:00 | 2026-12-05T20:00:00+00:00 | 2026-12-01T18:00:00+08:00 | 2026-12-06T04:00:00+08:00 |  |  |  |  | 106.00 | CD5 Standard IAM Maintenance |  |  | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ad335d87-3c53-4798-8bef-230f0198a8f1", "emailAddress": "dwayne.clarke@riotinto.com", "displayName": "Clarke, Dwayne (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
83688 | 2026-08-13T03:42:37.1167034+00:00 | 2026-08-13T11:42:37.1167034+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-10-16T06:04:35.3098756+00:00 | 2026-10-16T14:04:35.3098756+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336159 | TRUE | TRUE | 2026-10-16T06:04:35.3098756+00:00 | 2026-10-16T14:04:35.3098756+08:00 | #83688 - CLB: 120hrs - RC13 | 1.0 | FALSE |  | 2027-11-10T22:00:00+00:00 | 2027-11-15T22:00:00+00:00 | 2027-11-11T06:00:00+08:00 | 2027-11-16T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBY2745 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
67631 | 2025-06-09T23:49:58.4722476+00:00 | 2025-06-10T07:49:58.4722476+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:28.0381359+00:00 | 2026-08-31T14:41:28.0381359+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332360 | TRUE | TRUE | 2026-08-31T06:41:28.0381359+00:00 | 2026-08-31T14:41:28.0381359+08:00 | #67631 - CLA: 12hrs - RCL4 CAPD TESTING | 2.0 | FALSE |  | 2027-06-07T22:00:00+00:00 | 2027-06-08T10:00:00+00:00 | 2027-06-08T06:00:00+08:00 | 2027-06-08T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Tweaking CAPD timing |  | [{"equipmentGUID": "9627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC04", "name": "Reclaimer: CLA 04", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67691 | 2025-06-09T23:51:42.2502517+00:00 | 2025-06-10T07:51:42.2502517+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:28.5330297+00:00 | 2026-08-31T14:41:28.5330297+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332361 | TRUE | TRUE | 2026-08-31T06:41:28.5330297+00:00 | 2026-08-31T14:41:28.5330297+08:00 | #67691 - CLA: 12hrs - RCL3 CAPD TESTING | 2.0 | FALSE |  | 2027-06-27T22:00:00+00:00 | 2027-06-28T10:00:00+00:00 | 2027-06-28T06:00:00+08:00 | 2027-06-28T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67681 | 2025-06-09T23:51:40.6088314+00:00 | 2025-06-10T07:51:40.6088314+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:28.6913156+00:00 | 2026-08-31T14:41:28.6913156+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332362 | TRUE | TRUE | 2026-08-31T06:41:28.6913156+00:00 | 2026-08-31T14:41:28.6913156+08:00 | #67681 - CLA: 12hrs - STK3 CAPD TESTING | 2.0 | FALSE |  | 2027-06-27T22:00:00+00:00 | 2027-06-28T10:00:00+00:00 | 2027-06-28T06:00:00+08:00 | 2027-06-28T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67601 | 2025-06-09T23:49:53.6673782+00:00 | 2025-06-10T07:49:53.6673782+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:28.8508214+00:00 | 2026-08-31T14:41:28.8508214+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332363 | TRUE | TRUE | 2026-08-31T06:41:28.8508214+00:00 | 2026-08-31T14:41:28.8508214+08:00 | #67601 - CLA: 12hrs - STK5 CAPD TESTING | 2.0 | FALSE |  | 2027-06-28T22:00:00+00:00 | 2027-06-29T10:00:00+00:00 | 2027-06-29T06:00:00+08:00 | 2027-06-29T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67611 | 2025-06-09T23:49:55.1346321+00:00 | 2025-06-10T07:49:55.1346321+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:29.0045658+00:00 | 2026-08-31T14:41:29.0045658+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332364 | TRUE | TRUE | 2026-08-31T06:41:29.0045658+00:00 | 2026-08-31T14:41:29.0045658+08:00 | #67611 - CLA: 12hrs - RCL2 CAPD TESTING | 2.0 | FALSE |  | 2027-06-28T22:00:00+00:00 | 2027-06-29T10:00:00+00:00 | 2027-06-29T06:00:00+08:00 | 2027-06-29T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67721 | 2025-06-09T23:51:47.9809378+00:00 | 2025-06-10T07:51:47.9809378+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:29.1596784+00:00 | 2026-08-31T14:41:29.1596784+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332365 | TRUE | TRUE | 2026-08-31T06:41:29.1596784+00:00 | 2026-08-31T14:41:29.1596784+08:00 | #67721 - CLA: 12hrs - RCL1 CAPD TESTING | 2.0 | FALSE |  | 2027-06-29T22:00:00+00:00 | 2027-06-30T10:00:00+00:00 | 2027-06-30T06:00:00+08:00 | 2027-06-30T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67711 | 2025-06-09T23:51:45.9548238+00:00 | 2025-06-10T07:51:45.9548238+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:29.3169494+00:00 | 2026-08-31T14:41:29.3169494+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332366 | TRUE | TRUE | 2026-08-31T06:41:29.3169494+00:00 | 2026-08-31T14:41:29.3169494+08:00 | #67711 - CLA: 12hrs - STK4 CAPD TESTING | 2.0 | FALSE |  | 2027-06-29T22:00:00+00:00 | 2027-06-30T10:00:00+00:00 | 2027-06-30T06:00:00+08:00 | 2027-06-30T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Moving away from CLB CAPD |  | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67671 | 2025-06-09T23:51:38.9899181+00:00 | 2025-06-10T07:51:38.9899181+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-31T06:41:29.4797157+00:00 | 2026-08-31T14:41:29.4797157+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332367 | TRUE | TRUE | 2026-08-31T06:41:29.4797157+00:00 | 2026-08-31T14:41:29.4797157+08:00 | #67671 - CLA: 12hrs - STK2 CAPD TESTING | 2.0 | FALSE |  | 2027-06-30T22:00:00+00:00 | 2027-07-01T10:00:00+00:00 | 2027-07-01T06:00:00+08:00 | 2027-07-01T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Tweaking CAPD timing |  | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
83638 | 2026-08-03T03:31:06.8699812+00:00 | 2026-08-03T11:31:06.8699812+08:00 | {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "displayName": "Ross, Brad M (RTIO)"} | 2026-10-15T02:50:45.7681151+00:00 | 2026-10-15T10:50:45.7681151+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336040 | TRUE | TRUE | 2026-10-15T02:50:45.7681151+00:00 | 2026-10-15T10:50:45.7681151+08:00 | #83638 - CLB: 120hrs - RC12 IAM | 1.2 | FALSE |  | 2027-07-12T22:00:00+00:00 | 2027-07-17T22:00:00+00:00 | 2027-07-13T06:00:00+08:00 | 2027-07-18T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Shut |  | SCBO2728 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
83637 | 2026-08-03T03:21:10.1903424+00:00 | 2026-08-03T11:21:10.1903424+08:00 | {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "displayName": "Ross, Brad M (RTIO)"} | 2026-10-15T02:28:40.6458773+00:00 | 2026-10-15T10:28:40.6458773+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336024 | TRUE | TRUE | 2026-10-15T02:28:40.6458773+00:00 | 2026-10-15T10:28:40.6458773+08:00 | #83637 - CLB: 120hrs - RC11 IAM | 1.1 | FALSE |  | 2027-06-13T22:00:00+00:00 | 2027-06-18T22:00:00+00:00 | 2027-06-14T06:00:00+08:00 | 2027-06-19T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Shut |  | SCBO2724 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
67641 | 2025-06-09T23:50:00.4364282+00:00 | 2025-06-10T07:50:00.4364282+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-28T05:23:45.2409205+00:00 | 2026-08-28T13:23:45.2409205+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332138 | TRUE | TRUE | 2026-08-28T05:23:45.2409205+00:00 | 2026-08-28T13:23:45.2409205+08:00 | #67641 - CLA: 12hrs - SLD2 CAPD TESTING | 3.0 | TRUE |  | 2027-06-10T22:00:00+00:00 | 2027-06-11T10:00:00+00:00 | 2027-06-11T06:00:00+08:00 | 2027-06-11T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Aligning with SLD2 and moving to avoid other SLD shuts |  | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
67651 | 2025-06-09T23:50:02.5096306+00:00 | 2025-06-10T07:50:02.5096306+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-08-28T05:23:45.4578838+00:00 | 2026-08-28T13:23:45.4578838+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332139 | TRUE | TRUE | 2026-08-28T05:23:45.4578838+00:00 | 2026-08-28T13:23:45.4578838+08:00 | #67651 - CLA: 12hrs - SLD3 CAPD TESTING | 3.0 | TRUE |  | 2027-06-10T22:00:00+00:00 | 2027-06-11T10:00:00+00:00 | 2027-06-11T06:00:00+08:00 | 2027-06-11T18:00:00+08:00 |  |  |  |  | 12.00 | CAPD Testing - cannot move >54 days later than last test date, confirm last test date in machine book | Aligning with SLD3 and moving to avoid other SLD shuts |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "693be29b-085d-4e2d-ba54-bc08b890775c", "emailAddress": "steven.neilsen@riotinto.com", "displayName": "Neilsen, Steven (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
83677 | 2026-08-11T22:22:10.3126302+00:00 | 2026-08-12T06:22:10.3126302+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-10-02T08:49:37.8165681+00:00 | 2026-10-02T16:49:37.8165681+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335209 | TRUE | TRUE | 2026-10-02T08:49:37.8165681+00:00 | 2026-10-02T16:49:37.8165681+08:00 | #83677 - CLA: 84hrs - STACKER: CLA 03 | 1.0 | FALSE |  | 2027-09-20T04:00:00+00:00 | 2027-09-23T16:00:00+00:00 | 2027-09-20T12:00:00+08:00 | 2027-09-24T00:00:00+08:00 |  |  |  |  | 84.00 | STK3 Standard IAM Maintenance |  |  | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Create | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
83676 | 2026-08-11T22:12:19.8034158+00:00 | 2026-08-12T06:12:19.8034158+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | 2026-10-02T07:25:33.8689188+00:00 | 2026-10-02T15:25:33.8689188+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335197 | TRUE | TRUE | 2026-10-02T07:25:33.8689188+00:00 | 2026-10-02T15:25:33.8689188+08:00 | #83676 - CLA: 108hrs - CO11 BELT C/O | 1.0 | FALSE |  | 2027-09-26T22:00:00+00:00 | 2027-10-01T10:00:00+00:00 | 2027-09-27T06:00:00+08:00 | 2027-10-01T18:00:00+08:00 |  |  |  |  | 108.00 | CO11 Belt C/O Duration exceeds standard IAM |  |  | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "6e35f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVCO11", "name": "Conveyor: CLA CO11", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "80b2aed9-1bbb-4760-a197-a338b140a3b5", "emailAddress": "Michael.Stuart@riotinto.com", "displayName": "Stuart, Michael (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
45740 | 2022-01-25T00:11:13+00:00 | 2022-01-25T08:11:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000053", "displayName": "Paul Dundon"} | 2026-09-03T05:23:39.6070545+00:00 | 2026-09-03T13:23:39.6070545+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 333124 | TRUE | TRUE | 2026-09-03T05:23:39.6070545+00:00 | 2026-09-03T13:23:39.6070545+08:00 | #45740 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING | 3.0 | FALSE |  | 2027-03-22T22:00:00+00:00 | 2027-03-24T22:00:00+00:00 | 2027-03-23T06:00:00+08:00 | 2027-03-25T06:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut | misaligned with IAM shut sequence | SCAO2710 | [{"equipmentGUID": "2a0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV214", "name": "Conveyor: CLA 214 Lump Rescreening", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43512, "shutVersionId": 335970, "title": "#43512 - CLA: 138hrs - RCL3 IAM", "startDatetimeUTC": "2027-03-22T04:00:00+00:00", "endDatetimeUTC": "2027-03-27T22:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 43516, "shutVersionId": 335972, "title": "#43516 - CLA: 108hrs - STK3 IAM", "startDatetimeUTC": "2027-03-21T22:00:00+00:00", "endDatetimeUTC": "2027-03-26T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
45742 | 2022-01-25T00:11:18+00:00 | 2022-01-25T08:11:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000053", "displayName": "Paul Dundon"} | 2026-09-03T05:23:40.0097194+00:00 | 2026-09-03T13:23:40.0097194+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 333126 | TRUE | TRUE | 2026-09-03T05:23:40.0097194+00:00 | 2026-09-03T13:23:40.0097194+08:00 | #45742 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING | 3.0 | FALSE |  | 2027-09-20T22:00:00+00:00 | 2027-09-22T22:00:00+00:00 | 2027-09-21T06:00:00+08:00 | 2027-09-23T06:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut | misaligned to IAM sequence | SCAO2736 | [{"equipmentGUID": "2a0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV214", "name": "Conveyor: CLA 214 Lump Rescreening", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43514, "shutVersionId": 276212, "title": "#43514 - CLA: 138hrs - RECLAIMER: CLA 03", "startDatetimeUTC": "2027-09-20T04:00:00+00:00", "endDatetimeUTC": "2027-09-25T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
45743 | 2022-01-25T00:11:18+00:00 | 2022-01-25T08:11:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000053", "displayName": "Paul Dundon"} | 2026-10-14T23:49:28.2249065+00:00 | 2026-10-15T07:49:28.2249065+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335896 | TRUE | TRUE | 2026-10-14T23:49:28.2249065+00:00 | 2026-10-15T07:49:28.2249065+08:00 | #45743 - CLA: 48hrs - C214 IAM | 3.1 | FALSE |  | 2027-12-20T22:00:00+00:00 | 2027-12-22T22:00:00+00:00 | 2027-12-21T06:00:00+08:00 | 2027-12-23T06:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut |  | SCAO2749 | [{"equipmentGUID": "2a0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV214", "name": "Conveyor: CLA 214 Lump Rescreening", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43519, "shutVersionId": 332032, "title": "#43519 - CLA: 108hrs - STK3 IAM", "startDatetimeUTC": "2027-12-19T22:00:00+00:00", "endDatetimeUTC": "2027-12-24T10:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 43515, "shutVersionId": 332042, "title": "#43515 - CLA: 138hrs - RCL3 IAM", "startDatetimeUTC": "2027-12-20T04:00:00+00:00", "endDatetimeUTC": "2027-12-25T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
45741 | 2022-01-25T00:11:14+00:00 | 2022-01-25T08:11:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000053", "displayName": "Paul Dundon"} | 2026-10-15T02:30:33.6102523+00:00 | 2026-10-15T10:30:33.6102523+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336027 | TRUE | TRUE | 2026-10-15T02:30:33.6102523+00:00 | 2026-10-15T10:30:33.6102523+08:00 | #45741 - CLA: 48hrs - C214 IAM | 3.1 | FALSE |  | 2027-06-21T22:00:00+00:00 | 2027-06-23T22:00:00+00:00 | 2027-06-22T06:00:00+08:00 | 2027-06-24T06:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut |  | SCAY2725 | [{"equipmentGUID": "2a0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV214", "name": "Conveyor: CLA 214 Lump Rescreening", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43517, "shutVersionId": 336025, "title": "#43517 - CLA: 108hrs - STK3 IAM", "startDatetimeUTC": "2027-06-20T22:00:00+00:00", "endDatetimeUTC": "2027-06-25T10:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 43513, "shutVersionId": 336026, "title": "#43513 - CLA: 138hrs - RCL3 IAM", "startDatetimeUTC": "2027-06-21T04:00:00+00:00", "endDatetimeUTC": "2027-06-26T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
45739 | 2022-01-25T00:11:13+00:00 | 2022-01-25T08:11:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000053", "displayName": "Paul Dundon"} | 2025-10-17T05:49:22.6241803+00:00 | 2025-10-17T13:49:22.6241803+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 260148 | TRUE | TRUE | 2025-10-17T05:49:22.6241803+00:00 | 2025-10-17T13:49:22.6241803+08:00 | #45739 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING & SCREENHOUSE: CLA LUMP RESCREENING PLANT 02 | 4.0 | FALSE |  | 2026-12-14T22:00:00+00:00 | 2026-12-16T22:00:00+00:00 | 2026-12-15T06:00:00+08:00 | 2026-12-17T06:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut | Aligning to IAM | SCAO2649 | [{"equipmentGUID": "2a0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV214", "name": "Conveyor: CLA 214 Lump Rescreening", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 39288, "shutVersionId": 252556, "title": "#39288 - CLA: 108hrs - STACKER: CLA 03", "startDatetimeUTC": "2026-12-14T04:00:00+00:00", "endDatetimeUTC": "2026-12-18T16:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 39269, "shutVersionId": 252557, "title": "#39269 - CLA: 138hrs - RECLAIMER: CLA 03", "startDatetimeUTC": "2026-12-14T04:00:00+00:00", "endDatetimeUTC": "2026-12-19T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
53161 | 2022-11-14T06:58:22+00:00 | 2022-11-14T14:58:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-15T00:36:38.9362584+00:00 | 2026-10-15T08:36:38.9362584+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335939 | TRUE | TRUE | 2026-10-15T00:36:38.9362584+00:00 | 2026-10-15T08:36:38.9362584+08:00 | #53161 - CLA: 672hrs - CLAHDO SL2C BM WORKS & SAMPLE STATION CUT OVER | 10.1 | TRUE |  | 2027-01-19T22:00:00+00:00 | 2027-02-16T22:00:00+00:00 | 2027-01-20T06:00:00+08:00 | 2027-02-17T06:00:00+08:00 |  |  |  |  | 672.00 | CLAHDO SL2C BM WORKS AND SAMPLE STATION CUT OVER PLACEHOLDER |  | SCAO2705 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "cc6c96ea-6b8c-46ea-a62e-93cce43e9f17", "emailAddress": "Parsa.Rad@riotinto.com", "displayName": "Farjadrad, Parsa (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "0c7844c7-02f6-4f4a-af42-9b17b0a1ac0e", "emailAddress": "Trent.Boulos@riotinto.com", "displayName": "Boulos, Trent (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84196, "shutVersionId": 335407, "title": "#84196 - CLA: 72hrs - CLAHDO SL2C BM WORKS AND SAMPLE STATION CUT OVER COMMISSIONING PLACEHOLDER", "startDatetimeUTC": "2027-02-16T22:00:00+00:00", "endDatetimeUTC": "2027-02-19T22:00:00+00:00"}}] | [] | [{"code": "P-0511336", "name": "CLAHDO", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "840"}] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Major Projects | CLA | Australia/Perth
52713 | 2022-11-07T23:33:38+00:00 | 2022-11-08T07:33:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:13:34.1782711+00:00 | 2026-10-15T09:13:34.1782711+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335944 | TRUE | TRUE | 2026-10-15T01:13:34.1782711+00:00 | 2026-10-15T09:13:34.1782711+08:00 | #52713 - CLA: 130hrs - RUBBLE PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52745 | 2022-11-07T23:36:18+00:00 | 2022-11-08T07:36:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:13:57.8701687+00:00 | 2026-10-15T09:13:57.8701687+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335945 | TRUE | TRUE | 2026-10-15T01:13:57.8701687+00:00 | 2026-10-15T09:13:57.8701687+08:00 | #52745 - CLA: 130hrs - SEC1 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52873 | 2022-11-08T00:23:53+00:00 | 2022-11-08T08:23:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:15:01.7780504+00:00 | 2026-10-15T09:15:01.7780504+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335946 | TRUE | TRUE | 2026-10-15T01:15:01.7780504+00:00 | 2026-10-15T09:15:01.7780504+08:00 | #52873 - CLA: 130hrs - SEC2 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "9817ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT02", "name": "Crusher - Secondary: CLA Circuit 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52777 | 2022-11-07T23:37:34+00:00 | 2022-11-08T07:37:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:21:02.9861956+00:00 | 2026-10-15T09:21:02.9861956+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335947 | TRUE | TRUE | 2026-10-15T01:21:02.9861956+00:00 | 2026-10-15T09:21:02.9861956+08:00 | #52777 - CLA: 130hrs - SEC3 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52809 | 2022-11-07T23:38:48+00:00 | 2022-11-08T07:38:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:21:20.9538005+00:00 | 2026-10-15T09:21:20.9538005+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335948 | TRUE | TRUE | 2026-10-15T01:21:20.9538005+00:00 | 2026-10-15T09:21:20.9538005+08:00 | #52809 - CLA: 130hrs - TERT1 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52841 | 2022-11-07T23:40:04+00:00 | 2022-11-08T07:40:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:21:42.6476532+00:00 | 2026-10-15T09:21:42.6476532+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335949 | TRUE | TRUE | 2026-10-15T01:21:42.6476532+00:00 | 2026-10-15T09:21:42.6476532+08:00 | #52841 - CLA: 130hrs - TERT3 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52932 | 2022-11-08T00:26:00+00:00 | 2022-11-08T08:26:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:22:04.8227579+00:00 | 2026-10-15T09:22:04.8227579+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335950 | TRUE | TRUE | 2026-10-15T01:22:04.8227579+00:00 | 2026-10-15T09:22:04.8227579+08:00 | #52932 - CLA: 130hrs - TERT4 PLANT SHUT | 3.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52714 | 2022-11-07T23:33:39+00:00 | 2022-11-08T07:33:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T01:59:56.5743297+00:00 | 2026-10-15T09:59:56.5743297+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336004 | TRUE | TRUE | 2026-10-15T01:59:56.5743297+00:00 | 2026-10-15T09:59:56.5743297+08:00 | #52714 - CLA: 130hrs - RUBBLE PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52746 | 2022-11-07T23:36:19+00:00 | 2022-11-08T07:36:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:00:30.9216695+00:00 | 2026-10-15T10:00:30.9216695+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336005 | TRUE | TRUE | 2026-10-15T02:00:30.9216695+00:00 | 2026-10-15T10:00:30.9216695+08:00 | #52746 - CLA: 130hrs - SEC1 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52874 | 2022-11-08T00:23:53+00:00 | 2022-11-08T08:23:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:00:50.0405866+00:00 | 2026-10-15T10:00:50.0405866+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336006 | TRUE | TRUE | 2026-10-15T02:00:50.0405866+00:00 | 2026-10-15T10:00:50.0405866+08:00 | #52874 - CLA: 130hrs - SEC2 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "9817ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT02", "name": "Crusher - Secondary: CLA Circuit 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52778 | 2022-11-07T23:37:35+00:00 | 2022-11-08T07:37:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:01:10.1778387+00:00 | 2026-10-15T10:01:10.1778387+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336007 | TRUE | TRUE | 2026-10-15T02:01:10.1778387+00:00 | 2026-10-15T10:01:10.1778387+08:00 | #52778 - CLA: 130hrs - SEC3 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52810 | 2022-11-07T23:38:49+00:00 | 2022-11-08T07:38:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:04:50.6565075+00:00 | 2026-10-15T10:04:50.6565075+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336011 | TRUE | TRUE | 2026-10-15T02:04:50.6565075+00:00 | 2026-10-15T10:04:50.6565075+08:00 | #52810 - CLA: 130hrs - TERT1 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52842 | 2022-11-07T23:40:05+00:00 | 2022-11-08T07:40:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:05:06.4573909+00:00 | 2026-10-15T10:05:06.4573909+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336012 | TRUE | TRUE | 2026-10-15T02:05:06.4573909+00:00 | 2026-10-15T10:05:06.4573909+08:00 | #52842 - CLA: 130hrs - TERT3 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52933 | 2022-11-08T00:26:01+00:00 | 2022-11-08T08:26:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-15T02:05:24.6202118+00:00 | 2026-10-15T10:05:24.6202118+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336013 | TRUE | TRUE | 2026-10-15T02:05:24.6202118+00:00 | 2026-10-15T10:05:24.6202118+08:00 | #52933 - CLA: 130hrs - TERT4 PLANT SHUT | 4.1 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
52716 | 2022-11-07T23:33:45+00:00 | 2022-11-08T07:33:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-08-28T00:28:45.2665786+00:00 | 2026-08-28T08:28:45.2665786+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332115 | TRUE | TRUE | 2026-08-28T00:28:45.2665786+00:00 | 2026-08-28T08:28:45.2665786+08:00 | #52716 - CLA: 130hrs - PLANT IAM | 3.1 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2747 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56406 | 2023-07-13T07:29:41+00:00 | 2023-07-13T15:29:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T01:55:43.2015979+00:00 | 2026-10-15T09:55:43.2015979+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335997 | TRUE | TRUE | 2026-10-15T01:55:43.2015979+00:00 | 2026-10-15T09:55:43.2015979+08:00 | #56406 - CLB: 106hrs - C04 PLANT SHUT | 4.2 | TRUE |  | 2027-05-23T10:00:00+00:00 | 2027-05-27T20:00:00+00:00 | 2027-05-23T18:00:00+08:00 | 2027-05-28T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "4a6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV04", "name": "Conveyor: CLB C04", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
38793 | 2020-12-18T03:47:53+00:00 | 2020-12-18T11:47:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-10-15T01:42:55.7122435+00:00 | 2026-10-15T09:42:55.7122435+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335984 | TRUE | TRUE | 2026-10-15T01:42:55.7122435+00:00 | 2026-10-15T09:42:55.7122435+08:00 | #38793 - CLB: 106hrs - CD6 IAM | 4.1 | TRUE |  | 2027-04-05T10:00:00+00:00 | 2027-04-09T20:00:00+00:00 | 2027-04-05T18:00:00+08:00 | 2027-04-10T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2714 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "ad335d87-3c53-4798-8bef-230f0198a8f1", "emailAddress": "dwayne.clarke@riotinto.com", "displayName": "Clarke, Dwayne (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
39021 | 2020-12-18T04:03:14+00:00 | 2020-12-18T12:03:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-10-15T00:17:20.9743997+00:00 | 2026-10-15T08:17:20.9743997+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335915 | TRUE | TRUE | 2026-10-15T00:17:20.9743997+00:00 | 2026-10-15T08:17:20.9743997+08:00 | #39021 - CLB: 84hrs - ST12 IAM | 4.2 | FALSE |  | 2027-01-03T22:00:00+00:00 | 2027-01-07T10:00:00+00:00 | 2027-01-04T06:00:00+08:00 | 2027-01-07T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance |  | SCBI2701 | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
38792 | 2020-12-18T03:47:49+00:00 | 2020-12-18T11:47:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-10-15T00:17:33.5710919+00:00 | 2026-10-15T08:17:33.5710919+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335916 | TRUE | TRUE | 2026-10-15T00:17:33.5710919+00:00 | 2026-10-15T08:17:33.5710919+08:00 | #38792 - CLB: 156hrs - CD6C BIN LINER UPGRADE PROJECT | 9.1 | TRUE |  | 2027-01-04T10:00:00+00:00 | 2027-01-10T22:00:00+00:00 | 2027-01-04T18:00:00+08:00 | 2027-01-11T06:00:00+08:00 |  |  |  |  | 156.00 | CD6C Bin Liner Upgrade Project |  | SCBI2701 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "55436276-1baf-407b-bb99-9599270ea9ef", "emailAddress": "Adam.Parsons@riotinto.com", "displayName": "Parsons, Adam (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [{"code": "P-0604196", "name": "CLB Dumper Bin Liner Upgrade and Replacement", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "180"}] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
56359 | 2023-07-13T06:58:54+00:00 | 2023-07-13T14:58:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T01:55:12.2999128+00:00 | 2026-10-15T09:55:12.2999128+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335995 | TRUE | TRUE | 2026-10-15T01:55:12.2999128+00:00 | 2026-10-15T09:55:12.2999128+08:00 | #56359 - CLA: 130hrs - STK1 PLANT SHUT | 4.2 | TRUE |  | 2027-05-23T10:00:00+00:00 | 2027-05-28T20:00:00+00:00 | 2027-05-23T18:00:00+08:00 | 2027-05-29T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "65ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST01", "name": "Stacker: CLA 01 RV Coarse Ore", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
61973 | 2024-06-14T02:26:51+00:00 | 2024-06-14T10:26:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T02:42:37.9557484+00:00 | 2026-10-15T10:42:37.9557484+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336035 | TRUE | TRUE | 2026-10-15T02:42:37.9557484+00:00 | 2026-10-15T10:42:37.9557484+08:00 | #61973 - CLA: 36hrs - TERT4 IAM | 2.1 | FALSE |  | 2027-07-03T10:00:00+00:00 | 2027-07-04T22:00:00+00:00 | 2027-07-03T18:00:00+08:00 | 2027-07-05T06:00:00+08:00 |  |  |  |  | 36.00 | Standard IAM Maintenance |  | SCAL2726 | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
39590 | 2020-12-21T02:19:58+00:00 | 2020-12-21T10:19:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-08-12T23:53:35.8579521+00:00 | 2026-08-13T07:53:35.8579521+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331189 | TRUE | TRUE | 2026-08-12T23:53:35.8579521+00:00 | 2026-08-13T07:53:35.8579521+08:00 | #39590 - CLB: 9hrs - RC13 PIT STOP | 2.1 | FALSE |  | 2027-01-06T00:00:00+00:00 | 2027-01-06T09:00:00+00:00 | 2027-01-06T08:00:00+08:00 | 2027-01-06T17:00:00+08:00 |  |  |  |  | 9.00 | Reclaimer 13 Pitstop |  |  | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
39591 | 2020-12-21T02:22:48+00:00 | 2020-12-21T10:22:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-17T23:34:25.9379034+00:00 | 2025-10-18T07:34:25.9379034+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 260723 | TRUE | TRUE | 2025-10-17T23:34:25.9379034+00:00 | 2025-10-18T07:34:25.9379034+08:00 | #39591 - CLB: 9hrs - RC12 PIT STOP | 2.2 | FALSE |  | 2026-12-16T00:00:00+00:00 | 2026-12-16T09:00:00+00:00 | 2026-12-16T08:00:00+08:00 | 2026-12-16T17:00:00+08:00 |  |  |  |  | 9.00 | Reclaimer 12 Pitstop |  |  | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
39513 | 2020-12-21T01:43:14+00:00 | 2020-12-21T09:43:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-19T00:37:55.8487211+00:00 | 2025-10-19T08:37:55.8487211+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 260729 | TRUE | TRUE | 2025-10-19T00:37:55.8487211+00:00 | 2025-10-19T08:37:55.8487211+08:00 | #39513 - CLB: 48hrs - SH06 FINES ONLY | 3.1 | FALSE |  | 2026-12-22T16:00:00+00:00 | 2026-12-24T16:00:00+00:00 | 2026-12-23T00:00:00+08:00 | 2026-12-25T00:00:00+08:00 |  |  |  |  | 48.00 | SH6 FINES LOADING ONLY |  |  | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Site Constraint | CLB | Australia/Perth
38850 | 2020-12-18T03:52:28+00:00 | 2020-12-18T11:52:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-21T03:48:21.5661644+00:00 | 2025-10-21T11:48:21.5661644+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 261649 | TRUE | TRUE | 2025-10-21T03:48:21.5661644+00:00 | 2025-10-21T11:48:21.5661644+08:00 | #38850 - CLB: 72hrs - CLB RETURN FINES SHUT | 4.0 | FALSE |  | 2026-12-08T22:00:00+00:00 | 2026-12-11T22:00:00+00:00 | 2026-12-09T06:00:00+08:00 | 2026-12-12T06:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | IAM Alignment |  | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
38869 | 2020-12-18T03:54:38+00:00 | 2020-12-18T11:54:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-07-30T03:41:30.7268451+00:00 | 2026-07-30T11:41:30.7268451+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 330590 | TRUE | TRUE | 2026-07-30T03:41:30.7268451+00:00 | 2026-07-30T11:41:30.7268451+08:00 | #38869 - CLB: 120hrs - RECLAIMER: CLB 11 | 4.0 | FALSE |  | 2026-11-30T22:00:00+00:00 | 2026-12-05T22:00:00+00:00 | 2026-12-01T06:00:00+08:00 | 2026-12-06T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | Moving due to predicted stockyard constraints in canyon P |  | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
39002 | 2020-12-18T04:01:54+00:00 | 2020-12-18T12:01:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-07-10T07:21:31.659022+00:00 | 2026-07-10T15:21:31.659022+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 329812 | TRUE | TRUE | 2026-07-10T07:21:31.659022+00:00 | 2026-07-10T15:21:31.659022+08:00 | #39002 - CLB: 84hrs - STACKER: CLB 11 | 4.0 | FALSE |  | 2026-11-29T22:00:00+00:00 | 2026-12-03T10:00:00+00:00 | 2026-11-30T06:00:00+08:00 | 2026-12-03T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Extending STK shut to 84hrs |  | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
65706 | 2024-11-12T02:50:22+00:00 | 2024-11-12T10:50:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-08-06T04:50:09.4031018+00:00 | 2026-08-06T12:50:09.4031018+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 330900 | TRUE | TRUE | 2026-08-06T04:50:09.4031018+00:00 | 2026-08-06T12:50:09.4031018+08:00 | #65706 - CLA: 4hrs - SLD3/SFP196 - C208 IDLER PREP | 2.1 | TRUE |  | 2027-11-27T00:00:00+00:00 | 2027-11-27T04:00:00+00:00 | 2027-11-27T08:00:00+08:00 | 2027-11-27T12:00:00+08:00 |  |  |  |  | 4.00 | SLD3/SFP196 - C208 Idler Prep,Start time is flexible. Prep outage for SLD2 / C208 shut in the following week. |  |  | [{"equipmentGUID": "b9e3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP196", "name": "Conveyor: CLA SFP196 Outloading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | No Scheduled Production Impact | CLA | Australia/Perth
65705 | 2024-11-12T02:50:19+00:00 | 2024-11-12T10:50:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-08-06T04:50:34.4702895+00:00 | 2026-08-06T12:50:34.4702895+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 330901 | TRUE | TRUE | 2026-08-06T04:50:34.4702895+00:00 | 2026-08-06T12:50:34.4702895+08:00 | #65705 - CLA: 4hrs - SLD3/SFP196 - C208 IDLER PREP | 2.1 | TRUE |  | 2027-08-28T00:00:00+00:00 | 2027-08-28T04:00:00+00:00 | 2027-08-28T08:00:00+08:00 | 2027-08-28T12:00:00+08:00 |  |  |  |  | 4.00 | SLD3/SFP196 - C208 Idler Prep,Start time is flexible. Prep outage for SLD2 / C208 shut in the following week. |  |  | [{"equipmentGUID": "b9e3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP196", "name": "Conveyor: CLA SFP196 Outloading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | No Scheduled Production Impact | CLA | Australia/Perth
65704 | 2024-11-12T02:50:18+00:00 | 2024-11-12T10:50:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-08-06T04:52:20.2996043+00:00 | 2026-08-06T12:52:20.2996043+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 330902 | TRUE | TRUE | 2026-08-06T04:52:20.2996043+00:00 | 2026-08-06T12:52:20.2996043+08:00 | #65704 - CLA: 4hrs - SLD3/SFP196 - C208 IDLER PREP | 2.1 | TRUE |  | 2027-05-29T00:00:00+00:00 | 2027-05-29T04:00:00+00:00 | 2027-05-29T08:00:00+08:00 | 2027-05-29T12:00:00+08:00 |  |  |  |  | 4.00 | SLD3/SFP196 - C208 Idler Prep,Start time is flexible. Prep outage for SLD2 / C208 shut in the following week. |  |  | [{"equipmentGUID": "b9e3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP196", "name": "Conveyor: CLA SFP196 Outloading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | No Scheduled Production Impact | CLA | Australia/Perth
65703 | 2024-11-12T02:50:17+00:00 | 2024-11-12T10:50:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-08-06T04:53:02.5785539+00:00 | 2026-08-06T12:53:02.5785539+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 330903 | TRUE | TRUE | 2026-08-06T04:53:02.5785539+00:00 | 2026-08-06T12:53:02.5785539+08:00 | #65703 - CLA: 4hrs - SLD3/SFP196 - C208 IDLER PREP | 2.1 | TRUE |  | 2027-02-27T00:00:00+00:00 | 2027-02-27T04:00:00+00:00 | 2027-02-27T08:00:00+08:00 | 2027-02-27T12:00:00+08:00 |  |  |  |  | 4.00 | SLD3/SFP196 - C208 Idler Prep,Start time is flexible. Prep outage for SLD2 / C208 shut in the following week. |  |  | [{"equipmentGUID": "b9e3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP196", "name": "Conveyor: CLA SFP196 Outloading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | No Scheduled Production Impact | CLA | Australia/Perth
59254 | 2023-11-01T07:55:25+00:00 | 2023-11-01T15:55:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-08-28T00:16:50.6057447+00:00 | 2026-08-28T08:16:50.6057447+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332089 | TRUE | TRUE | 2026-08-28T00:16:50.6057447+00:00 | 2026-08-28T08:16:50.6057447+08:00 | #59254 - CLA: 120hrs - CD2 IAM | 5.1 | TRUE |  | 2027-07-31T10:00:00+00:00 | 2027-08-05T10:00:00+00:00 | 2027-07-31T18:00:00+08:00 | 2027-08-05T18:00:00+08:00 |  |  |  |  | 120.00 | New shut created to replace shut # 43490 for barrel replacement moved to 2028 |  | SCAI2730 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56360 | 2023-07-13T06:58:55+00:00 | 2023-07-13T14:58:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-08-28T00:20:36.8219255+00:00 | 2026-08-28T08:20:36.8219255+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332097 | TRUE | TRUE | 2026-08-28T00:20:36.8219255+00:00 | 2026-08-28T08:20:36.8219255+08:00 | #56360 - CLA: 250hrs - STK1 IAM | 5.3 | TRUE |  | 2027-08-18T10:00:00+00:00 | 2027-08-28T20:00:00+00:00 | 2027-08-18T18:00:00+08:00 | 2027-08-29T04:00:00+08:00 |  |  |  |  | 250.00 | Standard IAM Maintenance & Luff Cylinder C/O (192hrs) Extended to align with 250hr plant shut |  | SCAP2733 | [{"equipmentGUID": "65ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST01", "name": "Stacker: CLA 01 RV Coarse Ore", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83685, "shutVersionId": 331824, "title": "#83685 - CLA: 172hrs - STK1 LUFF CYLINDER C/O", "startDatetimeUTC": "2027-08-18T10:00:00+00:00", "endDatetimeUTC": "2027-08-25T14:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56361 | 2023-07-13T06:58:58+00:00 | 2023-07-13T14:58:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-08-28T00:27:18.5788313+00:00 | 2026-08-28T08:27:18.5788313+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332111 | TRUE | TRUE | 2026-08-28T00:27:18.5788313+00:00 | 2026-08-28T08:27:18.5788313+08:00 | #56361 - CLA: 130hrs - STK1 IAM | 4.1 | TRUE |  | 2027-11-21T10:00:00+00:00 | 2027-11-26T20:00:00+00:00 | 2027-11-21T18:00:00+08:00 | 2027-11-27T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2747 | [{"equipmentGUID": "65ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST01", "name": "Stacker: CLA 01 RV Coarse Ore", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56408 | 2023-07-13T07:29:42+00:00 | 2023-07-13T15:29:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-08-28T00:27:32.6848073+00:00 | 2026-08-28T08:27:32.6848073+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332112 | TRUE | TRUE | 2026-08-28T00:27:32.6848073+00:00 | 2026-08-28T08:27:32.6848073+08:00 | #56408 - CLB: 106hrs - CVC04 IAM | 4.1 | TRUE |  | 2027-11-21T10:00:00+00:00 | 2027-11-25T20:00:00+00:00 | 2027-11-21T18:00:00+08:00 | 2027-11-26T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCAP2747 | [{"equipmentGUID": "4a6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV04", "name": "Conveyor: CLB C04", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
61974 | 2024-06-14T02:26:52+00:00 | 2024-06-14T10:26:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-08-27T22:01:46.1854496+00:00 | 2026-08-28T06:01:46.1854496+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332030 | TRUE | TRUE | 2026-08-27T22:01:46.1854496+00:00 | 2026-08-28T06:01:46.1854496+08:00 | #61974 - CLA: 24hrs - TERT4 IAM | 2.1 | FALSE |  | 2027-12-31T22:00:00+00:00 | 2028-01-01T22:00:00+00:00 | 2028-01-01T06:00:00+08:00 | 2028-01-02T06:00:00+08:00 |  |  |  |  | 24.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
61935 | 2024-06-13T07:32:56+00:00 | 2024-06-13T15:32:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-14T23:51:27.3365704+00:00 | 2026-10-15T07:51:27.3365704+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335899 | TRUE | TRUE | 2026-10-14T23:51:27.3365704+00:00 | 2026-10-15T07:51:27.3365704+08:00 | #61935 - CLA: 84hrs - TERT4 IAM | 4.1 | FALSE |  | 2027-09-27T16:00:00+00:00 | 2027-10-01T04:00:00+00:00 | 2027-09-28T00:00:00+08:00 | 2027-10-01T12:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56358 | 2023-07-13T06:58:53+00:00 | 2023-07-13T14:58:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T01:26:53.1339667+00:00 | 2026-10-15T09:26:53.1339667+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335959 | TRUE | TRUE | 2026-10-15T01:26:53.1339667+00:00 | 2026-10-15T09:26:53.1339667+08:00 | #56358 - CLA: 130hrs - STK1 IAM | 4.1 | TRUE |  | 2027-02-21T10:00:00+00:00 | 2027-02-26T20:00:00+00:00 | 2027-02-21T18:00:00+08:00 | 2027-02-27T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "65ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST01", "name": "Stacker: CLA 01 RV Coarse Ore", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
56405 | 2023-07-13T07:29:37+00:00 | 2023-07-13T15:29:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T01:12:40.1061753+00:00 | 2026-10-15T09:12:40.1061753+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335942 | TRUE | TRUE | 2026-10-15T01:12:40.1061753+00:00 | 2026-10-15T09:12:40.1061753+08:00 | #56405 - CLB: 106hrs - C04 PLANT SHUT | 4.1 | TRUE |  | 2027-02-21T10:00:00+00:00 | 2027-02-25T20:00:00+00:00 | 2027-02-21T18:00:00+08:00 | 2027-02-26T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "4a6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV04", "name": "Conveyor: CLB C04", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "3d2b7140-f5e3-4368-829e-0565bf5c543d", "emailAddress": "Matt.McKiernan@riotinto.com", "displayName": "McKiernan, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
61934 | 2024-06-13T07:32:55+00:00 | 2024-06-13T15:32:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000031b", "displayName": "Ray Boskell"} | 2026-10-15T01:41:16.8875655+00:00 | 2026-10-15T09:41:16.8875655+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335979 | TRUE | TRUE | 2026-10-15T01:41:16.8875655+00:00 | 2026-10-15T09:41:16.8875655+08:00 | #61934 - CLA: 84hrs - TERT4 IAM | 4.1 | FALSE |  | 2027-03-30T10:00:00+00:00 | 2027-04-02T22:00:00+00:00 | 2027-03-30T18:00:00+08:00 | 2027-04-03T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance |  | SCAL2713 | [{"equipmentGUID": "f8c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT04", "name": "Crusher - Tertiary: CLA Circuit 04", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43632 | 2021-11-01T23:42:45+00:00 | 2021-11-02T07:42:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-07-10T07:21:28.5202524+00:00 | 2026-07-10T15:21:28.5202524+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 329799 | TRUE | TRUE | 2026-07-10T07:21:28.5202524+00:00 | 2026-07-10T15:21:28.5202524+08:00 | #43632 - CLB: 84hrs - STACKER: CLB 13 | 5.0 | FALSE |  | 2027-09-26T22:00:00+00:00 | 2027-09-30T10:00:00+00:00 | 2027-09-27T06:00:00+08:00 | 2027-09-30T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut | Extending STK shut to 84hrs | SCBY2737 | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43704 | 2021-11-02T00:03:17+00:00 | 2021-11-02T08:03:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:27:49.1383295+00:00 | 2026-08-28T08:27:49.1383295+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332113 | TRUE | TRUE | 2026-08-28T00:27:49.1383295+00:00 | 2026-08-28T08:27:49.1383295+08:00 | #43704 - CLB: 72hrs - X-LINK IAM | 7.1 | TRUE |  | 2027-11-21T10:00:00+00:00 | 2027-11-24T10:00:00+00:00 | 2027-11-21T18:00:00+08:00 | 2027-11-24T18:00:00+08:00 |  |  |  |  | 72.00 | Contact Shutdown Coordinator regarding shuttle positions for CLB dumper and stacker alignment Standard IMS Shut |  | SCAP2747 | [{"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43718 | 2021-11-02T01:52:13+00:00 | 2021-11-02T09:52:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:28:08.2144532+00:00 | 2026-08-28T08:28:08.2144532+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332114 | TRUE | TRUE | 2026-08-28T00:28:08.2144532+00:00 | 2026-08-28T08:28:08.2144532+08:00 | #43718 - CLA: 130hrs - STK2 IAM | 5.1 | FALSE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IMS Shut |  | SCAP2747 | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43624 | 2021-11-01T23:36:00+00:00 | 2021-11-02T07:36:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:21:30.4894483+00:00 | 2026-08-28T08:21:30.4894483+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332098 | TRUE | TRUE | 2026-08-28T00:21:30.4894483+00:00 | 2026-08-28T08:21:30.4894483+08:00 | #43624 - CLB: 84hrs - ST11 IAM | 6.1 | FALSE |  | 2027-09-05T22:00:00+00:00 | 2027-09-09T10:00:00+00:00 | 2027-09-06T06:00:00+08:00 | 2027-09-09T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2736 | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43620 | 2021-11-01T23:35:52+00:00 | 2021-11-02T07:35:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:21:47.7893123+00:00 | 2026-08-28T08:21:47.7893123+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332099 | TRUE | TRUE | 2026-08-28T00:21:47.7893123+00:00 | 2026-08-28T08:21:47.7893123+08:00 | #43620 - CLB: 106hrs - CD5 IAM | 8.1 | TRUE |  | 2027-09-06T10:00:00+00:00 | 2027-09-10T20:00:00+00:00 | 2027-09-06T18:00:00+08:00 | 2027-09-11T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2736 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43491 | 2021-11-01T22:52:56+00:00 | 2021-11-02T06:52:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:22:50.614107+00:00 | 2026-08-28T08:22:50.614107+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332100 | TRUE | TRUE | 2026-08-28T00:22:50.614107+00:00 | 2026-08-28T08:22:50.614107+08:00 | #43491 - CLA: 120hrs - CD2 IAM | 10.1 | TRUE |  | 2027-10-30T10:00:00+00:00 | 2027-11-04T10:00:00+00:00 | 2027-10-30T18:00:00+08:00 | 2027-11-04T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance Original duration was a placeholder for CD2 AF replacements - now moved to 2028 |  | SCAI2743 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43507 | 2021-11-01T22:55:41+00:00 | 2021-11-02T06:55:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:23:16.635223+00:00 | 2026-08-28T08:23:16.635223+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332101 | TRUE | TRUE | 2026-08-28T00:23:16.635223+00:00 | 2026-08-28T08:23:16.635223+08:00 | #43507 - CLA: 150hrs - RCL2 IAM | 7.1 | FALSE |  | 2027-10-30T04:00:00+00:00 | 2027-11-05T10:00:00+00:00 | 2027-10-30T12:00:00+08:00 | 2027-11-05T18:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAI2743 | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43511 | 2021-11-01T22:55:46+00:00 | 2021-11-02T06:55:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:23:31.0685761+00:00 | 2026-08-28T08:23:31.0685761+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332102 | TRUE | TRUE | 2026-08-28T00:23:31.0685761+00:00 | 2026-08-28T08:23:31.0685761+08:00 | #43511 - CLA: 120hrs - STK5 IAM | 5.1 | FALSE |  | 2027-10-29T22:00:00+00:00 | 2027-11-03T22:00:00+00:00 | 2027-10-30T06:00:00+08:00 | 2027-11-04T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2743 | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43502 | 2021-11-01T22:54:46+00:00 | 2021-11-02T06:54:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:24:13.493897+00:00 | 2026-08-28T08:24:13.493897+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332103 | TRUE | TRUE | 2026-08-28T00:24:13.493897+00:00 | 2026-08-28T08:24:13.493897+08:00 | #43502 - CLA: 108hrs - STK4 IAM | 5.1 | FALSE |  | 2027-10-17T22:00:00+00:00 | 2027-10-22T10:00:00+00:00 | 2027-10-18T06:00:00+08:00 | 2027-10-22T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2742 | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43498 | 2021-11-01T22:54:38+00:00 | 2021-11-02T06:54:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:24:27.5783318+00:00 | 2026-08-28T08:24:27.5783318+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332104 | TRUE | TRUE | 2026-08-28T00:24:27.5783318+00:00 | 2026-08-28T08:24:27.5783318+08:00 | #43498 - CLA: 138hrs - RCL1 IAM | 5.1 | FALSE |  | 2027-10-18T04:00:00+00:00 | 2027-10-23T22:00:00+00:00 | 2027-10-18T12:00:00+08:00 | 2027-10-24T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2742 | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43585 | 2021-11-01T23:04:27+00:00 | 2021-11-02T07:04:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:24:55.4187745+00:00 | 2026-08-28T08:24:55.4187745+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332105 | TRUE | TRUE | 2026-08-28T00:24:55.4187745+00:00 | 2026-08-28T08:24:55.4187745+08:00 | #43585 - CLA: 114hrs - SLD3 IAM | 6.1 | TRUE |  | 2027-11-06T10:00:00+00:00 | 2027-11-11T04:00:00+00:00 | 2027-11-06T18:00:00+08:00 | 2027-11-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2744 | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43485 | 2021-11-01T22:50:55+00:00 | 2021-11-02T06:50:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:25:14.6450084+00:00 | 2026-08-28T08:25:14.6450084+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332106 | TRUE | TRUE | 2026-08-28T00:25:14.6450084+00:00 | 2026-08-28T08:25:14.6450084+08:00 | #43485 - CLA: 114hrs - BERTH3 IAM | 6.1 | FALSE |  | 2027-11-06T10:00:00+00:00 | 2027-11-11T04:00:00+00:00 | 2027-11-06T18:00:00+08:00 | 2027-11-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2744 | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43589 | 2021-11-01T23:04:32+00:00 | 2021-11-02T07:04:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:25:26.837612+00:00 | 2026-08-28T08:25:26.837612+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332107 | TRUE | TRUE | 2026-08-28T00:25:26.837612+00:00 | 2026-08-28T08:25:26.837612+08:00 | #43589 - CLA: 150hrs - RCL4 IAM | 5.1 | FALSE |  | 2027-11-05T16:00:00+00:00 | 2027-11-11T22:00:00+00:00 | 2027-11-06T00:00:00+08:00 | 2027-11-12T06:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAO2744 | [{"equipmentGUID": "9627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC04", "name": "Reclaimer: CLA 04", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43486 | 2021-11-01T22:50:56+00:00 | 2021-11-02T06:50:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:25:36.9661541+00:00 | 2026-08-28T08:25:36.9661541+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332108 | TRUE | TRUE | 2026-08-28T00:25:36.9661541+00:00 | 2026-08-28T08:25:36.9661541+08:00 | #43486 - CLA: 114hrs - BERTH4 IAM | 6.1 | FALSE |  | 2027-11-06T10:00:00+00:00 | 2027-11-11T04:00:00+00:00 | 2027-11-06T18:00:00+08:00 | 2027-11-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2744 | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43709 | 2021-11-02T00:34:00+00:00 | 2021-11-02T08:34:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:26:12.7971916+00:00 | 2026-08-28T08:26:12.7971916+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332109 | TRUE | TRUE | 2026-08-28T00:26:12.7971916+00:00 | 2026-08-28T08:26:12.7971916+08:00 | #43709 - CLA: 84hrs - RUBBLE IAM | 5.1 | FALSE |  | 2027-11-18T04:00:00+00:00 | 2027-11-21T16:00:00+00:00 | 2027-11-18T12:00:00+08:00 | 2027-11-22T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCAL2746 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43568 | 2021-11-01T22:59:21+00:00 | 2021-11-02T06:59:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:26:36.3071951+00:00 | 2026-08-28T08:26:36.3071951+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332110 | TRUE | TRUE | 2026-08-28T00:26:36.3071951+00:00 | 2026-08-28T08:26:36.3071951+08:00 | #43568 - CLA: 84hrs - SEC3 IAM | 8.1 | FALSE |  | 2027-11-18T04:00:00+00:00 | 2027-11-21T16:00:00+00:00 | 2027-11-18T12:00:00+08:00 | 2027-11-22T00:00:00+08:00 |  |  |  |  | 84.00 | SEC3 - 84hr Shut |  | SCAL2746 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43684 | 2021-11-01T23:59:22+00:00 | 2021-11-02T07:59:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:09:32.9737812+00:00 | 2026-08-28T08:09:32.9737812+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332079 | TRUE | TRUE | 2026-08-28T00:09:32.9737812+00:00 | 2026-08-28T08:09:32.9737812+08:00 | #43684 - CLB: 120hrs - SH5 IAM | 7.1 | FALSE |  | 2027-06-14T10:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-14T18:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2724 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43639 | 2021-11-01T23:45:16+00:00 | 2021-11-02T07:45:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:12:03.0067474+00:00 | 2026-08-28T08:12:03.0067474+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332080 | TRUE | TRUE | 2026-08-28T00:12:03.0067474+00:00 | 2026-08-28T08:12:03.0067474+08:00 | #43639 - CLB: 84hrs - ST12 IAM | 8.1 | FALSE |  | 2027-07-04T22:00:00+00:00 | 2027-07-08T10:00:00+00:00 | 2027-07-05T06:00:00+08:00 | 2027-07-08T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2727 | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43631 | 2021-11-01T23:42:41+00:00 | 2021-11-02T07:42:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:12:46.9166415+00:00 | 2026-08-28T08:12:46.9166415+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332081 | TRUE | TRUE | 2026-08-28T00:12:46.9166415+00:00 | 2026-08-28T08:12:46.9166415+08:00 | #43631 - CLB: 84hrs - ST13 IAM | 5.1 | FALSE |  | 2027-06-27T22:00:00+00:00 | 2027-07-01T10:00:00+00:00 | 2027-06-28T06:00:00+08:00 | 2027-07-01T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2726 | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43627 | 2021-11-01T23:42:37+00:00 | 2021-11-02T07:42:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:13:46.1025077+00:00 | 2026-08-28T08:13:46.1025077+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332082 | TRUE | TRUE | 2026-08-28T00:13:46.1025077+00:00 | 2026-08-28T08:13:46.1025077+08:00 | #43627 - CLB: 106hrs - CD6 IAM | 7.1 | TRUE |  | 2027-07-05T10:00:00+00:00 | 2027-07-09T20:00:00+00:00 | 2027-07-05T18:00:00+08:00 | 2027-07-10T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2727 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43697 | 2021-11-02T00:01:23+00:00 | 2021-11-02T08:01:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:14:39.4940597+00:00 | 2026-08-28T08:14:39.4940597+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332083 | TRUE | TRUE | 2026-08-28T00:14:39.4940597+00:00 | 2026-08-28T08:14:39.4940597+08:00 | #43697 - CLB: 120hrs - SH6 IAM | 7.1 | FALSE |  | 2027-07-12T10:00:00+00:00 | 2027-07-17T10:00:00+00:00 | 2027-07-12T18:00:00+08:00 | 2027-07-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2728 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43691 | 2021-11-02T00:01:14+00:00 | 2021-11-02T08:01:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:14:58.8846345+00:00 | 2026-08-28T08:14:58.8846345+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332084 | TRUE | TRUE | 2026-08-28T00:14:58.8846345+00:00 | 2026-08-28T08:14:58.8846345+08:00 | #43691 - CLB: 120hrs - SL12 IAM | 7.1 | TRUE |  | 2027-07-12T10:00:00+00:00 | 2027-07-17T10:00:00+00:00 | 2027-07-12T18:00:00+08:00 | 2027-07-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2728 | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43615 | 2021-11-01T23:30:15+00:00 | 2021-11-02T07:30:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:15:14.4110277+00:00 | 2026-08-28T08:15:14.4110277+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332085 | TRUE | TRUE | 2026-08-28T00:15:14.4110277+00:00 | 2026-08-28T08:15:14.4110277+08:00 | #43615 - CLB: 120hrs - BERTH8 IAM | 7.1 | FALSE |  | 2027-07-12T10:00:00+00:00 | 2027-07-17T10:00:00+00:00 | 2027-07-12T18:00:00+08:00 | 2027-07-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2728 | [{"equipmentGUID": "", "code": "CLBBTH08", "name": "Berth: CLB 08", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43614 | 2021-11-01T23:30:14+00:00 | 2021-11-02T07:30:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:15:30.4114028+00:00 | 2026-08-28T08:15:30.4114028+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332086 | TRUE | TRUE | 2026-08-28T00:15:30.4114028+00:00 | 2026-08-28T08:15:30.4114028+08:00 | #43614 - CLB: 120hrs - BERTH7 IAM | 7.1 | FALSE |  | 2027-07-12T10:00:00+00:00 | 2027-07-17T10:00:00+00:00 | 2027-07-12T18:00:00+08:00 | 2027-07-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2728 | [{"equipmentGUID": "", "code": "CLBBTH07", "name": "Berth: CLB 07", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43715 | 2021-11-02T01:52:09+00:00 | 2021-11-02T09:52:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:22:30.8518168+00:00 | 2026-10-15T09:22:30.8518168+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335951 | TRUE | TRUE | 2026-10-15T01:22:30.8518168+00:00 | 2026-10-15T09:22:30.8518168+08:00 | #43715 - CLA: 130hrs - STK2 PLANT SHUT | 5.1 | FALSE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IMS Shut |  | SCAP2708 | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43492 | 2021-11-01T22:53:57+00:00 | 2021-11-02T06:53:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:22:48.6119855+00:00 | 2026-10-15T09:22:48.6119855+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335952 | TRUE | TRUE | 2026-10-15T01:22:48.6119855+00:00 | 2026-10-15T09:22:48.6119855+08:00 | #43492 - CLA: 130hrs - PLANT SHUT | 5.1 | TRUE |  | 2027-02-21T17:00:00+00:00 | 2027-02-27T03:00:00+00:00 | 2027-02-22T01:00:00+08:00 | 2027-02-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2708 | [{"equipmentGUID": "9a17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLAPLT", "name": "Plant: CLA", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "799e0d01-6f83-4824-bdbf-c66168353aed", "emailAddress": "Nicky.Murray@riotinto.com", "displayName": "Nicky Murray"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43635 | 2021-11-01T23:45:12+00:00 | 2021-11-02T07:45:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:23:42.1735418+00:00 | 2026-10-15T09:23:42.1735418+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335953 | TRUE | TRUE | 2026-10-15T01:23:42.1735418+00:00 | 2026-10-15T09:23:42.1735418+08:00 | #43635 - CLB: 260hrs - CD7C - TRUNNION AND ROLLING RAIL REPLACEMENT | 9.1 | TRUE |  | 2027-02-22T10:00:00+00:00 | 2027-03-05T06:00:00+00:00 | 2027-02-22T18:00:00+08:00 | 2027-03-05T14:00:00+08:00 |  |  |  |  | 260.00 | Placeholder - CD7C Trunnion & Rolling Rail C/O - 264hrs |  | SCBI2708 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [{"name": "Rolling Rail & Trunnion Replacement"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43619 | 2021-11-01T23:35:52+00:00 | 2021-11-02T07:35:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:28:25.348015+00:00 | 2026-10-15T09:28:25.348015+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335960 | TRUE | TRUE | 2026-10-15T01:28:25.348015+00:00 | 2026-10-15T09:28:25.348015+08:00 | #43619 - CLB: 260hrs - CD5C STD IAM C/O ROLLING RAIL & TRUNNIONS 260H | 9.1 | TRUE |  | 2027-03-08T10:00:00+00:00 | 2027-03-19T06:00:00+00:00 | 2027-03-08T18:00:00+08:00 | 2027-03-19T14:00:00+08:00 |  |  |  |  | 260.00 | Standard IMS Shut Extended 260HCD5C Trunnion & Rolling Rails Contact Duane Evans, Shaun Adamson. |  | SCBI2710 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [{"name": "Rolling Rail & Trunnion Replacement"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43831 | 2021-11-11T06:01:07+00:00 | 2021-11-11T14:01:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:28:52.2821615+00:00 | 2026-10-15T09:28:52.2821615+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335961 | TRUE | TRUE | 2026-10-15T01:28:52.2821615+00:00 | 2026-10-15T09:28:52.2821615+08:00 | #43831 - CLB: 4hrs - ILSUB01 SHUT (CD5/ST11/ST12/RF) | 6.1 | TRUE |  | 2027-03-08T02:00:00+00:00 | 2027-03-08T06:00:00+00:00 | 2027-03-08T10:00:00+08:00 | 2027-03-08T14:00:00+08:00 |  |  |  |  | 4.00 | Inload SUB 1 Electrical Shut - 12hrs Additional Info: Substation Shuts will be completed on a 26 weekly cycleTrack maintenance aligned to CLB yard 8hrs 19/02/2022 (please consider if shut was to move) |  | SCBI2710 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "bdf8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL01", "name": "Substation: CLB Inloading 01", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "dcf7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV853", "name": "Conveyor: CLB 853 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43647 | 2021-11-01T23:47:37+00:00 | 2021-11-02T07:47:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:29:35.1023942+00:00 | 2026-10-15T09:29:35.1023942+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335962 | TRUE | TRUE | 2026-10-15T01:29:35.1023942+00:00 | 2026-10-15T09:29:35.1023942+08:00 | #43647 - CLB: 120hrs - RCL11 IAM | 5.2 | FALSE |  | 2027-03-14T22:00:00+00:00 | 2027-03-19T22:00:00+00:00 | 2027-03-15T06:00:00+08:00 | 2027-03-20T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Shut |  | SCBO2711 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43602 | 2021-11-01T23:22:15+00:00 | 2021-11-02T07:22:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:30:01.2103976+00:00 | 2026-10-15T09:30:01.2103976+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335963 | TRUE | TRUE | 2026-10-15T01:30:01.2103976+00:00 | 2026-10-15T09:30:01.2103976+08:00 | #43602 - CLB: 120hrs - BERTH5 IAM | 6.1 | FALSE |  | 2027-03-15T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-15T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2711 | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43682 | 2021-11-01T23:59:17+00:00 | 2021-11-02T07:59:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:32:15.1260632+00:00 | 2026-10-15T09:32:15.1260632+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335965 | TRUE | TRUE | 2026-10-15T01:32:15.1260632+00:00 | 2026-10-15T09:32:15.1260632+08:00 | #43682 - CLB: 120hrs - SH5 IAM | 6.1 | FALSE |  | 2027-03-15T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-15T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2711 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43675 | 2021-11-01T23:59:08+00:00 | 2021-11-02T07:59:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:32:36.8288413+00:00 | 2026-10-15T09:32:36.8288413+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335966 | TRUE | TRUE | 2026-10-15T01:32:36.8288413+00:00 | 2026-10-15T09:32:36.8288413+08:00 | #43675 - CLB: 120hrs - SL11 IAM | 8.1 | TRUE |  | 2027-03-15T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-15T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2711 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43671, "shutVersionId": 335967, "title": "#43671 - CLB: 84hrs - RETURN FINES IAM", "startDatetimeUTC": "2027-03-16T10:00:00+00:00", "endDatetimeUTC": "2027-03-19T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43671 | 2021-11-01T23:54:42+00:00 | 2021-11-02T07:54:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:33:08.022954+00:00 | 2026-10-15T09:33:08.022954+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335967 | TRUE | TRUE | 2026-10-15T01:33:08.022954+00:00 | 2026-10-15T09:33:08.022954+08:00 | #43671 - CLB: 84hrs - RETURN FINES IAM | 5.1 | FALSE |  | 2027-03-16T10:00:00+00:00 | 2027-03-19T22:00:00+00:00 | 2027-03-16T18:00:00+08:00 | 2027-03-20T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBO2711 | [{"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43675, "shutVersionId": 335966, "title": "#43675 - CLB: 120hrs - SL11 IAM", "startDatetimeUTC": "2027-03-15T10:00:00+00:00", "endDatetimeUTC": "2027-03-20T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43558 | 2021-11-01T22:59:03+00:00 | 2021-11-02T06:59:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:09:35.2790476+00:00 | 2026-10-15T09:09:35.2790476+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335941 | TRUE | TRUE | 2026-10-15T01:09:35.2790476+00:00 | 2026-10-15T09:09:35.2790476+08:00 | #43558 - CLA: 84hrs - TERT1 IAM | 5.1 | FALSE |  | 2027-02-14T16:00:00+00:00 | 2027-02-18T04:00:00+00:00 | 2027-02-15T00:00:00+08:00 | 2027-02-18T12:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCAL2707 | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43572 | 2021-11-01T22:59:53+00:00 | 2021-11-02T06:59:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:27:39.6128435+00:00 | 2026-10-15T08:27:39.6128435+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335933 | TRUE | TRUE | 2026-10-15T00:27:39.6128435+00:00 | 2026-10-15T08:27:39.6128435+08:00 | #43572 - CLA: 114hrs - SLD2 IAM | 7.1 | TRUE |  | 2027-02-06T10:00:00+00:00 | 2027-02-11T04:00:00+00:00 | 2027-02-06T18:00:00+08:00 | 2027-02-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2705 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43472 | 2021-11-01T22:49:37+00:00 | 2021-11-02T06:49:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:28:15.9632062+00:00 | 2026-10-15T08:28:15.9632062+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335934 | TRUE | TRUE | 2026-10-15T00:28:15.9632062+00:00 | 2026-10-15T08:28:15.9632062+08:00 | #43472 - CLA: 114hrs - BERTH2 IAM | 6.1 | FALSE |  | 2027-02-06T10:00:00+00:00 | 2027-02-11T04:00:00+00:00 | 2027-02-06T18:00:00+08:00 | 2027-02-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2705 | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43681 | 2021-11-01T23:59:17+00:00 | 2021-11-02T07:59:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:28:57.6381656+00:00 | 2026-10-15T08:28:57.6381656+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335935 | TRUE | TRUE | 2026-10-15T00:28:57.6381656+00:00 | 2026-10-15T08:28:57.6381656+08:00 | #43681 - CLB: 48hrs - SH5 FINES ONLY | 6.1 | FALSE |  | 2027-02-12T18:00:00+00:00 | 2027-02-14T18:00:00+00:00 | 2027-02-13T02:00:00+08:00 | 2027-02-15T02:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS Shut SH5 Fines Loading Only |  | SCBY2706 | [{"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43562 | 2021-11-01T22:59:11+00:00 | 2021-11-02T06:59:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:30:15.9665973+00:00 | 2026-10-15T08:30:15.9665973+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335936 | TRUE | TRUE | 2026-10-15T00:30:15.9665973+00:00 | 2026-10-15T08:30:15.9665973+08:00 | #43562 - CLA: 91hrs - SEC3 IAM | 6.1 | FALSE |  | 2027-02-17T22:00:00+00:00 | 2027-02-21T17:00:00+00:00 | 2027-02-18T06:00:00+08:00 | 2027-02-22T01:00:00+08:00 |  |  |  |  | 91.00 | Standard IMS Shut |  | SCAL2707 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43706 | 2021-11-02T00:33:56+00:00 | 2021-11-02T08:33:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:30:34.9283402+00:00 | 2026-10-15T08:30:34.9283402+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335937 | TRUE | TRUE | 2026-10-15T00:30:34.9283402+00:00 | 2026-10-15T08:30:34.9283402+08:00 | #43706 - CLA: 91hrs - RUBBLE IAM | 6.1 | FALSE |  | 2027-02-17T22:00:00+00:00 | 2027-02-21T17:00:00+00:00 | 2027-02-18T06:00:00+08:00 | 2027-02-22T01:00:00+08:00 |  |  |  |  | 91.00 | Standard IMS Shut |  | SCAL2707 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43650 | 2021-11-01T23:49:57+00:00 | 2021-11-02T07:49:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:19:01.064753+00:00 | 2026-10-15T08:19:01.064753+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335919 | TRUE | TRUE | 2026-10-15T00:19:01.064753+00:00 | 2026-10-15T08:19:01.064753+08:00 | #43650 - CLB: 120hrs - RC12 IAM | 5.3 | FALSE |  | 2027-01-10T22:00:00+00:00 | 2027-01-15T22:00:00+00:00 | 2027-01-11T06:00:00+08:00 | 2027-01-16T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2702 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43821 | 2021-11-11T02:48:41+00:00 | 2021-11-11T10:48:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:19:53.8151167+00:00 | 2026-10-15T08:19:53.8151167+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335920 | TRUE | TRUE | 2026-10-15T00:19:53.8151167+00:00 | 2026-10-15T08:19:53.8151167+08:00 | #43821 - CLB: 4hrs - YDSUB03 SHUT (SL12/SH6/RC13/ST14) | 6.1 | TRUE |  | 2027-01-13T02:00:00+00:00 | 2027-01-13T06:00:00+00:00 | 2027-01-13T10:00:00+08:00 | 2027-01-13T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 3 Shut - 12hrs Additional Info: Yard SUB 3 Electrical Shut - 26 Weekly Cycle |  | SCBO2702 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "5b5cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD03", "name": "Substation: CLB Stockyard 03", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "2ad9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV660", "name": "Conveyor: CLB 660", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
39364 | 2020-12-18T05:07:36+00:00 | 2020-12-18T13:07:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:20:37.2398799+00:00 | 2026-10-15T08:20:37.2398799+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335922 | TRUE | TRUE | 2026-10-15T00:20:37.2398799+00:00 | 2026-10-15T08:20:37.2398799+08:00 | #39364 - CLA: 108hrs - STK4 IAM | 4.2 | FALSE |  | 2027-01-17T22:00:00+00:00 | 2027-01-22T10:00:00+00:00 | 2027-01-18T06:00:00+08:00 | 2027-01-22T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2703 | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
39345 | 2020-12-18T05:07:05+00:00 | 2020-12-18T13:07:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:20:48.4807634+00:00 | 2026-10-15T08:20:48.4807634+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335923 | TRUE | TRUE | 2026-10-15T00:20:48.4807634+00:00 | 2026-10-15T08:20:48.4807634+08:00 | #39345 - CLA: 138hrs - RCL1 IAM | 4.2 | FALSE |  | 2027-01-18T04:00:00+00:00 | 2027-01-23T22:00:00+00:00 | 2027-01-18T12:00:00+08:00 | 2027-01-24T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2703 | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43508 | 2021-11-01T22:55:41+00:00 | 2021-11-02T06:55:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:21:33.4694039+00:00 | 2026-10-15T08:21:33.4694039+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335924 | TRUE | TRUE | 2026-10-15T00:21:33.4694039+00:00 | 2026-10-15T08:21:33.4694039+08:00 | #43508 - CLA: 120hrs - STK5 IAM | 5.2 | FALSE |  | 2027-01-29T22:00:00+00:00 | 2027-02-03T22:00:00+00:00 | 2027-01-30T06:00:00+08:00 | 2027-02-04T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2704 | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43504 | 2021-11-01T22:55:37+00:00 | 2021-11-02T06:55:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:21:50.6562184+00:00 | 2026-10-15T08:21:50.6562184+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335925 | TRUE | TRUE | 2026-10-15T00:21:50.6562184+00:00 | 2026-10-15T08:21:50.6562184+08:00 | #43504 - CLA: 150hrs - RCL2 IAM | 5.2 | FALSE |  | 2027-01-30T04:00:00+00:00 | 2027-02-05T10:00:00+00:00 | 2027-01-30T12:00:00+08:00 | 2027-02-05T18:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAI2704 | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43488 | 2021-11-01T22:52:52+00:00 | 2021-11-02T06:52:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:22:19.7698164+00:00 | 2026-10-15T08:22:19.7698164+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335926 | TRUE | TRUE | 2026-10-15T00:22:19.7698164+00:00 | 2026-10-15T08:22:19.7698164+08:00 | #43488 - CLA: 120hrs - CD2 IAM | 6.1 | TRUE |  | 2027-01-30T10:00:00+00:00 | 2027-02-04T10:00:00+00:00 | 2027-01-30T18:00:00+08:00 | 2027-02-04T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2704 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43586 | 2021-11-01T23:04:27+00:00 | 2021-11-02T07:04:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:22:54.4200079+00:00 | 2026-10-15T08:22:54.4200079+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335927 | TRUE | TRUE | 2026-10-15T00:22:54.4200079+00:00 | 2026-10-15T08:22:54.4200079+08:00 | #43586 - CLA: 150hrs - RCL4 IAM | 9.1 | FALSE |  | 2027-02-05T22:00:00+00:00 | 2027-02-12T04:00:00+00:00 | 2027-02-06T06:00:00+08:00 | 2027-02-12T12:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAO2705 | [{"equipmentGUID": "9627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC04", "name": "Reclaimer: CLA 04", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43471 | 2021-11-01T22:49:37+00:00 | 2021-11-02T06:49:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:23:42.5623305+00:00 | 2026-10-15T08:23:42.5623305+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335928 | TRUE | TRUE | 2026-10-15T00:23:42.5623305+00:00 | 2026-10-15T08:23:42.5623305+08:00 | #43471 - CLA: 114hrs - BERTH1 IAM | 6.1 | FALSE |  | 2027-02-06T10:00:00+00:00 | 2027-02-11T04:00:00+00:00 | 2027-02-06T18:00:00+08:00 | 2027-02-11T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2705 | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43610 | 2021-11-01T23:30:10+00:00 | 2021-11-02T07:30:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:24:16.2237553+00:00 | 2026-10-15T08:24:16.2237553+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335929 | TRUE | TRUE | 2026-10-15T00:24:16.2237553+00:00 | 2026-10-15T08:24:16.2237553+08:00 | #43610 - CLB: 120hrs - BERTH7 IAM | 6.1 | FALSE |  | 2027-01-11T10:00:00+00:00 | 2027-01-16T10:00:00+00:00 | 2027-01-11T18:00:00+08:00 | 2027-01-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2702 | [{"equipmentGUID": "", "code": "CLBBTH07", "name": "Berth: CLB 07", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43611 | 2021-11-01T23:30:11+00:00 | 2021-11-02T07:30:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:24:33.1879083+00:00 | 2026-10-15T08:24:33.1879083+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335930 | TRUE | TRUE | 2026-10-15T00:24:33.1879083+00:00 | 2026-10-15T08:24:33.1879083+08:00 | #43611 - CLB: 120hrs - BERTH8 IAM | 6.1 | FALSE |  | 2027-01-11T10:00:00+00:00 | 2027-01-16T10:00:00+00:00 | 2027-01-11T18:00:00+08:00 | 2027-01-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2702 | [{"equipmentGUID": "", "code": "CLBBTH08", "name": "Berth: CLB 08", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44009 | 2021-11-16T01:13:33+00:00 | 2021-11-16T09:13:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:48:44.6462201+00:00 | 2026-10-15T09:48:44.6462201+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335988 | TRUE | TRUE | 2026-10-15T01:48:44.6462201+00:00 | 2026-10-15T09:48:44.6462201+08:00 | #44009 - CLB: 12hrs - SL12 OUTLOAD CIRCUIT FS SYSTEM TESTING | 4.1 | TRUE |  | 2027-04-19T22:00:00+00:00 | 2027-04-20T10:00:00+00:00 | 2027-04-20T06:00:00+08:00 | 2027-04-20T18:00:00+08:00 |  |  |  |  | 12.00 | OLSLC2 Electrical System Test Additional Info: Electrical System Testing is completed on a 52 week cycle |  |  | [{"equipmentGUID": "0f05f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV721", "name": "Conveyor: CLB 721 Shiploading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "a46efbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV665", "name": "Conveyor: CLB 665", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43912 | 2021-11-15T08:03:25+00:00 | 2021-11-15T16:03:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:49:09.8849232+00:00 | 2026-10-15T09:49:09.8849232+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335989 | TRUE | TRUE | 2026-10-15T01:49:09.8849232+00:00 | 2026-10-15T09:49:09.8849232+08:00 | #43912 - CLB: 12hrs - CV450 REMSAFE | 3.2 | TRUE |  | 2027-04-30T22:00:00+00:00 | 2027-05-01T10:00:00+00:00 | 2027-05-01T06:00:00+08:00 | 2027-05-01T18:00:00+08:00 |  |  |  |  | 12.00 | CV450 Inload Remsafe Testing - 12hrs |  |  | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "f9e7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV450", "name": "Conveyor: CLB 450 Car Dumper 5C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43509 | 2021-11-01T22:55:42+00:00 | 2021-11-02T06:55:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:49:34.4106833+00:00 | 2026-10-15T09:49:34.4106833+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335990 | TRUE | TRUE | 2026-10-15T01:49:34.4106833+00:00 | 2026-10-15T09:49:34.4106833+08:00 | #43509 - CLA: 120hrs - STK5 IAM | 5.2 | FALSE |  | 2027-04-30T22:00:00+00:00 | 2027-05-05T22:00:00+00:00 | 2027-05-01T06:00:00+08:00 | 2027-05-06T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2717 | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
44004 | 2021-11-16T01:03:32+00:00 | 2021-11-16T09:03:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:51:38.0671635+00:00 | 2026-10-15T09:51:38.0671635+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335991 | TRUE | TRUE | 2026-10-15T01:51:38.0671635+00:00 | 2026-10-15T09:51:38.0671635+08:00 | #44004 - CLB: 12hrs - SL11 OUTLOAD CIRCUIT FS SYSTEM TESTING | 4.1 | TRUE |  | 2027-04-18T22:00:00+00:00 | 2027-04-19T10:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-19T18:00:00+08:00 |  |  |  |  | 12.00 | OLSLC1 Electrical System Test Additional Info: Electrical System Testing is completed on a 52 week cycle |  |  | [{"equipmentGUID": "7aefe8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV655", "name": "Conveyor: CLB 655", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "dd23f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV711", "name": "Conveyor: CLB 711 Shiploading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43889 | 2021-11-15T05:45:51+00:00 | 2021-11-15T13:45:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:51:49.9839175+00:00 | 2026-10-15T09:51:49.9839175+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335992 | TRUE | TRUE | 2026-10-15T01:51:49.9839175+00:00 | 2026-10-15T09:51:49.9839175+08:00 | #43889 - CLB: 12hrs - SL11 FS SYSTEM TESTING | 5.2 | TRUE |  | 2027-04-18T22:00:00+00:00 | 2027-04-19T10:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-19T18:00:00+08:00 |  |  |  |  | 12.00 | SL11 Functional Safety System Test - 12hrs Functional Safety System Testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43669 | 2021-11-01T23:54:41+00:00 | 2021-11-02T07:54:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:53:52.3688838+00:00 | 2026-10-15T09:53:52.3688838+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335994 | TRUE | TRUE | 2026-10-15T01:53:52.3688838+00:00 | 2026-10-15T09:53:52.3688838+08:00 | #43669 - CLB: 228hrs - RCL13 MAJOR BUCKET WHEEL MAINTENANCE | 7.1 | FALSE |  | 2027-05-09T22:00:00+00:00 | 2027-05-19T10:00:00+00:00 | 2027-05-10T06:00:00+08:00 | 2027-05-19T18:00:00+08:00 |  |  |  |  | 228.00 | Standard IAM Shut RC13 228hr Extend Outage Bucket Wheel Major Maintenance Inclusive 52WK ring chute, radial liner, domite C/O + all 13 buckets) |  | SCBY2719 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43974 | 2021-11-16T00:14:32+00:00 | 2021-11-16T08:14:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-31T08:13:20.9522181+00:00 | 2026-08-31T16:13:20.9522181+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332372 | TRUE | TRUE | 2026-08-31T08:13:20.9522181+00:00 | 2026-08-31T16:13:20.9522181+08:00 | #43974 - CLB: 12hrs - RC13 CAPD TESTING | 4.0 | FALSE |  | 2027-07-01T22:00:00+00:00 | 2027-07-02T10:00:00+00:00 | 2027-07-02T06:00:00+08:00 | 2027-07-02T18:00:00+08:00 |  |  |  |  | 12.00 | RC13 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. | Moving to second grouping of CAPD shuts so SLD2 and SLD3 can avoid other SLD shuts | SCBY2724 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44027 | 2021-11-16T01:57:27+00:00 | 2021-11-16T09:57:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-31T08:16:02.6213534+00:00 | 2026-08-31T16:16:02.6213534+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332373 | TRUE | TRUE | 2026-08-31T08:16:02.6213534+00:00 | 2026-08-31T16:16:02.6213534+08:00 | #44027 - CLB: 12hrs - CV654 REMSAFE TESTING | 5.0 | FALSE |  | 2027-03-21T22:00:00+00:00 | 2027-03-22T10:00:00+00:00 | 2027-03-22T06:00:00+08:00 | 2027-03-22T18:00:00+08:00 |  |  |  |  | 12.00 | CV654 Outload Remsafe Testing - 12hrs | moving away from SL11 IAM shut | SCBO2711 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "110df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV654", "name": "Conveyor: CLB 654", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43943 | 2021-11-15T23:13:01+00:00 | 2021-11-16T07:13:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-09-01T09:02:28.6011908+00:00 | 2026-09-01T17:02:28.6011908+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332402 | TRUE | TRUE | 2026-09-01T09:02:28.6011908+00:00 | 2026-09-01T17:02:28.6011908+08:00 | #43943 - CLB: 4hrs - YDSUB01 SHUT (ST11/RC11/RFSAMPLING) | 3.0 | FALSE |  | 2027-06-16T02:00:00+00:00 | 2027-06-16T06:00:00+00:00 | 2027-06-16T10:00:00+08:00 | 2027-06-16T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 1 Shut - 12hrs Additional Info: Substation Shuts will be completed on a 26 weekly cycle | Reducing to 4hrs, no 208WK inspection for this sub for this period Aligning to RC11 and return fines shut | SCBY2720 | [{"equipmentGUID": "7b17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSARF", "name": "Sample Station: CLB Fines Return", "assetClass": {"name": "Sample Station"}}, {"equipmentGUID": "173df6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD01", "name": "Substation: CLB Stockyard 01", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43905 | 2021-11-15T07:14:26+00:00 | 2021-11-15T15:14:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-09-01T09:02:28.7918918+00:00 | 2026-09-01T17:02:28.7918918+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332403 | TRUE | TRUE | 2026-09-01T09:02:28.7918918+00:00 | 2026-09-01T17:02:28.7918918+08:00 | #43905 - CLB: 4hrs - YDSUB02 SHUT (CV650/ST12/RC12) | 4.0 | FALSE |  | 2027-09-14T02:00:00+00:00 | 2027-09-14T06:00:00+00:00 | 2027-09-14T10:00:00+08:00 | 2027-09-14T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 2 Shut - 12hrs Additional Info: SH5 Must be fed from RC11 during this time. | Reducing to 4hrs, no 208WK inspection for this sub for this period Aligning with SH5 shut | SCBY2737 | [{"equipmentGUID": "2420f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD02", "name": "Substation: CLB Stockyard 02", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "14f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV650", "name": "Conveyor: CLB 650", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43944 | 2021-11-15T23:13:02+00:00 | 2021-11-16T07:13:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-09-01T09:02:28.9902019+00:00 | 2026-09-01T17:02:28.9902019+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332404 | TRUE | TRUE | 2026-09-01T09:02:28.9902019+00:00 | 2026-09-01T17:02:28.9902019+08:00 | #43944 - CLB: 4hrs - YDSUB01 SHUT (ST11/RC11/RFSAMPLING) | 3.0 | FALSE |  | 2027-12-08T02:00:00+00:00 | 2027-12-08T06:00:00+00:00 | 2027-12-08T10:00:00+08:00 | 2027-12-08T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 1 Shut - 12hrs Additional Info: Substation Shuts will be completed on a 26 weekly cycle | Reducing to 4hrs, no 208WK inspection for this sub for this period aligning with ST11 shut | SCBY2746 | [{"equipmentGUID": "7b17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSARF", "name": "Sample Station: CLB Fines Return", "assetClass": {"name": "Sample Station"}}, {"equipmentGUID": "173df6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD01", "name": "Substation: CLB Stockyard 01", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43541 | 2021-11-01T22:57:56+00:00 | 2021-11-02T06:57:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:42:13.1346534+00:00 | 2026-10-15T09:42:13.1346534+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335981 | TRUE | TRUE | 2026-10-15T01:42:13.1346534+00:00 | 2026-10-15T09:42:13.1346534+08:00 | #43541 - CLA: 24hrs - TERT3 IAM | 7.1 | FALSE |  | 2027-04-02T22:00:00+00:00 | 2027-04-03T22:00:00+00:00 | 2027-04-03T06:00:00+08:00 | 2027-04-04T06:00:00+08:00 |  |  |  |  | 24.00 | Standard IAM TERT3 24hr Pitstop Shut |  | SCAL2713 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43516 | 2021-11-01T22:56:16+00:00 | 2021-11-02T06:56:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:35:50.6015596+00:00 | 2026-10-15T09:35:50.6015596+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335972 | TRUE | TRUE | 2026-10-15T01:35:50.6015596+00:00 | 2026-10-15T09:35:50.6015596+08:00 | #43516 - CLA: 108hrs - STK3 IAM | 5.1 | FALSE |  | 2027-03-21T22:00:00+00:00 | 2027-03-26T10:00:00+00:00 | 2027-03-22T06:00:00+08:00 | 2027-03-26T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2712 | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45740, "shutVersionId": 333124, "title": "#45740 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING", "startDatetimeUTC": "2027-03-22T22:00:00+00:00", "endDatetimeUTC": "2027-03-24T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43622 | 2021-11-01T23:35:55+00:00 | 2021-11-02T07:35:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:37:41.2939906+00:00 | 2026-10-15T09:37:41.2939906+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335974 | TRUE | TRUE | 2026-10-15T01:37:41.2939906+00:00 | 2026-10-15T09:37:41.2939906+08:00 | #43622 - CLB: 84hrs - ST11 IAM | 7.1 | FALSE |  | 2027-03-07T22:00:00+00:00 | 2027-03-11T10:00:00+00:00 | 2027-03-08T06:00:00+08:00 | 2027-03-11T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2710 | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43630 | 2021-11-01T23:42:41+00:00 | 2021-11-02T07:42:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:39:34.482227+00:00 | 2026-10-15T09:39:34.482227+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335976 | TRUE | TRUE | 2026-10-15T01:39:34.482227+00:00 | 2026-10-15T09:39:34.482227+08:00 | #43630 - CLB: 84hrs - ST13 IAM | 6.1 | FALSE |  | 2027-03-28T22:00:00+00:00 | 2027-04-01T10:00:00+00:00 | 2027-03-29T06:00:00+08:00 | 2027-04-01T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2713 | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43533 | 2021-11-01T22:57:43+00:00 | 2021-11-02T06:57:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:40:14.0071629+00:00 | 2026-10-15T09:40:14.0071629+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335977 | TRUE | TRUE | 2026-10-15T01:40:14.0071629+00:00 | 2026-10-15T09:40:14.0071629+08:00 | #43533 - CLA: 84hrs - SEC1 IAM | 7.1 | FALSE |  | 2027-03-28T22:00:00+00:00 | 2027-04-01T10:00:00+00:00 | 2027-03-29T06:00:00+08:00 | 2027-04-01T18:00:00+08:00 |  |  |  |  | 84.00 | SEC1 - 84hr Shut |  | SCAL2713 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43701 | 2021-11-02T00:03:13+00:00 | 2021-11-02T08:03:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:13:12.642638+00:00 | 2026-10-15T09:13:12.642638+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335943 | TRUE | TRUE | 2026-10-15T01:13:12.642638+00:00 | 2026-10-15T09:13:12.642638+08:00 | #43701 - CLB: 72hrs - X LINK PLANT SHUT | 9.1 | TRUE |  | 2027-02-21T10:00:00+00:00 | 2027-02-24T10:00:00+00:00 | 2027-02-21T18:00:00+08:00 | 2027-02-24T18:00:00+08:00 |  |  |  |  | 72.00 | Contact Shutdown Coordinator regarding shuttle positions for CLB dumper and stacker alignment Standard IMS Shut |  | SCAP2708 | [{"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43904 | 2021-11-15T07:14:24+00:00 | 2021-11-15T15:14:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:34:17.6031671+00:00 | 2026-10-15T09:34:17.6031671+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335969 | TRUE | TRUE | 2026-10-15T01:34:17.6031671+00:00 | 2026-10-15T09:34:17.6031671+08:00 | #43904 - CLB: 4hrs - YDSUB02 SHUT (CV650/ST12/RC12) | 4.1 | FALSE |  | 2027-03-17T02:00:00+00:00 | 2027-03-17T06:00:00+00:00 | 2027-03-17T10:00:00+08:00 | 2027-03-17T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 2 Shut - 12hrs Additional Info: SH5 Must be fed from RC11 during this time. |  | SCBO2711 | [{"equipmentGUID": "2420f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD02", "name": "Substation: CLB Stockyard 02", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "14f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV650", "name": "Conveyor: CLB 650", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43512 | 2021-11-01T22:56:12+00:00 | 2021-11-02T06:56:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:34:56.3751132+00:00 | 2026-10-15T09:34:56.3751132+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335970 | TRUE | TRUE | 2026-10-15T01:34:56.3751132+00:00 | 2026-10-15T09:34:56.3751132+08:00 | #43512 - CLA: 138hrs - RCL3 IAM | 5.1 | FALSE |  | 2027-03-22T04:00:00+00:00 | 2027-03-27T22:00:00+00:00 | 2027-03-22T12:00:00+08:00 | 2027-03-28T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2712 | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45740, "shutVersionId": 333124, "title": "#45740 - CLA: 48hrs - CONVEYOR: CLA 214 LUMP RESCREENING", "startDatetimeUTC": "2027-03-22T22:00:00+00:00", "endDatetimeUTC": "2027-03-24T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43480 | 2021-11-01T22:50:47+00:00 | 2021-11-02T06:50:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:24:42.2378238+00:00 | 2026-10-15T09:24:42.2378238+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335955 | TRUE | TRUE | 2026-10-15T01:24:42.2378238+00:00 | 2026-10-15T09:24:42.2378238+08:00 | #43480 - CLA: 114hrs - BERTH4 IAM | 6.1 | FALSE |  | 2027-03-01T10:00:00+00:00 | 2027-03-06T04:00:00+00:00 | 2027-03-01T18:00:00+08:00 | 2027-03-06T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2709 | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43479 | 2021-11-01T22:50:47+00:00 | 2021-11-02T06:50:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:25:01.4159511+00:00 | 2026-10-15T09:25:01.4159511+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335956 | TRUE | TRUE | 2026-10-15T01:25:01.4159511+00:00 | 2026-10-15T09:25:01.4159511+08:00 | #43479 - CLA: 114hrs - BERTH3 IAM | 6.1 | FALSE |  | 2027-03-01T10:00:00+00:00 | 2027-03-06T04:00:00+00:00 | 2027-03-01T18:00:00+08:00 | 2027-03-06T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2709 | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43582 | 2021-11-01T23:04:23+00:00 | 2021-11-02T07:04:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:25:22.7564749+00:00 | 2026-10-15T09:25:22.7564749+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335957 | TRUE | TRUE | 2026-10-15T01:25:22.7564749+00:00 | 2026-10-15T09:25:22.7564749+08:00 | #43582 - CLA: 114hrs - SLD3 IAM | 7.1 | TRUE |  | 2027-03-01T10:00:00+00:00 | 2027-03-06T04:00:00+00:00 | 2027-03-01T18:00:00+08:00 | 2027-03-06T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2709 | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43578 | 2021-11-01T23:00:01+00:00 | 2021-11-02T07:00:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:25:52.2025197+00:00 | 2026-10-15T09:25:52.2025197+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335958 | TRUE | TRUE | 2026-10-15T01:25:52.2025197+00:00 | 2026-10-15T09:25:52.2025197+08:00 | #43578 - CLA: 126hrs - LRP2 IAM | 5.1 | FALSE |  | 2027-03-01T10:00:00+00:00 | 2027-03-06T16:00:00+00:00 | 2027-03-01T18:00:00+08:00 | 2027-03-07T00:00:00+08:00 |  |  |  |  | 126.00 | Standard IMS Shut |  | SCAO2709 | [{"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43649 | 2021-11-01T23:47:41+00:00 | 2021-11-02T07:47:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-09-03T02:34:45.649571+00:00 | 2026-09-03T10:34:45.649571+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 333110 | TRUE | TRUE | 2026-09-03T02:34:45.649571+00:00 | 2026-09-03T10:34:45.649571+08:00 | #43649 - CLB: 228hrs - RC11 MAJOR BUCKET WHEEL MAINTENANCE | 7.0 | FALSE |  | 2027-09-12T22:00:00+00:00 | 2027-09-22T10:00:00+00:00 | 2027-09-13T06:00:00+08:00 | 2027-09-22T18:00:00+08:00 |  |  |  |  | 228.00 | Standard IMS Shut RC11 228hr Extend Outage Bucket Wheel Major Maintenance Inclusive 52WK ring chute, radial liner, domite C/O + all 13 buckets) | Re-align with IAM sequence and maintenance strategy |  | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
60653 | 2024-02-16T04:13:01+00:00 | 2024-02-16T12:13:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-08-17T04:44:42.5431181+00:00 | 2026-08-17T12:44:42.5431181+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331332 | TRUE | TRUE | 2026-08-17T04:44:42.5431181+00:00 | 2026-08-17T12:44:42.5431181+08:00 | #60653 - CLB: 72hrs - SL12 RMP REMEDIAL REPAIRS | 5.2 | TRUE |  | 2027-05-24T16:00:00+00:00 | 2027-05-27T16:00:00+00:00 | 2027-05-25T00:00:00+08:00 | 2027-05-28T00:00:00+08:00 |  |  |  |  | 72.00 | Further confirmation will be provided once the scope, schedule impacts, and required approvals have been reviewed. |  |  | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43884 | 2021-11-15T05:19:19+00:00 | 2021-11-15T13:19:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-17T22:05:11.7935473+00:00 | 2026-08-18T06:05:11.7935473+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331360 | TRUE | TRUE | 2026-08-17T22:05:11.7935473+00:00 | 2026-08-18T06:05:11.7935473+08:00 | #43884 - CLB: 4hrs - SUBSTATION: CLB PROCESS WATER PLANT WR01 | 3.0 | FALSE |  | 2027-09-20T22:00:00+00:00 | 2027-09-21T02:00:00+00:00 | 2027-09-21T06:00:00+08:00 | 2027-09-21T10:00:00+08:00 |  |  |  |  | 4.00 | CLB Process Water Substation Electrical Inspection - 12hrs Additional Info: Water will need to be diverted from CLA for Statutory Work.Substation Shuts will be completed on a 26 weekly cycle | No 208WK inspection for this sub for this period | N/A | [{"equipmentGUID": "2e20f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBWR01", "name": "Substation: CLB Process Water Plant WR01", "assetClass": {"name": "Substation"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43873 | 2021-11-15T04:45:22+00:00 | 2021-11-15T12:45:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-16T23:27:59.4064427+00:00 | 2026-08-17T07:27:59.4064427+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331294 | TRUE | TRUE | 2026-08-16T23:27:59.4064427+00:00 | 2026-08-17T07:27:59.4064427+08:00 | #43873 - CLB: 12hrs - ILSUB02 SHUT (CD7/ST13/ST14) | 4.2 | TRUE |  | 2027-08-27T22:00:00+00:00 | 2027-08-28T10:00:00+00:00 | 2027-08-28T06:00:00+08:00 | 2027-08-28T18:00:00+08:00 |  |  |  |  | 12.00 | Inload SUB 2 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycleTrack maintenance aligned to CLB yard 8hrs 19/02/2022 (please consider if shut was to move) |  | SCBI2736 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "bc5efbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL02", "name": "Substation: CLB Inloading 02", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44022 | 2021-11-16T01:43:01+00:00 | 2021-11-16T09:43:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-16T23:31:58.6745409+00:00 | 2026-08-17T07:31:58.6745409+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331298 | TRUE | TRUE | 2026-08-16T23:31:58.6745409+00:00 | 2026-08-17T07:31:58.6745409+08:00 | #44022 - CLB: 12hrs - ILSUB03 SHUT (CD6 + CV500) | 3.3 | TRUE |  | 2027-12-29T22:00:00+00:00 | 2027-12-30T10:00:00+00:00 | 2027-12-30T06:00:00+08:00 | 2027-12-30T18:00:00+08:00 |  |  |  |  | 12.00 | Inload SUB 3 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycle |  | SBCL2751 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "4f73fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL03", "name": "Substation: CLB Inloading 03", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43872 | 2021-11-15T04:45:20+00:00 | 2021-11-15T12:45:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-20T02:35:47.5179486+00:00 | 2026-08-20T10:35:47.5179486+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331442 | TRUE | TRUE | 2026-08-20T02:35:47.5179486+00:00 | 2026-08-20T10:35:47.5179486+08:00 | #43872 - CLB: 4hrs - ILSUB02 SHUT (CD7/ST13/ST14) | 4.0 | TRUE |  | 2027-03-02T22:00:00+00:00 | 2027-03-03T02:00:00+00:00 | 2027-03-03T06:00:00+08:00 | 2027-03-03T10:00:00+08:00 |  |  |  |  | 4.00 | Inload SUB 2 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycleTrack maintenance aligned to CLB yard 8hrs 19/02/2022 (please consider if shut was to move) | No 208WK inspection for this sub for this period Aligning with CD7 shut | SCBI2710 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "bc5efbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL02", "name": "Substation: CLB Inloading 02", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43676 | 2021-11-01T23:59:09+00:00 | 2021-11-02T07:59:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-20T03:52:42.2643049+00:00 | 2026-08-20T11:52:42.2643049+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331448 | TRUE | TRUE | 2026-08-20T03:52:42.2643049+00:00 | 2026-08-20T11:52:42.2643049+08:00 | #43676 - CLB: 12hrs - CLB DUAL SHIPLOADER SHUT | 6.0 | TRUE |  | 2027-04-13T22:00:00+00:00 | 2027-04-14T10:00:00+00:00 | 2027-04-14T06:00:00+08:00 | 2027-04-14T18:00:00+08:00 |  |  |  |  | 12.00 | Standard IMS Dual Shiploader Shut | Work requiring dual SLD shut is 26WKly No Major shut works in 2027 - duration reduced to 12hrs | SCBO2715 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43690, "shutVersionId": 332051, "title": "#43690 - CLB: 120hrs - SL12 IAM", "startDatetimeUTC": "2027-04-12T10:00:00+00:00", "endDatetimeUTC": "2027-04-17T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43982 | 2021-11-16T00:33:06+00:00 | 2021-11-16T08:33:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-21T04:42:18.7634321+00:00 | 2026-08-21T12:42:18.7634321+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331496 | TRUE | TRUE | 2026-08-21T04:42:18.7634321+00:00 | 2026-08-21T12:42:18.7634321+08:00 | #43982 - CLB: 12hrs - SL11 CAPD TESTING | 6.0 | TRUE |  | 2027-07-02T22:00:00+00:00 | 2027-07-03T10:00:00+00:00 | 2027-07-03T06:00:00+08:00 | 2027-07-03T18:00:00+08:00 |  |  |  |  | 12.00 | SL11 CAPD Testing - 12hrs CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. | aligning with the other CAPD shuts | SCBO2724 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43820 | 2021-11-11T02:48:37+00:00 | 2021-11-11T10:48:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-21T05:05:49.5787953+00:00 | 2026-08-21T13:05:49.5787953+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331498 | TRUE | TRUE | 2026-08-21T05:05:49.5787953+00:00 | 2026-08-21T13:05:49.5787953+08:00 | #43820 - CLB: 4hrs - YDSUB03 SHUT (SL12/SH6/CV660/RC13/ST14) | 7.0 | TRUE |  | 2027-07-13T02:00:00+00:00 | 2027-07-13T06:00:00+00:00 | 2027-07-13T10:00:00+08:00 | 2027-07-13T14:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 3 Shut - 12hrs Additional Info: Yard SUB 3 Electrical Shut - 26 Weekly Cycle | reducing to 4hrs, no 208WK inspection for this sub in this shut Aligning to SL12 shut | SCBO2628 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "5b5cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD03", "name": "Substation: CLB Stockyard 03", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "2ad9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV660", "name": "Conveyor: CLB 660", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43679 | 2021-11-01T23:59:12+00:00 | 2021-11-02T07:59:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-21T07:39:28.6675032+00:00 | 2026-08-21T15:39:28.6675032+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331509 | TRUE | TRUE | 2026-08-21T07:39:28.6675032+00:00 | 2026-08-21T15:39:28.6675032+08:00 | #43679 - CLB: 12hrs - CLB DUAL SHIP LOADER SHUT | 6.0 | TRUE |  | 2027-10-12T22:00:00+00:00 | 2027-10-13T10:00:00+00:00 | 2027-10-13T06:00:00+08:00 | 2027-10-13T18:00:00+08:00 |  |  |  |  | 12.00 | Standard IMS Dual Shiploader Shut | Work requiring dual SLD shut is 26WKly No Major shut works in 2027 - duration reduced to 12hrs | SCBO2741 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43692, "shutVersionId": 335897, "title": "#43692 - CLB: 120hrs - SL12 IAM", "startDatetimeUTC": "2027-10-11T10:00:00+00:00", "endDatetimeUTC": "2027-10-16T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43576 | 2021-11-01T22:59:57+00:00 | 2021-11-02T06:59:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-21T07:51:40.1538577+00:00 | 2026-08-21T15:51:40.1538577+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331510 | TRUE | TRUE | 2026-08-21T07:51:40.1538577+00:00 | 2026-08-21T15:51:40.1538577+08:00 | #43576 - CLA: 72hrs - CLA DUAL SHIP LOADER SHUT | 7.0 | TRUE |  | 2027-11-06T16:00:00+00:00 | 2027-11-09T16:00:00+00:00 | 2027-11-07T00:00:00+08:00 | 2027-11-10T00:00:00+08:00 |  |  |  |  | 72.00 | Standard IMS CLA - Dual Shiploader Shut Substation maintenance | deleted #43573 - 72hr dual shiploader shut, extending this shut from 48hr to 72hr to allow consolidation of all major RSUB05 and Surge bin dust collector maint | SCAO2742 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43928 | 2021-11-15T09:27:23+00:00 | 2021-11-15T17:27:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-21T08:24:27.2336442+00:00 | 2026-08-21T16:24:27.2336442+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331511 | TRUE | TRUE | 2026-08-21T08:24:27.2336442+00:00 | 2026-08-21T16:24:27.2336442+08:00 | #43928 - CLB: 4hrs - ILSUB04 SHUT (CV500/CV502) | 4.0 | TRUE |  | 2027-11-23T02:00:00+00:00 | 2027-11-23T06:00:00+00:00 | 2027-11-23T10:00:00+08:00 | 2027-11-23T14:00:00+08:00 |  |  |  |  | 4.00 | Inload SUB 4 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycle | Reducing to 4hrs, no 208WK inspection for this sub for this period Aligning with the plant shut | SBCL2744 | [{"equipmentGUID": "d860fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL04", "name": "Substation: CLB Inloading 04", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "0cd9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV502", "name": "Conveyor: CLB 502 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43633 | 2021-11-01T23:42:46+00:00 | 2021-11-02T07:42:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:02:27.6397864+00:00 | 2026-08-28T06:02:27.6397864+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332031 | TRUE | TRUE | 2026-08-27T22:02:27.6397864+00:00 | 2026-08-28T06:02:27.6397864+08:00 | #43633 - CLB: 84hrs - ST13 IAM | 5.1 | FALSE |  | 2027-12-26T22:00:00+00:00 | 2027-12-30T10:00:00+00:00 | 2027-12-27T06:00:00+08:00 | 2027-12-30T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2750 | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43519 | 2021-11-01T22:56:21+00:00 | 2021-11-02T06:56:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:14:01.9230792+00:00 | 2026-08-28T06:14:01.9230792+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332032 | TRUE | TRUE | 2026-08-27T22:14:01.9230792+00:00 | 2026-08-28T06:14:01.9230792+08:00 | #43519 - CLA: 108hrs - STK3 IAM | 5.1 | FALSE |  | 2027-12-19T22:00:00+00:00 | 2027-12-24T10:00:00+00:00 | 2027-12-20T06:00:00+08:00 | 2027-12-24T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2751 | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45743, "shutVersionId": 335896, "title": "#45743 - CLA: 48hrs - C214 IAM", "startDatetimeUTC": "2027-12-20T22:00:00+00:00", "endDatetimeUTC": "2027-12-22T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43680 | 2021-11-01T23:59:13+00:00 | 2021-11-02T07:59:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:14:46.3828614+00:00 | 2026-08-28T06:14:46.3828614+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332033 | TRUE | TRUE | 2026-08-27T22:14:46.3828614+00:00 | 2026-08-28T06:14:46.3828614+08:00 | #43680 - CLB: 120hrs - SL11 IAM | 7.1 | TRUE |  | 2027-12-13T10:00:00+00:00 | 2027-12-18T10:00:00+00:00 | 2027-12-13T18:00:00+08:00 | 2027-12-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2750 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43645 | 2021-11-01T23:47:36+00:00 | 2021-11-02T07:47:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:15:52.7955898+00:00 | 2026-08-28T06:15:52.7955898+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332034 | TRUE | TRUE | 2026-08-27T22:15:52.7955898+00:00 | 2026-08-28T06:15:52.7955898+08:00 | #43645 - CLB: 120hrs - RC11 IAM | 5.1 | FALSE |  | 2027-12-12T22:00:00+00:00 | 2027-12-17T22:00:00+00:00 | 2027-12-13T06:00:00+08:00 | 2027-12-18T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IMS Shut |  | SCBY2750 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43621 | 2021-11-01T23:35:55+00:00 | 2021-11-02T07:35:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:17:19.3481616+00:00 | 2026-08-28T06:17:19.3481616+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332035 | TRUE | TRUE | 2026-08-27T22:17:19.3481616+00:00 | 2026-08-28T06:17:19.3481616+08:00 | #43621 - CLB: 106hrs - CD5 IAM | 6.1 | TRUE |  | 2027-12-06T10:00:00+00:00 | 2027-12-10T20:00:00+00:00 | 2027-12-06T18:00:00+08:00 | 2027-12-11T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2749 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43695 | 2021-11-02T00:01:22+00:00 | 2021-11-02T08:01:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:53:03.908165+00:00 | 2026-08-28T07:53:03.908165+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332048 | TRUE | TRUE | 2026-08-27T23:53:03.908165+00:00 | 2026-08-28T07:53:03.908165+08:00 | #43695 - CLB: 120hrs - SH6 IAM | 6.1 | FALSE |  | 2027-04-12T10:00:00+00:00 | 2027-04-17T10:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2715 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43613 | 2021-11-01T23:30:14+00:00 | 2021-11-02T07:30:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:53:17.4508423+00:00 | 2026-08-28T07:53:17.4508423+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332049 | TRUE | TRUE | 2026-08-27T23:53:17.4508423+00:00 | 2026-08-28T07:53:17.4508423+08:00 | #43613 - CLB: 120hrs - BERTH8 IAM | 6.1 | FALSE |  | 2027-04-12T10:00:00+00:00 | 2027-04-17T10:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2715 | [{"equipmentGUID": "", "code": "CLBBTH08", "name": "Berth: CLB 08", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43612 | 2021-11-01T23:30:12+00:00 | 2021-11-02T07:30:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:53:30.6077852+00:00 | 2026-08-28T07:53:30.6077852+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332050 | TRUE | TRUE | 2026-08-27T23:53:30.6077852+00:00 | 2026-08-28T07:53:30.6077852+08:00 | #43612 - CLB: 120hrs - BERTH7 IAM | 6.1 | FALSE |  | 2027-04-12T10:00:00+00:00 | 2027-04-17T10:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2715 | [{"equipmentGUID": "", "code": "CLBBTH07", "name": "Berth: CLB 07", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43690 | 2021-11-02T00:01:14+00:00 | 2021-11-02T08:01:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:54:08.8000183+00:00 | 2026-08-28T07:54:08.8000183+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332051 | TRUE | TRUE | 2026-08-27T23:54:08.8000183+00:00 | 2026-08-28T07:54:08.8000183+08:00 | #43690 - CLB: 120hrs - SL12 IAM | 9.1 | TRUE |  | 2027-04-12T10:00:00+00:00 | 2027-04-17T10:00:00+00:00 | 2027-04-12T18:00:00+08:00 | 2027-04-17T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Shut |  | SCBO2715 | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "852c75dd-fa14-4228-9344-139df547acf0", "emailAddress": "Taron.Brown@riotinto.com", "displayName": "Brown, Taron (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43676, "shutVersionId": 331448, "title": "#43676 - CLB: 12hrs - CLB DUAL SHIPLOADER SHUT", "startDatetimeUTC": "2027-04-13T22:00:00+00:00", "endDatetimeUTC": "2027-04-14T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43496 | 2021-11-01T22:54:37+00:00 | 2021-11-02T06:54:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:54:43.4459776+00:00 | 2026-08-28T07:54:43.4459776+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332052 | TRUE | TRUE | 2026-08-27T23:54:43.4459776+00:00 | 2026-08-28T07:54:43.4459776+08:00 | #43496 - CLA: 138hrs - RCL1 IAM | 5.1 | FALSE |  | 2027-04-19T04:00:00+00:00 | 2027-04-24T22:00:00+00:00 | 2027-04-19T12:00:00+08:00 | 2027-04-25T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2716 | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43500 | 2021-11-01T22:54:41+00:00 | 2021-11-02T06:54:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:55:09.6171577+00:00 | 2026-08-28T07:55:09.6171577+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332053 | TRUE | TRUE | 2026-08-27T23:55:09.6171577+00:00 | 2026-08-28T07:55:09.6171577+08:00 | #43500 - CLA: 108hrs - STK4 IAM | 5.1 | FALSE |  | 2027-04-18T22:00:00+00:00 | 2027-04-23T10:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-23T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2716 | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43587 | 2021-11-01T23:04:28+00:00 | 2021-11-02T07:04:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:56:10.2933282+00:00 | 2026-08-28T07:56:10.2933282+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332054 | TRUE | TRUE | 2026-08-27T23:56:10.2933282+00:00 | 2026-08-28T07:56:10.2933282+08:00 | #43587 - CLA: 150hrs - RCL4 IAM | 7.1 | FALSE |  | 2027-05-07T16:00:00+00:00 | 2027-05-13T22:00:00+00:00 | 2027-05-08T00:00:00+08:00 | 2027-05-14T06:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAO2718 | [{"equipmentGUID": "9627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC04", "name": "Reclaimer: CLA 04", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43489 | 2021-11-01T22:52:52+00:00 | 2021-11-02T06:52:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:56:44.4057549+00:00 | 2026-08-28T07:56:44.4057549+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332055 | TRUE | TRUE | 2026-08-27T23:56:44.4057549+00:00 | 2026-08-28T07:56:44.4057549+08:00 | #43489 - CLA: 120hrs - CD2 IAM | 6.1 | TRUE |  | 2027-05-01T10:00:00+00:00 | 2027-05-06T10:00:00+00:00 | 2027-05-01T18:00:00+08:00 | 2027-05-06T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2717 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "b254fcf2-3e27-4fb9-bee2-2a087657fcda", "emailAddress": "Shane.Christie@riotinto.com", "displayName": "Shane Christie"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43583 | 2021-11-01T23:04:23+00:00 | 2021-11-02T07:04:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:57:09.6397997+00:00 | 2026-08-28T07:57:09.6397997+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332056 | TRUE | TRUE | 2026-08-27T23:57:09.6397997+00:00 | 2026-08-28T07:57:09.6397997+08:00 | #43583 - CLA: 114hrs - SLD3 IAM | 6.1 | TRUE |  | 2027-05-08T10:00:00+00:00 | 2027-05-13T04:00:00+00:00 | 2027-05-08T18:00:00+08:00 | 2027-05-13T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2718 | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83648, "shutVersionId": 335993, "title": "#83648 - CLA: 72hrs - C205/C206 CHUTE REPAIRS", "startDatetimeUTC": "2027-05-08T16:00:00+00:00", "endDatetimeUTC": "2027-05-11T16:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43505 | 2021-11-01T22:55:38+00:00 | 2021-11-02T06:55:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:57:47.3495706+00:00 | 2026-08-28T07:57:47.3495706+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332057 | TRUE | TRUE | 2026-08-27T23:57:47.3495706+00:00 | 2026-08-28T07:57:47.3495706+08:00 | #43505 - CLA: 150hrs - RCL2 IAM | 7.1 | FALSE |  | 2027-05-01T04:00:00+00:00 | 2027-05-07T10:00:00+00:00 | 2027-05-01T12:00:00+08:00 | 2027-05-07T18:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Shut NOTE: Slew Bearing C/O moved to 2031 as a standalone shutdown |  | SCAY2717 | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43481 | 2021-11-01T22:50:48+00:00 | 2021-11-02T06:50:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:58:44.4240863+00:00 | 2026-08-28T07:58:44.4240863+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332059 | TRUE | TRUE | 2026-08-27T23:58:44.4240863+00:00 | 2026-08-28T07:58:44.4240863+08:00 | #43481 - CLA: 114hrs - BERTH3 IAM | 5.1 | FALSE |  | 2027-05-08T10:00:00+00:00 | 2027-05-13T04:00:00+00:00 | 2027-05-08T18:00:00+08:00 | 2027-05-13T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2718 | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43482 | 2021-11-01T22:50:50+00:00 | 2021-11-02T06:50:50+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:58:59.7013375+00:00 | 2026-08-28T07:58:59.7013375+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332060 | TRUE | TRUE | 2026-08-27T23:58:59.7013375+00:00 | 2026-08-28T07:58:59.7013375+08:00 | #43482 - CLA: 114hrs - BERTH4 IAM | 5.1 | FALSE |  | 2027-05-08T10:00:00+00:00 | 2027-05-13T04:00:00+00:00 | 2027-05-08T18:00:00+08:00 | 2027-05-13T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2718 | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43707 | 2021-11-02T00:33:57+00:00 | 2021-11-02T08:33:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:00:12.3417132+00:00 | 2026-08-28T08:00:12.3417132+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332062 | TRUE | TRUE | 2026-08-28T00:00:12.3417132+00:00 | 2026-08-28T08:00:12.3417132+08:00 | #43707 - CLA: 84hrs - RUBBLE IAM | 5.1 | FALSE |  | 2027-05-20T04:00:00+00:00 | 2027-05-23T16:00:00+00:00 | 2027-05-20T12:00:00+08:00 | 2027-05-24T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCAL2720 | [{"equipmentGUID": "175e242f-6f9d-ee11-a847-000d3acacefd", "code": "CLAPLTRUBBLE03", "name": "Plant: CLA Rubble 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43564 | 2021-11-01T22:59:12+00:00 | 2021-11-02T06:59:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:00:36.6732357+00:00 | 2026-08-28T08:00:36.6732357+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332063 | TRUE | TRUE | 2026-08-28T00:00:36.6732357+00:00 | 2026-08-28T08:00:36.6732357+08:00 | #43564 - CLA: 84hrs - SEC3 IAM | 8.1 | FALSE |  | 2027-05-20T04:00:00+00:00 | 2027-05-23T16:00:00+00:00 | 2027-05-20T12:00:00+08:00 | 2027-05-24T00:00:00+08:00 |  |  |  |  | 84.00 | SEC3 - 84hr Shut |  | SCAL2720 | [{"equipmentGUID": "9717ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT03", "name": "Crusher - Secondary: CLA Circuit 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43474 | 2021-11-01T22:49:40+00:00 | 2021-11-02T06:49:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:05:09.7426461+00:00 | 2026-08-28T08:05:09.7426461+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332070 | TRUE | TRUE | 2026-08-28T00:05:09.7426461+00:00 | 2026-08-28T08:05:09.7426461+08:00 | #43474 - CLA: 114hrs - BERTH2 IAM | 5.1 | FALSE |  | 2027-05-31T10:00:00+00:00 | 2027-06-05T04:00:00+00:00 | 2027-05-31T18:00:00+08:00 | 2027-06-05T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2722 | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43473 | 2021-11-01T22:49:38+00:00 | 2021-11-02T06:49:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:05:27.8893973+00:00 | 2026-08-28T08:05:27.8893973+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332071 | TRUE | TRUE | 2026-08-28T00:05:27.8893973+00:00 | 2026-08-28T08:05:27.8893973+08:00 | #43473 - CLA: 114hrs - BERTH1 IAM | 5.1 | FALSE |  | 2027-05-31T10:00:00+00:00 | 2027-06-05T04:00:00+00:00 | 2027-05-31T18:00:00+08:00 | 2027-06-05T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2722 | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43574 | 2021-11-01T22:59:53+00:00 | 2021-11-02T06:59:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:05:42.748998+00:00 | 2026-08-28T08:05:42.748998+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332072 | TRUE | TRUE | 2026-08-28T00:05:42.748998+00:00 | 2026-08-28T08:05:42.748998+08:00 | #43574 - CLA: 114hrs - SLD2 IAM | 8.1 | TRUE |  | 2027-05-31T10:00:00+00:00 | 2027-06-05T04:00:00+00:00 | 2027-05-31T18:00:00+08:00 | 2027-06-05T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2722 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43579 | 2021-11-01T23:00:02+00:00 | 2021-11-02T07:00:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:06:36.7750057+00:00 | 2026-08-28T08:06:36.7750057+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332074 | TRUE | TRUE | 2026-08-28T00:06:36.7750057+00:00 | 2026-08-28T08:06:36.7750057+08:00 | #43579 - CLA: 126hrs - LRP2 IAM | 5.1 | FALSE |  | 2027-05-31T10:00:00+00:00 | 2027-06-05T16:00:00+00:00 | 2027-05-31T18:00:00+08:00 | 2027-06-06T00:00:00+08:00 |  |  |  |  | 126.00 | Standard IMS Shut |  | SCAO2722 | [{"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43677 | 2021-11-01T23:59:09+00:00 | 2021-11-02T07:59:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:08:44.7014514+00:00 | 2026-08-28T08:08:44.7014514+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332076 | TRUE | TRUE | 2026-08-28T00:08:44.7014514+00:00 | 2026-08-28T08:08:44.7014514+08:00 | #43677 - CLB: 120hrs - SL11 IAM | 9.1 | TRUE |  | 2027-06-14T10:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-14T18:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Shut |  | SCBO2724 | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43604 | 2021-11-01T23:22:16+00:00 | 2021-11-02T07:22:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:09:01.9968122+00:00 | 2026-08-28T08:09:01.9968122+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332077 | TRUE | TRUE | 2026-08-28T00:09:01.9968122+00:00 | 2026-08-28T08:09:01.9968122+08:00 | #43604 - CLB: 120hrs - BERTH5 IAM | 7.1 | FALSE |  | 2027-06-14T10:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-14T18:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2724 | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43605 | 2021-11-01T23:22:18+00:00 | 2021-11-02T07:22:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:09:18.3711521+00:00 | 2026-08-28T08:09:18.3711521+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332078 | TRUE | TRUE | 2026-08-28T00:09:18.3711521+00:00 | 2026-08-28T08:09:18.3711521+08:00 | #43605 - CLB: 120hrs - BERTH6 IAM | 7.1 | FALSE |  | 2027-06-14T10:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-14T18:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2724 | [{"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43646 | 2021-11-01T23:47:36+00:00 | 2021-11-02T07:47:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:53:55.5199017+00:00 | 2026-08-13T07:53:55.5199017+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331190 | TRUE | TRUE | 2026-08-12T23:53:55.5199017+00:00 | 2026-08-13T07:53:55.5199017+08:00 | #43646 - CLB: 9hrs - RC11 PIT STOP | 4.1 | FALSE |  | 2027-02-24T00:00:00+00:00 | 2027-02-24T09:00:00+00:00 | 2027-02-24T08:00:00+08:00 | 2027-02-24T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2707 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43651 | 2021-11-01T23:49:58+00:00 | 2021-11-02T07:49:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:54:42.9239652+00:00 | 2026-08-13T07:54:42.9239652+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331192 | TRUE | TRUE | 2026-08-12T23:54:42.9239652+00:00 | 2026-08-13T07:54:42.9239652+08:00 | #43651 - CLB: 9hrs - RC12 PIT STOP | 4.1 | FALSE |  | 2027-04-01T00:00:00+00:00 | 2027-04-01T09:00:00+00:00 | 2027-04-01T08:00:00+08:00 | 2027-04-01T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2712 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43828 | 2021-11-11T05:22:36+00:00 | 2021-11-11T13:22:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:56:12.5141173+00:00 | 2026-08-13T07:56:12.5141173+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331195 | TRUE | TRUE | 2026-08-12T23:56:12.5141173+00:00 | 2026-08-13T07:56:12.5141173+08:00 | #43828 - CLB: 12hrs - CD5 FS SYSTEM TESTING | 4.1 | TRUE |  | 2027-02-19T22:00:00+00:00 | 2027-02-20T10:00:00+00:00 | 2027-02-20T06:00:00+08:00 | 2027-02-20T18:00:00+08:00 |  |  |  |  | 12.00 | CD5 Functional Safety System Test - 12hrs The functional safety system test is completed on a 52 weekly cycle. |  | SCBI2706 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44032 | 2021-11-16T02:08:13+00:00 | 2021-11-16T10:08:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:58:45.8930221+00:00 | 2026-08-13T07:58:45.8930221+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331198 | TRUE | TRUE | 2026-08-12T23:58:45.8930221+00:00 | 2026-08-13T07:58:45.8930221+08:00 | #44032 - CLB: 12hrs - CV664 REMSAFE | 3.2 | FALSE |  | 2027-03-20T22:00:00+00:00 | 2027-03-21T10:00:00+00:00 | 2027-03-21T06:00:00+08:00 | 2027-03-21T18:00:00+08:00 |  |  |  |  | 12.00 | CV664 Outload Remsafe Testing - 12hrs |  | SCBO2711 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "54df00c0-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV664", "name": "Conveyor: CLB 664", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43911 | 2021-11-15T07:41:43+00:00 | 2021-11-15T15:41:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-13T00:01:37.5751197+00:00 | 2026-08-13T08:01:37.5751197+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331200 | TRUE | TRUE | 2026-08-13T00:01:37.5751197+00:00 | 2026-08-13T08:01:37.5751197+08:00 | #43911 - CLB: 12hrs - RETURN FINES FS SYSTEM TESTING | 4.1 | FALSE |  | 2027-04-07T22:00:00+00:00 | 2027-04-08T10:00:00+00:00 | 2027-04-08T06:00:00+08:00 | 2027-04-08T18:00:00+08:00 |  |  |  |  | 12.00 | CLB: 12hrs - CONVEYOR: CLB 851 FINES RETURN FS, SH05 & SH06 Fines Loading Only Return Fines Functional Safety System Test Fines only for SH5 & SH6 during this time Additional Info: Fines only for SH5 & SH6 during this time Electrical system Testing is Completed on a 52 Week Cycle |  | SCBO2713 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43517 | 2021-11-01T22:56:17+00:00 | 2021-11-02T06:56:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:29:22.3268217+00:00 | 2026-10-15T10:29:22.3268217+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336025 | TRUE | TRUE | 2026-10-15T02:29:22.3268217+00:00 | 2026-10-15T10:29:22.3268217+08:00 | #43517 - CLA: 108hrs - STK3 IAM | 5.1 | FALSE |  | 2027-06-20T22:00:00+00:00 | 2027-06-25T10:00:00+00:00 | 2027-06-21T06:00:00+08:00 | 2027-06-25T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  | SCAY2725 | [{"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43513, "shutVersionId": 336026, "title": "#43513 - CLA: 138hrs - RCL3 IAM", "startDatetimeUTC": "2027-06-21T04:00:00+00:00", "endDatetimeUTC": "2027-06-26T22:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 45741, "shutVersionId": 336027, "title": "#45741 - CLA: 48hrs - C214 IAM", "startDatetimeUTC": "2027-06-21T22:00:00+00:00", "endDatetimeUTC": "2027-06-23T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43513 | 2021-11-01T22:56:13+00:00 | 2021-11-02T06:56:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:30:05.2695008+00:00 | 2026-10-15T10:30:05.2695008+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336026 | TRUE | TRUE | 2026-10-15T02:30:05.2695008+00:00 | 2026-10-15T10:30:05.2695008+08:00 | #43513 - CLA: 138hrs - RCL3 IAM | 5.1 | FALSE |  | 2027-06-21T04:00:00+00:00 | 2027-06-26T22:00:00+00:00 | 2027-06-21T12:00:00+08:00 | 2027-06-27T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2725 | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43517, "shutVersionId": 336025, "title": "#43517 - CLA: 108hrs - STK3 IAM", "startDatetimeUTC": "2027-06-20T22:00:00+00:00", "endDatetimeUTC": "2027-06-25T10:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 45741, "shutVersionId": 336027, "title": "#45741 - CLA: 48hrs - C214 IAM", "startDatetimeUTC": "2027-06-21T22:00:00+00:00", "endDatetimeUTC": "2027-06-23T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43933 | 2021-11-15T22:56:45+00:00 | 2021-11-16T06:56:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-13T00:09:23.5211639+00:00 | 2026-08-13T08:09:23.5211639+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331210 | TRUE | TRUE | 2026-08-13T00:09:23.5211639+00:00 | 2026-08-13T08:09:23.5211639+08:00 | #43933 - CLB: 12hrs - CD6 FS SYSTEM TESTING | 4.1 | TRUE |  | 2027-05-15T22:00:00+00:00 | 2027-05-16T10:00:00+00:00 | 2027-05-16T06:00:00+08:00 | 2027-05-16T18:00:00+08:00 |  |  |  |  | 12.00 | CD6 Functional Safety System Test - 12hrs The functional safety system test is completed on a 52 weekly cycle. |  | SCBI2719 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43642 | 2021-11-01T23:47:32+00:00 | 2021-11-02T07:47:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T05:34:34.5541544+00:00 | 2026-08-12T13:34:34.5541544+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331136 | TRUE | TRUE | 2026-08-12T05:34:34.5541544+00:00 | 2026-08-12T13:34:34.5541544+08:00 | #43642 - CLB: 9hrs - RC11 PIT STOP | 3.1 | FALSE |  | 2027-08-25T00:00:00+00:00 | 2027-08-25T09:00:00+00:00 | 2027-08-25T08:00:00+08:00 | 2027-08-25T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2733 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43668 | 2021-11-01T23:54:37+00:00 | 2021-11-02T07:54:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T06:09:29.4210512+00:00 | 2026-08-12T14:09:29.4210512+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331153 | TRUE | TRUE | 2026-08-12T06:09:29.4210512+00:00 | 2026-08-12T14:09:29.4210512+08:00 | #43668 - CLB: 9hrs - RC13 PIT STOP | 3.1 | FALSE |  | 2027-10-13T00:00:00+00:00 | 2027-10-13T09:00:00+00:00 | 2027-10-13T08:00:00+08:00 | 2027-10-13T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2740 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44043 | 2021-11-16T02:57:01+00:00 | 2021-11-16T10:57:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T06:10:02.555756+00:00 | 2026-08-12T14:10:02.555756+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331154 | TRUE | TRUE | 2026-08-12T06:10:02.555756+00:00 | 2026-08-12T14:10:02.555756+08:00 | #44043 - CLB: 12hrs - ST12 FS SYSTEM TESTING | 4.1 | FALSE |  | 2027-10-07T22:00:00+00:00 | 2027-10-08T10:00:00+00:00 | 2027-10-08T06:00:00+08:00 | 2027-10-08T18:00:00+08:00 |  |  |  |  | 12.00 | ST12 - Stacker Functional Safety System Tests |  |  | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44070 | 2021-11-16T04:03:29+00:00 | 2021-11-16T12:03:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T06:10:44.8233582+00:00 | 2026-08-12T14:10:44.8233582+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331155 | TRUE | TRUE | 2026-08-12T06:10:44.8233582+00:00 | 2026-08-12T14:10:44.8233582+08:00 | #44070 - CLB: 12hrs - CV470 REMSAFE | 3.1 | TRUE |  | 2027-10-16T22:00:00+00:00 | 2027-10-17T10:00:00+00:00 | 2027-10-17T06:00:00+08:00 | 2027-10-17T18:00:00+08:00 |  |  |  |  | 12.00 | CV470 Inload Remsafe Testing - 12hrs |  | SCBI2738 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "67d400c0-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV470", "name": "Conveyor: CLB 470 Car Dumper 7C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43657 | 2021-11-01T23:50:06+00:00 | 2021-11-02T07:50:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:33:16.6611883+00:00 | 2026-08-13T07:33:16.6611883+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331176 | TRUE | TRUE | 2026-08-12T23:33:16.6611883+00:00 | 2026-08-13T07:33:16.6611883+08:00 | #43657 - CLB: 9hrs - RC12 PIT STOP | 3.1 | FALSE |  | 2027-12-29T00:00:00+00:00 | 2027-12-29T09:00:00+00:00 | 2027-12-29T08:00:00+08:00 | 2027-12-29T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2751 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43666 | 2021-11-01T23:54:36+00:00 | 2021-11-02T07:54:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:52:33.0095973+00:00 | 2026-08-13T07:52:33.0095973+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331186 | TRUE | TRUE | 2026-08-12T23:52:33.0095973+00:00 | 2026-08-13T07:52:33.0095973+08:00 | #43666 - CLB: 9hrs - RC13 PIT STOP | 3.1 | FALSE |  | 2027-07-14T00:00:00+00:00 | 2027-07-14T09:00:00+00:00 | 2027-07-14T08:00:00+08:00 | 2027-07-14T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2727 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43655 | 2021-11-01T23:50:02+00:00 | 2021-11-02T07:50:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:52:51.8352117+00:00 | 2026-08-13T07:52:51.8352117+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331187 | TRUE | TRUE | 2026-08-12T23:52:51.8352117+00:00 | 2026-08-13T07:52:51.8352117+08:00 | #43655 - CLB: 9hrs - RC12 PIT STOP | 4.1 | FALSE |  | 2027-09-30T00:00:00+00:00 | 2027-09-30T09:00:00+00:00 | 2027-09-30T08:00:00+08:00 | 2027-09-30T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2738 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43644 | 2021-11-01T23:47:33+00:00 | 2021-11-02T07:47:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-12T23:53:18.3719333+00:00 | 2026-08-13T07:53:18.3719333+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331188 | TRUE | TRUE | 2026-08-12T23:53:18.3719333+00:00 | 2026-08-13T07:53:18.3719333+08:00 | #43644 - CLB: 9hrs - RC11 PIT STOP | 3.1 | FALSE |  | 2027-11-24T00:00:00+00:00 | 2027-11-24T09:00:00+00:00 | 2027-11-24T08:00:00+08:00 | 2027-11-24T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2746 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43535 | 2021-11-01T22:57:46+00:00 | 2021-11-02T06:57:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:31:32.4319065+00:00 | 2026-10-15T10:31:32.4319065+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336028 | TRUE | TRUE | 2026-10-15T02:31:32.4319065+00:00 | 2026-10-15T10:31:32.4319065+08:00 | #43535 - CLA: 84hrs - SEC1 IAM | 6.1 | FALSE |  | 2027-06-27T22:00:00+00:00 | 2027-07-01T10:00:00+00:00 | 2027-06-28T06:00:00+08:00 | 2027-07-01T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCAL2726 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43949 | 2021-11-15T23:28:43+00:00 | 2021-11-16T07:28:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:27:12.2885355+00:00 | 2026-10-15T10:27:12.2885355+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336021 | TRUE | TRUE | 2026-10-15T02:27:12.2885355+00:00 | 2026-10-15T10:27:12.2885355+08:00 | #43949 - CLB: 12hrs - ST11 CAPD TESTING | 4.1 | FALSE |  | 2027-06-11T22:00:00+00:00 | 2027-06-12T10:00:00+00:00 | 2027-06-12T06:00:00+08:00 | 2027-06-12T18:00:00+08:00 |  |  |  |  | 12.00 | ST11 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43958 | 2021-11-15T23:49:44+00:00 | 2021-11-16T07:49:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:27:24.7905105+00:00 | 2026-10-15T10:27:24.7905105+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336022 | TRUE | TRUE | 2026-10-15T02:27:24.7905105+00:00 | 2026-10-15T10:27:24.7905105+08:00 | #43958 - CLB: 12hrs - ST12 CAPD TESTING | 4.1 | FALSE |  | 2027-06-12T22:00:00+00:00 | 2027-06-13T10:00:00+00:00 | 2027-06-13T06:00:00+08:00 | 2027-06-13T18:00:00+08:00 |  |  |  |  | 12.00 | ST12 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43969 | 2021-11-16T00:03:26+00:00 | 2021-11-16T08:03:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:27:45.7996762+00:00 | 2026-10-15T10:27:45.7996762+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336023 | TRUE | TRUE | 2026-10-15T02:27:45.7996762+00:00 | 2026-10-15T10:27:45.7996762+08:00 | #43969 - CLB: 12hrs - ST13 CAPD TESTING | 4.1 | FALSE |  | 2027-06-13T22:00:00+00:00 | 2027-06-14T10:00:00+00:00 | 2027-06-14T06:00:00+08:00 | 2027-06-14T18:00:00+08:00 |  |  |  |  | 12.00 | ST13 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43994 | 2021-11-16T00:48:36+00:00 | 2021-11-16T08:48:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-10T21:19:18.3604037+00:00 | 2026-08-11T05:19:18.3604037+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331017 | TRUE | TRUE | 2026-08-10T21:19:18.3604037+00:00 | 2026-08-11T05:19:18.3604037+08:00 | #43994 - CLB: 12hrs - SH5 FS SYSTEM TESTING | 4.1 | FALSE |  | 2027-06-23T22:00:00+00:00 | 2027-06-24T10:00:00+00:00 | 2027-06-24T06:00:00+08:00 | 2027-06-24T18:00:00+08:00 |  |  |  |  | 12.00 | SH5 Conveyor Functional Safety System Tests - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBO2724 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43999 | 2021-11-16T00:53:56+00:00 | 2021-11-16T08:53:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-10T21:20:36.4565846+00:00 | 2026-08-11T05:20:36.4565846+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331018 | TRUE | TRUE | 2026-08-10T21:20:36.4565846+00:00 | 2026-08-11T05:20:36.4565846+08:00 | #43999 - CLB: 12hrs - SH6 FS SYSTEM TESTING | 4.1 | FALSE |  | 2027-06-24T22:00:00+00:00 | 2027-06-25T10:00:00+00:00 | 2027-06-25T06:00:00+08:00 | 2027-06-25T18:00:00+08:00 |  |  |  |  | 12.00 | SH6 Conveyor Functional Safety System Tests - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBO2724 | [{"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44042 | 2021-11-16T02:37:36+00:00 | 2021-11-16T10:37:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-10T21:21:36.6369945+00:00 | 2026-08-11T05:21:36.6369945+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331019 | TRUE | TRUE | 2026-08-10T21:21:36.6369945+00:00 | 2026-08-11T05:21:36.6369945+08:00 | #44042 - CLB: 12hrs - X-LINK FS SYSTEM TESTING | 3.2 | TRUE |  | 2027-06-30T22:00:00+00:00 | 2027-07-01T10:00:00+00:00 | 2027-07-01T06:00:00+08:00 | 2027-07-01T18:00:00+08:00 |  |  |  |  | 12.00 | Link Conveyors Electrical System Test The functional safety system test is completed on a 52 weekly cycle. |  | SCBL2725 | [{"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "dc18f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV501", "name": "Conveyor: CLB 501 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "0cd9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV502", "name": "Conveyor: CLB 502 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "d220f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV503", "name": "Conveyor: CLB 503 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "57e000c0-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV504", "name": "Conveyor: CLB 504 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "eed000c0-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV505", "name": "Conveyor: CLB 505 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43653 | 2021-11-01T23:50:01+00:00 | 2021-11-02T07:50:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-10T22:51:04.8175264+00:00 | 2026-08-11T06:51:04.8175264+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331038 | TRUE | TRUE | 2026-08-10T22:51:04.8175264+00:00 | 2026-08-11T06:51:04.8175264+08:00 | #43653 - CLB: 9hrs - RC12 PIT STOP | 3.1 | FALSE |  | 2027-06-30T00:00:00+00:00 | 2027-06-30T09:00:00+00:00 | 2027-06-30T08:00:00+08:00 | 2027-06-30T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  | SCBY2725 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44071 | 2021-11-16T04:12:25+00:00 | 2021-11-16T12:12:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T21:48:01.1649786+00:00 | 2026-08-12T05:48:01.1649786+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331076 | TRUE | TRUE | 2026-08-11T21:48:01.1649786+00:00 | 2026-08-12T05:48:01.1649786+08:00 | #44071 - CLB: 12hrs - ST13 FS SYSTEM TESTING | 4.1 | FALSE |  | 2027-09-09T22:00:00+00:00 | 2027-09-10T10:00:00+00:00 | 2027-09-10T06:00:00+08:00 | 2027-09-10T18:00:00+08:00 |  |  |  |  | 12.00 | ST13 - Stacker Functional Safety System Tests |  | SCBY2739 | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43518 | 2021-11-01T22:56:21+00:00 | 2021-11-02T06:56:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T22:17:44.2312519+00:00 | 2026-08-12T06:17:44.2312519+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331082 | TRUE | TRUE | 2026-08-11T22:17:44.2312519+00:00 | 2026-08-12T06:17:44.2312519+08:00 | #43518 - CLA: 108hrs - C202 BELT C/O | 5.1 | FALSE |  | 2027-09-20T04:00:00+00:00 | 2027-09-24T16:00:00+00:00 | 2027-09-20T12:00:00+08:00 | 2027-09-25T00:00:00+08:00 |  |  |  |  | 108.00 | Standard IMS Shut C202 Belt change out due |  | SCAY2736 | [{"equipmentGUID": "8f06f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV202", "name": "Conveyor: CLA 202", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8a43f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST03", "name": "Stacker: CLA 03", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
44055 | 2021-11-16T03:25:00+00:00 | 2021-11-16T11:25:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T22:19:27.4253011+00:00 | 2026-08-12T06:19:27.4253011+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331084 | TRUE | TRUE | 2026-08-11T22:19:27.4253011+00:00 | 2026-08-12T06:19:27.4253011+08:00 | #44055 - CLB: 12hrs - RC11 FS SYSTEM TESTING | 2.1 | FALSE |  | 2027-09-20T22:00:00+00:00 | 2027-09-21T10:00:00+00:00 | 2027-09-21T06:00:00+08:00 | 2027-09-21T18:00:00+08:00 |  |  |  |  | 12.00 | RC11 Functional Safety System Test - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBY2737 | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44065 | 2021-11-16T03:42:16+00:00 | 2021-11-16T11:42:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T22:20:07.4250723+00:00 | 2026-08-12T06:20:07.4250723+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331085 | TRUE | TRUE | 2026-08-11T22:20:07.4250723+00:00 | 2026-08-12T06:20:07.4250723+08:00 | #44065 - CLB: 12hrs - RC13 FS SYSTEM TESTING | 2.1 | FALSE |  | 2027-09-24T22:00:00+00:00 | 2027-09-25T10:00:00+00:00 | 2027-09-25T06:00:00+08:00 | 2027-09-25T18:00:00+08:00 |  |  |  |  | 12.00 | RC13 Functional Safety System Test - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBY2737 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43862 | 2021-11-15T03:58:51+00:00 | 2021-11-15T11:58:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T22:24:46.1677453+00:00 | 2026-08-12T06:24:46.1677453+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331087 | TRUE | TRUE | 2026-08-11T22:24:46.1677453+00:00 | 2026-08-12T06:24:46.1677453+08:00 | #43862 - CLB: 12hrs - ST14 FS SYSTEM TESTING | 3.1 | FALSE |  | 2027-09-28T22:00:00+00:00 | 2027-09-29T10:00:00+00:00 | 2027-09-29T06:00:00+08:00 | 2027-09-29T18:00:00+08:00 |  |  |  |  | 12.00 | ST14 Functional Safety System Test - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBY2706 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44060 | 2021-11-16T03:33:31+00:00 | 2021-11-16T11:33:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-11T22:26:34.4151406+00:00 | 2026-08-12T06:26:34.4151406+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331088 | TRUE | TRUE | 2026-08-11T22:26:34.4151406+00:00 | 2026-08-12T06:26:34.4151406+08:00 | #44060 - CLB: 12hrs - RC12 FS SYSTEM TESTING | 2.1 | FALSE |  | 2027-09-22T22:00:00+00:00 | 2027-09-23T10:00:00+00:00 | 2027-09-23T06:00:00+08:00 | 2027-09-23T18:00:00+08:00 |  |  |  |  | 12.00 | RC12 Functional Safety System Test - 12hrs Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  | SCBY2737 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43608 | 2021-11-01T23:22:23+00:00 | 2021-11-02T07:22:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:18:23.2289103+00:00 | 2026-08-28T06:18:23.2289103+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332036 | TRUE | TRUE | 2026-08-27T22:18:23.2289103+00:00 | 2026-08-28T06:18:23.2289103+08:00 | #43608 - CLB: 120hrs - BERTH5 IAM | 7.1 | FALSE |  | 2027-12-13T10:00:00+00:00 | 2027-12-18T10:00:00+00:00 | 2027-12-13T18:00:00+08:00 | 2027-12-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2750 | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43609 | 2021-11-01T23:22:24+00:00 | 2021-11-02T07:22:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:18:47.6185807+00:00 | 2026-08-28T06:18:47.6185807+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332037 | TRUE | TRUE | 2026-08-27T22:18:47.6185807+00:00 | 2026-08-28T06:18:47.6185807+08:00 | #43609 - CLB: 120hrs - BERTH6 IAM | 7.1 | FALSE |  | 2027-12-13T10:00:00+00:00 | 2027-12-18T10:00:00+00:00 | 2027-12-13T18:00:00+08:00 | 2027-12-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2750 | [{"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43581 | 2021-11-01T23:00:06+00:00 | 2021-11-02T07:00:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:20:31.0401813+00:00 | 2026-08-28T06:20:31.0401813+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332038 | TRUE | TRUE | 2026-08-27T22:20:31.0401813+00:00 | 2026-08-28T06:20:31.0401813+08:00 | #43581 - CLA: 126hrs - LRP2 IAM | 6.1 | FALSE |  | 2027-11-29T10:00:00+00:00 | 2027-12-04T16:00:00+00:00 | 2027-11-29T18:00:00+08:00 | 2027-12-05T00:00:00+08:00 |  |  |  |  | 126.00 | Standard IAM Shut |  | SCAO2748 | [{"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43477 | 2021-11-01T22:49:45+00:00 | 2021-11-02T06:49:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:21:07.5973579+00:00 | 2026-08-28T06:21:07.5973579+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332039 | TRUE | TRUE | 2026-08-27T22:21:07.5973579+00:00 | 2026-08-28T06:21:07.5973579+08:00 | #43477 - CLA: 114hrs - BERTH1 IAM | 6.1 | FALSE |  | 2027-11-29T10:00:00+00:00 | 2027-12-04T04:00:00+00:00 | 2027-11-29T18:00:00+08:00 | 2027-12-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2748 | [{"equipmentGUID": "", "code": "CLABTH01", "name": "Berth: CLA 01", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43478 | 2021-11-01T22:49:46+00:00 | 2021-11-02T06:49:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:21:28.0920155+00:00 | 2026-08-28T06:21:28.0920155+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332040 | TRUE | TRUE | 2026-08-27T22:21:28.0920155+00:00 | 2026-08-28T06:21:28.0920155+08:00 | #43478 - CLA: 114hrs - BERTH2 IAM | 6.1 | FALSE |  | 2027-11-29T10:00:00+00:00 | 2027-12-04T04:00:00+00:00 | 2027-11-29T18:00:00+08:00 | 2027-12-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2748 | [{"equipmentGUID": "", "code": "CLABTH02", "name": "Berth: CLA 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43577 | 2021-11-01T22:59:57+00:00 | 2021-11-02T06:59:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:21:53.0192999+00:00 | 2026-08-28T06:21:53.0192999+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332041 | TRUE | TRUE | 2026-08-27T22:21:53.0192999+00:00 | 2026-08-28T06:21:53.0192999+08:00 | #43577 - CLA: 114hrs - SLD2 IAM | 8.1 | TRUE |  | 2027-11-29T10:00:00+00:00 | 2027-12-04T04:00:00+00:00 | 2027-11-29T18:00:00+08:00 | 2027-12-04T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2748 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43515 | 2021-11-01T22:56:16+00:00 | 2021-11-02T06:56:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:22:32.9467623+00:00 | 2026-08-28T06:22:32.9467623+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332042 | TRUE | TRUE | 2026-08-27T22:22:32.9467623+00:00 | 2026-08-28T06:22:32.9467623+08:00 | #43515 - CLA: 138hrs - RCL3 IAM | 5.1 | FALSE |  | 2027-12-20T04:00:00+00:00 | 2027-12-25T22:00:00+00:00 | 2027-12-20T12:00:00+08:00 | 2027-12-26T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2751 | [{"equipmentGUID": "6d40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC03", "name": "Reclaimer: CLA 03", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45743, "shutVersionId": 335896, "title": "#45743 - CLA: 48hrs - C214 IAM", "startDatetimeUTC": "2027-12-20T22:00:00+00:00", "endDatetimeUTC": "2027-12-22T22:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43688 | 2021-11-01T23:59:27+00:00 | 2021-11-02T07:59:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:23:14.2938162+00:00 | 2026-08-28T06:23:14.2938162+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332043 | TRUE | TRUE | 2026-08-27T22:23:14.2938162+00:00 | 2026-08-28T06:23:14.2938162+08:00 | #43688 - CLB: 120hrs - SH5 IAM | 7.1 | FALSE |  | 2027-12-13T10:00:00+00:00 | 2027-12-18T10:00:00+00:00 | 2027-12-13T18:00:00+08:00 | 2027-12-18T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2750 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43625 | 2021-11-01T23:36:00+00:00 | 2021-11-02T07:36:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:24:04.5223517+00:00 | 2026-08-28T06:24:04.5223517+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332044 | TRUE | TRUE | 2026-08-27T22:24:04.5223517+00:00 | 2026-08-28T06:24:04.5223517+08:00 | #43625 - CLB: 84hrs - ST11 IAM | 6.1 | FALSE |  | 2027-12-05T22:00:00+00:00 | 2027-12-09T10:00:00+00:00 | 2027-12-06T06:00:00+08:00 | 2027-12-09T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2749 | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43637 | 2021-11-01T23:45:15+00:00 | 2021-11-02T07:45:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:24:55.1157343+00:00 | 2026-08-28T06:24:55.1157343+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332045 | TRUE | TRUE | 2026-08-27T22:24:55.1157343+00:00 | 2026-08-28T06:24:55.1157343+08:00 | #43637 - CLB: 106hrs - CD7 IAM | 6.1 | TRUE |  | 2027-11-22T10:00:00+00:00 | 2027-11-26T20:00:00+00:00 | 2027-11-22T18:00:00+08:00 | 2027-11-27T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2747 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43495 | 2021-11-01T22:54:01+00:00 | 2021-11-02T06:54:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T22:27:42.3328601+00:00 | 2026-08-28T06:27:42.3328601+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332046 | TRUE | TRUE | 2026-08-27T22:27:42.3328601+00:00 | 2026-08-28T06:27:42.3328601+08:00 | #43495 - CLA: 130hrs - PLANT IAM | 5.1 | TRUE |  | 2027-11-21T17:00:00+00:00 | 2027-11-27T03:00:00+00:00 | 2027-11-22T01:00:00+08:00 | 2027-11-27T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2747 | [{"equipmentGUID": "9a17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLAPLT", "name": "Plant: CLA", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "799e0d01-6f83-4824-bdbf-c66168353aed", "emailAddress": "Nicky.Murray@riotinto.com", "displayName": "Nicky Murray"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43652 | 2021-11-01T23:49:58+00:00 | 2021-11-02T07:49:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-27T23:52:44.4371994+00:00 | 2026-08-28T07:52:44.4371994+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332047 | TRUE | TRUE | 2026-08-27T23:52:44.4371994+00:00 | 2026-08-28T07:52:44.4371994+08:00 | #43652 - CLB: 120hrs - RC12 IAM | 5.2 | FALSE |  | 2027-04-11T22:00:00+00:00 | 2027-04-16T22:00:00+00:00 | 2027-04-12T06:00:00+08:00 | 2027-04-17T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2715 | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43979 | 2021-11-16T00:25:58+00:00 | 2021-11-16T08:25:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-31T07:58:16.0854502+00:00 | 2026-08-31T15:58:16.0854502+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332369 | TRUE | TRUE | 2026-08-31T07:58:16.0854502+00:00 | 2026-08-31T15:58:16.0854502+08:00 | #43979 - CLB: 12hrs - ST14 CAPD TESTING | 4.0 | FALSE |  | 2027-06-14T22:00:00+00:00 | 2027-06-15T10:00:00+00:00 | 2027-06-15T06:00:00+08:00 | 2027-06-15T18:00:00+08:00 |  |  |  |  | 12.00 | ST14 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. | Tweaking CAPD timing | SCBY2724 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43483 | 2021-11-01T22:50:51+00:00 | 2021-11-02T06:50:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:17:15.4830069+00:00 | 2026-08-28T08:17:15.4830069+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332090 | TRUE | TRUE | 2026-08-28T00:17:15.4830069+00:00 | 2026-08-28T08:17:15.4830069+08:00 | #43483 - CLA: 114hrs - BERTH3 IAM | 6.1 | FALSE |  | 2027-08-07T10:00:00+00:00 | 2027-08-12T04:00:00+00:00 | 2027-08-07T18:00:00+08:00 | 2027-08-12T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2731 | [{"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43484 | 2021-11-01T22:50:51+00:00 | 2021-11-02T06:50:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:17:37.0306611+00:00 | 2026-08-28T08:17:37.0306611+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332091 | TRUE | TRUE | 2026-08-28T00:17:37.0306611+00:00 | 2026-08-28T08:17:37.0306611+08:00 | #43484 - CLA: 114hrs - BERTH4 IAM | 6.1 | FALSE |  | 2027-08-07T10:00:00+00:00 | 2027-08-12T04:00:00+00:00 | 2027-08-07T18:00:00+08:00 | 2027-08-12T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IMS Shut |  | SCAO2731 | [{"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43584 | 2021-11-01T23:04:24+00:00 | 2021-11-02T07:04:24+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:17:55.8586675+00:00 | 2026-08-28T08:17:55.8586675+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332092 | TRUE | TRUE | 2026-08-28T00:17:55.8586675+00:00 | 2026-08-28T08:17:55.8586675+08:00 | #43584 - CLA: 114hrs - SLD3 IAM | 6.1 | TRUE |  | 2027-08-07T10:00:00+00:00 | 2027-08-12T04:00:00+00:00 | 2027-08-07T18:00:00+08:00 | 2027-08-12T12:00:00+08:00 |  |  |  |  | 114.00 | Standard IAM Maintenance |  | SCAO2731 | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 60495, "shutVersionId": 286475, "title": "#60495 - CLA: 264hrs - SL3C – WHARF SUB1 MAJOR WORKS (SUS CAP)", "startDatetimeUTC": "2027-08-01T04:00:00+00:00", "endDatetimeUTC": "2027-08-12T04:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43588 | 2021-11-01T23:04:32+00:00 | 2021-11-02T07:04:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:18:16.0333526+00:00 | 2026-08-28T08:18:16.0333526+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332093 | TRUE | TRUE | 2026-08-28T00:18:16.0333526+00:00 | 2026-08-28T08:18:16.0333526+08:00 | #43588 - CLA: 150hrs - RCL4 IAM | 5.1 | FALSE |  | 2027-08-06T16:00:00+00:00 | 2027-08-12T22:00:00+00:00 | 2027-08-07T00:00:00+08:00 | 2027-08-13T06:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAO231 | [{"equipmentGUID": "9627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC04", "name": "Reclaimer: CLA 04", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43494 | 2021-11-01T22:53:58+00:00 | 2021-11-02T06:53:58+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T00:19:01.3096922+00:00 | 2026-08-28T08:19:01.3096922+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332094 | TRUE | TRUE | 2026-08-28T00:19:01.3096922+00:00 | 2026-08-28T08:19:01.3096922+08:00 | #43494 - CLA: 250hrs - PLANT IAM | 7.2 | TRUE |  | 2027-08-18T17:00:00+00:00 | 2027-08-29T03:00:00+00:00 | 2027-08-19T01:00:00+08:00 | 2027-08-29T11:00:00+08:00 |  |  |  |  | 250.00 | Plant Sinter Fines Screen 2 C/O's CLA PLANT SHUT 250H & SECONDARY CRUSHER MAIN FRAME C/O |  | SCAP2733 | [{"equipmentGUID": "9a17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLAPLT", "name": "Plant: CLA", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "799e0d01-6f83-4824-bdbf-c66168353aed", "emailAddress": "Nicky.Murray@riotinto.com", "displayName": "Nicky Murray"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
60590 | 2024-02-15T04:57:43+00:00 | 2024-02-15T12:57:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-10-15T01:44:05.9349969+00:00 | 2026-10-15T09:44:05.9349969+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335986 | TRUE | TRUE | 2026-10-15T01:44:05.9349969+00:00 | 2026-10-15T09:44:05.9349969+08:00 | #60590 - CLB: 50hrs - CD6C - ENG RING DUST SEALS & COVERS | 4.1 | TRUE |  | 2027-04-09T20:00:00+00:00 | 2027-04-11T22:00:00+00:00 | 2027-04-10T04:00:00+08:00 | 2027-04-12T06:00:00+08:00 |  |  |  |  | 50.00 | CD6C - Eng Ring Dust Seals & Covers - DEFECTS SHUT- Placement to be confirmed/adjusted or removed in QF timeframe with IOPs team. Do not place work or align with this shut prior to QF confirmation. |  | SCBI2714 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "423b6bb1-0045-43ea-9031-297314d2eb65", "emailAddress": "Scott.Clamp@riotinto.com", "displayName": "Scott Clamp"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
60603 | 2024-02-15T07:06:01+00:00 | 2024-02-15T15:06:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-10-15T00:25:58.6531233+00:00 | 2026-10-15T08:25:58.6531233+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335932 | TRUE | TRUE | 2026-10-15T00:25:58.6531233+00:00 | 2026-10-15T08:25:58.6531233+08:00 | #60603 - CLA: 42hrs - CD2C - BIN LINER MAINTENANCE | 5.2 | TRUE |  | 2027-02-04T10:00:00+00:00 | 2027-02-06T04:00:00+00:00 | 2027-02-04T18:00:00+08:00 | 2027-02-06T12:00:00+08:00 |  |  |  |  | 42.00 | Contingency Placeholder - Placement to be confirmed/adjusted or removed in QF timeframe with IOPs team. Do not place work or align with this shut prior to QF confirmation. |  | SCAI2704 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
60628 | 2024-02-16T03:28:20+00:00 | 2024-02-16T11:28:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-10-15T00:18:27.9152768+00:00 | 2026-10-15T08:18:27.9152768+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335918 | TRUE | TRUE | 2026-10-15T00:18:27.9152768+00:00 | 2026-10-15T08:18:27.9152768+08:00 | #60628 - CLA: 96hrs - SL3C RMP REMEDIAL REPAIRS | 5.1 | TRUE |  | 2027-01-04T22:00:00+00:00 | 2027-01-08T22:00:00+00:00 | 2027-01-05T06:00:00+08:00 | 2027-01-09T06:00:00+08:00 |  |  |  |  | 96.00 | Standalone SL3C_RMP - Corrosion & Structural Work See attached SDN reports and repair procedure Repair will require multiple slew movements that will inhibit other maintenance and require several isolation/de-isolations reducing overall tool time Contact Matt Manning 0418957532 Dale Payne 0457197802 |  | SCAO2701 | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "", "code": "CLABTH03", "name": "Berth: CLA 03", "assetClass": {"name": "Berth"}}, {"equipmentGUID": "", "code": "CLABTH04", "name": "Berth: CLA 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "a66163f9-e6aa-440b-9ce3-30151d63e74d", "emailAddress": "dale.payne@riotinto.com", "displayName": "Payne, Dale (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
65376 | 2024-10-16T00:14:57+00:00 | 2024-10-16T08:14:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-11T22:19:01.0241098+00:00 | 2026-08-12T06:19:01.0241098+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331083 | TRUE | TRUE | 2026-08-11T22:19:01.0241098+00:00 | 2026-08-12T06:19:01.0241098+08:00 | #65376 - CLB: 12hrs - ST13 FS SYSTEM TESTING | 2.1 | FALSE |  | 2027-09-27T22:00:00+00:00 | 2027-09-28T10:00:00+00:00 | 2027-09-28T06:00:00+08:00 | 2027-09-28T18:00:00+08:00 |  |  |  |  | 12.00 | ST13 - Stacker Functional Safety System Tests Additional Info: "The functional safety system test is completed on a 52 weekly cycle." |  |  | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
65375 | 2024-10-16T00:11:28+00:00 | 2024-10-16T08:11:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-11T22:41:33.8021113+00:00 | 2026-08-12T06:41:33.8021113+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331090 | TRUE | TRUE | 2026-08-11T22:41:33.8021113+00:00 | 2026-08-12T06:41:33.8021113+08:00 | #65375 - CLB: 12hrs - ST12 FS SYSTEM TESTING | 2.1 | FALSE |  | 2027-09-26T22:00:00+00:00 | 2027-09-27T10:00:00+00:00 | 2027-09-27T06:00:00+08:00 | 2027-09-27T18:00:00+08:00 |  |  |  |  | 12.00 | ST12 - Stacker Functional Safety System Tests Additional Info: "The functional safety system test is completed on a 52 weekly cycle." |  |  | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
64800 | 2024-10-03T05:32:25+00:00 | 2024-10-03T13:32:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-11T22:42:22.2984434+00:00 | 2026-08-12T06:42:22.2984434+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331091 | TRUE | TRUE | 2026-08-11T22:42:22.2984434+00:00 | 2026-08-12T06:42:22.2984434+08:00 | #64800 - CLB: 12hrs - RC11 FS SYSTEM TESTING | 1.1 | FALSE |  | 2027-09-24T22:00:00+00:00 | 2027-09-25T10:00:00+00:00 | 2027-09-25T06:00:00+08:00 | 2027-09-25T18:00:00+08:00 |  |  |  |  | 12.00 | ST11 - Stacker Functional Safety System Tests 12H Additional Info: The functional safety system test is completed on a 52 weekly cycle. |  |  | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
52937 | 2022-11-08T02:46:00+00:00 | 2022-11-08T10:46:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-11T23:22:51.801867+00:00 | 2026-08-12T07:22:51.801867+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331100 | TRUE | TRUE | 2026-08-11T23:22:51.801867+00:00 | 2026-08-12T07:22:51.801867+08:00 | #52937 - CLB: 12hrs - CD7 FS SYSTEM TESTING | 5.1 | TRUE |  | 2027-08-07T22:00:00+00:00 | 2027-08-08T10:00:00+00:00 | 2027-08-08T06:00:00+08:00 | 2027-08-08T18:00:00+08:00 |  |  |  |  | 12.00 | CD7 Functional Safety System Test - 12hrs The functional safety system test is completed on a 52 weekly cycle. |  |  | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
61965 | 2024-06-14T01:59:33+00:00 | 2024-06-14T09:59:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-13T00:07:05.2247432+00:00 | 2026-08-13T08:07:05.2247432+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331208 | TRUE | TRUE | 2026-08-13T00:07:05.2247432+00:00 | 2026-08-13T08:07:05.2247432+08:00 | #61965 - CLB: 12hrs - SL12 FS SYSTEM TESTING | 2.1 | TRUE |  | 2027-04-19T22:00:00+00:00 | 2027-04-20T10:00:00+00:00 | 2027-04-20T06:00:00+08:00 | 2027-04-20T18:00:00+08:00 |  |  |  |  | 12.00 | SL12 Functional Safety System Test - 12hrs Functional Safety System Testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43661 | 2021-11-01T23:50:12+00:00 | 2021-11-02T07:50:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:35.161399+00:00 | 2026-10-16T14:04:35.161399+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336158 | TRUE | TRUE | 2026-10-16T06:04:35.161399+00:00 | 2026-10-16T14:04:35.161399+08:00 | #43661 - CLB: 84hrs - ST14 IAM | 7.0 | FALSE |  | 2027-11-10T22:00:00+00:00 | 2027-11-14T10:00:00+00:00 | 2027-11-11T06:00:00+08:00 | 2027-11-14T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | misaligned to IAM sequence | SCBY2745 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43545 | 2021-11-01T22:58:02+00:00 | 2021-11-02T06:58:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:25:34.2445492+00:00 | 2026-10-02T15:25:34.2445492+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335199 | TRUE | TRUE | 2026-10-02T07:25:34.2445492+00:00 | 2026-10-02T15:25:34.2445492+08:00 | #43545 - CLA: 24hrs - CRUSHER - TERTIARY: CLA CIRCUIT 03 | 7.0 | FALSE |  | 2027-10-01T22:00:00+00:00 | 2027-10-02T22:00:00+00:00 | 2027-10-02T06:00:00+08:00 | 2027-10-03T06:00:00+08:00 |  |  |  |  | 24.00 | Standard IMS TERT3 24hr Pitstop Shut | misaligned to IAM sequence | SCP2738 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43539 | 2021-11-01T22:57:51+00:00 | 2021-11-02T06:57:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:25:34.629582+00:00 | 2026-10-02T15:25:34.629582+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335201 | TRUE | TRUE | 2026-10-02T07:25:34.629582+00:00 | 2026-10-02T15:25:34.629582+08:00 | #43539 - CLA: 84hrs - CRUSHER - SECONDARY: CLA CIRCUIT 01 | 6.0 | FALSE |  | 2027-12-26T22:00:00+00:00 | 2027-12-30T10:00:00+00:00 | 2027-12-27T06:00:00+08:00 | 2027-12-30T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut | Aligning with IAM Sequence |  | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43664 | 2021-11-01T23:54:33+00:00 | 2021-11-02T07:54:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:32:04.7052987+00:00 | 2026-10-02T15:32:04.7052987+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335203 | TRUE | TRUE | 2026-10-02T07:32:04.7052987+00:00 | 2026-10-02T15:32:04.7052987+08:00 | #43664 - CLB: 9hrs - RC13 PIT STOP | 4.0 | FALSE |  | 2027-04-09T00:00:00+00:00 | 2027-04-09T09:00:00+00:00 | 2027-04-09T08:00:00+08:00 | 2027-04-09T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut | moving away from RC12 IAM shut | SCBY2714 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43654 | 2021-11-01T23:50:01+00:00 | 2021-11-02T07:50:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-02T07:33:40.1940198+00:00 | 2026-10-02T15:33:40.1940198+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335204 | TRUE | TRUE | 2026-10-02T07:33:40.1940198+00:00 | 2026-10-02T15:33:40.1940198+08:00 | #43654 - CLB: 228hrs - RCL12 MAJOR BUCKET WHEEL MAINTENANCE | 7.0 | FALSE |  | 2027-07-11T22:00:00+00:00 | 2027-07-21T10:00:00+00:00 | 2027-07-12T06:00:00+08:00 | 2027-07-21T18:00:00+08:00 |  |  |  |  | 228.00 | Standard IAM Shut RC12 228hr Extend Outage Bucket Wheel Major Maintenance Inclusive 52WK ring chute, radial liner, domite C/O + all 13 buckets) | Re-align with IAM sequence |  | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43638 | 2021-11-01T23:45:16+00:00 | 2021-11-02T07:45:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:42:35.7232534+00:00 | 2026-10-15T09:42:35.7232534+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335983 | TRUE | TRUE | 2026-10-15T01:42:35.7232534+00:00 | 2026-10-15T09:42:35.7232534+08:00 | #43638 - CLB: 84hrs - ST12 IAM | 5.1 | FALSE |  | 2027-04-04T22:00:00+00:00 | 2027-04-08T10:00:00+00:00 | 2027-04-05T06:00:00+08:00 | 2027-04-08T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2714 | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43626 | 2021-11-01T23:42:36+00:00 | 2021-11-02T07:42:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:17:50.2911356+00:00 | 2026-10-15T08:17:50.2911356+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335917 | TRUE | TRUE | 2026-10-15T00:17:50.2911356+00:00 | 2026-10-15T08:17:50.2911356+08:00 | #43626 - CLB: 106hrs - CD6 IAM | 9.2 | TRUE |  | 2027-01-04T10:00:00+00:00 | 2027-01-08T20:00:00+00:00 | 2027-01-04T18:00:00+08:00 | 2027-01-09T04:00:00+08:00 |  |  |  |  | 106.00 | CD6C Standard IAM |  | SCBI2701 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43673 | 2021-11-01T23:54:47+00:00 | 2021-11-02T07:54:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:07:59.4796542+00:00 | 2026-10-15T08:07:59.4796542+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335902 | TRUE | TRUE | 2026-10-15T00:07:59.4796542+00:00 | 2026-10-15T08:07:59.4796542+08:00 | #43673 - CLB: 84hrs - RETURN FINES IAM | 5.1 | FALSE |  | 2027-09-14T10:00:00+00:00 | 2027-09-17T22:00:00+00:00 | 2027-09-14T18:00:00+08:00 | 2027-09-18T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2735 | [{"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43678, "shutVersionId": 263598, "title": "#43678 - CLB: 120hrs - SHIPLOADER: CLB 11C", "startDatetimeUTC": "2027-09-13T10:00:00+00:00", "endDatetimeUTC": "2027-09-18T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43674 | 2021-11-01T23:54:47+00:00 | 2021-11-02T07:54:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:08:28.5459082+00:00 | 2026-10-15T08:08:28.5459082+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335903 | TRUE | TRUE | 2026-10-15T00:08:28.5459082+00:00 | 2026-10-15T08:08:28.5459082+08:00 | #43674 - CLB: 84hrs - RETURN FINES IAM | 5.1 | FALSE |  | 2027-12-14T10:00:00+00:00 | 2027-12-17T22:00:00+00:00 | 2027-12-14T18:00:00+08:00 | 2027-12-18T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2748 | [{"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "f4ec87d0-8bce-4225-8e94-785512b80676", "emailAddress": "Callan.Oakes@riotinto.com", "displayName": "Oakes, Callan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43501 | 2021-11-01T22:54:42+00:00 | 2021-11-02T06:54:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:09:35.3211504+00:00 | 2026-10-15T08:09:35.3211504+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335904 | TRUE | TRUE | 2026-10-15T00:09:35.3211504+00:00 | 2026-10-15T08:09:35.3211504+08:00 | #43501 - CLA: 120hrs - STK4 IAM | 7.2 | FALSE |  | 2027-07-18T22:00:00+00:00 | 2027-07-23T22:00:00+00:00 | 2027-07-19T06:00:00+08:00 | 2027-07-24T06:00:00+08:00 |  |  |  |  | 120.00 | Std IAM shut |  | SCAY2726 | [{"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43497 | 2021-11-01T22:54:37+00:00 | 2021-11-02T06:54:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:10:23.2523761+00:00 | 2026-10-15T08:10:23.2523761+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335906 | TRUE | TRUE | 2026-10-15T00:10:23.2523761+00:00 | 2026-10-15T08:10:23.2523761+08:00 | #43497 - CLA: 138hrs - RCL1 IAM | 5.1 | FALSE |  | 2027-07-19T04:00:00+00:00 | 2027-07-24T22:00:00+00:00 | 2027-07-19T12:00:00+08:00 | 2027-07-25T06:00:00+08:00 |  |  |  |  | 138.00 | Standard IAM Maintenance |  | SCAY2726 | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43689 | 2021-11-02T00:01:13+00:00 | 2021-11-02T08:01:13+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T00:13:04.364741+00:00 | 2026-10-15T08:13:04.364741+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335909 | TRUE | TRUE | 2026-10-15T00:13:04.364741+00:00 | 2026-10-15T08:13:04.364741+08:00 | #43689 - CLB: 120hrs - SL12 IAM | 7.1 | TRUE |  | 2027-01-11T10:00:00+00:00 | 2027-01-16T10:00:00+00:00 | 2027-01-11T18:00:00+08:00 | 2027-01-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2702 | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43537 | 2021-11-01T22:57:47+00:00 | 2021-11-02T06:57:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-14T23:51:53.0914707+00:00 | 2026-10-15T07:51:53.0914707+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335900 | TRUE | TRUE | 2026-10-14T23:51:53.0914707+00:00 | 2026-10-15T07:51:53.0914707+08:00 | #43537 - CLA: 84hrs - SEC1 IAM | 7.1 | FALSE |  | 2027-09-26T22:00:00+00:00 | 2027-09-30T10:00:00+00:00 | 2027-09-27T06:00:00+08:00 | 2027-09-30T18:00:00+08:00 |  |  |  |  | 84.00 | SEC1 84hr Shut |  | SCP2738 | [{"equipmentGUID": "9917ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLASCSCCT01", "name": "Crusher - Secondary: CLA Circuit 01", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43692 | 2021-11-02T00:01:17+00:00 | 2021-11-02T08:01:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-14T23:50:43.4324668+00:00 | 2026-10-15T07:50:43.4324668+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335897 | TRUE | TRUE | 2026-10-14T23:50:43.4324668+00:00 | 2026-10-15T07:50:43.4324668+08:00 | #43692 - CLB: 120hrs - SL12 IAM | 7.1 | TRUE |  | 2027-10-11T10:00:00+00:00 | 2027-10-16T10:00:00+00:00 | 2027-10-11T18:00:00+08:00 | 2027-10-16T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCBO2741 | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43679, "shutVersionId": 331509, "title": "#43679 - CLB: 12hrs - CLB DUAL SHIP LOADER SHUT", "startDatetimeUTC": "2027-10-12T22:00:00+00:00", "endDatetimeUTC": "2027-10-13T10:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43640 | 2021-11-01T23:45:25+00:00 | 2021-11-02T07:45:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-14T23:51:04.3448634+00:00 | 2026-10-15T07:51:04.3448634+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335898 | TRUE | TRUE | 2026-10-14T23:51:04.3448634+00:00 | 2026-10-15T07:51:04.3448634+08:00 | #43640 - CLB: 84hrs - ST12 IAM | 5.1 | FALSE |  | 2027-10-03T22:00:00+00:00 | 2027-10-07T10:00:00+00:00 | 2027-10-04T06:00:00+08:00 | 2027-10-07T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBY2738 | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43547 | 2021-11-01T22:58:06+00:00 | 2021-11-02T06:58:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-14T23:47:02.4626058+00:00 | 2026-10-15T07:47:02.4626058+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335894 | TRUE | TRUE | 2026-10-14T23:47:02.4626058+00:00 | 2026-10-15T07:47:02.4626058+08:00 | #43547 - CLA: 84hrs - TERT3 IAM | 8.1 | FALSE |  | 2027-11-15T04:00:00+00:00 | 2027-11-18T16:00:00+00:00 | 2027-11-15T12:00:00+08:00 | 2027-11-19T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCP2750 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43560 | 2021-11-01T22:59:07+00:00 | 2021-11-02T06:59:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-14T23:48:17.4668473+00:00 | 2026-10-15T07:48:17.4668473+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335895 | TRUE | TRUE | 2026-10-14T23:48:17.4668473+00:00 | 2026-10-15T07:48:17.4668473+08:00 | #43560 - CLA: 84hrs - TERT3 IAM | 7.1 | FALSE |  | 2027-12-27T16:00:00+00:00 | 2027-12-31T04:00:00+00:00 | 2027-12-28T00:00:00+08:00 | 2027-12-31T12:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS TERT3 24hr Pitstop Shut |  | SCP2751 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43660 | 2021-11-01T23:50:11+00:00 | 2021-11-02T07:50:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:35.4764965+00:00 | 2026-10-16T14:04:35.4764965+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336160 | TRUE | TRUE | 2026-10-16T06:04:35.4764965+00:00 | 2026-10-16T14:04:35.4764965+08:00 | #43660 - CLB: 84hrs - ST14 IAM | 7.0 | FALSE |  | 2027-08-13T10:00:00+00:00 | 2027-08-16T22:00:00+00:00 | 2027-08-13T18:00:00+08:00 | 2027-08-17T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Looking to start on Friday 18:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2732 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43667 | 2021-11-01T23:54:37+00:00 | 2021-11-02T07:54:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:35.718592+00:00 | 2026-10-16T14:04:35.718592+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336161 | TRUE | TRUE | 2026-10-16T06:04:35.718592+00:00 | 2026-10-16T14:04:35.718592+08:00 | #43667 - CLB: 120hrs - RC13 IAM | 6.0 | FALSE |  | 2027-08-12T22:00:00+00:00 | 2027-08-17T22:00:00+00:00 | 2027-08-13T06:00:00+08:00 | 2027-08-18T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | Looking to start on Friday 06:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2732 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43659 | 2021-11-01T23:50:11+00:00 | 2021-11-02T07:50:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:35.864746+00:00 | 2026-10-16T14:04:35.864746+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336162 | TRUE | TRUE | 2026-10-16T06:04:35.864746+00:00 | 2026-10-16T14:04:35.864746+08:00 | #43659 - CLB: 84hrs - ST14 IAM | 7.0 | FALSE |  | 2027-05-13T10:00:00+00:00 | 2027-05-16T22:00:00+00:00 | 2027-05-13T18:00:00+08:00 | 2027-05-17T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Looking to start on Thursday 18:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2719 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43665 | 2021-11-01T23:54:34+00:00 | 2021-11-02T07:54:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:36.0217666+00:00 | 2026-10-16T14:04:36.0217666+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336163 | TRUE | TRUE | 2026-10-16T06:04:36.0217666+00:00 | 2026-10-16T14:04:36.0217666+08:00 | #43665 - CLB: 120hrs - RC13 IAM | 6.0 | FALSE |  | 2027-05-12T22:00:00+00:00 | 2027-05-17T22:00:00+00:00 | 2027-05-13T06:00:00+08:00 | 2027-05-18T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | Looking to start on Thursday 06:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2719 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43663 | 2021-11-01T23:54:33+00:00 | 2021-11-02T07:54:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:36.1779695+00:00 | 2026-10-16T14:04:36.1779695+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336164 | TRUE | TRUE | 2026-10-16T06:04:36.1779695+00:00 | 2026-10-16T14:04:36.1779695+08:00 | #43663 - CLB: 120hrs - CLB RC13 | 6.0 | FALSE |  | 2027-02-10T22:00:00+00:00 | 2027-02-15T22:00:00+00:00 | 2027-02-11T06:00:00+08:00 | 2027-02-16T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | Looking to start on Thursday 06:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2706 | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43658 | 2021-11-01T23:50:07+00:00 | 2021-11-02T07:50:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:36.3499447+00:00 | 2026-10-16T14:04:36.3499447+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336165 | TRUE | TRUE | 2026-10-16T06:04:36.3499447+00:00 | 2026-10-16T14:04:36.3499447+08:00 | #43658 - CLB: 84hrs - ST14 IAM | 5.0 | FALSE |  | 2027-02-11T10:00:00+00:00 | 2027-02-14T22:00:00+00:00 | 2027-02-11T18:00:00+08:00 | 2027-02-15T06:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Looking to start on Thursday 18:00 to minimise overlap with SLD3/RCL4 shuts and also the following CLA line shuts This timing best suits ops and the shutdown teams | SCBY2706 | [{"equipmentGUID": "4ee6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST14", "name": "Stacker: CLB 14", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43603 | 2021-11-01T23:22:15+00:00 | 2021-11-02T07:22:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:36.5099055+00:00 | 2026-10-16T14:04:36.5099055+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336166 | TRUE | TRUE | 2026-10-16T06:04:36.5099055+00:00 | 2026-10-16T14:04:36.5099055+08:00 | #43603 - CLB: 120hrs - BERTH6 IAM | 7.0 | FALSE |  | 2027-03-15T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-15T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | removed berth 5 from equipment - double up with #43602 | SCBO2711 | [{"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43618 | 2021-11-01T23:35:51+00:00 | 2021-11-02T07:35:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-16T06:04:36.6925496+00:00 | 2026-10-16T14:04:36.6925496+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336167 | TRUE | TRUE | 2026-10-16T06:04:36.6925496+00:00 | 2026-10-16T14:04:36.6925496+08:00 | #43618 - CLB: 156hrs - CAR DUMPER: CLB 5C | 7.0 | TRUE |  | 2027-06-07T10:00:00+00:00 | 2027-06-13T22:00:00+00:00 | 2027-06-07T18:00:00+08:00 | 2027-06-14T06:00:00+08:00 |  |  |  |  | 156.00 | Extend Outage to 156h for CD5C PM01 - Liner Maintenance, MSP, Common Discharge, AF Head Chute, Dust Bags Maintenance Contact Dwayne Clarke 0436855516 | Moving outage due to CD5C rolling Rail and Trunnion work needs to be completed earlier | TBC | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43623 | 2021-11-01T23:35:56+00:00 | 2021-11-02T07:35:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:10:05.729982+00:00 | 2026-10-15T10:10:05.729982+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336018 | TRUE | TRUE | 2026-10-15T02:10:05.729982+00:00 | 2026-10-15T10:10:05.729982+08:00 | #43623 - CLB: 84hrs - ST11 IAM | 7.2 | FALSE |  | 2027-06-06T22:00:00+00:00 | 2027-06-10T10:00:00+00:00 | 2027-06-07T06:00:00+08:00 | 2027-06-10T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBI2722 | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43964 | 2021-11-15T23:56:31+00:00 | 2021-11-16T07:56:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:34:13.0675634+00:00 | 2026-10-15T10:34:13.0675634+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336032 | TRUE | TRUE | 2026-10-15T02:34:13.0675634+00:00 | 2026-10-15T10:34:13.0675634+08:00 | #43964 - CLB: 12hrs - RC12 CAPD TESTING | 4.1 | FALSE |  | 2027-06-09T22:00:00+00:00 | 2027-06-10T10:00:00+00:00 | 2027-06-10T06:00:00+08:00 | 2027-06-10T18:00:00+08:00 |  |  |  |  | 12.00 | RC12 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43672 | 2021-11-01T23:54:46+00:00 | 2021-11-02T07:54:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:35:55.998129+00:00 | 2026-10-15T10:35:55.998129+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336034 | TRUE | TRUE | 2026-10-15T02:35:55.998129+00:00 | 2026-10-15T10:35:55.998129+08:00 | #43672 - CLB: 84hrs - RETURN FINES IAM | 5.2 | FALSE |  | 2027-06-15T22:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-16T06:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCBO2724 | [{"equipmentGUID": "6a07f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV851", "name": "Conveyor: CLB 851 Fines Return", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44021 | 2021-11-16T01:43:00+00:00 | 2021-11-16T09:43:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:47:52.2233888+00:00 | 2026-10-15T10:47:52.2233888+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336036 | TRUE | TRUE | 2026-10-15T02:47:52.2233888+00:00 | 2026-10-15T10:47:52.2233888+08:00 | #44021 - CLB: 4hrs - ILSUB03 SHUT (CD6/CV500) | 5.1 | TRUE |  | 2027-07-06T02:00:00+00:00 | 2027-07-06T06:00:00+00:00 | 2027-07-06T10:00:00+08:00 | 2027-07-06T14:00:00+08:00 |  |  |  |  | 4.00 | Inload SUB 3 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycle |  | SBCI2727 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "4f73fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL03", "name": "Substation: CLB Inloading 03", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43989 | 2021-11-16T00:37:54+00:00 | 2021-11-16T08:37:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:49:20.4437859+00:00 | 2026-10-15T10:49:20.4437859+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336037 | TRUE | TRUE | 2026-10-15T02:49:20.4437859+00:00 | 2026-10-15T10:49:20.4437859+08:00 | #43989 - CLB: 12hrs - SL12 CAPD TESTING | 6.1 | TRUE |  | 2027-07-03T22:00:00+00:00 | 2027-07-04T10:00:00+00:00 | 2027-07-04T06:00:00+08:00 | 2027-07-04T18:00:00+08:00 |  |  |  |  | 12.00 | SL12 CAPD Testing - 12hrs CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "f351fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD12C", "name": "Shiploader: CLB 12C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43510 | 2021-11-01T22:55:46+00:00 | 2021-11-02T06:55:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:49:55.7611784+00:00 | 2026-10-15T10:49:55.7611784+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336038 | TRUE | TRUE | 2026-10-15T02:49:55.7611784+00:00 | 2026-10-15T10:49:55.7611784+08:00 | #43510 - CLA: 120hrs - STK5 IAM | 7.2 | FALSE |  | 2027-07-30T22:00:00+00:00 | 2027-08-04T22:00:00+00:00 | 2027-07-31T06:00:00+08:00 | 2027-08-05T06:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance |  | SCAI2730 | [{"equipmentGUID": "e3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST05", "name": "Stacker: CLA 05", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43506 | 2021-11-01T22:55:38+00:00 | 2021-11-02T06:55:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:50:08.3764193+00:00 | 2026-10-15T10:50:08.3764193+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336039 | TRUE | TRUE | 2026-10-15T02:50:08.3764193+00:00 | 2026-10-15T10:50:08.3764193+08:00 | #43506 - CLA: 150hrs - RCL2 IAM | 8.2 | FALSE |  | 2027-07-31T04:00:00+00:00 | 2027-08-06T10:00:00+00:00 | 2027-07-31T12:00:00+08:00 | 2027-08-06T18:00:00+08:00 |  |  |  |  | 150.00 | Standard IAM Maintenance |  | SCAI2730 | [{"equipmentGUID": "e332f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC02", "name": "Reclaimer: CLA 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43954 | 2021-11-15T23:37:44+00:00 | 2021-11-16T07:37:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:10:31.7632307+00:00 | 2026-10-15T10:10:31.7632307+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336020 | TRUE | TRUE | 2026-10-15T02:10:31.7632307+00:00 | 2026-10-15T10:10:31.7632307+08:00 | #43954 - CLB: 12hrs - RC11 CAPD TESTING | 3.2 | FALSE |  | 2027-06-08T22:00:00+00:00 | 2027-06-09T10:00:00+00:00 | 2027-06-09T06:00:00+08:00 | 2027-06-09T18:00:00+08:00 |  |  |  |  | 12.00 | RC11 CAPD Testing - 12hrs Additional Info: CAPD (Control and Protective Device) testing is a critical requirement to ensure the balance machine operates within the designed safety limits. This testing is completed on a 52 week cycle. |  |  | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43543 | 2021-11-01T22:57:57+00:00 | 2021-11-02T06:57:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:31:53.79114+00:00 | 2026-10-15T10:31:53.79114+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336029 | TRUE | TRUE | 2026-10-15T02:31:53.79114+00:00 | 2026-10-15T10:31:53.79114+08:00 | #43543 - CLA: 84hrs - TERT3 IAM | 5.1 | FALSE |  | 2027-06-29T04:00:00+00:00 | 2027-07-02T16:00:00+00:00 | 2027-06-29T12:00:00+08:00 | 2027-07-03T00:00:00+08:00 |  |  |  |  | 84.00 | Standard IMS Shut |  | SCAL2726 | [{"equipmentGUID": "f7c91c21-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT03", "name": "Crusher - Tertiary: CLA Circuit 03", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43883 | 2021-11-15T05:19:18+00:00 | 2021-11-15T13:19:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:33:05.4713115+00:00 | 2026-10-15T10:33:05.4713115+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336030 | TRUE | TRUE | 2026-10-15T02:33:05.4713115+00:00 | 2026-10-15T10:33:05.4713115+08:00 | #43883 - CLB: 4hrs - SUBSTATION: CLB PROCESS WATER PLANT WR01 | 3.1 | FALSE |  | 2027-03-23T02:00:00+00:00 | 2027-03-23T06:00:00+00:00 | 2027-03-23T10:00:00+08:00 | 2027-03-23T14:00:00+08:00 |  |  |  |  | 4.00 | CLB Process Water Substation Electrical Inspection - 12hrs Additional Info: Water will need to be diverted from CLA for Statutory Work.Substation Shuts will be completed on a 26 weekly cycle |  |  | [{"equipmentGUID": "2e20f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBWR01", "name": "Substation: CLB Process Water Plant WR01", "assetClass": {"name": "Substation"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43634 | 2021-11-01T23:45:12+00:00 | 2021-11-02T07:45:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:06:54.2922789+00:00 | 2026-10-15T10:06:54.2922789+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336014 | TRUE | TRUE | 2026-10-15T02:06:54.2922789+00:00 | 2026-10-15T10:06:54.2922789+08:00 | #43634 - CLB: 156hrs - CD7C - LINER MAINTENANCE, MSP, COMMON DISCHARGE, AF HEAD CHUTE, DUST BAGS MAINTENANCE | 10.2 | TRUE |  | 2027-05-24T10:00:00+00:00 | 2027-05-30T22:00:00+00:00 | 2027-05-24T18:00:00+08:00 | 2027-05-31T06:00:00+08:00 |  |  |  |  | 156.00 | Extend Outage to 156h for CD7C PM01 - Liner Maintenance, MSP, Common Discharge, AF Head Chute, Dust Bags Maintenance Contact Dwayne Clarke 0436855516 |  | SCBI2721 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43927 | 2021-11-15T09:27:22+00:00 | 2021-11-15T17:27:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:08:24.1020952+00:00 | 2026-10-15T10:08:24.1020952+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336015 | TRUE | TRUE | 2026-10-15T02:08:24.1020952+00:00 | 2026-10-15T10:08:24.1020952+08:00 | #43927 - CLB: 4hrs - ILSUB04 SHUT (CV500/CV502) | 4.1 | TRUE |  | 2027-05-24T22:00:00+00:00 | 2027-05-25T02:00:00+00:00 | 2027-05-25T06:00:00+08:00 | 2027-05-25T10:00:00+08:00 |  |  |  |  | 4.00 | Inload SUB 4 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycle |  | SCBI2721 | [{"equipmentGUID": "d860fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL04", "name": "Substation: CLB Inloading 04", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "dc18f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV501", "name": "Conveyor: CLB 501 Link", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "0cd9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV502", "name": "Conveyor: CLB 502 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43648 | 2021-11-01T23:47:41+00:00 | 2021-11-02T07:47:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T02:08:43.7688467+00:00 | 2026-10-15T10:08:43.7688467+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336016 | TRUE | TRUE | 2026-10-15T02:08:43.7688467+00:00 | 2026-10-15T10:08:43.7688467+08:00 | #43648 - CLB: 9hrs - RC11 PIT STOP | 3.2 | FALSE |  | 2027-05-26T00:00:00+00:00 | 2027-05-26T09:00:00+00:00 | 2027-05-26T08:00:00+08:00 | 2027-05-26T17:00:00+08:00 |  |  |  |  | 9.00 | Standard IMS Pit Stop Shut |  |  | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
44037 | 2021-11-16T02:21:14+00:00 | 2021-11-16T10:21:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:55:23.4719256+00:00 | 2026-10-15T09:55:23.4719256+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335996 | TRUE | TRUE | 2026-10-15T01:55:23.4719256+00:00 | 2026-10-15T09:55:23.4719256+08:00 | #44037 - CLB: 12hrs - CV460 REMSAFE | 4.3 | TRUE |  | 2027-05-21T22:00:00+00:00 | 2027-05-22T10:00:00+00:00 | 2027-05-22T06:00:00+08:00 | 2027-05-22T18:00:00+08:00 |  |  |  |  | 12.00 | CV460 Inload Remsafe Testing - 12hrs |  |  | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "0912f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV460", "name": "Conveyor: CLB 460 Car Dumper 6C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43556 | 2021-11-01T22:59:02+00:00 | 2021-11-02T06:59:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:59:00.9755399+00:00 | 2026-10-15T09:59:00.9755399+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336002 | TRUE | TRUE | 2026-10-15T01:59:00.9755399+00:00 | 2026-10-15T09:59:00.9755399+08:00 | #43556 - CLA: 48hrs - TERT1 IAM | 7.1 | FALSE |  | 2027-05-17T16:00:00+00:00 | 2027-05-19T16:00:00+00:00 | 2027-05-18T00:00:00+08:00 | 2027-05-20T00:00:00+08:00 |  |  |  |  | 48.00 | Standard IMS TERT1 24hr Pitstop Shut |  | SCAL2720 | [{"equipmentGUID": "357acc10-7584-ef11-a853-000d3acacefd", "code": "CLATCSCCT01", "name": "Crusher - Tertiary: CLA Circuit 01", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43493 | 2021-11-01T22:53:57+00:00 | 2021-11-02T06:53:57+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:59:31.6293189+00:00 | 2026-10-15T09:59:31.6293189+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336003 | TRUE | TRUE | 2026-10-15T01:59:31.6293189+00:00 | 2026-10-15T09:59:31.6293189+08:00 | #43493 - CLA: 130hrs - PLANT SHUT | 7.2 | TRUE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance |  | SCAP2721 | [{"equipmentGUID": "9a17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLAPLT", "name": "Plant: CLA", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "85615dee-bfb9-41ac-ba46-76cf6fe94380", "emailAddress": "Elizabeth.Thompson@riotinto.com", "displayName": "Elizabeth Thompson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "799e0d01-6f83-4824-bdbf-c66168353aed", "emailAddress": "Nicky.Murray@riotinto.com", "displayName": "Nicky Murray"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
43702 | 2021-11-02T00:03:14+00:00 | 2021-11-02T08:03:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:56:04.2654157+00:00 | 2026-10-15T09:56:04.2654157+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335998 | TRUE | TRUE | 2026-10-15T01:56:04.2654157+00:00 | 2026-10-15T09:56:04.2654157+08:00 | #43702 - CLB: 72hrs - X-LINK PLANT SHUT | 7.2 | TRUE |  | 2027-05-23T10:00:00+00:00 | 2027-05-26T10:00:00+00:00 | 2027-05-23T18:00:00+08:00 | 2027-05-26T18:00:00+08:00 |  |  |  |  | 72.00 | Contact Shutdown Coordinator regarding shuttle positions for CLB dumper and stacker alignment Standard IMS Shut |  | SCBI2721 | [{"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
43716 | 2021-11-02T01:52:10+00:00 | 2021-11-02T09:52:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T01:56:20.8936643+00:00 | 2026-10-15T09:56:20.8936643+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335999 | TRUE | TRUE | 2026-10-15T01:56:20.8936643+00:00 | 2026-10-15T09:56:20.8936643+08:00 | #43716 - CLA: 130hrs - STK2 PLANT SHUT | 5.2 | FALSE |  | 2027-05-23T17:00:00+00:00 | 2027-05-29T03:00:00+00:00 | 2027-05-24T01:00:00+08:00 | 2027-05-29T11:00:00+08:00 |  |  |  |  | 130.00 | Standard IMS Shut |  | SCAP2721 | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
74771 | 2026-01-19T04:01:41.0716817+00:00 | 2026-01-19T12:01:41.0716817+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-15T01:24:01.2203901+00:00 | 2026-10-15T09:24:01.2203901+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335954 | TRUE | TRUE | 2026-10-15T01:24:01.2203901+00:00 | 2026-10-15T09:24:01.2203901+08:00 | #74771 - CLB: 106hrs - CD7 IAM | 1.1 | TRUE |  | 2027-02-22T10:00:00+00:00 | 2027-02-26T20:00:00+00:00 | 2027-02-22T18:00:00+08:00 | 2027-02-27T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2708 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
75296 | 2026-02-20T00:30:53.410131+00:00 | 2026-02-20T08:30:53.410131+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T02:09:50.5896476+00:00 | 2026-10-15T10:09:50.5896476+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336017 | TRUE | TRUE | 2026-10-15T02:09:50.5896476+00:00 | 2026-10-15T10:09:50.5896476+08:00 | #75296 - CLA: 72hrs - SLD2 520WK WATER REELER HOSE C/O | 1.1 | TRUE |  | 2027-06-05T04:00:00+00:00 | 2027-06-08T04:00:00+00:00 | 2027-06-05T12:00:00+08:00 | 2027-06-08T12:00:00+08:00 |  |  |  |  | 72.00 | SLD2 520Wk Water Reeler Hose C/O Standalone Machine long travel movements required |  | SCAO2722 | [{"equipmentGUID": "00e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD2C", "name": "Shiploader: CLA 2C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d1fed2a-6b4a-4e36-b33e-0ff0c5aa26f6", "emailAddress": "Chris.Morgan@riotinto.com", "displayName": "Morgan, Chris (RTIO)"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "69f5b1cb-f079-417a-b1e8-391ac1c88836", "emailAddress": "Jason.Lyall@riotinto.com", "displayName": "Lyall, Jason (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "80b2aed9-1bbb-4760-a197-a338b140a3b5", "emailAddress": "Michael.Stuart@riotinto.com", "displayName": "Stuart, Michael (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
66940 | 2025-03-25T06:34:42.4319967+00:00 | 2025-03-25T14:34:42.4319967+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T02:33:46.1193487+00:00 | 2026-10-15T10:33:46.1193487+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 336031 | TRUE | TRUE | 2026-10-15T02:33:46.1193487+00:00 | 2026-10-15T10:33:46.1193487+08:00 | #66940 - CLB: 172hrs - CLB ST11 DUAL LUFF CYLINDER C/O STANDALONE 192H | 3.1 | FALSE |  | 2027-06-04T22:00:00+00:00 | 2027-06-12T02:00:00+00:00 | 2027-06-05T06:00:00+08:00 | 2027-06-12T10:00:00+08:00 |  |  |  |  | 172.00 | CLB ST11 Dual Luff Cylinder C/O Standalone 192H Reduces to 172hrs (discussed with S.Adamson) |  | SCBI2722 | [{"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}] | [] | [] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
75281 | 2026-02-18T05:44:34.607095+00:00 | 2026-02-18T13:44:34.607095+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T01:07:07.3332627+00:00 | 2026-10-15T09:07:07.3332627+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335940 | TRUE | TRUE | 2026-10-15T01:07:07.3332627+00:00 | 2026-10-15T09:07:07.3332627+08:00 | #75281 - CLA: 260hrs - CLAHDO CONV C198 DRIVE FINAL STRUCTURE & ELECTRICAL UPGRADE | 2.1 | TRUE |  | 2027-01-26T22:00:00+00:00 | 2027-02-06T18:00:00+00:00 | 2027-01-27T06:00:00+08:00 | 2027-02-07T02:00:00+08:00 |  |  |  |  | 260.00 | Splitting C198 and C199 drive upgrades into 2 separate shuts, Separating C198 into Structural and Electrical Work 260H Wk18 /19 and 320H Wk 30 - 32 |  | SCAI2704 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "9bfde8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV198", "name": "Conveyor: CLA 198", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d6d965c9-4aaa-44f2-9cbf-1b18cec73cc2", "emailAddress": "Sharam.Tabai@riotinto.com", "displayName": "Tabai, Sharam (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "ac99d10f-681a-456b-a858-b0d94417ada2", "emailAddress": "Mark.Sobey@riotinto.com", "displayName": "Sobey, Mark (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Major Projects | CLA | Australia/Perth
82863 | 2026-06-09T05:33:05.5120495+00:00 | 2026-06-09T13:33:05.5120495+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T00:25:29.7503373+00:00 | 2026-10-15T08:25:29.7503373+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335931 | TRUE | TRUE | 2026-10-15T00:25:29.7503373+00:00 | 2026-10-15T08:25:29.7503373+08:00 | #82863 - CLA: 192hrs - C199 GTU PHASE UPGRADE | 2.1 | TRUE |  | 2027-01-26T22:00:00+00:00 | 2027-02-03T22:00:00+00:00 | 2027-01-27T06:00:00+08:00 | 2027-02-04T06:00:00+08:00 |  |  |  |  | 192.00 | C199 GTU Phase 3 Upgrade Project Contact Adian Han 0419 965 742 Align with CLAHDO outage |  | SCAI2704 | [{"equipmentGUID": "155afbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACD2C", "name": "Car Dumper: CLA 2C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "686efbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV199", "name": "Conveyor: CLA 199", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "faae154b-1778-4bf4-838c-17b3fe52bb30", "emailAddress": "Adrian.Han@riotinto.com", "displayName": "Han, Adrian (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "570e2b43-4ba6-4151-b2a1-7f58165218cf", "emailAddress": "Hayley.Pilgrim@riotinto.com", "displayName": "Pilgrim, Hayley (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 75280, "shutVersionId": 327276, "title": "#75280 - CLA: 320hrs - CLAHDO CONV C199 DRIVE FINAL STRUCTURE & ELECTRICAL UPGRADE", "startDatetimeUTC": "2026-10-18T22:00:00+00:00", "endDatetimeUTC": "2026-11-01T06:00:00+00:00"}}] | [] | [{"code": "P-0603155", "name": "GTU Phase 3 Upgrade Project", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "192"}] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
75286 | 2026-02-19T02:09:38.1574209+00:00 | 2026-02-19T10:09:38.1574209+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T01:43:13.6075912+00:00 | 2026-10-15T09:43:13.6075912+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335985 | TRUE | TRUE | 2026-10-15T01:43:13.6075912+00:00 | 2026-10-15T09:43:13.6075912+08:00 | #75286 - CLB: 156hrs - CD6C - DUST COLLECTOR DUCTING REPLACEMENT | 2.1 | TRUE |  | 2027-04-05T10:00:00+00:00 | 2027-04-11T22:00:00+00:00 | 2027-04-05T18:00:00+08:00 | 2027-04-12T06:00:00+08:00 |  |  |  |  | 156.00 | CD6C - Dust Collector Ducting Replacement Utilized hours from #60590 - CLB: 94hrs - CD6C - DEFECTS SHUT |  | SCBI2714 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ad335d87-3c53-4798-8bef-230f0198a8f1", "emailAddress": "dwayne.clarke@riotinto.com", "displayName": "Clarke, Dwayne (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "41954d2c-e9eb-4ec2-acbe-0b5dc73af9e7", "emailAddress": "James.Brakespeare@riotinto.com", "displayName": "Brakespeare, James (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
83648 | 2026-08-05T22:20:07.9313833+00:00 | 2026-08-06T06:20:07.9313833+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-15T01:53:12.3799245+00:00 | 2026-10-15T09:53:12.3799245+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335993 | TRUE | TRUE | 2026-10-15T01:53:12.3799245+00:00 | 2026-10-15T09:53:12.3799245+08:00 | #83648 - CLA: 72hrs - C205/C206 CHUTE REPAIRS | 2.1 | TRUE |  | 2027-05-08T16:00:00+00:00 | 2027-05-11T16:00:00+00:00 | 2027-05-09T00:00:00+08:00 | 2027-05-12T00:00:00+08:00 |  |  |  |  | 72.00 | C205/C206 Chute Repairs C205 Shuttle needs to be retracted Cannot feed C207 for duration Contact Dale Payne 0457197802 |  | SCAO2718 | [{"equipmentGUID": "d866fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV205", "name": "Conveyor: CLA 205 Lump Rescreening", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "9ff3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV206", "name": "Conveyor: CLA 206 Outloading", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "69f5b1cb-f079-417a-b1e8-391ac1c88836", "emailAddress": "Jason.Lyall@riotinto.com", "displayName": "Lyall, Jason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "a66163f9-e6aa-440b-9ce3-30151d63e74d", "emailAddress": "dale.payne@riotinto.com", "displayName": "Payne, Dale (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 43583, "shutVersionId": 332056, "title": "#43583 - CLA: 114hrs - SLD3 IAM", "startDatetimeUTC": "2027-05-08T10:00:00+00:00", "endDatetimeUTC": "2027-05-13T04:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
74770 | 2026-01-19T04:00:55.0634225+00:00 | 2026-01-19T12:00:55.0634225+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-08-28T00:04:42.0935447+00:00 | 2026-08-28T08:04:42.0935447+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 332069 | TRUE | TRUE | 2026-08-28T00:04:42.0935447+00:00 | 2026-08-28T08:04:42.0935447+08:00 | #74770 - CLB: 106hrs - CD7 IAM | 1.1 | TRUE |  | 2027-05-24T10:00:00+00:00 | 2027-05-28T20:00:00+00:00 | 2027-05-24T18:00:00+08:00 | 2027-05-29T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance |  | SCBI2721 | [{"equipmentGUID": "8b24f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD7C", "name": "Car Dumper: CLB 7C", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "emailAddress": "Robert.Ellis5@riotinto.com", "displayName": "Ellis, Robert 1 (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
60694 | 2024-02-16T05:20:04+00:00 | 2024-02-16T13:20:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-17T04:28:33.583481+00:00 | 2026-08-17T12:28:33.583481+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331322 | TRUE | TRUE | 2026-08-17T04:28:33.583481+00:00 | 2026-08-17T12:28:33.583481+08:00 | #60694 - CLB: 96hrs - SL11 RMP REMEDIAL REPAIRS | 4.1 | TRUE |  | 2027-08-22T22:00:00+00:00 | 2027-08-26T22:00:00+00:00 | 2027-08-23T06:00:00+08:00 | 2027-08-27T06:00:00+08:00 |  |  |  |  | 96.00 | Standalone outage 96hrs SL11_RMP - Corrosion & Structural Repairs Contact Mat Mckiernan 0400141769 Brad Ross 0400949892 |  |  | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "423b6bb1-0045-43ea-9031-297314d2eb65", "emailAddress": "Scott.Clamp@riotinto.com", "displayName": "Scott Clamp"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
60647 | 2024-02-16T04:06:56+00:00 | 2024-02-16T12:06:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b69", "displayName": "Robert Ellis"} | 2026-08-17T04:33:56.4911989+00:00 | 2026-08-17T12:33:56.4911989+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331326 | TRUE | TRUE | 2026-08-17T04:33:56.4911989+00:00 | 2026-08-17T12:33:56.4911989+08:00 | #60647 - CLA: 96hrs - SL3C RMP REMEDIAL REPAIRS | 4.1 | TRUE |  | 2027-08-03T10:00:00+00:00 | 2027-08-07T10:00:00+00:00 | 2027-08-03T18:00:00+08:00 | 2027-08-07T18:00:00+08:00 |  |  |  |  | 96.00 | Standalone SL3C_RMP - Corrosion & Structural Work Contact Matt Manning 0418957532 Joel Cappellano 0413579483 |  |  | [{"equipmentGUID": "3428f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASLD3C", "name": "Shiploader: CLA 3C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5f436aa5-f07d-4adf-bf1f-d21334886168", "emailAddress": "Joel.Cappellano@riotinto.com", "displayName": "Joel Cappellano"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
75366 | 2026-02-23T22:17:31.0123339+00:00 | 2026-02-24T06:17:31.0123339+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-10-09T03:30:26.5054744+00:00 | 2026-10-09T11:30:26.5054744+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 335749 | TRUE | TRUE | 2026-10-09T03:30:26.5054744+00:00 | 2026-10-09T11:30:26.5054744+08:00 | #75366 - CLB: 180hrs - RC13 RMP REMEDIAL REPAIRS | 2.0 | FALSE |  | 2027-11-07T22:00:00+00:00 | 2027-11-15T10:00:00+00:00 | 2027-11-08T06:00:00+08:00 | 2027-11-15T18:00:00+08:00 |  |  |  |  | 180.00 | Reclaimer 13 Corrosion Repairs Slew Deck Area Blast & Paint | Incorrect outage. re-aligned to IAM sequence |  | [{"equipmentGUID": "5c55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC13", "name": "Reclaimer: CLB 13", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "69efd3bc-6563-401c-a502-629449dd2c12", "emailAddress": "Subin.ChangazhikunnelThomas@riotinto.com", "displayName": "Changazhikunnel Thomas, Subin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
75367 | 2026-02-23T22:20:07.8740177+00:00 | 2026-02-24T06:20:07.8740177+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-08-17T04:26:09.4331522+00:00 | 2026-08-17T12:26:09.4331522+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331320 | TRUE | TRUE | 2026-08-17T04:26:09.4331522+00:00 | 2026-08-17T12:26:09.4331522+08:00 | #75367 - CLB: 180hrs - RC12 RMP REMEDIAL REPAIRS | 1.1 | FALSE |  | 2027-10-15T22:00:00+00:00 | 2027-10-23T10:00:00+00:00 | 2027-10-16T06:00:00+08:00 | 2027-10-23T18:00:00+08:00 |  |  |  |  | 180.00 | Reclaimer 12 Corrosion Repairs Slew Deck Area Blast & Paint Contact Subin Thomas 0469076331 Brad Ross 0400949892 |  |  | [{"equipmentGUID": "452ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC12", "name": "Reclaimer: CLB 12", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "69efd3bc-6563-401c-a502-629449dd2c12", "emailAddress": "Subin.ChangazhikunnelThomas@riotinto.com", "displayName": "Changazhikunnel Thomas, Subin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
75368 | 2026-02-23T23:14:52.2041784+00:00 | 2026-02-24T07:14:52.2041784+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-08-17T04:34:34.3391388+00:00 | 2026-08-17T12:34:34.3391388+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331327 | TRUE | TRUE | 2026-08-17T04:34:34.3391388+00:00 | 2026-08-17T12:34:34.3391388+08:00 | #75368 - CLA: 100hrs - STK2 RMP REMEDIAL REPAIRS | 1.2 | FALSE |  | 2027-05-29T03:00:00+00:00 | 2027-06-02T07:00:00+00:00 | 2027-05-29T11:00:00+08:00 | 2027-06-02T15:00:00+08:00 |  |  |  |  | 100.00 | ST02 RMP Repairs Corrosion Blast & Paint Standalone |  |  | [{"equipmentGUID": "9bf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST02", "name": "Stacker: CLA 02", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "c5f6d490-1651-4210-9710-9db046dd7c02", "emailAddress": "Brendan.Smith3@riotinto.com", "displayName": "Smith, Brendan (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "5511d6db-a4d3-499c-a22a-24b2a63a1979", "emailAddress": "Ethan.Lenton@riotinto.com", "displayName": "Lenton, Ethan (RTIO)"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "emailAddress": "Matt.Manning@riotinto.com", "displayName": "Manning, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
75365 | 2026-02-23T22:13:59.2851538+00:00 | 2026-02-24T06:13:59.2851538+08:00 | {"principalGUID": "76ece3aa-944d-4ce5-b660-14e60dba1fa4", "displayName": "Ellis, Robert 1 (RTIO)"} | 2026-08-17T04:28:55.3989963+00:00 | 2026-08-17T12:28:55.3989963+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 331323 | TRUE | TRUE | 2026-08-17T04:28:55.3989963+00:00 | 2026-08-17T12:28:55.3989963+08:00 | #75365 - CLB: 180hrs - RC11 RMP REMEDIAL REPAIRS | 1.2 | FALSE |  | 2027-03-19T22:00:00+00:00 | 2027-03-27T10:00:00+00:00 | 2027-03-20T06:00:00+08:00 | 2027-03-27T18:00:00+08:00 |  |  |  |  | 180.00 | Reclaimer 11 Corrosion Repairs Slew Deck Area Blast & Paint, |  |  | [{"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "69efd3bc-6563-401c-a502-629449dd2c12", "emailAddress": "Subin.ChangazhikunnelThomas@riotinto.com", "displayName": "Changazhikunnel Thomas, Subin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLB | Australia/Perth
83649 | 2026-08-05T22:33:14.7269086+00:00 | 2026-08-06T06:33:14.7269086+08:00 | {"principalGUID": "a66163f9-e6aa-440b-9ce3-30151d63e74d", "displayName": "Payne, Dale (RTIO)"} | 2026-09-03T07:08:19.0387591+00:00 | 2026-09-03T15:08:19.0387591+08:00 | {"principalGUID": "87d8fe62-a6bc-42c5-8a4e-925cfd876e68", "displayName": "Manning, Matt (RTIO)"} | {"name": "Fixed Plant"} | 333131 | TRUE | TRUE | 2026-09-03T07:08:19.0387591+00:00 | 2026-09-03T15:08:19.0387591+08:00 | #83649 - CLA: 48hrs - C205/C206 CHUTE REPAIRS | 1.0 | FALSE |  | 2027-11-06T16:00:00+00:00 | 2027-11-08T16:00:00+00:00 | 2027-11-07T00:00:00+08:00 | 2027-11-09T00:00:00+08:00 |  |  |  |  | 48.00 | C205/C206 Chute repairs C205 shuttle required in the retracted position (cannot feed either C206 or C207) |  |  | [{"equipmentGUID": "d866fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLACV205", "name": "Conveyor: CLA 205 Lump Rescreening", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "4327f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLASCHLRP02", "name": "Screenhouse: CLA Lump Rescreening Plant 02", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "69f5b1cb-f079-417a-b1e8-391ac1c88836", "emailAddress": "Jason.Lyall@riotinto.com", "displayName": "Lyall, Jason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "a66163f9-e6aa-440b-9ce3-30151d63e74d", "emailAddress": "dale.payne@riotinto.com", "displayName": "Payne, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 87d8fe62-a6bc-42c5-8a4e-925cfd876e68 | Manning, Matt (RTIO) | Scheduled | CLA | Australia/Perth
84080 | 2026-10-01T06:06:10.6586616+00:00 | 2026-10-01T14:06:10.6586616+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | 2026-10-06T00:12:17.0578082+00:00 | 2026-10-06T08:12:17.0578082+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | {"name": "Fixed Plant"} | 335333 | TRUE | TRUE | 2026-10-06T00:12:17.0578082+00:00 | 2026-10-06T08:12:17.0578082+08:00 | #84080 - EII: 84hrs - STACKER: EII 2EN | 1.0 | FALSE |  | 2027-01-15T22:00:00+00:00 | 2027-01-19T10:00:00+00:00 | 2027-01-16T06:00:00+08:00 | 2027-01-19T18:00:00+08:00 |  |  |  |  | 84.00 | Stand alone shutdown for Fitment of Underboom Sprays by Bennco, no other work to be entered that will interfere with working on boom and under boom and on slew deck. Boom to be luffed to 0' does not matter which runway however Stacker will need to be parked at Dampier Salt end of Runway so no isolations will be required for cannnons. |  | SEYD2602 | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "emailAddress": "Sally.Wild@riotinto.com", "displayName": "Wild, Sally (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | 1d601d15-db3b-42ff-8946-99eb7cee834c | Wild, Sally (RTIO) | Scheduled | EII | Australia/Perth
84079 | 2026-10-01T06:00:53.5896292+00:00 | 2026-10-01T14:00:53.5896292+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | 2026-10-06T00:12:17.2931919+00:00 | 2026-10-06T08:12:17.2931919+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | {"name": "Fixed Plant"} | 335334 | TRUE | TRUE | 2026-10-06T00:12:17.2931919+00:00 | 2026-10-06T08:12:17.2931919+08:00 | #84079 - EII: 108hrs - STACKER: EII 1EN | 1.0 | FALSE |  | 2027-01-10T22:00:00+00:00 | 2027-01-15T10:00:00+00:00 | 2027-01-11T06:00:00+08:00 | 2027-01-15T18:00:00+08:00 |  |  |  |  | 108.00 | Stand alone shutdown for Fitment of Underboom Sprays by Bennco, no other work to be entered that will interfere with working on boom and under boom and on slew deck. Boom to be luffed to 0' does not matter which runway however Stacker will need to be parked at Dampier Salt end of Runway so no isolations will be required for cannnons. |  | SEYD2602 | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "emailAddress": "Sally.Wild@riotinto.com", "displayName": "Wild, Sally (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | 1d601d15-db3b-42ff-8946-99eb7cee834c | Wild, Sally (RTIO) | Scheduled | EII | Australia/Perth
83690 | 2026-08-13T03:48:27.6074097+00:00 | 2026-08-13T11:48:27.6074097+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | 2026-08-13T03:48:27.6074097+00:00 | 2026-08-13T11:48:27.6074097+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | {"name": "Fixed Plant"} | 331248 | TRUE | TRUE | 2026-08-13T03:48:27.6074097+00:00 | 2026-08-13T11:48:27.6074097+08:00 | #83690 - EII: 88hrs - STOCKPILE: EII 10.2 | 1.0 | FALSE |  | 2026-12-06T22:00:00+00:00 | 2026-12-10T14:00:00+00:00 | 2026-12-07T06:00:00+08:00 | 2026-12-10T22:00:00+08:00 |  |  |  |  | 88.00 | ***STOCKPIL 10.2 ro be empty @ tripper End @ Cannon #1 for Bennco Access inside Stockpile @ Cannon#1 |  | seyd2650 | [{"equipmentGUID": "", "code": "EIISTOCKPILE10.2", "name": "Stockpile: EII 10.2", "assetClass": {"name": "Stockpile"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "emailAddress": "Sally.Wild@riotinto.com", "displayName": "Wild, Sally (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Create | 1d601d15-db3b-42ff-8946-99eb7cee834c | Wild, Sally (RTIO) | Site Constraint | EII | Australia/Perth
83689 | 2026-08-13T03:44:41.8331733+00:00 | 2026-08-13T11:44:41.8331733+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | 2026-09-29T05:37:29.9855251+00:00 | 2026-09-29T13:37:29.9855251+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | {"name": "Fixed Plant"} | 334230 | TRUE | TRUE | 2026-09-29T05:37:29.9855251+00:00 | 2026-09-29T13:37:29.9855251+08:00 | #83689 - EII: 88hrs - CONVEYOR: EII 10E & STOCKPILE: EII 10.2 | 1.0 | FALSE |  | 2026-12-06T22:00:00+00:00 | 2026-12-10T14:00:00+00:00 | 2026-12-07T06:00:00+08:00 | 2026-12-10T22:00:00+08:00 |  |  |  |  | 88.00 | Underground Water Pipe dig required By Bennco - no machines and stockpile to be empty @tripper end @ cannon#1 |  | SEYD2650 | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "5fa801e8-4a8c-ee11-a847-000d3acacefd", "code": "EIITP10E", "name": "Tripper: EII 10E Long Travel System", "assetClass": {"name": "Tripper"}}, {"equipmentGUID": "", "code": "EIISTOCKPILE10.2", "name": "Stockpile: EII 10.2", "assetClass": {"name": "Stockpile"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "emailAddress": "Sally.Wild@riotinto.com", "displayName": "Wild, Sally (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 39819, "shutVersionId": 261387, "title": "#39819 - EII: 80hrs - CONVEYOR: EII 10E", "startDatetimeUTC": "2026-12-07T06:00:00+00:00", "endDatetimeUTC": "2026-12-10T14:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 1d601d15-db3b-42ff-8946-99eb7cee834c | Wild, Sally (RTIO) | Scheduled | EII | Australia/Perth
83877 | 2026-09-03T03:04:12.9618846+00:00 | 2026-09-03T11:04:12.9618846+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | 2026-09-03T03:04:12.9618846+00:00 | 2026-09-03T11:04:12.9618846+08:00 | {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "displayName": "Wild, Sally (RTIO)"} | {"name": "Fixed Plant"} | 333112 | TRUE | TRUE | 2026-09-03T03:04:12.9618846+00:00 | 2026-09-03T11:04:12.9618846+08:00 | #83877 - EII: 192hrs - STOCKPILE: EII 11.1 | 1.0 | FALSE |  | 2027-01-18T20:00:00+00:00 | 2027-01-26T20:00:00+00:00 | 2027-01-19T04:00:00+08:00 | 2027-01-27T04:00:00+08:00 |  |  |  |  | 192.00 | ***STOCKYARD TO BE EMPTY ******* Winyama to remove slump at Cannon #9 and 10 for water repairs |  | SEYD2603 | [{"equipmentGUID": "", "code": "EIISTOCKPILE11.1", "name": "Stockpile: EII 11.1", "assetClass": {"name": "Stockpile"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "1d601d15-db3b-42ff-8946-99eb7cee834c", "emailAddress": "Sally.Wild@riotinto.com", "displayName": "Wild, Sally (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 82945, "shutVersionId": 329791, "title": "#82945 - EII: 192hrs - CONVEYOR: EII 11E", "startDatetimeUTC": "2027-01-18T20:00:00+00:00", "endDatetimeUTC": "2027-01-26T20:00:00+00:00"}}] | [] | [] | [{"name": "Canyon Access Permit"}] | Approved | Create | 1d601d15-db3b-42ff-8946-99eb7cee834c | Wild, Sally (RTIO) | Site Constraint | EII | Australia/Perth
44020 | 2021-11-16T01:42:56+00:00 | 2021-11-16T09:42:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-15T05:37:26.3301033+00:00 | 2026-10-15T13:37:26.3301033+08:00 | {"principalGUID": "0fd0321d-ddbe-4e67-9710-aa1b9e3826e5", "displayName": "Sopp, Maddison (RTIO)"} | {"name": "Fixed Plant"} | 336101 | TRUE | TRUE | 2026-10-15T05:37:26.3301033+00:00 | 2026-10-15T13:37:26.3301033+08:00 | #44020 - CLB: 10hrs - ILSUB03 SHUT (CD6 + CV500) | 5.0 | TRUE |  | 2027-01-04T23:00:00+00:00 | 2027-01-05T09:00:00+00:00 | 2027-01-05T07:00:00+08:00 | 2027-01-05T17:00:00+08:00 |  |  |  |  | 10.00 | Inload SUB 3 Electrical Shut - 12hrs Substation Shuts will be completed on a 26 weekly cycle | aligning with CD6C IAM and increasing hours to factor in work that requires completion | SBCL2651 | [{"equipmentGUID": "1e56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD6C", "name": "Car Dumper: CLB 6C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "4f73fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL03", "name": "Substation: CLB Inloading 03", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "510cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV500", "name": "Conveyor: CLB 500 Link", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0fd0321d-ddbe-4e67-9710-aa1b9e3826e5 | Sopp, Maddison (RTIO) | Scheduled | CLB | Australia/Perth
43942 | 2021-11-15T23:12:59+00:00 | 2021-11-16T07:12:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-10-21T02:51:52.8303326+00:00 | 2026-10-21T10:51:52.8303326+08:00 | {"principalGUID": "0fd0321d-ddbe-4e67-9710-aa1b9e3826e5", "displayName": "Sopp, Maddison (RTIO)"} | {"name": "Fixed Plant"} | 336257 | TRUE | TRUE | 2026-10-21T02:51:52.8303326+00:00 | 2026-10-21T10:51:52.8303326+08:00 | #43942 - CLB: 4hrs - YDSUB01 ELEC SHUT | 3.0 | FALSE |  | 2026-12-10T00:00:00+00:00 | 2026-12-10T04:00:00+00:00 | 2026-12-10T08:00:00+08:00 | 2026-12-10T12:00:00+08:00 |  |  |  |  | 4.00 | Yard SUB 1 Shut - 12hrs Additional Info: Substation Shuts will be completed on a 26 weekly cycle | Moving to align with when these assets are in shut | SCBY2650 | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7b17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSARF", "name": "Sample Station: CLB Fines Return", "assetClass": {"name": "Sample Station"}}, {"equipmentGUID": "7c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH06", "name": "Screenhouse: CLB 06 Outloading", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "173df6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBYD01", "name": "Substation: CLB Stockyard 01", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "dcf7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV853", "name": "Conveyor: CLB 853 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "57e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBRC11", "name": "Reclaimer: CLB 11", "assetClass": {"name": "Reclaimer"}}, {"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0fd0321d-ddbe-4e67-9710-aa1b9e3826e5 | Sopp, Maddison (RTIO) | Scheduled | CLB | Australia/Perth
83895 | 2026-09-08T06:21:36.2818896+00:00 | 2026-09-08T14:21:36.2818896+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-09-08T09:35:46.6347341+00:00 | 2026-09-08T17:35:46.6347341+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 333236 | TRUE | TRUE | 2026-09-08T09:35:46.6347341+00:00 | 2026-09-08T17:35:46.6347341+08:00 | #83895 - UTL: 11hrs - GENERATION: PPS GTG1 | 1.0 | FALSE |  | 2026-12-03T23:00:00+00:00 | 2026-12-04T10:00:00+00:00 | 2026-12-04T07:00:00+08:00 | 2026-12-04T18:00:00+08:00 |  |  |  |  | 11.00 | filter house inspection - contractor engineering MO 74704710 |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG1 PPS", "name": "Generation: PPS GTG1", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
83896 | 2026-09-08T06:26:00.0609174+00:00 | 2026-09-08T14:26:00.0609174+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-09-08T09:35:46.7730922+00:00 | 2026-09-08T17:35:46.7730922+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 333237 | TRUE | TRUE | 2026-09-08T09:35:46.7730922+00:00 | 2026-09-08T17:35:46.7730922+08:00 | #83896 - UTL: 11.5hrs - GENERATION: PPS GTG2 | 1.0 | FALSE |  | 2026-12-04T22:30:00+00:00 | 2026-12-05T10:00:00+00:00 | 2026-12-05T06:30:00+08:00 | 2026-12-05T18:00:00+08:00 |  |  |  |  | 11.50 | FILTER HOUSE LEAKAGE INSPECTION ENGINEERING CONTRACTOR |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG2 PPS", "name": "Generation: PPS GTG2", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
84473 | 2026-10-12T23:57:56.841046+00:00 | 2026-10-13T07:57:56.841046+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-10-14T01:03:24.0628962+00:00 | 2026-10-14T09:03:24.0628962+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 335887 | TRUE | TRUE | 2026-10-14T01:03:24.0628962+00:00 | 2026-10-14T09:03:24.0628962+08:00 | #84473 - UTL: 7hrs - GENERATION: PPS GTG3 | 1.0 | FALSE |  | 2027-01-02T00:00:00+00:00 | 2027-01-02T07:00:00+00:00 | 2027-01-02T08:00:00+08:00 | 2027-01-02T15:00:00+08:00 |  |  |  |  | 7.00 | WATER WASH ROUTINE 2000 HRS WASH DAYTIME ONLY AVAILABLE TO RETURN TO FULL SERVICE IF REQUIRED MO 116239896 GTG3 Water Wash |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG3 PPS", "name": "Generation: PPS GTG3", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
84468 | 2026-10-12T03:19:13.7585094+00:00 | 2026-10-12T11:19:13.7585094+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-10-12T05:05:01.829222+00:00 | 2026-10-12T13:05:01.829222+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 335820 | TRUE | TRUE | 2026-10-12T05:05:01.829222+00:00 | 2026-10-12T13:05:01.829222+08:00 | #84468 - UTL: 6hrs - GENERATION: PPS GTG1 | 1.0 | FALSE |  | 2027-01-03T02:00:00+00:00 | 2027-01-03T08:00:00+00:00 | 2027-01-03T10:00:00+08:00 | 2027-01-03T16:00:00+08:00 |  |  |  |  | 6.00 | Pre bushing change water wash daytime only machine will come offline following day for 3-day bushing change |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG1 PPS", "name": "Generation: PPS GTG1", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
84469 | 2026-10-12T03:23:03.3319214+00:00 | 2026-10-12T11:23:03.3319214+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-10-12T05:05:02.088926+00:00 | 2026-10-12T13:05:02.088926+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 335821 | TRUE | TRUE | 2026-10-12T05:05:02.088926+00:00 | 2026-10-12T13:05:02.088926+08:00 | #84469 - UTL: 81hrs - GENERATION: PPS GTG1 | 1.0 | FALSE |  | 2027-01-03T22:00:00+00:00 | 2027-01-07T07:00:00+00:00 | 2027-01-04T06:00:00+08:00 | 2027-01-07T15:00:00+08:00 |  |  |  |  | 81.00 | 12,500 vsv bushing change out follwed by a water wash post bushing change on the Thursday fly out day . |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG1 PPS", "name": "Generation: PPS GTG1", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
84470 | 2026-10-12T03:29:10.3122818+00:00 | 2026-10-12T11:29:10.3122818+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-10-12T05:05:02.2576005+00:00 | 2026-10-12T13:05:02.2576005+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 335822 | TRUE | TRUE | 2026-10-12T05:05:02.2576005+00:00 | 2026-10-12T13:05:02.2576005+08:00 | #84470 - UTL: 6hrs - GENERATION: PPS GTG2 | 1.0 | FALSE |  | 2027-01-17T02:00:00+00:00 | 2027-01-17T08:00:00+00:00 | 2027-01-17T10:00:00+08:00 | 2027-01-17T16:00:00+08:00 |  |  |  |  | 6.00 | pre water wash for the 12500 bushing change, following day. day time only, however; machine comes offl;ine next day |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG2 PPS", "name": "Generation: PPS GTG2", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
84471 | 2026-10-12T03:47:44.4694995+00:00 | 2026-10-12T11:47:44.4694995+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-10-12T05:05:02.4267145+00:00 | 2026-10-12T13:05:02.4267145+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 335823 | TRUE | TRUE | 2026-10-12T05:05:02.4267145+00:00 | 2026-10-12T13:05:02.4267145+08:00 | #84471 - UTL: 81hrs - GENERATION: PPS GTG2 | 1.0 | FALSE |  | 2027-01-17T22:00:00+00:00 | 2027-01-21T07:00:00+00:00 | 2027-01-18T06:00:00+08:00 | 2027-01-21T15:00:00+08:00 |  |  |  |  | 81.00 | 12,500 vsv bushing change out - contractors on site final day 21 Jan is a water wash - post bushing change and will be returned to service as soon as done |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG2 PPS", "name": "Generation: PPS GTG2", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
83678 | 2026-08-11T22:59:56.1893409+00:00 | 2026-08-12T06:59:56.1893409+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-08-11T23:51:58.9980944+00:00 | 2026-08-12T07:51:58.9980944+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 331106 | TRUE | TRUE | 2026-08-11T23:51:58.9980944+00:00 | 2026-08-12T07:51:58.9980944+08:00 | #83678 - UTL: 24hrs - NETWORK: TRANSMISSION | 1.0 | FALSE |  | 2027-04-09T21:00:00+00:00 | 2027-04-10T21:00:00+00:00 | 2027-04-10T05:00:00+08:00 | 2027-04-11T05:00:00+08:00 |  |  |  |  | 24.00 | 6Y switchgear maintenance on PBO-TP 220kV line deferred from 2025 & June 26 shut, line will be off, Paraburdoo will be isolated from the network but should still have GTG1,2,3 available |  |  | [{"equipmentGUID": "", "code": "UTLNETTRANSMISSION", "name": "Network: Transmission", "assetClass": {"name": "Network"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "1477e34e-5f15-4205-b229-95572630ba93", "emailAddress": "Ken.VanDerPutten2@riotinto.com", "displayName": "Ken Van Der Putten"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "14d0d6c9-04ce-4d81-ac1a-c72e317d023e", "emailAddress": "Daryl.Lee@riotinto.com", "displayName": "Lee, Daryl (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "61090d31-cfd6-4161-a3bc-4198675ceb4b", "emailAddress": "James.Pakay@riotinto.com", "displayName": "Pakay, James (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "9445a1c9-fef8-4894-89d7-fb4da1b0a267", "emailAddress": "Mostyn.Jones@riotinto.com", "displayName": "Jones, Mostyn (RTIO)"}}] | [{"name": "PDO"}, {"name": "MTP"}] | [] | [] | [] | [] | Approved | Create | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Placeholder |  | Australia/Perth
75279 | 2026-02-18T02:47:58.6118207+00:00 | 2026-02-18T10:47:58.6118207+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | 2026-07-08T07:53:55.3356+00:00 | 2026-07-08T15:53:55.3356+08:00 | {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "displayName": "Foster, Tony (RTIO)"} | {"name": "Utilities"} | 329716 | TRUE | TRUE | 2026-07-08T07:53:55.3356+00:00 | 2026-07-08T15:53:55.3356+08:00 | #75279 - UTL: 35hrs - GENERATION: PPS GTG3 | 3.0 | FALSE |  | 2027-03-14T23:00:00+00:00 | 2027-03-16T10:00:00+00:00 | 2027-03-15T07:00:00+08:00 | 2027-03-16T18:00:00+08:00 |  |  |  |  | 35.00 | leak test ENGINE R & R pre alignment combustor change for now October (moved from April) and moved from Sept 26, to March 27 still waiting on confirmed combustor date - TF | re alignment combustor change for now October (moved from April) and moved from Sept 26, to March 27 still waiting on confirmed combustor date - TF |  | [{"equipmentGUID": "", "code": "UTLGENGTG3 PPS", "name": "Generation: PPS GTG3", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "56022e41-6356-4f18-96fb-563c02ea421d", "emailAddress": "Matt.Kowalewycz@riotinto.com", "displayName": "Kowalewycz, Matt (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 66546fbf-790f-481d-bf06-af4bd7a9d4ea | Foster, Tony (RTIO) | Scheduled |  | Australia/Perth
81757 | 2026-03-18T04:15:10.8196588+00:00 | 2026-03-18T12:15:10.8196588+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6082941+00:00 | 2026-03-26T12:50:09.6082941+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324281 | TRUE | TRUE | 2026-03-26T04:50:09.6082941+00:00 | 2026-03-26T12:50:09.6082941+08:00 | #81757 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-12-25T01:00:00+00:00 | 2027-12-25T05:00:00+00:00 | 2027-12-25T09:00:00+08:00 | 2027-12-25T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81756 | 2026-03-18T04:15:10.8195721+00:00 | 2026-03-18T12:15:10.8195721+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087159+00:00 | 2026-03-26T12:50:09.6087159+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324282 | TRUE | TRUE | 2026-03-26T04:50:09.6087159+00:00 | 2026-03-26T12:50:09.6087159+08:00 | #81756 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-12-18T01:00:00+00:00 | 2027-12-18T05:00:00+00:00 | 2027-12-18T09:00:00+08:00 | 2027-12-18T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81755 | 2026-03-18T04:15:10.8194823+00:00 | 2026-03-18T12:15:10.8194823+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087479+00:00 | 2026-03-26T12:50:09.6087479+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324283 | TRUE | TRUE | 2026-03-26T04:50:09.6087479+00:00 | 2026-03-26T12:50:09.6087479+08:00 | #81755 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-12-04T01:00:00+00:00 | 2027-12-04T05:00:00+00:00 | 2027-12-04T09:00:00+08:00 | 2027-12-04T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81754 | 2026-03-18T04:15:10.8193945+00:00 | 2026-03-18T12:15:10.8193945+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087522+00:00 | 2026-03-26T12:50:09.6087522+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324284 | TRUE | TRUE | 2026-03-26T04:50:09.6087522+00:00 | 2026-03-26T12:50:09.6087522+08:00 | #81754 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-11-27T01:00:00+00:00 | 2027-11-27T05:00:00+00:00 | 2027-11-27T09:00:00+08:00 | 2027-11-27T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81753 | 2026-03-18T04:15:10.8193085+00:00 | 2026-03-18T12:15:10.8193085+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087557+00:00 | 2026-03-26T12:50:09.6087557+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324285 | TRUE | TRUE | 2026-03-26T04:50:09.6087557+00:00 | 2026-03-26T12:50:09.6087557+08:00 | #81753 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-11-20T01:00:00+00:00 | 2027-11-20T05:00:00+00:00 | 2027-11-20T09:00:00+08:00 | 2027-11-20T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81752 | 2026-03-18T04:15:10.8192222+00:00 | 2026-03-18T12:15:10.8192222+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087596+00:00 | 2026-03-26T12:50:09.6087596+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324286 | TRUE | TRUE | 2026-03-26T04:50:09.6087596+00:00 | 2026-03-26T12:50:09.6087596+08:00 | #81752 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-11-06T01:00:00+00:00 | 2027-11-06T05:00:00+00:00 | 2027-11-06T09:00:00+08:00 | 2027-11-06T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81751 | 2026-03-18T04:15:10.8191332+00:00 | 2026-03-18T12:15:10.8191332+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087626+00:00 | 2026-03-26T12:50:09.6087626+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324287 | TRUE | TRUE | 2026-03-26T04:50:09.6087626+00:00 | 2026-03-26T12:50:09.6087626+08:00 | #81751 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-10-30T01:00:00+00:00 | 2027-10-30T05:00:00+00:00 | 2027-10-30T09:00:00+08:00 | 2027-10-30T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81750 | 2026-03-18T04:15:10.8190478+00:00 | 2026-03-18T12:15:10.8190478+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087658+00:00 | 2026-03-26T12:50:09.6087658+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324288 | TRUE | TRUE | 2026-03-26T04:50:09.6087658+00:00 | 2026-03-26T12:50:09.6087658+08:00 | #81750 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-10-23T01:00:00+00:00 | 2027-10-23T05:00:00+00:00 | 2027-10-23T09:00:00+08:00 | 2027-10-23T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81749 | 2026-03-18T04:15:10.8189619+00:00 | 2026-03-18T12:15:10.8189619+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087728+00:00 | 2026-03-26T12:50:09.6087728+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324289 | TRUE | TRUE | 2026-03-26T04:50:09.6087728+00:00 | 2026-03-26T12:50:09.6087728+08:00 | #81749 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-10-16T01:00:00+00:00 | 2027-10-16T05:00:00+00:00 | 2027-10-16T09:00:00+08:00 | 2027-10-16T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81748 | 2026-03-18T04:15:10.8188755+00:00 | 2026-03-18T12:15:10.8188755+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087765+00:00 | 2026-03-26T12:50:09.6087765+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324290 | TRUE | TRUE | 2026-03-26T04:50:09.6087765+00:00 | 2026-03-26T12:50:09.6087765+08:00 | #81748 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-10-02T01:00:00+00:00 | 2027-10-02T05:00:00+00:00 | 2027-10-02T09:00:00+08:00 | 2027-10-02T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81747 | 2026-03-18T04:15:10.8187879+00:00 | 2026-03-18T12:15:10.8187879+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087797+00:00 | 2026-03-26T12:50:09.6087797+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324291 | TRUE | TRUE | 2026-03-26T04:50:09.6087797+00:00 | 2026-03-26T12:50:09.6087797+08:00 | #81747 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-09-25T01:00:00+00:00 | 2027-09-25T05:00:00+00:00 | 2027-09-25T09:00:00+08:00 | 2027-09-25T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81746 | 2026-03-18T04:15:10.8187017+00:00 | 2026-03-18T12:15:10.8187017+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087832+00:00 | 2026-03-26T12:50:09.6087832+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324292 | TRUE | TRUE | 2026-03-26T04:50:09.6087832+00:00 | 2026-03-26T12:50:09.6087832+08:00 | #81746 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-09-18T01:00:00+00:00 | 2027-09-18T05:00:00+00:00 | 2027-09-18T09:00:00+08:00 | 2027-09-18T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81745 | 2026-03-18T04:15:10.8186149+00:00 | 2026-03-18T12:15:10.8186149+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087863+00:00 | 2026-03-26T12:50:09.6087863+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324293 | TRUE | TRUE | 2026-03-26T04:50:09.6087863+00:00 | 2026-03-26T12:50:09.6087863+08:00 | #81745 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-09-04T01:00:00+00:00 | 2027-09-04T05:00:00+00:00 | 2027-09-04T09:00:00+08:00 | 2027-09-04T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81744 | 2026-03-18T04:15:10.8185271+00:00 | 2026-03-18T12:15:10.8185271+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087896+00:00 | 2026-03-26T12:50:09.6087896+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324294 | TRUE | TRUE | 2026-03-26T04:50:09.6087896+00:00 | 2026-03-26T12:50:09.6087896+08:00 | #81744 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-08-28T01:00:00+00:00 | 2027-08-28T05:00:00+00:00 | 2027-08-28T09:00:00+08:00 | 2027-08-28T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81743 | 2026-03-18T04:15:10.8184416+00:00 | 2026-03-18T12:15:10.8184416+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087944+00:00 | 2026-03-26T12:50:09.6087944+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324295 | TRUE | TRUE | 2026-03-26T04:50:09.6087944+00:00 | 2026-03-26T12:50:09.6087944+08:00 | #81743 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-08-21T01:00:00+00:00 | 2027-08-21T05:00:00+00:00 | 2027-08-21T09:00:00+08:00 | 2027-08-21T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81742 | 2026-03-18T04:15:10.8183553+00:00 | 2026-03-18T12:15:10.8183553+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6087992+00:00 | 2026-03-26T12:50:09.6087992+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324296 | TRUE | TRUE | 2026-03-26T04:50:09.6087992+00:00 | 2026-03-26T12:50:09.6087992+08:00 | #81742 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-08-07T01:00:00+00:00 | 2027-08-07T05:00:00+00:00 | 2027-08-07T09:00:00+08:00 | 2027-08-07T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81741 | 2026-03-18T04:15:10.8182663+00:00 | 2026-03-18T12:15:10.8182663+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088025+00:00 | 2026-03-26T12:50:09.6088025+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324297 | TRUE | TRUE | 2026-03-26T04:50:09.6088025+00:00 | 2026-03-26T12:50:09.6088025+08:00 | #81741 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-07-31T01:00:00+00:00 | 2027-07-31T05:00:00+00:00 | 2027-07-31T09:00:00+08:00 | 2027-07-31T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81740 | 2026-03-18T04:15:10.8181809+00:00 | 2026-03-18T12:15:10.8181809+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088056+00:00 | 2026-03-26T12:50:09.6088056+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324298 | TRUE | TRUE | 2026-03-26T04:50:09.6088056+00:00 | 2026-03-26T12:50:09.6088056+08:00 | #81740 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-07-24T01:00:00+00:00 | 2027-07-24T05:00:00+00:00 | 2027-07-24T09:00:00+08:00 | 2027-07-24T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81739 | 2026-03-18T04:15:10.8180945+00:00 | 2026-03-18T12:15:10.8180945+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.608809+00:00 | 2026-03-26T12:50:09.608809+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324299 | TRUE | TRUE | 2026-03-26T04:50:09.608809+00:00 | 2026-03-26T12:50:09.608809+08:00 | #81739 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-07-17T01:00:00+00:00 | 2027-07-17T05:00:00+00:00 | 2027-07-17T09:00:00+08:00 | 2027-07-17T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81738 | 2026-03-18T04:15:10.8180055+00:00 | 2026-03-18T12:15:10.8180055+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088123+00:00 | 2026-03-26T12:50:09.6088123+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324300 | TRUE | TRUE | 2026-03-26T04:50:09.6088123+00:00 | 2026-03-26T12:50:09.6088123+08:00 | #81738 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-06-26T01:00:00+00:00 | 2027-06-26T05:00:00+00:00 | 2027-06-26T09:00:00+08:00 | 2027-06-26T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81737 | 2026-03-18T04:15:10.8179197+00:00 | 2026-03-18T12:15:10.8179197+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088192+00:00 | 2026-03-26T12:50:09.6088192+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324301 | TRUE | TRUE | 2026-03-26T04:50:09.6088192+00:00 | 2026-03-26T12:50:09.6088192+08:00 | #81737 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-06-19T01:00:00+00:00 | 2027-06-19T05:00:00+00:00 | 2027-06-19T09:00:00+08:00 | 2027-06-19T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81736 | 2026-03-18T04:15:10.8178331+00:00 | 2026-03-18T12:15:10.8178331+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088226+00:00 | 2026-03-26T12:50:09.6088226+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324302 | TRUE | TRUE | 2026-03-26T04:50:09.6088226+00:00 | 2026-03-26T12:50:09.6088226+08:00 | #81736 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-06-05T01:00:00+00:00 | 2027-06-05T05:00:00+00:00 | 2027-06-05T09:00:00+08:00 | 2027-06-05T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81735 | 2026-03-18T04:15:10.8177442+00:00 | 2026-03-18T12:15:10.8177442+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088271+00:00 | 2026-03-26T12:50:09.6088271+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324303 | TRUE | TRUE | 2026-03-26T04:50:09.6088271+00:00 | 2026-03-26T12:50:09.6088271+08:00 | #81735 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-05-29T01:00:00+00:00 | 2027-05-29T05:00:00+00:00 | 2027-05-29T09:00:00+08:00 | 2027-05-29T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81734 | 2026-03-18T04:15:10.8176475+00:00 | 2026-03-18T12:15:10.8176475+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.60883+00:00 | 2026-03-26T12:50:09.60883+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324304 | TRUE | TRUE | 2026-03-26T04:50:09.60883+00:00 | 2026-03-26T12:50:09.60883+08:00 | #81734 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-05-22T01:00:00+00:00 | 2027-05-22T05:00:00+00:00 | 2027-05-22T09:00:00+08:00 | 2027-05-22T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81733 | 2026-03-18T04:15:10.8175617+00:00 | 2026-03-18T12:15:10.8175617+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088332+00:00 | 2026-03-26T12:50:09.6088332+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324305 | TRUE | TRUE | 2026-03-26T04:50:09.6088332+00:00 | 2026-03-26T12:50:09.6088332+08:00 | #81733 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-05-01T01:00:00+00:00 | 2027-05-01T05:00:00+00:00 | 2027-05-01T09:00:00+08:00 | 2027-05-01T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81732 | 2026-03-18T04:15:10.8174753+00:00 | 2026-03-18T12:15:10.8174753+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088437+00:00 | 2026-03-26T12:50:09.6088437+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324306 | TRUE | TRUE | 2026-03-26T04:50:09.6088437+00:00 | 2026-03-26T12:50:09.6088437+08:00 | #81732 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-04-24T01:00:00+00:00 | 2027-04-24T05:00:00+00:00 | 2027-04-24T09:00:00+08:00 | 2027-04-24T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81731 | 2026-03-18T04:15:10.8173868+00:00 | 2026-03-18T12:15:10.8173868+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.608849+00:00 | 2026-03-26T12:50:09.608849+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324307 | TRUE | TRUE | 2026-03-26T04:50:09.608849+00:00 | 2026-03-26T12:50:09.608849+08:00 | #81731 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-04-17T01:00:00+00:00 | 2027-04-17T05:00:00+00:00 | 2027-04-17T09:00:00+08:00 | 2027-04-17T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81730 | 2026-03-18T04:15:10.8173015+00:00 | 2026-03-18T12:15:10.8173015+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088544+00:00 | 2026-03-26T12:50:09.6088544+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324308 | TRUE | TRUE | 2026-03-26T04:50:09.6088544+00:00 | 2026-03-26T12:50:09.6088544+08:00 | #81730 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-04-03T01:00:00+00:00 | 2027-04-03T05:00:00+00:00 | 2027-04-03T09:00:00+08:00 | 2027-04-03T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81729 | 2026-03-18T04:15:10.8172164+00:00 | 2026-03-18T12:15:10.8172164+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088592+00:00 | 2026-03-26T12:50:09.6088592+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324309 | TRUE | TRUE | 2026-03-26T04:50:09.6088592+00:00 | 2026-03-26T12:50:09.6088592+08:00 | #81729 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-03-27T01:00:00+00:00 | 2027-03-27T05:00:00+00:00 | 2027-03-27T09:00:00+08:00 | 2027-03-27T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81728 | 2026-03-18T04:15:10.8171277+00:00 | 2026-03-18T12:15:10.8171277+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088646+00:00 | 2026-03-26T12:50:09.6088646+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324310 | TRUE | TRUE | 2026-03-26T04:50:09.6088646+00:00 | 2026-03-26T12:50:09.6088646+08:00 | #81728 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-03-20T01:00:00+00:00 | 2027-03-20T05:00:00+00:00 | 2027-03-20T09:00:00+08:00 | 2027-03-20T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81727 | 2026-03-18T04:15:10.8170427+00:00 | 2026-03-18T12:15:10.8170427+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088685+00:00 | 2026-03-26T12:50:09.6088685+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324311 | TRUE | TRUE | 2026-03-26T04:50:09.6088685+00:00 | 2026-03-26T12:50:09.6088685+08:00 | #81727 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-03-06T01:00:00+00:00 | 2027-03-06T05:00:00+00:00 | 2027-03-06T09:00:00+08:00 | 2027-03-06T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81726 | 2026-03-18T04:15:10.8169568+00:00 | 2026-03-18T12:15:10.8169568+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088726+00:00 | 2026-03-26T12:50:09.6088726+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324312 | TRUE | TRUE | 2026-03-26T04:50:09.6088726+00:00 | 2026-03-26T12:50:09.6088726+08:00 | #81726 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-02-27T01:00:00+00:00 | 2027-02-27T05:00:00+00:00 | 2027-02-27T09:00:00+08:00 | 2027-02-27T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81725 | 2026-03-18T04:15:10.8168699+00:00 | 2026-03-18T12:15:10.8168699+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088794+00:00 | 2026-03-26T12:50:09.6088794+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324313 | TRUE | TRUE | 2026-03-26T04:50:09.6088794+00:00 | 2026-03-26T12:50:09.6088794+08:00 | #81725 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-02-20T01:00:00+00:00 | 2027-02-20T05:00:00+00:00 | 2027-02-20T09:00:00+08:00 | 2027-02-20T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81724 | 2026-03-18T04:15:10.8167812+00:00 | 2026-03-18T12:15:10.8167812+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088838+00:00 | 2026-03-26T12:50:09.6088838+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324314 | TRUE | TRUE | 2026-03-26T04:50:09.6088838+00:00 | 2026-03-26T12:50:09.6088838+08:00 | #81724 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-02-06T01:00:00+00:00 | 2027-02-06T05:00:00+00:00 | 2027-02-06T09:00:00+08:00 | 2027-02-06T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81723 | 2026-03-18T04:15:10.8166928+00:00 | 2026-03-18T12:15:10.8166928+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088883+00:00 | 2026-03-26T12:50:09.6088883+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324315 | TRUE | TRUE | 2026-03-26T04:50:09.6088883+00:00 | 2026-03-26T12:50:09.6088883+08:00 | #81723 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-01-30T01:00:00+00:00 | 2027-01-30T05:00:00+00:00 | 2027-01-30T09:00:00+08:00 | 2027-01-30T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81722 | 2026-03-18T04:15:10.8166022+00:00 | 2026-03-18T12:15:10.8166022+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088942+00:00 | 2026-03-26T12:50:09.6088942+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324316 | TRUE | TRUE | 2026-03-26T04:50:09.6088942+00:00 | 2026-03-26T12:50:09.6088942+08:00 | #81722 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-01-23T01:00:00+00:00 | 2027-01-23T05:00:00+00:00 | 2027-01-23T09:00:00+08:00 | 2027-01-23T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81721 | 2026-03-18T04:15:10.8165013+00:00 | 2026-03-18T12:15:10.8165013+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6088993+00:00 | 2026-03-26T12:50:09.6088993+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324317 | TRUE | TRUE | 2026-03-26T04:50:09.6088993+00:00 | 2026-03-26T12:50:09.6088993+08:00 | #81721 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-01-16T01:00:00+00:00 | 2027-01-16T05:00:00+00:00 | 2027-01-16T09:00:00+08:00 | 2027-01-16T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81720 | 2026-03-18T04:15:10.8163638+00:00 | 2026-03-18T12:15:10.8163638+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6089041+00:00 | 2026-03-26T12:50:09.6089041+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324318 | TRUE | TRUE | 2026-03-26T04:50:09.6089041+00:00 | 2026-03-26T12:50:09.6089041+08:00 | #81720 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2027-01-02T01:00:00+00:00 | 2027-01-02T05:00:00+00:00 | 2027-01-02T09:00:00+08:00 | 2027-01-02T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81719 | 2026-03-18T04:15:10.8162215+00:00 | 2026-03-18T12:15:10.8162215+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6089087+00:00 | 2026-03-26T12:50:09.6089087+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324319 | TRUE | TRUE | 2026-03-26T04:50:09.6089087+00:00 | 2026-03-26T12:50:09.6089087+08:00 | #81719 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2026-12-26T01:00:00+00:00 | 2026-12-26T05:00:00+00:00 | 2026-12-26T09:00:00+08:00 | 2026-12-26T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81718 | 2026-03-18T04:15:10.8160342+00:00 | 2026-03-18T12:15:10.8160342+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.608912+00:00 | 2026-03-26T12:50:09.608912+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324320 | TRUE | TRUE | 2026-03-26T04:50:09.608912+00:00 | 2026-03-26T12:50:09.608912+08:00 | #81718 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2026-12-19T01:00:00+00:00 | 2026-12-19T05:00:00+00:00 | 2026-12-19T09:00:00+08:00 | 2026-12-19T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
81717 | 2026-03-18T04:15:10.8159489+00:00 | 2026-03-18T12:15:10.8159489+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | 2026-03-26T04:50:09.6089153+00:00 | 2026-03-26T12:50:09.6089153+08:00 | {"principalGUID": "3f4d4c0f-4502-4903-827c-afb4b94cb4a2", "displayName": "Soares, John (RTIO)"} | {"name": "Fixed Plant"} | 324321 | TRUE | TRUE | 2026-03-26T04:50:09.6089153+00:00 | 2026-03-26T12:50:09.6089153+08:00 | #81717 - BM4: 4hrs - TRAIN LOADOUT: BM4 | 1.1 | TRUE |  | 2026-12-12T01:00:00+00:00 | 2026-12-12T05:00:00+00:00 | 2026-12-12T09:00:00+08:00 | 2026-12-12T13:00:00+08:00 |  |  |  |  | 4.00 | Spill Face Clean, Belt Thickness Test, Lube Top Ups - Flexible Timing – Schedule within train gap |  |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "9435f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4RC501", "name": "Reclaimer: BM4 501", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 3f4d4c0f-4502-4903-827c-afb4b94cb4a2 | Soares, John (RTIO) | Scheduled | BM4 | Australia/Perth
83767 | 2026-08-26T04:18:17.1541203+00:00 | 2026-08-26T12:18:17.1541203+08:00 | {"principalGUID": "022d4bbf-5972-42fe-bfa6-b3ae42bb42c1", "displayName": "VanStaden, Justin (RTIO)"} | 2026-08-26T07:11:19.3468289+00:00 | 2026-08-26T15:11:19.3468289+08:00 | {"principalGUID": "022d4bbf-5972-42fe-bfa6-b3ae42bb42c1", "displayName": "VanStaden, Justin (RTIO)"} | {"name": "Utilities"} | 331842 | TRUE | TRUE | 2026-08-26T07:11:19.3468289+00:00 | 2026-08-26T15:11:19.3468289+08:00 | #83767 - UTL: 106hrs - GENERATION: GAS SUPPLY & GENERATION: PPS GTG1 | 1.0 | FALSE |  | 2027-04-11T22:00:00+00:00 | 2027-04-16T08:00:00+00:00 | 2027-04-12T06:00:00+08:00 | 2027-04-16T16:00:00+08:00 |  |  |  |  | 106.00 | Rectification of Valve issues within Area 200 and Area 100 requires complete station outage with lateral blowdown to execute. Date / duration is currently tentative |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG1 PPS", "name": "Generation: PPS GTG1", "assetClass": {"name": "Generation"}}, {"equipmentGUID": "", "code": "UTLGENGTG2 PPS", "name": "Generation: PPS GTG2", "assetClass": {"name": "Generation"}}, {"equipmentGUID": "", "code": "UTLGENGTG3 PPS", "name": "Generation: PPS GTG3", "assetClass": {"name": "Generation"}}, {"equipmentGUID": "", "code": "UTLGENGAS", "name": "Generation: Gas Supply", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "66546fbf-790f-481d-bf06-af4bd7a9d4ea", "emailAddress": "Tony.Foster@riotinto.com", "displayName": "Foster, Tony (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "022d4bbf-5972-42fe-bfa6-b3ae42bb42c1", "emailAddress": "justin.vanstaden@riotinto.com", "displayName": "VanStaden, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 022d4bbf-5972-42fe-bfa6-b3ae42bb42c1 | VanStaden, Justin (RTIO) | Major Projects |  | Australia/Perth
69723 | 2025-10-14T03:49:25.5988061+00:00 | 2025-10-14T11:49:25.5988061+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2025-10-16T00:35:24.5091619+00:00 | 2025-10-16T08:35:24.5091619+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 257967 | TRUE | TRUE | 2025-10-16T00:35:24.5091619+00:00 | 2025-10-16T08:35:24.5091619+08:00 | #69723 - WTS: 216hrs - CRUSHER - PRIMARY: WTS2 04 | 1.0 | TRUE |  | 2027-06-05T11:00:00+00:00 | 2027-06-14T11:00:00+00:00 | 2027-06-05T19:00:00+08:00 | 2027-06-14T19:00:00+08:00 |  |  |  |  | 216.00 | PC04 to go down 2 days before Conveyor shut |  |  | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 73405, "shutVersionId": 287142, "title": "#73405 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH", "startDatetimeUTC": "2027-03-08T20:00:00+00:00", "endDatetimeUTC": "2027-03-09T18:00:00+00:00"}}] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
83097 | 2026-06-29T05:56:11.8084341+00:00 | 2026-06-29T13:56:11.8084341+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T01:33:53.0787737+00:00 | 2026-07-03T09:33:53.0787737+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329309 | TRUE | TRUE | 2026-07-03T01:33:53.0787737+00:00 | 2026-07-03T09:33:53.0787737+08:00 | #83097 - MTP: 474hrs - PLANT: MTP LOW GRADE & TRAIN LOADOUT: MTP LOADOUT TUNNEL 02 | 1.0 | TRUE |  | 2027-08-16T17:00:00+00:00 | 2027-09-05T11:00:00+00:00 | 2027-08-17T01:00:00+08:00 | 2027-09-05T19:00:00+08:00 |  |  |  |  | 474.00 | MTPTLOLOT02 Dozing for gate replacements |  |  | [{"equipmentGUID": "8d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTLG", "name": "Plant: MTP Low Grade", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "bb28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST82", "name": "Stacker: MTP 82 Lump", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "08b4c95e-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT02", "name": "Train Loadout: MTP Loadout Tunnel 02", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Dozing"}] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Site Constraint | MTP | Australia/Perth
83060 | 2026-06-29T05:48:08.8090758+00:00 | 2026-06-29T13:48:08.8090758+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T01:33:53.2906496+00:00 | 2026-07-03T09:33:53.2906496+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329310 | TRUE | TRUE | 2026-07-03T01:33:53.2906496+00:00 | 2026-07-03T09:33:53.2906496+08:00 | #83060 - MTP: 6hrs - TRAIN LOADOUT: MTP FINES | 1.0 | TRUE |  | 2027-12-15T11:00:00+00:00 | 2027-12-15T17:00:00+00:00 | 2027-12-15T19:00:00+08:00 | 2027-12-16T01:00:00+08:00 |  |  |  |  | 6.00 | MTPRC42 Install/remove Camera in slew |  |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "85e100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPRC42", "name": "Reclaimer: MTP 42", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
83059 | 2026-06-29T05:48:08.6297478+00:00 | 2026-06-29T13:48:08.6297478+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T01:33:53.4944321+00:00 | 2026-07-03T09:33:53.4944321+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329311 | TRUE | TRUE | 2026-07-03T01:33:53.4944321+00:00 | 2026-07-03T09:33:53.4944321+08:00 | #83059 - MTP: 6hrs - TRAIN LOADOUT: MTP FINES | 1.0 | TRUE |  | 2027-09-15T11:00:00+00:00 | 2027-09-15T17:00:00+00:00 | 2027-09-15T19:00:00+08:00 | 2027-09-16T01:00:00+08:00 |  |  |  |  | 6.00 | MTPRC42 Install/remove Camera in slew |  |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "85e100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPRC42", "name": "Reclaimer: MTP 42", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
83058 | 2026-06-29T05:48:08.4381746+00:00 | 2026-06-29T13:48:08.4381746+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T01:33:53.6948916+00:00 | 2026-07-03T09:33:53.6948916+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329312 | TRUE | TRUE | 2026-07-03T01:33:53.6948916+00:00 | 2026-07-03T09:33:53.6948916+08:00 | #83058 - MTP: 6hrs - TRAIN LOADOUT: MTP FINES | 1.0 | TRUE |  | 2027-06-16T11:00:00+00:00 | 2027-06-16T17:00:00+00:00 | 2027-06-16T19:00:00+08:00 | 2027-06-17T01:00:00+08:00 |  |  |  |  | 6.00 | MTPRC42 Install/remove Camera in slew |  |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "85e100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPRC42", "name": "Reclaimer: MTP 42", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
83057 | 2026-06-29T05:48:07.8215686+00:00 | 2026-06-29T13:48:07.8215686+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T01:33:53.9043712+00:00 | 2026-07-03T09:33:53.9043712+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329313 | TRUE | TRUE | 2026-07-03T01:33:53.9043712+00:00 | 2026-07-03T09:33:53.9043712+08:00 | #83057 - MTP: 6hrs - TRAIN LOADOUT: MTP FINES | 1.0 | TRUE |  | 2027-03-17T11:00:00+00:00 | 2027-03-17T17:00:00+00:00 | 2027-03-17T19:00:00+08:00 | 2027-03-18T01:00:00+08:00 |  |  |  |  | 6.00 | MTPRC42 Install/remove Camera in slew |  |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "85e100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPRC42", "name": "Reclaimer: MTP 42", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
76231 | 2026-02-25T05:11:52.5193288+00:00 | 2026-02-25T13:11:52.5193288+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-02-26T08:16:12.5849958+00:00 | 2026-02-26T16:16:12.5849958+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 289823 | TRUE | TRUE | 2026-02-26T08:16:12.5849958+00:00 | 2026-02-26T16:16:12.5849958+08:00 | #76231 - WTS: 216hrs - CRUSHER - PRIMARY: WTS2 04 | 1.0 | TRUE |  | 2027-12-04T11:00:00+00:00 | 2027-12-13T11:00:00+00:00 | 2027-12-04T19:00:00+08:00 | 2027-12-13T19:00:00+08:00 |  |  |  |  | 216.00 | WTS2 04 |  |  | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
57502 | 2023-08-15T06:55:41+00:00 | 2023-08-15T14:55:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000002e5", "displayName": "Jason Machura"} | 2026-07-03T01:33:54.110232+00:00 | 2026-07-03T09:33:54.110232+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329314 | TRUE | TRUE | 2026-07-03T01:33:54.110232+00:00 | 2026-07-03T09:33:54.110232+08:00 | #57502 - MTP: 120hrs - PLANT: MTP LOW GRADE | 6.0 | TRUE |  | 2027-03-05T16:00:00+00:00 | 2027-03-10T16:00:00+00:00 | 2027-03-06T00:00:00+08:00 | 2027-03-11T00:00:00+08:00 |  |  |  |  | 120.00 | Low Grade Down due to 85C being down Additional Info: Downtime Only not maintenance no labour required DO NOT DELETE COMMENT | Need to add in MTPST82 Stacker: MTP 82 Lump |  | [{"equipmentGUID": "8d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTLG", "name": "Plant: MTP Low Grade", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "bb28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST82", "name": "Stacker: MTP 82 Lump", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
57386 | 2023-08-11T01:50:34+00:00 | 2023-08-11T09:50:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000002e5", "displayName": "Jason Machura"} | 2026-02-27T05:14:18.0062966+00:00 | 2026-02-27T13:14:18.0062966+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 289935 | TRUE | TRUE | 2026-02-27T05:14:18.0062966+00:00 | 2026-02-27T13:14:18.0062966+08:00 | #57386 - MTP: 336hrs - CRUSHER - PRIMARY: MTP 02 | 5.1 | FALSE |  | 2027-07-19T13:00:00+00:00 | 2027-08-02T13:00:00+00:00 | 2027-07-19T21:00:00+08:00 | 2027-08-02T21:00:00+08:00 |  |  |  |  | 336.00 | PC2 |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
57510 | 2023-08-15T07:02:39+00:00 | 2023-08-15T15:02:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000002e5", "displayName": "Jason Machura"} | 2026-03-03T06:27:03.9962616+00:00 | 2026-03-03T14:27:03.9962616+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 290276 | TRUE | TRUE | 2026-03-03T06:27:03.9962616+00:00 | 2026-03-03T14:27:03.9962616+08:00 | #57510 - MTP: 150hrs - PLANT: MTP LOW GRADE | 5.0 | TRUE |  | 2027-09-03T16:00:00+00:00 | 2027-09-09T22:00:00+00:00 | 2027-09-04T00:00:00+08:00 | 2027-09-10T06:00:00+08:00 |  |  |  |  | 150.00 | Low Grade Down due to 85C being down Additional Info: Downtime Only not maintenance no labour required DO NOT DELETE COMMENT | To Aline with IAM |  | [{"equipmentGUID": "8d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTLG", "name": "Plant: MTP Low Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44937 | 2021-11-30T08:31:40+00:00 | 2021-11-30T16:31:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322231+00:00 | 2026-06-29T13:36:11.9322231+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328752 | TRUE | TRUE | 2026-06-29T05:36:11.9322231+00:00 | 2026-06-29T13:36:11.9322231+08:00 | #44937 - MTP: 66hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 02 | 9.0 | TRUE |  | 2027-12-10T11:00:00+00:00 | 2027-12-13T05:00:00+00:00 | 2027-12-10T19:00:00+08:00 | 2027-12-13T13:00:00+08:00 |  |  |  |  | 66.00 | MTP TLO2 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "08b4c95e-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT02", "name": "Train Loadout: MTP Loadout Tunnel 02", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44931 | 2021-11-30T08:23:43+00:00 | 2021-11-30T16:23:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322238+00:00 | 2026-06-29T13:36:11.9322238+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328753 | TRUE | TRUE | 2026-06-29T05:36:11.9322238+00:00 | 2026-06-29T13:36:11.9322238+08:00 | #44931 - MTP: 168hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 01 | 9.0 | TRUE |  | 2027-12-08T11:00:00+00:00 | 2027-12-15T11:00:00+00:00 | 2027-12-08T19:00:00+08:00 | 2027-12-15T19:00:00+08:00 |  |  |  |  | 168.00 | MTP TLO1 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "b5d7495f-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT01", "name": "Train Loadout: MTP Loadout Tunnel 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44935 | 2021-11-30T08:29:19+00:00 | 2021-11-30T16:29:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322244+00:00 | 2026-06-29T13:36:11.9322244+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328754 | TRUE | TRUE | 2026-06-29T05:36:11.9322244+00:00 | 2026-06-29T13:36:11.9322244+08:00 | #44935 - MTP: 168hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 02 | 10.0 | TRUE |  | 2027-09-04T11:00:00+00:00 | 2027-09-11T11:00:00+00:00 | 2027-09-04T19:00:00+08:00 | 2027-09-11T19:00:00+08:00 |  |  |  |  | 168.00 | MTP TLO2 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "08b4c95e-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT02", "name": "Train Loadout: MTP Loadout Tunnel 02", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
54643 | 2023-03-16T09:13:00+00:00 | 2023-03-16T17:13:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322251+00:00 | 2026-06-29T13:36:11.9322251+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328755 | TRUE | TRUE | 2026-06-29T05:36:11.9322251+00:00 | 2026-06-29T13:36:11.9322251+08:00 | #54643 - MTP: 168hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 01 | 6.0 | TRUE |  | 2027-09-08T11:00:00+00:00 | 2027-09-15T11:00:00+00:00 | 2027-09-08T19:00:00+08:00 | 2027-09-15T19:00:00+08:00 |  |  |  |  | 168.00 | MTP TLO1 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "b5d7495f-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT01", "name": "Train Loadout: MTP Loadout Tunnel 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44933 | 2021-11-30T08:27:27+00:00 | 2021-11-30T16:27:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322261+00:00 | 2026-06-29T13:36:11.9322261+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328756 | TRUE | TRUE | 2026-06-29T05:36:11.9322261+00:00 | 2026-06-29T13:36:11.9322261+08:00 | #44933 - MTP: 66hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 02 | 10.0 | TRUE |  | 2027-06-11T11:00:00+00:00 | 2027-06-14T05:00:00+00:00 | 2027-06-11T19:00:00+08:00 | 2027-06-14T13:00:00+08:00 |  |  |  |  | 66.00 | MTP TLO2 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "08b4c95e-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT02", "name": "Train Loadout: MTP Loadout Tunnel 02", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44928 | 2021-11-30T08:21:42+00:00 | 2021-11-30T16:21:42+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322266+00:00 | 2026-06-29T13:36:11.9322266+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328757 | TRUE | TRUE | 2026-06-29T05:36:11.9322266+00:00 | 2026-06-29T13:36:11.9322266+08:00 | #44928 - MTP: 168hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 01 | 8.0 | TRUE |  | 2027-06-09T11:00:00+00:00 | 2027-06-16T11:00:00+00:00 | 2027-06-09T19:00:00+08:00 | 2027-06-16T19:00:00+08:00 |  |  |  |  | 168.00 | MTP TLO1 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "b5d7495f-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT01", "name": "Train Loadout: MTP Loadout Tunnel 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
42175 | 2021-07-06T02:13:18+00:00 | 2021-07-06T10:13:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322274+00:00 | 2026-06-29T13:36:11.9322274+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328758 | TRUE | TRUE | 2026-06-29T05:36:11.9322274+00:00 | 2026-06-29T13:36:11.9322274+08:00 | #42175 - MTP: 66hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 02 | 9.0 | TRUE |  | 2027-03-12T11:00:00+00:00 | 2027-03-15T05:00:00+00:00 | 2027-03-12T19:00:00+08:00 | 2027-03-15T13:00:00+08:00 |  |  |  |  | 66.00 | MTP TLO2 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "08b4c95e-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT02", "name": "Train Loadout: MTP Loadout Tunnel 02", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
41724 | 2021-05-25T06:33:47+00:00 | 2021-05-25T14:33:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-29T05:36:11.9322282+00:00 | 2026-06-29T13:36:11.9322282+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 328759 | TRUE | TRUE | 2026-06-29T05:36:11.9322282+00:00 | 2026-06-29T13:36:11.9322282+08:00 | #41724 - MTP: 168hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 01 | 13.0 | TRUE |  | 2027-03-10T11:00:00+00:00 | 2027-03-17T11:00:00+00:00 | 2027-03-10T19:00:00+08:00 | 2027-03-17T19:00:00+08:00 |  |  |  |  | 168.00 | MTP TLO1 | This is to aline with the TLO Plan |  | [{"equipmentGUID": "b5d7495f-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT01", "name": "Train Loadout: MTP Loadout Tunnel 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
47638 | 2022-08-17T06:35:34+00:00 | 2022-08-17T14:35:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.3944544+00:00 | 2026-06-11T15:00:59.3944544+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327778 | TRUE | TRUE | 2026-06-11T07:00:59.3944544+00:00 | 2026-06-11T15:00:59.3944544+08:00 | #47638 - MTP: 168hrs - PLANT: MTP HIGH GRADE | 8.1 | TRUE |  | 2027-12-06T11:00:00+00:00 | 2027-12-13T11:00:00+00:00 | 2027-12-06T19:00:00+08:00 | 2027-12-13T19:00:00+08:00 |  |  |  |  | 168.00 | High Grade Maintenance |  | 47638 | [{"equipmentGUID": "8617ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTHG", "name": "Plant: MTP High Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44946 | 2021-11-30T09:20:52+00:00 | 2021-11-30T17:20:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.3944747+00:00 | 2026-06-11T15:00:59.3944747+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327780 | TRUE | TRUE | 2026-06-11T07:00:59.3944747+00:00 | 2026-06-11T15:00:59.3944747+08:00 | #44946 - MTP: 336hrs - PLANT: MTP HIGH GRADE | 11.2 | TRUE |  | 2027-08-30T11:00:00+00:00 | 2027-09-13T11:00:00+00:00 | 2027-08-30T19:00:00+08:00 | 2027-09-13T19:00:00+08:00 |  |  |  |  | 336.00 | MTP HGP |  | 44946 | [{"equipmentGUID": "8617ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTHG", "name": "Plant: MTP High Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "24713643-0a19-4bcb-9af5-00656909b2b4", "emailAddress": "Rene.Barrett@riotinto.com", "displayName": "Barrett, Rene (STP)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}, {"code": "P-0508316", "name": "TP HG Screening House Strengthening", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44945 | 2021-11-30T09:20:19+00:00 | 2021-11-30T17:20:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.3945366+00:00 | 2026-06-11T15:00:59.3945366+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327781 | TRUE | TRUE | 2026-06-11T07:00:59.3945366+00:00 | 2026-06-11T15:00:59.3945366+08:00 | #44945 - MTP: 168hrs - PLANT: MTP HIGH GRADE | 10.1 | TRUE |  | 2027-06-07T11:00:00+00:00 | 2027-06-14T11:00:00+00:00 | 2027-06-07T19:00:00+08:00 | 2027-06-14T19:00:00+08:00 |  |  |  |  | 168.00 | High Grade Maintenance |  | 44945 | [{"equipmentGUID": "8617ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTHG", "name": "Plant: MTP High Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}, {"code": "P-0508316", "name": "TP HG Screening House Strengthening", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44956 | 2021-12-01T00:41:46+00:00 | 2021-12-01T08:41:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.394553+00:00 | 2026-06-11T15:00:59.394553+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327782 | TRUE | TRUE | 2026-06-11T07:00:59.394553+00:00 | 2026-06-11T15:00:59.394553+08:00 | #44956 - MTP: 264hrs - PLANT: MTP LOW GRADE | 10.1 | TRUE |  | 2027-05-04T11:00:00+00:00 | 2027-05-15T11:00:00+00:00 | 2027-05-04T19:00:00+08:00 | 2027-05-15T19:00:00+08:00 |  |  |  |  | 264.00 | Thickener Maintenance |  | 44956 | [{"equipmentGUID": "8d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTLG", "name": "Plant: MTP Low Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83680, "shutVersionId": 331384, "title": "#83680 - MTP: 121hrs - W&S MOD 5 POSTSHUT TRIPLE CHUTE C/O", "startDatetimeUTC": "2027-05-15T11:00:00+00:00", "endDatetimeUTC": "2027-05-20T12:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 83679, "shutVersionId": 331385, "title": "#83679 - MTP: 135hrs - W&S MOD 5 PRESHUT TRIPLE CHUTE C/O", "startDatetimeUTC": "2027-04-28T20:00:00+00:00", "endDatetimeUTC": "2027-05-04T11:00:00+00:00"}}] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "264"}, {"code": "P-0507684", "name": "TP Concentrator COS Tunnel Dust Mitigation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "264"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44944 | 2021-11-30T09:19:28+00:00 | 2021-11-30T17:19:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.3945635+00:00 | 2026-06-11T15:00:59.3945635+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327783 | TRUE | TRUE | 2026-06-11T07:00:59.3945635+00:00 | 2026-06-11T15:00:59.3945635+08:00 | #44944 - MTP: 336hrs - PLANT: MTP HIGH GRADE | 12.1 | TRUE |  | 2027-03-01T11:00:00+00:00 | 2027-03-15T11:00:00+00:00 | 2027-03-01T19:00:00+08:00 | 2027-03-15T19:00:00+08:00 |  |  |  |  | 336.00 | High Grade Maintenance |  | 44944 | [{"equipmentGUID": "8617ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTHG", "name": "Plant: MTP High Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}, {"code": "P-0508316", "name": "TP HG Screening House Strengthening", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
42165 | 2021-07-06T01:29:47+00:00 | 2021-07-06T09:29:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T07:00:59.3945732+00:00 | 2026-06-11T15:00:59.3945732+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 327784 | TRUE | TRUE | 2026-06-11T07:00:59.3945732+00:00 | 2026-06-11T15:00:59.3945732+08:00 | #42165 - MTP: 168hrs - PLANT: MTP HIGH GRADE | 12.1 | TRUE |  | 2026-11-30T11:00:00+00:00 | 2026-12-07T11:00:00+00:00 | 2026-11-30T19:00:00+08:00 | 2026-12-07T19:00:00+08:00 |  |  |  |  | 168.00 | High Grade Maintenance |  | 42165 | [{"equipmentGUID": "8617ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTHG", "name": "Plant: MTP High Grade", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}, {"code": "P-0508316", "name": "TP HG Screening House Strengthening", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
54730 | 2023-03-24T05:39:38+00:00 | 2023-03-24T13:39:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T00:35:34.7604268+00:00 | 2025-10-16T08:35:34.7604268+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 257981 | TRUE | TRUE | 2025-10-16T00:35:34.7604268+00:00 | 2025-10-16T08:35:34.7604268+08:00 | #54730 - WTS: 240hrs - CRUSHER - PRIMARY: WTS1 03 | 5.0 | TRUE |  | 2027-11-01T11:00:00+00:00 | 2027-11-11T11:00:00+00:00 | 2027-11-01T19:00:00+08:00 | 2027-11-11T19:00:00+08:00 |  |  |  |  | 240.00 | WTS PC3 aligned with LG shut | Moved to a line to the LG |  | [{"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
44936 | 2021-11-30T08:31:00+00:00 | 2021-11-30T16:31:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T00:35:36.8714624+00:00 | 2025-10-16T08:35:36.8714624+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 257984 | TRUE | TRUE | 2025-10-16T00:35:36.8714624+00:00 | 2025-10-16T08:35:36.8714624+08:00 | #44936 - MTP: 168hrs - TRAIN LOADOUT: MTP FINES | 7.0 | TRUE |  | 2027-12-08T11:00:00+00:00 | 2027-12-15T11:00:00+00:00 | 2027-12-08T19:00:00+08:00 | 2027-12-15T19:00:00+08:00 |  |  |  |  | 168.00 | Fines TLO shut | Change to aline with the new IAM |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44957 | 2021-12-01T00:42:34+00:00 | 2021-12-01T08:42:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T01:33:52.8464889+00:00 | 2026-07-03T09:33:52.8464889+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 329308 | TRUE | TRUE | 2026-07-03T01:33:52.8464889+00:00 | 2026-07-03T09:33:52.8464889+08:00 | #44957 - MTP: 744hrs - PLANT: MTP LOW GRADE | 12.0 | TRUE |  | 2027-10-29T11:00:00+00:00 | 2027-11-29T11:00:00+00:00 | 2027-10-29T19:00:00+08:00 | 2027-11-29T19:00:00+08:00 |  |  |  |  | 744.00 | Thickener Maintenance C/O Drive and Electrical Upgrade | Thickener Maintenance C/O Drive and Electrical Upgrade | 44957 | [{"equipmentGUID": "8d17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPPLTLG", "name": "Plant: MTP Low Grade", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "bb28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST82", "name": "Stacker: MTP 82 Lump", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "568fa2e7-1416-472c-9428-feb5267da8cb", "emailAddress": "Cobus.Viljoen2@riotinto.com", "displayName": "Viljoen, Cobus (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "24713643-0a19-4bcb-9af5-00656909b2b4", "emailAddress": "Rene.Barrett@riotinto.com", "displayName": "Barrett, Rene (STP)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "aba64ce2-a00e-4d22-82f6-2ff8406645df", "emailAddress": "Valerie.Pereira@riotinto.com", "displayName": "Pereira, Valerie (RTIO)"}}] | [] | [] | [] | [{"code": "P-0504885", "name": "TP SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "504"}, {"code": "P-0507684", "name": "TP Concentrator COS Tunnel Dust Mitigation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "504"}] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
47655 | 2022-08-17T07:52:49+00:00 | 2022-08-17T15:52:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-02-26T08:16:13.2558341+00:00 | 2026-02-26T16:16:13.2558341+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 289824 | TRUE | TRUE | 2026-02-26T08:16:13.2558341+00:00 | 2026-02-26T16:16:13.2558341+08:00 | #47655 - WTS: 168hrs - CONVEYOR: WTS1 OVERLAND & CRUSHER - PRIMARY: WTS1 03 | 9.0 | TRUE |  | 2027-12-06T11:00:00+00:00 | 2027-12-13T11:00:00+00:00 | 2027-12-06T19:00:00+08:00 | 2027-12-13T19:00:00+08:00 |  |  |  |  | 168.00 | WTS1 PLT PC4 | fixing the data |  | [{"equipmentGUID": "185e242f-6f9d-ee11-a847-000d3acacefd", "code": "WTS1CVOLCV", "name": "Conveyor: WTS1 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
47893 | 2022-08-29T08:30:03+00:00 | 2022-08-29T16:30:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-02-27T06:38:13.3373025+00:00 | 2026-02-27T14:38:13.3373025+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 290094 | TRUE | TRUE | 2026-02-27T06:38:13.3373025+00:00 | 2026-02-27T14:38:13.3373025+08:00 | #47893 - MTP: 150hrs - CONVEYOR: MTP 85C | 11.0 | TRUE |  | 2027-09-03T16:00:00+00:00 | 2027-09-09T22:00:00+00:00 | 2027-09-04T00:00:00+08:00 | 2027-09-10T06:00:00+08:00 |  |  |  |  | 150.00 | 85C Maintenance | To Aline with IAM |  | [{"equipmentGUID": "e867fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV85C", "name": "Conveyor: MTP 85C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
47892 | 2022-08-29T08:29:17+00:00 | 2022-08-29T16:29:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-03T05:16:33.2365044+00:00 | 2026-03-03T13:16:33.2365044+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 290199 | TRUE | TRUE | 2026-03-03T05:16:33.2365044+00:00 | 2026-03-03T13:16:33.2365044+08:00 | #47892 - MTP: 120hrs - CONVEYOR: MTP 85C | 10.0 | TRUE |  | 2027-03-05T16:00:00+00:00 | 2027-03-10T16:00:00+00:00 | 2027-03-06T00:00:00+08:00 | 2027-03-11T00:00:00+08:00 |  |  |  |  | 120.00 | 85C Maintenance | To Aline with IAM |  | [{"equipmentGUID": "e867fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV85C", "name": "Conveyor: MTP 85C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
56799 | 2023-08-04T03:12:27+00:00 | 2023-08-04T11:12:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-02-27T05:14:17.5981854+00:00 | 2026-02-27T13:14:17.5981854+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 289934 | TRUE | TRUE | 2026-02-27T05:14:17.5981854+00:00 | 2026-02-27T13:14:17.5981854+08:00 | #56799 - MTP: 168hrs - CRUSHER - PRIMARY: MTP 02 | 7.2 | FALSE |  | 2027-01-18T13:00:00+00:00 | 2027-01-25T13:00:00+00:00 | 2027-01-18T21:00:00+08:00 | 2027-01-25T21:00:00+08:00 |  |  |  |  | 168.00 | PC2 |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
56800 | 2023-08-04T03:14:16+00:00 | 2023-08-04T11:14:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-02-27T05:14:18.0654328+00:00 | 2026-02-27T13:14:18.0654328+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 289936 | TRUE | TRUE | 2026-02-27T05:14:18.0654328+00:00 | 2026-02-27T13:14:18.0654328+08:00 | #56800 - MTP: 168hrs - CRUSHER - PRIMARY: MTP 02 | 7.1 | FALSE |  | 2028-01-17T13:00:00+00:00 | 2028-01-24T13:00:00+00:00 | 2028-01-17T21:00:00+08:00 | 2028-01-24T21:00:00+08:00 |  |  |  |  | 168.00 | PC2 |  |  | [{"equipmentGUID": "6ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPPCS02", "name": "Crusher - Primary: MTP 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
44932 | 2021-11-30T08:25:34+00:00 | 2021-11-30T16:25:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-20T00:43:27.7616628+00:00 | 2025-10-20T08:43:27.7616628+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 260769 | TRUE | TRUE | 2025-10-20T00:43:27.7616628+00:00 | 2025-10-20T08:43:27.7616628+08:00 | #44932 - MTP: 168hrs - TRAIN LOADOUT: MTP FINES | 9.0 | TRUE |  | 2027-06-09T11:00:00+00:00 | 2027-06-16T11:00:00+00:00 | 2027-06-09T19:00:00+08:00 | 2027-06-16T19:00:00+08:00 |  |  |  |  | 168.00 | Fines TLO shut. | Taking out the Tunnel 1 |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | MTP | Australia/Perth
54729 | 2023-03-24T05:39:04+00:00 | 2023-03-24T13:39:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T00:35:23.8012828+00:00 | 2025-10-16T08:35:23.8012828+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 257966 | TRUE | TRUE | 2025-10-16T00:35:23.8012828+00:00 | 2025-10-16T08:35:23.8012828+08:00 | #54729 - WTS: 240hrs - CRUSHER - PRIMARY: WTS1 03 | 5.0 | TRUE |  | 2027-05-04T11:00:00+00:00 | 2027-05-14T11:00:00+00:00 | 2027-05-04T19:00:00+08:00 | 2027-05-14T19:00:00+08:00 |  |  |  |  | 240.00 | WTS PC3 aligned with LG shut | To a line with LG |  | [{"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
47654 | 2022-08-17T07:52:10+00:00 | 2022-08-17T15:52:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-16T00:35:25.9597689+00:00 | 2025-10-16T08:35:25.9597689+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | {"name": "Fixed Plant"} | 257969 | TRUE | TRUE | 2025-10-16T00:35:25.9597689+00:00 | 2025-10-16T08:35:25.9597689+08:00 | #47654 - WTS: 168hrs - CONVEYOR: WTS1 OVERLAND & CRUSHER - PRIMARY: WTS1 03 | 9.0 | TRUE |  | 2027-06-07T11:00:00+00:00 | 2027-06-14T11:00:00+00:00 | 2027-06-07T19:00:00+08:00 | 2027-06-14T19:00:00+08:00 |  |  |  |  | 168.00 | WTS1 PLT PC4 | CS04 has it own shut |  | [{"equipmentGUID": "185e242f-6f9d-ee11-a847-000d3acacefd", "code": "WTS1CVOLCV", "name": "Conveyor: WTS1 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d4c9aa3-f543-4ea0-87e0-36bb5fb7265a", "emailAddress": "David.Sturzaker@riotinto.com", "displayName": "Sturzaker, David (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | af6a772b-ff36-45cc-943b-b4157ff73947 | Machura, Jason (RTIO) | Scheduled | WTS | Australia/Perth
83541 | 2026-07-21T05:39:39.8618753+00:00 | 2026-07-21T13:39:39.8618753+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | 2026-09-03T04:27:37.7078374+00:00 | 2026-09-03T12:27:37.7078374+08:00 | {"principalGUID": "fd46ebc7-e750-4909-bd6d-b55966e60e01", "displayName": "Venter, Tahlea (RTIO)"} | {"name": "System"} | 333120 | TRUE | TRUE | 2026-09-03T04:27:37.7078374+00:00 | 2026-09-03T12:27:37.7078374+08:00 | #83541 - SYSTEM: 9hrs - TW: CENTRAL CORRIDOR | 2.0 | TRUE |  | 2026-11-30T23:00:00+00:00 | 2026-12-01T08:00:00+00:00 | 2026-12-01T07:00:00+08:00 | 2026-12-01T16:00:00+08:00 |  |  |  |  | 9.00 | 10hr Dual Track Closure Emu to Gull (IAM50 & IAM01 & IAM02 & IAM03 & IAM04 & IAM05 & IAM06)) MLTP 89.2km Level Crossing GCP Upgrade - D2/5 | As per conversation with Sus Cap, reducing from 10 to 9 hours to account for travel and pre-start and to provide additional rail capacity back to the system in a rail constraint week. |  | [{"equipmentGUID": "", "code": "TRACK WORK IMPACTING CENTRAL CORRIDOR", "name": "TW: Central Corridor", "assetClass": {"name": "Rail Network"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "emailAddress": "Bradley.Gallagher@riotinto.com", "displayName": "Bradley Gallagher"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "649e69a1-9850-4527-be76-b6ff02b32dd7", "emailAddress": "Tori.Antonovich@riotinto.com", "displayName": "Antonovich, Tori (RTIO)"}}] | [{"name": "PDO"}, {"name": "MDO"}, {"name": "WAN"}, {"name": "YAN"}, {"name": "MTP"}, {"name": "HD1"}, {"name": "BM4"}, {"name": "HD4"}, {"name": "CLB"}, {"name": "NBWT"}, {"name": "PPT"}, {"name": "BM2"}, {"name": "CLA"}, {"name": "EII"}, {"name": "GDI"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | fd46ebc7-e750-4909-bd6d-b55966e60e01 | Venter, Tahlea (RTIO) | Site Constraint |  | Australia/Perth
83542 | 2026-07-21T05:39:39.8620202+00:00 | 2026-07-21T13:39:39.8620202+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | 2026-09-03T04:28:38.1250239+00:00 | 2026-09-03T12:28:38.1250239+08:00 | {"principalGUID": "fd46ebc7-e750-4909-bd6d-b55966e60e01", "displayName": "Venter, Tahlea (RTIO)"} | {"name": "System"} | 333121 | TRUE | TRUE | 2026-09-03T04:28:38.1250239+00:00 | 2026-09-03T12:28:38.1250239+08:00 | #83542 - SYSTEM: 9hrs - TW: CENTRAL CORRIDOR | 2.0 | TRUE |  | 2026-12-01T23:00:00+00:00 | 2026-12-02T08:00:00+00:00 | 2026-12-02T07:00:00+08:00 | 2026-12-02T16:00:00+08:00 |  |  |  |  | 9.00 | 10hr Dual Track Closure Emu to Gull (IAM50 & IAM01 & IAM02 & IAM03 & IAM04 & IAM05 & IAM06)) MLTP 89.2km Level Crossing GCP Upgrade - D3/5 | As per conversation with Sus Cap, reducing from 10 to 9 hours to account for travel and pre-start and to provide additional rail capacity back to the system in a rail constraint week. |  | [{"equipmentGUID": "", "code": "TRACK WORK IMPACTING CENTRAL CORRIDOR", "name": "TW: Central Corridor", "assetClass": {"name": "Rail Network"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "emailAddress": "Bradley.Gallagher@riotinto.com", "displayName": "Bradley Gallagher"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "649e69a1-9850-4527-be76-b6ff02b32dd7", "emailAddress": "Tori.Antonovich@riotinto.com", "displayName": "Antonovich, Tori (RTIO)"}}] | [{"name": "PDO"}, {"name": "MDO"}, {"name": "WAN"}, {"name": "YAN"}, {"name": "MTP"}, {"name": "HD1"}, {"name": "BM4"}, {"name": "HD4"}, {"name": "CLB"}, {"name": "NBWT"}, {"name": "PPT"}, {"name": "BM2"}, {"name": "CLA"}, {"name": "EII"}, {"name": "GDI"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | fd46ebc7-e750-4909-bd6d-b55966e60e01 | Venter, Tahlea (RTIO) | Site Constraint |  | Australia/Perth
83543 | 2026-07-21T05:39:39.8621596+00:00 | 2026-07-21T13:39:39.8621596+08:00 | {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "displayName": "Gallagher, Bradley (RTIO)"} | 2026-09-03T04:29:19.5528512+00:00 | 2026-09-03T12:29:19.5528512+08:00 | {"principalGUID": "fd46ebc7-e750-4909-bd6d-b55966e60e01", "displayName": "Venter, Tahlea (RTIO)"} | {"name": "System"} | 333122 | TRUE | TRUE | 2026-09-03T04:29:19.5528512+00:00 | 2026-09-03T12:29:19.5528512+08:00 | #83543 - SYSTEM: 9hrs - TW: CENTRAL CORRIDOR | 2.0 | TRUE |  | 2026-12-02T23:00:00+00:00 | 2026-12-03T08:00:00+00:00 | 2026-12-03T07:00:00+08:00 | 2026-12-03T16:00:00+08:00 |  |  |  |  | 9.00 | 10hr Dual Track Closure Emu to Gull (IAM50 & IAM01 & IAM02 & IAM03 & IAM04 & IAM05 & IAM06)) MLTP 89.2km Level Crossing GCP Upgrade - D4/5 | As per conversation with Sus Cap, reducing from 10 to 9 hours to account for travel and pre-start and to provide additional rail capacity back to the system in a rail constraint week. |  | [{"equipmentGUID": "", "code": "TRACK WORK IMPACTING CENTRAL CORRIDOR", "name": "TW: Central Corridor", "assetClass": {"name": "Rail Network"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "e66894fa-d615-4ac5-8967-f24780e04d56", "emailAddress": "Bradley.Gallagher@riotinto.com", "displayName": "Bradley Gallagher"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "649e69a1-9850-4527-be76-b6ff02b32dd7", "emailAddress": "Tori.Antonovich@riotinto.com", "displayName": "Antonovich, Tori (RTIO)"}}] | [{"name": "PDO"}, {"name": "MDO"}, {"name": "WAN"}, {"name": "YAN"}, {"name": "MTP"}, {"name": "HD1"}, {"name": "BM4"}, {"name": "HD4"}, {"name": "CLB"}, {"name": "NBWT"}, {"name": "PPT"}, {"name": "BM2"}, {"name": "CLA"}, {"name": "EII"}, {"name": "GDI"}] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | fd46ebc7-e750-4909-bd6d-b55966e60e01 | Venter, Tahlea (RTIO) | Site Constraint |  | Australia/Perth
68205 | 2025-06-30T06:51:33.5018643+00:00 | 2025-06-30T14:51:33.5018643+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2025-06-30T06:51:33.5018643+00:00 | 2025-06-30T14:51:33.5018643+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 241190 | TRUE | TRUE | 2025-06-30T06:51:33.5018643+00:00 | 2025-06-30T14:51:33.5018643+08:00 | #68205 - YAN: 250hrs - 08H345 CAT D10T2 TRACK DOZER | 1.0 | FALSE |  | 2026-12-01T22:00:00+00:00 | 2026-12-12T08:00:00+00:00 | 2026-12-02T06:00:00+08:00 | 2026-12-12T16:00:00+08:00 |  |  |  |  | 250.00 | Engine, Equaliser Bar, Track Frame, Final Drive |  |  | [{"equipmentGUID": "f0ece8bf-7c7b-ee11-a846-000d3acacefd", "code": "08H345", "name": "08H345 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "c44eb75e-8a1f-448e-9911-1320ee0b0575", "emailAddress": "Ashleigh.Royer@riotinto.com", "displayName": "Royer, Ashleigh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83316 | 2026-07-02T05:06:19.4761275+00:00 | 2026-07-02T13:06:19.4761275+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.4761275+00:00 | 2026-07-02T13:06:19.4761275+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329142 | TRUE | TRUE | 2026-07-02T05:06:19.4761275+00:00 | 2026-07-02T13:06:19.4761275+08:00 | #83316 - WAN: 120hrs - 06R267 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-01-10T22:00:00+00:00 | 2027-01-15T22:00:00+00:00 | 2027-01-11T06:00:00+08:00 | 2027-01-16T06:00:00+08:00 |  |  |  |  | 120.00 | 06R267 C/O Engine Module |  | S06R267 | [{"equipmentGUID": "bd13f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R267", "name": "06R267 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83319 | 2026-07-02T05:06:19.5586315+00:00 | 2026-07-02T13:06:19.5586315+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5586315+00:00 | 2026-07-02T13:06:19.5586315+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329145 | TRUE | TRUE | 2026-07-02T05:06:19.5586315+00:00 | 2026-07-02T13:06:19.5586315+08:00 | #83319 - WAN: 120hrs - 06H789 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-02-07T22:00:00+00:00 | 2027-02-12T22:00:00+00:00 | 2027-02-08T06:00:00+08:00 | 2027-02-13T06:00:00+08:00 |  |  |  |  | 120.00 | 06H789 C/O Engine Module |  | S06H789 | [{"equipmentGUID": "ccd500c0-7c7b-ee11-a846-000d3acacefd", "code": "06H789", "name": "06H789 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83325 | 2026-07-02T05:06:19.5592613+00:00 | 2026-07-02T13:06:19.5592613+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5592613+00:00 | 2026-07-02T13:06:19.5592613+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329151 | TRUE | TRUE | 2026-07-02T05:06:19.5592613+00:00 | 2026-07-02T13:06:19.5592613+08:00 | #83325 - MTP: 120hrs - 06H33 KOMATSU 830E-17AC HAUL TRUCK | 1.0 | FALSE |  | 2027-04-25T22:00:00+00:00 | 2027-04-30T22:00:00+00:00 | 2027-04-26T06:00:00+08:00 | 2027-05-01T06:00:00+08:00 |  |  |  |  | 120.00 | 06H33 C/O Engine Module |  | S06H33 | [{"equipmentGUID": "83de00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H33", "name": "06H33 Komatsu 830E-17AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | MTP | Australia/Perth |  | Site Team
83327 | 2026-07-02T05:06:19.5594614+00:00 | 2026-07-02T13:06:19.5594614+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5594614+00:00 | 2026-07-02T13:06:19.5594614+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329153 | TRUE | TRUE | 2026-07-02T05:06:19.5594614+00:00 | 2026-07-02T13:06:19.5594614+08:00 | #83327 - YAN: 120hrs - 06H911 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-05-09T22:00:00+00:00 | 2027-05-14T22:00:00+00:00 | 2027-05-10T06:00:00+08:00 | 2027-05-15T06:00:00+08:00 |  |  |  |  | 120.00 | 06H911 C/O Engine Module |  | S06H911 | [{"equipmentGUID": "76d400c0-7c7b-ee11-a846-000d3acacefd", "code": "06H911", "name": "06H911 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83341 | 2026-07-02T05:06:19.5610619+00:00 | 2026-07-02T13:06:19.5610619+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5610619+00:00 | 2026-07-02T13:06:19.5610619+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329167 | TRUE | TRUE | 2026-07-02T05:06:19.5610619+00:00 | 2026-07-02T13:06:19.5610619+08:00 | #83341 - WAN: 120hrs - 06R914 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-09-05T22:00:00+00:00 | 2027-09-10T22:00:00+00:00 | 2027-09-06T06:00:00+08:00 | 2027-09-11T06:00:00+08:00 |  |  |  |  | 120.00 | 06R914 C/O Engine Module |  | S06R914 | [{"equipmentGUID": "0fe1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06R914", "name": "06R914 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | WAN | Australia/Perth |  | Site Team
83353 | 2026-07-02T05:06:19.5624641+00:00 | 2026-07-02T13:06:19.5624641+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5624641+00:00 | 2026-07-02T13:06:19.5624641+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329179 | TRUE | TRUE | 2026-07-02T05:06:19.5624641+00:00 | 2026-07-02T13:06:19.5624641+08:00 | #83353 - BM4: 120hrs - 06H438 KOMATSU 830E-5AT HAUL TRUCK | 1.0 | FALSE |  | 2027-11-14T22:00:00+00:00 | 2027-11-19T22:00:00+00:00 | 2027-11-15T06:00:00+08:00 | 2027-11-20T06:00:00+08:00 |  |  |  |  | 120.00 | 06H438 C/O Engine Module |  | S06H438 | [{"equipmentGUID": "9e36f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H438", "name": "06H438 Komatsu 830E-5AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | BM4 | Australia/Perth |  | Site Team
83355 | 2026-07-02T05:06:19.5626604+00:00 | 2026-07-02T13:06:19.5626604+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5626604+00:00 | 2026-07-02T13:06:19.5626604+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329181 | TRUE | TRUE | 2026-07-02T05:06:19.5626604+00:00 | 2026-07-02T13:06:19.5626604+08:00 | #83355 - NBWT: 120hrs - 06H482 KOMATSU 830E-1AT HAUL TRUCK | 1.0 | FALSE |  | 2027-12-05T22:00:00+00:00 | 2027-12-10T22:00:00+00:00 | 2027-12-06T06:00:00+08:00 | 2027-12-11T06:00:00+08:00 |  |  |  |  | 120.00 | 06H482 C/O Engine Module |  | S06H482 | [{"equipmentGUID": "f71ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H482", "name": "06H482 Komatsu 830E-1AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | NBWT | Australia/Perth |  | Site Team
83356 | 2026-07-02T05:06:19.5627585+00:00 | 2026-07-02T13:06:19.5627585+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5627585+00:00 | 2026-07-02T13:06:19.5627585+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329182 | TRUE | TRUE | 2026-07-02T05:06:19.5627585+00:00 | 2026-07-02T13:06:19.5627585+08:00 | #83356 - YAN: 120hrs - 06H816 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-12-05T22:00:00+00:00 | 2027-12-10T22:00:00+00:00 | 2027-12-06T06:00:00+08:00 | 2027-12-11T06:00:00+08:00 |  |  |  |  | 120.00 | 06H816 C/O Engine Module |  | S06H816 | [{"equipmentGUID": "68dbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H816", "name": "06H816 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | YAN | Australia/Perth |  | Site Team
83358 | 2026-07-02T05:06:19.5629533+00:00 | 2026-07-02T13:06:19.5629533+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-02T05:06:19.5629533+00:00 | 2026-07-02T13:06:19.5629533+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | {"name": "HME"} | 329184 | TRUE | TRUE | 2026-07-02T05:06:19.5629533+00:00 | 2026-07-02T13:06:19.5629533+08:00 | #83358 - HD4: 120hrs - 06H301 KOMATSU 830E-1AC HAUL TRUCK | 1.0 | FALSE |  | 2027-12-19T22:00:00+00:00 | 2027-12-24T22:00:00+00:00 | 2027-12-20T06:00:00+08:00 | 2027-12-25T06:00:00+08:00 |  |  |  |  | 120.00 | 06H301 C/O Engine Module |  | S06H301 | [{"equipmentGUID": "6929f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H301", "name": "06H301 Komatsu 830E-1AC Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "018d7d16-a883-4402-a3fc-0d3cda9bcdbe", "emailAddress": "n.mcilhatton@riotinto.com", "displayName": "Mcilhatton, Neil (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [] | [] | [] | Approved | Create | cf08fc0e-7e97-4396-ad44-b9c93bcc13c7 | Manlod, Rogelio (RTIO) | Scheduled | HD4 | Australia/Perth |  | Site Team
84195 | 2026-10-07T00:15:57.2298549+00:00 | 2026-10-07T08:15:57.2298549+08:00 | {"principalGUID": "f522ddf7-727f-4580-9b02-c52103c43a79", "displayName": "Peacock, Michael (RTIO)"} | 2026-10-07T02:51:48.4400577+00:00 | 2026-10-07T10:51:48.4400577+08:00 | {"principalGUID": "f522ddf7-727f-4580-9b02-c52103c43a79", "displayName": "Peacock, Michael (RTIO)"} | {"name": "Fixed Plant"} | 335395 | TRUE | TRUE | 2026-10-07T02:51:48.4400577+00:00 | 2026-10-07T10:51:48.4400577+08:00 | #84195 - PPT: 43hrs - BIN: PPT 03 SURGE | 1.0 | FALSE |  | 2026-11-29T16:00:00+00:00 | 2026-12-01T11:00:00+00:00 | 2026-11-30T00:00:00+08:00 | 2026-12-01T19:00:00+08:00 |  |  |  |  | 43.00 | Extension of Surge Bin 3 IAM Outage. |  | SPYD2649 | [{"equipmentGUID": "f5f5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBFD304P", "name": "Belt Feeder: PPT 304P", "assetClass": {"name": "Belt Feeder"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | f522ddf7-727f-4580-9b02-c52103c43a79 | Peacock, Michael (RTIO) | Scheduled | PPT | Australia/Perth
71527 | 2025-10-27T07:41:32.1224243+00:00 | 2025-10-27T15:41:32.1224243+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | 2026-10-22T00:53:23.9191059+00:00 | 2026-10-22T08:53:23.9191059+08:00 | {"principalGUID": "91a8bb9d-e600-45b8-8bc0-cac251e935d0", "displayName": "Singe, Aaron (RTIO)"} | {"name": "Fixed Plant"} | 336279 | TRUE | TRUE | 2026-10-22T00:53:23.9191059+00:00 | 2026-10-22T08:53:23.9191059+08:00 | #71527 - PPT: 130hrs - RECLAIMER: PPT 1P | 3.0 | FALSE |  | 2026-12-19T10:00:00+00:00 | 2026-12-24T20:00:00+00:00 | 2026-12-19T18:00:00+08:00 | 2026-12-25T04:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | We would like to start Reclaimer 1P 12 hours after Shiploader 2P, due to the labour availability for the washdown and isolations. This will also assist with labour during commissioning. |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 91a8bb9d-e600-45b8-8bc0-cac251e935d0 | Singe, Aaron (RTIO) | Scheduled | PPT | Australia/Perth
71430 | 2025-10-21T04:39:53.3593494+00:00 | 2025-10-21T12:39:53.3593494+08:00 | {"principalGUID": "525fafd3-f92c-4ab1-8128-03f01d79425d", "displayName": "OBrien, Conor (RTIO)"} | 2026-10-15T07:05:10.9109924+00:00 | 2026-10-15T15:05:10.9109924+08:00 | {"principalGUID": "91a8bb9d-e600-45b8-8bc0-cac251e935d0", "displayName": "Singe, Aaron (RTIO)"} | {"name": "Fixed Plant"} | 336109 | TRUE | TRUE | 2026-10-15T07:05:10.9109924+00:00 | 2026-10-15T15:05:10.9109924+08:00 | #71430 - PPT: 130hrs - BERTH: PPT 03 | 3.0 | FALSE |  | 2026-12-18T22:00:00+00:00 | 2026-12-24T08:00:00+00:00 | 2026-12-19T06:00:00+08:00 | 2026-12-24T16:00:00+08:00 |  |  |  |  | 130.00 | PPt B3- IAM. Created to align with shiploader / BERTH 3 - MARINE STRUCTUAL LIFE EXTENSION WORKS. | We would like to start this outage earlier so that we can avoid the Christmas period where we are limited on labour and accommodation. This will also allow us to fly out people before Christmas day where flights will be an issue. |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "525fafd3-f92c-4ab1-8128-03f01d79425d", "emailAddress": "conor.obrien@riotinto.com", "displayName": "OBrien, Conor (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 91a8bb9d-e600-45b8-8bc0-cac251e935d0 | Singe, Aaron (RTIO) | Scheduled | PPT | Australia/Perth
71429 | 2025-10-21T04:37:21.1552245+00:00 | 2025-10-21T12:37:21.1552245+08:00 | {"principalGUID": "525fafd3-f92c-4ab1-8128-03f01d79425d", "displayName": "OBrien, Conor (RTIO)"} | 2026-10-15T07:05:11.0619602+00:00 | 2026-10-15T15:05:11.0619602+08:00 | {"principalGUID": "91a8bb9d-e600-45b8-8bc0-cac251e935d0", "displayName": "Singe, Aaron (RTIO)"} | {"name": "Fixed Plant"} | 336110 | TRUE | TRUE | 2026-10-15T07:05:11.0619602+00:00 | 2026-10-15T15:05:11.0619602+08:00 | #71429 - PPT: 130hrs - BERTH: PPT 02 | 3.0 | FALSE |  | 2026-12-18T22:00:00+00:00 | 2026-12-24T08:00:00+00:00 | 2026-12-19T06:00:00+08:00 | 2026-12-24T16:00:00+08:00 |  |  |  |  | 130.00 | PPt B2- IAM. Created to align with shiploader | We would like to start this outage earlier so that we can avoid the Christmas period where we are limited on labour and accommodation. This will also allow us to fly out people before Christmas day where flights will be an issue. |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "525fafd3-f92c-4ab1-8128-03f01d79425d", "emailAddress": "conor.obrien@riotinto.com", "displayName": "OBrien, Conor (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 91a8bb9d-e600-45b8-8bc0-cac251e935d0 | Singe, Aaron (RTIO) | Scheduled | PPT | Australia/Perth
70705 | 2025-10-16T01:58:08.0928731+00:00 | 2025-10-16T09:58:08.0928731+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-15T07:05:11.1985821+00:00 | 2026-10-15T15:05:11.1985821+08:00 | {"principalGUID": "91a8bb9d-e600-45b8-8bc0-cac251e935d0", "displayName": "Singe, Aaron (RTIO)"} | {"name": "Fixed Plant"} | 336111 | TRUE | TRUE | 2026-10-15T07:05:11.1985821+00:00 | 2026-10-15T15:05:11.1985821+08:00 | #70705 - PPT: 130hrs - SHIPLOADER: PPT 3P | 3.0 | TRUE |  | 2026-12-18T22:00:00+00:00 | 2026-12-24T08:00:00+00:00 | 2026-12-19T06:00:00+08:00 | 2026-12-24T16:00:00+08:00 |  |  |  |  | 130.00 | SL3P - IAM | We would like to start this outage earlier so that we can avoid the Christmas period where we are limited on labour and accommodation. This will also allow us to fly out people before Christmas day where flights will be an issue. |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 91a8bb9d-e600-45b8-8bc0-cac251e935d0 | Singe, Aaron (RTIO) | Scheduled | PPT | Australia/Perth
44758 | 2021-11-29T01:30:32+00:00 | 2021-11-29T09:30:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:15:30.4076646+00:00 | 2026-07-03T12:15:30.4076646+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329338 | TRUE | TRUE | 2026-07-03T04:15:30.4076646+00:00 | 2026-07-03T12:15:30.4076646+08:00 | #44758 - MDO: 114hrs - TRAIN LOADOUT: MDO | 8.1 | TRUE |  | 2027-02-15T16:00:00+00:00 | 2027-02-20T10:00:00+00:00 | 2027-02-16T00:00:00+08:00 | 2027-02-20T18:00:00+08:00 |  |  |  |  | 114.00 | MDO TLO 114Hr Shut P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com |  |  | [{"equipmentGUID": "6d6afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOTLO", "name": "Train Loadout: MDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "114"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
45472 | 2021-12-21T02:21:08+00:00 | 2021-12-21T10:21:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:18:28.5916769+00:00 | 2026-07-03T12:18:28.5916769+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329340 | TRUE | TRUE | 2026-07-03T04:18:28.5916769+00:00 | 2026-07-03T12:18:28.5916769+08:00 | #45472 - MDO: 114hrs - TRAIN LOADOUT: MDO | 8.1 | TRUE |  | 2027-05-17T16:00:00+00:00 | 2027-05-22T10:00:00+00:00 | 2027-05-18T00:00:00+08:00 | 2027-05-22T18:00:00+08:00 |  |  |  |  | 114.00 | MDO TLO 114Hr Shut P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com |  |  | [{"equipmentGUID": "6d6afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOTLO", "name": "Train Loadout: MDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "114"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44759 | 2021-11-29T01:32:59+00:00 | 2021-11-29T09:32:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:20:39.9158999+00:00 | 2026-07-03T12:20:39.9158999+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329342 | TRUE | TRUE | 2026-07-03T04:20:39.9158999+00:00 | 2026-07-03T12:20:39.9158999+08:00 | #44759 - MDO: 114hrs - TRAIN LOADOUT: MDO | 8.1 | TRUE |  | 2027-08-16T16:00:00+00:00 | 2027-08-21T10:00:00+00:00 | 2027-08-17T00:00:00+08:00 | 2027-08-21T18:00:00+08:00 |  |  |  |  | 114.00 | MDO TLO 114Hr Shut P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com |  |  | [{"equipmentGUID": "6d6afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOTLO", "name": "Train Loadout: MDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "114"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44761 | 2021-11-29T01:38:08+00:00 | 2021-11-29T09:38:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:22:47.8892495+00:00 | 2026-07-03T12:22:47.8892495+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329344 | TRUE | TRUE | 2026-07-03T04:22:47.8892495+00:00 | 2026-07-03T12:22:47.8892495+08:00 | #44761 - MDO: 114hrs - TRAIN LOADOUT: MDO | 9.1 | TRUE |  | 2027-11-15T16:00:00+00:00 | 2027-11-20T10:00:00+00:00 | 2027-11-16T00:00:00+08:00 | 2027-11-20T18:00:00+08:00 |  |  |  |  | 114.00 | MDO TLO 114Hr Shut P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com |  |  | [{"equipmentGUID": "6d6afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOTLO", "name": "Train Loadout: MDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "114"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44794 | 2021-11-29T04:00:56+00:00 | 2021-11-29T12:00:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-13T05:18:04.0772988+00:00 | 2026-07-13T13:18:04.0772988+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329875 | TRUE | TRUE | 2026-07-13T05:18:04.0772988+00:00 | 2026-07-13T13:18:04.0772988+08:00 | #44794 - MDO: 174hrs - PLANT: MDO | 10.0 | TRUE |  | 2027-02-09T04:00:00+00:00 | 2027-02-16T10:00:00+00:00 | 2027-02-09T12:00:00+08:00 | 2027-02-16T18:00:00+08:00 |  |  |  |  | 174.00 | MDO Plant shut 174Hr. P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "174"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44796 | 2021-11-29T04:05:37+00:00 | 2021-11-29T12:05:37+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-13T05:18:04.0773021+00:00 | 2026-07-13T13:18:04.0773021+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329877 | TRUE | TRUE | 2026-07-13T05:18:04.0773021+00:00 | 2026-07-13T13:18:04.0773021+08:00 | #44796 - MDO: 174hrs - PLANT: MDO | 12.0 | TRUE |  | 2027-05-11T04:00:00+00:00 | 2027-05-18T10:00:00+00:00 | 2027-05-11T12:00:00+08:00 | 2027-05-18T18:00:00+08:00 |  |  |  |  | 174.00 | MDO Plant shut 174Hr P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "174"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44795 | 2021-11-29T04:02:56+00:00 | 2021-11-29T12:02:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-13T05:18:04.0773034+00:00 | 2026-07-13T13:18:04.0773034+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329879 | TRUE | TRUE | 2026-07-13T05:18:04.0773034+00:00 | 2026-07-13T13:18:04.0773034+08:00 | #44795 - MDO: 174hrs - PLANT: MDO | 12.0 | TRUE |  | 2027-08-10T04:00:00+00:00 | 2027-08-17T10:00:00+00:00 | 2027-08-10T12:00:00+08:00 | 2027-08-17T18:00:00+08:00 |  |  |  |  | 174.00 | MDO Plant shut 174Hr P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "174"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
44800 | 2021-11-29T04:13:07+00:00 | 2021-11-29T12:13:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-13T05:18:04.0773045+00:00 | 2026-07-13T13:18:04.0773045+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329880 | TRUE | TRUE | 2026-07-13T05:18:04.0773045+00:00 | 2026-07-13T13:18:04.0773045+08:00 | #44800 - MDO: 174hrs - PLANT: MDO | 9.0 | TRUE |  | 2027-11-09T04:00:00+00:00 | 2027-11-16T10:00:00+00:00 | 2027-11-09T12:00:00+08:00 | 2027-11-16T18:00:00+08:00 |  |  |  |  | 174.00 | MDO Plant shut 174Hr. P-0508816 - MDO SI Phase IV - Asset Inspected 2022 [removal of redundant assets] work being completed away from Shut work areas Contact: Troy Lindsey troy.lindsey@riotinto.com | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-000000000063", "emailAddress": "Jeffrey.acton@riotinto.com", "displayName": "Jeffrey Acton"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f6a826e6-b786-4ef9-98cf-b05244e86594", "emailAddress": "Darren.Graham@riotinto.com", "displayName": "Graham, Darren (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2e966e23-f38b-4e0c-b11e-7fc6f98a12fe", "emailAddress": "Troy.Lindsey@riotinto.com", "displayName": "Lindsey, Troy (RTIO)"}}] | [] | [] | [] | [{"code": "P-0508816", "name": "MDO SI Phase IV - Asset Inspected 2022", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "174"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
48052 | 2022-09-08T05:59:19+00:00 | 2022-09-08T13:59:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:10.1289925+00:00 | 2026-07-31T08:52:10.1289925+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330643 | TRUE | TRUE | 2026-07-31T00:52:10.1289925+00:00 | 2026-07-31T08:52:10.1289925+08:00 | #48052 - WAN: 144hrs - CRUSHER - PRIMARY: WAN 02 | 10.0 | FALSE |  | 2027-01-14T10:30:00+00:00 | 2027-01-20T10:30:00+00:00 | 2027-01-14T18:30:00+08:00 | 2027-01-20T18:30:00+08:00 |  |  |  |  | 144.00 | Primary Crusher CS60 | MOC approved |  | [{"equipmentGUID": "3c6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV061", "name": "Conveyor: WAN 061 Primary Crushing", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "1926f6bf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV062", "name": "Conveyor: WAN 062 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6063fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS02", "name": "Crusher - Primary: WAN 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
44327 | 2021-11-23T10:21:16+00:00 | 2021-11-23T18:21:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:10.3657536+00:00 | 2026-07-31T08:52:10.3657536+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330644 | TRUE | TRUE | 2026-07-31T00:52:10.3657536+00:00 | 2026-07-31T08:52:10.3657536+08:00 | #44327 - WAN: 144hrs - PLANT: WAN | 11.0 | TRUE |  | 2027-01-14T10:30:00+00:00 | 2027-01-20T10:30:00+00:00 | 2027-01-14T18:30:00+08:00 | 2027-01-20T18:30:00+08:00 |  |  |  |  | 144.00 | Standard 120hrs Maintenance | MOC approved |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
48053 | 2022-09-08T05:59:53+00:00 | 2022-09-08T13:59:53+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:10.5949482+00:00 | 2026-07-31T08:52:10.5949482+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330645 | TRUE | TRUE | 2026-07-31T00:52:10.5949482+00:00 | 2026-07-31T08:52:10.5949482+08:00 | #48053 - WAN: 144hrs - CRUSHER - PRIMARY: WAN 02 | 8.0 | FALSE |  | 2027-04-15T10:30:00+00:00 | 2027-04-21T10:30:00+00:00 | 2027-04-15T18:30:00+08:00 | 2027-04-21T18:30:00+08:00 |  |  |  |  | 144.00 | Primary Crusher CS60 | MOC approved |  | [{"equipmentGUID": "3c6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV061", "name": "Conveyor: WAN 061 Primary Crushing", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "1926f6bf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV062", "name": "Conveyor: WAN 062 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6063fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS02", "name": "Crusher - Primary: WAN 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
44328 | 2021-11-23T10:22:16+00:00 | 2021-11-23T18:22:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:10.8222664+00:00 | 2026-07-31T08:52:10.8222664+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330646 | TRUE | TRUE | 2026-07-31T00:52:10.8222664+00:00 | 2026-07-31T08:52:10.8222664+08:00 | #44328 - WAN: 144hrs - PLANT: WAN | 11.0 | TRUE |  | 2027-04-15T10:30:00+00:00 | 2027-04-21T10:30:00+00:00 | 2027-04-15T18:30:00+08:00 | 2027-04-21T18:30:00+08:00 |  |  |  |  | 144.00 | Standard 120hrs Maintenance | MOC approved |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 73404, "shutVersionId": 324275, "title": "#73404 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH", "startDatetimeUTC": "2027-04-18T20:00:00+00:00", "endDatetimeUTC": "2027-04-19T18:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
48054 | 2022-09-08T06:00:29+00:00 | 2022-09-08T14:00:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:11.0293221+00:00 | 2026-07-31T08:52:11.0293221+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330647 | TRUE | TRUE | 2026-07-31T00:52:11.0293221+00:00 | 2026-07-31T08:52:11.0293221+08:00 | #48054 - WAN: 144hrs - CRUSHER - PRIMARY: WAN 02 | 8.0 | FALSE |  | 2027-07-15T10:30:00+00:00 | 2027-07-21T10:30:00+00:00 | 2027-07-15T18:30:00+08:00 | 2027-07-21T18:30:00+08:00 |  |  |  |  | 144.00 | Primary Crusher CS60 | MOC approved |  | [{"equipmentGUID": "3c6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV061", "name": "Conveyor: WAN 061 Primary Crushing", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "1926f6bf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV062", "name": "Conveyor: WAN 062 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6063fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS02", "name": "Crusher - Primary: WAN 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
44330 | 2021-11-23T10:23:36+00:00 | 2021-11-23T18:23:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:11.2555337+00:00 | 2026-07-31T08:52:11.2555337+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330648 | TRUE | TRUE | 2026-07-31T00:52:11.2555337+00:00 | 2026-07-31T08:52:11.2555337+08:00 | #44330 - WAN: 144hrs - PLANT: WAN | 14.0 | TRUE |  | 2027-07-15T10:30:00+00:00 | 2027-07-21T10:30:00+00:00 | 2027-07-15T18:30:00+08:00 | 2027-07-21T18:30:00+08:00 |  |  |  |  | 144.00 | Standard IMS 120hrs Maintenance Additional Info: reduced back to 120 based on rev 2 of 10 yr plan | MOC approved |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
48055 | 2022-09-08T06:01:11+00:00 | 2022-09-08T14:01:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:11.4731102+00:00 | 2026-07-31T08:52:11.4731102+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330649 | TRUE | TRUE | 2026-07-31T00:52:11.4731102+00:00 | 2026-07-31T08:52:11.4731102+08:00 | #48055 - WAN: 144hrs - CRUSHER - PRIMARY: WAN 02 | 8.0 | FALSE |  | 2027-10-14T10:30:00+00:00 | 2027-10-20T10:30:00+00:00 | 2027-10-14T18:30:00+08:00 | 2027-10-20T18:30:00+08:00 |  |  |  |  | 144.00 | Primary Crusher CS60 | MOC approved |  | [{"equipmentGUID": "3c6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV061", "name": "Conveyor: WAN 061 Primary Crushing", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "1926f6bf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV062", "name": "Conveyor: WAN 062 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6063fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS02", "name": "Crusher - Primary: WAN 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
44331 | 2021-11-23T10:25:30+00:00 | 2021-11-23T18:25:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T00:52:11.690722+00:00 | 2026-07-31T08:52:11.690722+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330650 | TRUE | TRUE | 2026-07-31T00:52:11.690722+00:00 | 2026-07-31T08:52:11.690722+08:00 | #44331 - WAN: 144hrs - PLANT: WAN | 10.0 | TRUE |  | 2027-10-14T10:30:00+00:00 | 2027-10-20T10:30:00+00:00 | 2027-10-14T18:30:00+08:00 | 2027-10-20T18:30:00+08:00 |  |  |  |  | 144.00 | Standard IMS 120hrs Maintenance | MOC approved |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11f08f4e-8fcc-4a37-a840-028bbdd9dc3e", "emailAddress": "Robert.Hegarty@riotinto.com", "displayName": "Robert Hegarty"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9d5086c8-43c4-4029-91d1-4eb7f1843952", "emailAddress": "Shane.Bilston2@riotinto.com", "displayName": "Bilston, Shane D (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
82866 | 2026-06-09T07:17:40.29207+00:00 | 2026-06-09T15:17:40.29207+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-06-09T08:14:48.1698548+00:00 | 2026-06-09T16:14:48.1698548+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 327510 | TRUE | TRUE | 2026-06-09T08:14:48.1698548+00:00 | 2026-06-09T16:14:48.1698548+08:00 | #82866 - WAN: 288hrs - AF62 C/O | 2.1 | FALSE |  | 2027-10-14T10:30:00+00:00 | 2027-10-26T10:30:00+00:00 | 2027-10-14T18:30:00+08:00 | 2027-10-26T18:30:00+08:00 |  |  |  |  | 288.00 | Apron Feeder 62 C/O (retrofit)- Capital funded Componentisation PM05 Task Approx 25 - 40 rooms will be required at WAN accommodation Estimated 30% reduced rate |  |  | [{"equipmentGUID": "f0d400c0-7c7b-ee11-a846-000d3acacefd", "code": "WANAF62", "name": "Apron Feeder: WAN Surge Bin 62", "assetClass": {"name": "Apron Feeder"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d2d35dfb-3e7c-4a54-afe4-2b74da80f182", "emailAddress": "Anto.Bilic@riotinto.com", "displayName": "Anto Bilic"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [{"code": "P-0605457", "name": "C/O AF62", "projectTeam": {"name": "Other"}, "totalProjectTime": "288"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83898 | 2026-09-09T06:17:36.2897895+00:00 | 2026-09-09T14:17:36.2897895+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-09-09T08:18:25.3073946+00:00 | 2026-09-09T16:18:25.3073946+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 333288 | TRUE | TRUE | 2026-09-09T08:18:25.3073946+00:00 | 2026-09-09T16:18:25.3073946+08:00 | #83898 - WAN: 144hrs - RC01 RAIL REPLACEMENT PROJECT (P-0605809)­­ | 1.0 | TRUE |  | 2027-04-18T22:30:00+00:00 | 2027-04-24T22:30:00+00:00 | 2027-04-19T06:30:00+08:00 | 2027-04-25T06:30:00+08:00 |  |  |  |  | 144.00 | Project Contact: Walter(Jinshui) Lin M +61 (0) 412 562 349 Walter.Lin@riotinto.com The high-level scope includes: • Removal and disposal of the existing reclaimer rails and associated components. • Supply and installation of new rail and associated rail components, including rail clips, resilient pads, fastening systems and rail bolts. • Localised remediation and replacement of rail assemblies where required, including grout bed repairs. • Rail welding, grinding, non-destructive testing and installation of transition rail interfaces where required. • Surveying and alignment verification to confirm compliance with applicable Rio Tinto and Australian Standards. |  |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8e4aea6d-1a1f-49c2-984a-60d0ee194831", "emailAddress": "Walter.Lin@riotinto.com", "displayName": "Jinshui Lin (RTIO)"}}] | [] | [] | [] | [{"code": "P-0605809", "name": "RC01 Reclaimer Rail Replacement Project", "projectTeam": {"name": "Other"}, "totalProjectTime": "144"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83899 | 2026-09-09T06:19:23.0396236+00:00 | 2026-09-09T14:19:23.0396236+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-09-09T08:18:25.4627727+00:00 | 2026-09-09T16:18:25.4627727+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 333289 | TRUE | TRUE | 2026-09-09T08:18:25.4627727+00:00 | 2026-09-09T16:18:25.4627727+08:00 | #83899 - WAN: 144hrs - RC01 RAIL REPLACEMENT PROJECT (P-0605809)­­ | 1.0 | TRUE |  | 2027-07-21T16:00:00+00:00 | 2027-07-27T16:00:00+00:00 | 2027-07-22T00:00:00+08:00 | 2027-07-28T00:00:00+08:00 |  |  |  |  | 144.00 | Project Contact: Walter(Jinshui) Lin M +61 (0) 412 562 349 Walter.Lin@riotinto.com The high-level scope includes: • Removal and disposal of the existing reclaimer rails and associated components. • Supply and installation of new rail and associated rail components, including rail clips, resilient pads, fastening systems and rail bolts. • Localised remediation and replacement of rail assemblies where required, including grout bed repairs. • Rail welding, grinding, non-destructive testing and installation of transition rail interfaces where required. • Surveying and alignment verification to confirm compliance with applicable Rio Tinto and Australian Standards. |  |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8e4aea6d-1a1f-49c2-984a-60d0ee194831", "emailAddress": "Walter.Lin@riotinto.com", "displayName": "Jinshui Lin (RTIO)"}}] | [] | [] | [] | [{"code": "P-0605809", "name": "RC01 Reclaimer Rail Replacement Project", "projectTeam": {"name": "Other"}, "totalProjectTime": "144"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83900 | 2026-09-09T06:21:57.0275187+00:00 | 2026-09-09T14:21:57.0275187+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-09-09T08:18:25.6206528+00:00 | 2026-09-09T16:18:25.6206528+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 333290 | TRUE | TRUE | 2026-09-09T08:18:25.6206528+00:00 | 2026-09-09T16:18:25.6206528+08:00 | #83900 - WAN: 144hrs - RC01 RAIL REPLACEMENT PROJECT (P-0605809)­­ | 1.0 | TRUE |  | 2027-10-17T22:30:00+00:00 | 2027-10-23T22:30:00+00:00 | 2027-10-18T06:30:00+08:00 | 2027-10-24T06:30:00+08:00 |  |  |  |  | 144.00 | Project Contact: Walter(Jinshui) Lin M +61 (0) 412 562 349 Walter.Lin@riotinto.com The high-level scope includes: • Removal and disposal of the existing reclaimer rails and associated components. • Supply and installation of new rail and associated rail components, including rail clips, resilient pads, fastening systems and rail bolts. • Localised remediation and replacement of rail assemblies where required, including grout bed repairs. • Rail welding, grinding, non-destructive testing and installation of transition rail interfaces where required. • Surveying and alignment verification to confirm compliance with applicable Rio Tinto and Australian Standards. |  |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8e4aea6d-1a1f-49c2-984a-60d0ee194831", "emailAddress": "Walter.Lin@riotinto.com", "displayName": "Jinshui Lin (RTIO)"}}] | [] | [] | [] | [{"code": "P-0605809", "name": "RC01 Reclaimer Rail Replacement Project", "projectTeam": {"name": "Other"}, "totalProjectTime": "144"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83112 | 2026-06-30T02:59:06.4771409+00:00 | 2026-06-30T10:59:06.4771409+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-10-09T06:24:40.8428915+00:00 | 2026-10-09T14:24:40.8428915+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 335768 | TRUE | TRUE | 2026-10-09T06:24:40.8428915+00:00 | 2026-10-09T14:24:40.8428915+08:00 | #83112 - WAN: 176hrs - WAN SUB STATION EOL UPGRADES - TLO HV UPGRADES (INCLUDES ENABLING WORKS FOR RECLAIMER PROJECT) - P-0602957 | 2.0 | TRUE |  | 2027-07-20T08:00:00+00:00 | 2027-07-27T16:00:00+00:00 | 2027-07-20T16:00:00+08:00 | 2027-07-28T00:00:00+08:00 |  |  |  |  | 176.00 | WAN Sub Station EOL Upgrades - TLO HV Upgrades (includes enabling works for Reclaimer Project) Contact: Daryl Seel M +61 460 033 668 daryl.seel@riotinto.com | Amendment to reduce production impact as per attached email |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3bc40955-3aff-45ab-baed-273a3d3f2a34", "emailAddress": "Daryl.Seel@riotinto.com", "displayName": "Seel, Daryl (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "WAN Sub Station EOL Upgrades", "name": "P-0602957", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "176"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
73290 | 2025-11-12T03:47:14.6093161+00:00 | 2025-11-12T11:47:14.6093161+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-29T03:23:07.5364216+00:00 | 2026-07-29T11:23:07.5364216+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330528 | TRUE | TRUE | 2026-07-29T03:23:07.5364216+00:00 | 2026-07-29T11:23:07.5364216+08:00 | #73290 - MDO: 330hrs - FL2701 BELT FILTER CARRIER C/O | 4.0 | TRUE |  | 2027-05-11T04:00:00+00:00 | 2027-05-24T22:00:00+00:00 | 2027-05-11T12:00:00+08:00 | 2027-05-25T06:00:00+08:00 |  |  |  |  | 330.00 | MDO Plant shut 174Hr and 102hrs at reduced capacity due to FL2701 belt filter carrier C/O | Correcting error for MSF mapping |  | [{"equipmentGUID": "1414b296-1f82-ef11-a853-000d3acacefd", "code": "MDOPLTMOD01", "name": "Module - Plant: MDO 01", "assetClass": {"name": "Module"}}, {"equipmentGUID": "e7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "MDOBFT2701", "name": "Belt Filter: MDO 2701 Train 01", "assetClass": {"name": "Belt Filter"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}] | [] | [] | [{"name": "Belt Filter Changeout"}] | [] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
75177 | 2026-02-11T23:18:19.6539819+00:00 | 2026-02-12T07:18:19.6539819+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-13T05:18:04.0773029+00:00 | 2026-07-13T13:18:04.0773029+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329878 | TRUE | TRUE | 2026-07-13T05:18:04.0773029+00:00 | 2026-07-13T13:18:04.0773029+08:00 | #75177 - MDO: 222hrs - AF2132 C/O | 5.0 | TRUE |  | 2027-05-11T04:00:00+00:00 | 2027-05-20T10:00:00+00:00 | 2027-05-11T12:00:00+08:00 | 2027-05-20T18:00:00+08:00 |  |  |  |  | 222.00 | PM05 Componentisation Task - AF2132 C/O | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "9a30f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MDOAF2132", "name": "Apron Feeder: MDO 2132 T2 Scrubber Feed ", "assetClass": {"name": "Apron Feeder"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [{"code": "P-0513346", "name": "C/O Apron Feeder Overhaul AF2132", "projectTeam": {"name": "Other"}, "totalProjectTime": "222"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
83443 | 2026-07-03T00:40:31.4697176+00:00 | 2026-07-03T08:40:31.4697176+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-13T05:18:04.0772993+00:00 | 2026-07-13T13:18:04.0772993+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 329876 | TRUE | TRUE | 2026-07-13T05:18:04.0772993+00:00 | 2026-07-13T13:18:04.0772993+08:00 | #83443 - MDO: 174hrs - MDO SUBSTN UPGRADE - PHASE II - P-0509338 | 2.0 | TRUE |  | 2027-02-09T04:00:00+00:00 | 2027-02-16T10:00:00+00:00 | 2027-02-09T12:00:00+08:00 | 2027-02-16T18:00:00+08:00 |  |  |  |  | 174.00 | Shut 2 - Contingency Shut 6 - Contingency Marley Puru marley.puru@riotinto.com M +61 (0) 488 299 511 | MOC approved |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "8f975ab6-7471-4bd9-919a-3815898ea065", "emailAddress": "Marley.Puru@riotinto.com", "displayName": "Puru, Marley (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0509338", "name": "MDO Substation Upgrades Phase II", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "174"}] | [] | Approved | Update | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
83111 | 2026-06-30T02:47:24.7342641+00:00 | 2026-06-30T10:47:24.7342641+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-31T00:31:59.0648752+00:00 | 2026-07-31T08:31:59.0648752+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330638 | TRUE | TRUE | 2026-07-31T00:31:59.0648752+00:00 | 2026-07-31T08:31:59.0648752+08:00 | #83111 - WAN: 212hrs - WAN SUB STATION EOL UPGRADES - SCREENING HV UPGRADES - P-0602957 | 1.0 | TRUE |  | 2027-07-15T10:30:00+00:00 | 2027-07-24T06:30:00+00:00 | 2027-07-15T18:30:00+08:00 | 2027-07-24T14:30:00+08:00 |  |  |  |  | 212.00 | WAN Sub Station EOL Upgrades - Screening HV Upgrades Contact: Daryl Seel M +61 460 033 668 daryl.seel@riotinto.com |  |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3bc40955-3aff-45ab-baed-273a3d3f2a34", "emailAddress": "Daryl.Seel@riotinto.com", "displayName": "Seel, Daryl (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0602957", "name": "WAN Sub Station EOL Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "212"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83113 | 2026-06-30T03:02:58.6234843+00:00 | 2026-06-30T11:02:58.6234843+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-31T00:31:59.4428199+00:00 | 2026-07-31T08:31:59.4428199+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330640 | TRUE | TRUE | 2026-07-31T00:31:59.4428199+00:00 | 2026-07-31T08:31:59.4428199+08:00 | #83113 - WAN: 196hrs - WAN SUB STATION EOL UPGRADES - CRUSHING LV UPGRADES - P-0602957 | 1.0 | TRUE |  | 2027-10-14T10:30:00+00:00 | 2027-10-22T14:30:00+00:00 | 2027-10-14T18:30:00+08:00 | 2027-10-22T22:30:00+08:00 |  |  |  |  | 196.00 | WAN Sub Station EOL Upgrades - Crushing LV Upgrades Contact: Daryl Seel M +61 460 033 668 daryl.seel@riotinto.com |  |  | [{"equipmentGUID": "6917ee47-4b9a-ee11-a847-000d3acacefd", "code": "WANPLT", "name": "Plant: WAN", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "3bc40955-3aff-45ab-baed-273a3d3f2a34", "emailAddress": "Daryl.Seel@riotinto.com", "displayName": "Seel, Daryl (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0602957", "name": "WAN Sub Station EOL Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "196"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
83117 | 2026-06-30T04:33:39.2020429+00:00 | 2026-06-30T12:33:39.2020429+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-07-31T00:31:59.6207526+00:00 | 2026-07-31T08:31:59.6207526+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 330641 | TRUE | TRUE | 2026-07-31T00:31:59.6207526+00:00 | 2026-07-31T08:31:59.6207526+08:00 | #83117 - WAN: 288hrs - ROCKBREAKER UPGRADE - ROM RB REPLACEMENT - P-0602957 | 1.0 | FALSE |  | 2027-10-14T10:30:00+00:00 | 2027-10-26T10:30:00+00:00 | 2027-10-14T18:30:00+08:00 | 2027-10-26T18:30:00+08:00 |  |  |  |  | 288.00 | Rockbreaker Upgrade - ROM RB Replacement Contact: Fehmi Ursavas M +61 447 206 113 fehmi.ursavas@riotinto.com |  |  | [{"equipmentGUID": "0fe9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANPCS01", "name": "Crusher - Primary: WAN 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b830702c-0f55-469a-932c-d013e4f53a7c", "emailAddress": "Fehmi.Ursavas@riotinto.com", "displayName": "Ursavas, Fehmi (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0603135", "name": "Rockbreaker Upgrade - ROM RB Replacement", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "288"}] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | WAN | Australia/Perth
74728 | 2026-01-14T05:49:42.8501639+00:00 | 2026-01-14T13:49:42.8501639+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-02-12T01:43:23.9562178+00:00 | 2026-02-12T09:43:23.9562178+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 286798 | TRUE | TRUE | 2026-02-12T01:43:23.9562178+00:00 | 2026-02-12T09:43:23.9562178+08:00 | #74728 - MDO: 108hrs - CRUSHER - SECONDARY: MDO 02 | 1.0 | FALSE |  | 2027-01-24T22:00:00+00:00 | 2027-01-29T10:00:00+00:00 | 2027-01-25T06:00:00+08:00 | 2027-01-29T18:00:00+08:00 |  |  |  |  | 108.00 | CR02 Strip & Inspect 2027 |  |  | [{"equipmentGUID": "fa71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOSCS02", "name": "Crusher - Secondary: MDO 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8d178a7e-e839-48f9-a4e5-4e25cb674f21", "emailAddress": "Ian.Coles@riotinto.com", "displayName": "Ian Coles"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "96c749e2-905f-41ab-a9c7-446cf5805ead", "emailAddress": "alexandre.coutoferreira@riotinto.com", "displayName": "Couto Ferreira, Alex (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8496ffcc-9edd-4f99-a3e3-4c2dc428eab9", "emailAddress": "Ashleigh.Scarr@riotinto.com", "displayName": "Scarr, Ashleigh (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
74730 | 2026-01-14T05:56:44.8679535+00:00 | 2026-01-14T13:56:44.8679535+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-02-12T01:43:24.7106413+00:00 | 2026-02-12T09:43:24.7106413+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 286799 | TRUE | TRUE | 2026-02-12T01:43:24.7106413+00:00 | 2026-02-12T09:43:24.7106413+08:00 | #74730 - MDO: 108hrs - CRUSHER - SECONDARY: MDO 03 | 1.0 | FALSE |  | 2027-05-02T22:00:00+00:00 | 2027-05-07T10:00:00+00:00 | 2027-05-03T06:00:00+08:00 | 2027-05-07T18:00:00+08:00 |  |  |  |  | 108.00 | CR03 Strip & Inspect 2027 |  |  | [{"equipmentGUID": "cfda00c0-7c7b-ee11-a846-000d3acacefd", "code": "MDOSCS03", "name": "Crusher - Secondary: MDO 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8d178a7e-e839-48f9-a4e5-4e25cb674f21", "emailAddress": "Ian.Coles@riotinto.com", "displayName": "Ian Coles"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "96c749e2-905f-41ab-a9c7-446cf5805ead", "emailAddress": "alexandre.coutoferreira@riotinto.com", "displayName": "Couto Ferreira, Alex (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8496ffcc-9edd-4f99-a3e3-4c2dc428eab9", "emailAddress": "Ashleigh.Scarr@riotinto.com", "displayName": "Scarr, Ashleigh (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
74731 | 2026-01-14T05:58:30.0649136+00:00 | 2026-01-14T13:58:30.0649136+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-02-12T01:43:25.4416621+00:00 | 2026-02-12T09:43:25.4416621+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 286800 | TRUE | TRUE | 2026-02-12T01:43:25.4416621+00:00 | 2026-02-12T09:43:25.4416621+08:00 | #74731 - MDO: 108hrs - CRUSHER - SECONDARY: MDO 03 | 1.0 | FALSE |  | 2027-10-31T22:00:00+00:00 | 2027-11-05T10:00:00+00:00 | 2027-11-01T06:00:00+08:00 | 2027-11-05T18:00:00+08:00 |  |  |  |  | 108.00 | CR03 Strip & Inspect 2027 |  |  | [{"equipmentGUID": "cfda00c0-7c7b-ee11-a846-000d3acacefd", "code": "MDOSCS03", "name": "Crusher - Secondary: MDO 03", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8d178a7e-e839-48f9-a4e5-4e25cb674f21", "emailAddress": "Ian.Coles@riotinto.com", "displayName": "Ian Coles"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "96c749e2-905f-41ab-a9c7-446cf5805ead", "emailAddress": "alexandre.coutoferreira@riotinto.com", "displayName": "Couto Ferreira, Alex (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8496ffcc-9edd-4f99-a3e3-4c2dc428eab9", "emailAddress": "Ashleigh.Scarr@riotinto.com", "displayName": "Scarr, Ashleigh (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
74729 | 2026-01-14T05:52:34.9163628+00:00 | 2026-01-14T13:52:34.9163628+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-02-12T01:43:26.1195745+00:00 | 2026-02-12T09:43:26.1195745+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | {"name": "Fixed Plant"} | 286801 | TRUE | TRUE | 2026-02-12T01:43:26.1195745+00:00 | 2026-02-12T09:43:26.1195745+08:00 | #74729 - MDO: 108hrs - CRUSHER - SECONDARY: MDO 02 | 1.0 | FALSE |  | 2027-07-25T22:00:00+00:00 | 2027-07-30T10:00:00+00:00 | 2027-07-26T06:00:00+08:00 | 2027-07-30T18:00:00+08:00 |  |  |  |  | 108.00 | CR02 Strip & Inspect 2027 |  |  | [{"equipmentGUID": "fa71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MDOSCS02", "name": "Crusher - Secondary: MDO 02", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8d178a7e-e839-48f9-a4e5-4e25cb674f21", "emailAddress": "Ian.Coles@riotinto.com", "displayName": "Ian Coles"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "96c749e2-905f-41ab-a9c7-446cf5805ead", "emailAddress": "alexandre.coutoferreira@riotinto.com", "displayName": "Couto Ferreira, Alex (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "456b8257-958f-430d-a63a-284afee0e39d", "emailAddress": "Michelle.Scott@riotinto.com", "displayName": "Scott, Michelle (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "8496ffcc-9edd-4f99-a3e3-4c2dc428eab9", "emailAddress": "Ashleigh.Scarr@riotinto.com", "displayName": "Scarr, Ashleigh (RTIO)"}}] | [] | [] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | 2a17f19f-14db-4d5d-915b-d2a45c51cd0e | McMurray, Sarah J (RTIO) | Scheduled | MDO | Australia/Perth
83941 | 2026-09-21T00:51:28.1425379+00:00 | 2026-09-21T08:51:28.1425379+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-09-21T07:25:09.2856117+00:00 | 2026-09-21T15:25:09.2856117+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 333663 | TRUE | TRUE | 2026-09-21T07:25:09.2856117+00:00 | 2026-09-21T15:25:09.2856117+08:00 | #83941 - PPT: 18hrs - RECLAIMER: PPT 2P | 1.0 | FALSE |  | 2026-12-06T23:00:00+00:00 | 2026-12-07T17:00:00+00:00 | 2026-12-07T07:00:00+08:00 | 2026-12-08T01:00:00+08:00 |  |  |  |  | 18.00 | Standalone outage for REC2P CAPD |  |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "62f20914-7a78-46c7-b2eb-f82b689798db", "emailAddress": "Justin.Neil@riotinto.com", "displayName": "Neil, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
71708 | 2025-10-28T05:36:16.5504834+00:00 | 2025-10-28T13:36:16.5504834+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-09-23T05:19:19.2133239+00:00 | 2026-09-23T13:19:19.2133239+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 334049 | TRUE | TRUE | 2026-09-23T05:19:19.2133239+00:00 | 2026-09-23T13:19:19.2133239+08:00 | #71708 - PPT: 106hrs - BIN: PPT 03 SURGE & SCREENHOUSE: PPT 3P | 3.0 | FALSE |  | 2026-12-01T11:00:00+00:00 | 2026-12-05T21:00:00+00:00 | 2026-12-01T19:00:00+08:00 | 2026-12-06T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Moving the Screenhouse outage to the end of the week to allow for commissioning of REC3P extension |  | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83944 | 2026-09-21T01:18:38.5855101+00:00 | 2026-09-21T09:18:38.5855101+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-09-30T23:59:25.2305571+00:00 | 2026-10-01T07:59:25.2305571+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 334745 | TRUE | TRUE | 2026-09-30T23:59:25.2305571+00:00 | 2026-10-01T07:59:25.2305571+08:00 | #83944 - EII: 60hrs - STANDALONE OUTAGE FOR FUNCTIONAL SAFETY TR32EN | 2.0 | FALSE |  | 2026-11-29T23:00:00+00:00 | 2026-12-02T11:00:00+00:00 | 2026-11-30T07:00:00+08:00 | 2026-12-02T19:00:00+08:00 |  |  |  |  | 60.00 | Standalone outage for FUNCTIONAL SAFETY TR32EN | ST3EN required to complete TR32E Functional Safety. Aligning the outage to reflect |  | [{"equipmentGUID": "16d200c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV32E", "name": "Conveyor: EII 32E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "7108e9e7-4a8c-ee11-a847-000d3acacefd", "code": "EIITP32E", "name": "Tripper: EII 32E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | EII | Australia/Perth
83866 | 2026-09-01T00:12:19.030653+00:00 | 2026-09-01T08:12:19.030653+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-09T06:15:31.8915068+00:00 | 2026-10-09T14:15:31.8915068+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335767 | TRUE | TRUE | 2026-10-09T06:15:31.8915068+00:00 | 2026-10-09T14:15:31.8915068+08:00 | #83866 - PPT: 106hrs - PPT: 106HRS - CONVEYOR: PPT 102P | 1.0 | FALSE |  | 2027-03-22T23:00:00+00:00 | 2027-03-27T09:00:00+00:00 | 2027-03-23T07:00:00+08:00 | 2027-03-27T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 102P This has been unlinked from ST4P and created individually due to site request to stager start time from ST4P (see email attached). |  |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
45686 | 2022-01-20T09:07:29+00:00 | 2022-01-20T17:07:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T06:16:57.3902631+00:00 | 2026-10-07T14:16:57.3902631+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335413 | TRUE | TRUE | 2026-10-07T06:16:57.3902631+00:00 | 2026-10-07T14:16:57.3902631+08:00 | #45686 - PPT: 106hrs - STACKER: PPT 4P | 10.0 | FALSE |  | 2027-03-22T23:00:00+00:00 | 2027-03-27T09:00:00+00:00 | 2027-03-23T07:00:00+08:00 | 2027-03-27T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | We are aligning the outage to begin 12hrs after the CD3P outage begins. |  | [{"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
40013 | 2021-01-27T07:47:19+00:00 | 2021-01-27T15:47:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-21T00:51:30.3154202+00:00 | 2026-10-21T08:51:30.3154202+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 336238 | TRUE | TRUE | 2026-10-21T00:51:30.3154202+00:00 | 2026-10-21T08:51:30.3154202+08:00 | #40013 - PPT: 194hrs - #40013 - PPT: 194HRS RECLAIMER: PPT 3P, 310P & 311P | 8.0 | FALSE |  | 2026-11-23T04:00:00+00:00 | 2026-12-01T06:00:00+00:00 | 2026-11-23T12:00:00+08:00 | 2026-12-01T14:00:00+08:00 |  |  |  |  | 194.00 | Standard IAM Maintenance Additional Info: 112P, 117P, 114P | 310 & 311 need to be in shut with REC3P |  | [{"equipmentGUID": "07e1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV310P", "name": "Conveyor: PPT 310P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "c72bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV311P", "name": "Conveyor: PPT 311P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 82852, "shutVersionId": 327982, "title": "#82852 - PPT: 130hrs - PPSS - REC3P SMPT STRUCTURAL MODIFICATIONS", "startDatetimeUTC": "2026-11-23T04:00:00+00:00", "endDatetimeUTC": "2026-11-28T14:00:00+00:00"}}] | [] | [] | [] | Approved | Update | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83978 | 2026-09-22T08:46:20.2535117+00:00 | 2026-09-22T16:46:20.2535117+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-16T01:24:48.3760607+00:00 | 2026-10-16T09:24:48.3760607+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 336150 | TRUE | TRUE | 2026-10-16T01:24:48.3760607+00:00 | 2026-10-16T09:24:48.3760607+08:00 | #83978 - PPT: 12hrs - ST3P CAPD - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-05-27T23:00:00+00:00 | 2027-05-28T11:00:00+00:00 | 2027-05-28T07:00:00+08:00 | 2027-05-28T19:00:00+08:00 |  |  |  |  | 12.00 | ST3P CAPD - Standalone Outage |  |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83977 | 2026-09-22T08:44:22.1824+00:00 | 2026-09-22T16:44:22.1824+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-12T04:32:31.4145512+00:00 | 2026-10-12T12:32:31.4145512+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335814 | TRUE | TRUE | 2026-10-12T04:32:31.4145512+00:00 | 2026-10-12T12:32:31.4145512+08:00 | #83977 - PPT: 12hrs - SL3P CAPD - STANDALONE OUTAGE | 1.0 | TRUE |  | 2027-04-17T23:00:00+00:00 | 2027-04-18T11:00:00+00:00 | 2027-04-18T07:00:00+08:00 | 2027-04-18T19:00:00+08:00 |  |  |  |  | 12.00 | SL3P CAPD - Standalone Outage |  |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83968 | 2026-09-22T07:37:25.6142055+00:00 | 2026-09-22T15:37:25.6142055+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-12T04:33:32.8278948+00:00 | 2026-10-12T12:33:32.8278948+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335815 | TRUE | TRUE | 2026-10-12T04:33:32.8278948+00:00 | 2026-10-12T12:33:32.8278948+08:00 | #83968 - EII: 12hrs - CAPD - REC1E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-02-05T23:00:00+00:00 | 2027-02-06T11:00:00+00:00 | 2027-02-06T07:00:00+08:00 | 2027-02-06T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD - REC1E - Standalone Outage |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | EII | Australia/Perth
83969 | 2026-09-22T07:40:17.7859476+00:00 | 2026-09-22T15:40:17.7859476+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-12T04:35:54.430739+00:00 | 2026-10-12T12:35:54.430739+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335816 | TRUE | TRUE | 2026-10-12T04:35:54.430739+00:00 | 2026-10-12T12:35:54.430739+08:00 | #83969 - EII: 12hrs - CAPD - REC2E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-02-06T23:00:00+00:00 | 2027-02-07T11:00:00+00:00 | 2027-02-07T07:00:00+08:00 | 2027-02-07T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD - REC2E - Standalone Outage |  |  | [{"equipmentGUID": "75dfe8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV7E", "name": "Conveyor: EII 7E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | EII | Australia/Perth
83974 | 2026-09-22T08:35:19.3189654+00:00 | 2026-09-22T16:35:19.3189654+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-09T01:05:10.0250857+00:00 | 2026-10-09T09:05:10.0250857+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335485 | TRUE | TRUE | 2026-10-09T01:05:10.0250857+00:00 | 2026-10-09T09:05:10.0250857+08:00 | #83974 - PPT: 12hrs - CAPD SL2P - STANDALONE OUTAGE | 1.0 | TRUE |  | 2027-01-29T23:00:00+00:00 | 2027-01-30T11:00:00+00:00 | 2027-01-30T07:00:00+08:00 | 2027-01-30T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD SL2P - Standalone Outage |  |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83982 | 2026-09-23T04:00:22.0737949+00:00 | 2026-09-23T12:00:22.0737949+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-09T01:05:10.2088451+00:00 | 2026-10-09T09:05:10.2088451+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335486 | TRUE | TRUE | 2026-10-09T01:05:10.2088451+00:00 | 2026-10-09T09:05:10.2088451+08:00 | #83982 - PPT: 6hrs - SL2P/SL3P COLLISION TEST - STANDALONE OUTAGE | 1.0 | TRUE |  | 2027-01-30T23:00:00+00:00 | 2027-01-31T05:00:00+00:00 | 2027-01-31T07:00:00+08:00 | 2027-01-31T13:00:00+08:00 |  |  |  |  | 6.00 | SL2P/SL3P COLLISION TEST - Standalone Outage |  |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}, {"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83971 | 2026-09-22T08:11:07.7710781+00:00 | 2026-09-22T16:11:07.7710781+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T07:11:55.4941454+00:00 | 2026-10-07T15:11:55.4941454+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 335428 | TRUE | TRUE | 2026-10-07T07:11:55.4941454+00:00 | 2026-10-07T15:11:55.4941454+08:00 | #83971 - PPT: 12hrs - CAPD ST5P - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-06-18T23:00:00+00:00 | 2027-06-19T11:00:00+00:00 | 2027-06-19T07:00:00+08:00 | 2027-06-19T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD ST5P - Standalone Outage |  |  | [{"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
83981 | 2026-09-23T02:39:42.6932508+00:00 | 2026-09-23T10:39:42.6932508+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-02T06:01:13.2759233+00:00 | 2026-10-02T14:01:13.2759233+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | {"name": "Fixed Plant"} | 334997 | TRUE | TRUE | 2026-10-02T06:01:13.2759233+00:00 | 2026-10-02T14:01:13.2759233+08:00 | #83981 - PPT: 12hrs - CAPD REC3P - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-04-02T23:00:00+00:00 | 2027-04-03T11:00:00+00:00 | 2027-04-03T07:00:00+08:00 | 2027-04-03T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD REC3P - Standalone Outage |  |  | [{"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | de5432e8-0dda-4c34-b773-d7b9f536f315 | Carlton, Clint (RTIO) | Scheduled | PPT | Australia/Perth
71423 | 2025-10-20T09:03:21.6610832+00:00 | 2025-10-20T17:03:21.6610832+08:00 | {"principalGUID": "2b2dd0e0-c0f1-4997-b7f1-e37e03561f08", "displayName": "Zolnier, Amy (RTIO)"} | 2025-10-21T03:59:53.3501736+00:00 | 2025-10-21T11:59:53.3501736+08:00 | {"principalGUID": "2b2dd0e0-c0f1-4997-b7f1-e37e03561f08", "displayName": "Zolnier, Amy (RTIO)"} | {"name": "Fixed Plant"} | 261680 | TRUE | TRUE | 2025-10-21T03:59:53.3501736+00:00 | 2025-10-21T11:59:53.3501736+08:00 | #71423 - WAN: 48hrs - CONVEYOR: WAN 050 PRODUCT SCREENS FEED | 1.0 | TRUE |  | 2026-12-07T22:30:00+00:00 | 2026-12-09T22:30:00+00:00 | 2026-12-08T06:30:00+08:00 | 2026-12-10T06:30:00+08:00 |  |  |  |  | 48.00 | Poke scheduled 48hr outage for required offline maintenance - Part of 13week scheduled strategy |  |  | [{"equipmentGUID": "4a6bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV050", "name": "Conveyor: WAN 050 Product Screens Feed", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a00c46b-21d4-49f4-9ba7-794d24550e97", "emailAddress": "Craig.Boyce@riotinto.com", "displayName": "Boyce, Craig (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2b2dd0e0-c0f1-4997-b7f1-e37e03561f08 | Zolnier, Amy (RTIO) | Scheduled | WAN | Australia/Perth
71471 | 2025-10-27T02:31:13.1161632+00:00 | 2025-10-27T10:31:13.1161632+08:00 | {"principalGUID": "f0731cb1-b9e2-4f23-9860-f27d8e017dcf", "displayName": "Cawthray, Jodie (RTIO)"} | 2026-09-08T09:34:06.5080094+00:00 | 2026-09-08T17:34:06.5080094+08:00 | {"principalGUID": "f5401de2-23e5-49c7-bb6c-e952898b6f2a", "displayName": "McCubbin, Rob (RTIO)"} | {"name": "Utilities"} | 333235 | TRUE | TRUE | 2026-09-08T09:34:06.5080094+00:00 | 2026-09-08T17:34:06.5080094+08:00 | #71471 - UTL: 206hrs - GENERATION: YMPS GTG7 | 2.0 | FALSE |  | 2026-12-07T20:00:00+00:00 | 2026-12-16T10:00:00+00:00 | 2026-12-08T04:00:00+08:00 | 2026-12-16T18:00:00+08:00 |  |  |  |  | 206.00 | GTG7 4000H Maintenance GTG7 8000H Calibrations GTG7 Gas Skid Valves Replacement GTG7 Offline Inspections | Swapping from GTG8 to GTG7 to align to maintenance requirements and reducing hours to allow for CLG1 outage. |  | [{"equipmentGUID": "", "code": "UTLGENGTG7 YMPS", "name": "Generation: YMPS GTG7", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | f5401de2-23e5-49c7-bb6c-e952898b6f2a | McCubbin, Rob (RTIO) | Scheduled |  | Australia/Perth
83884 | 2026-09-07T02:39:05.2795952+00:00 | 2026-09-07T10:39:05.2795952+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | 2026-09-08T09:39:06.4514535+00:00 | 2026-09-08T17:39:06.4514535+08:00 | {"principalGUID": "f5401de2-23e5-49c7-bb6c-e952898b6f2a", "displayName": "McCubbin, Rob (RTIO)"} | {"name": "Utilities"} | 333243 | TRUE | TRUE | 2026-09-08T09:39:06.4514535+00:00 | 2026-09-08T17:39:06.4514535+08:00 | #83884 - UTL: 182hrs - GENERATION: YMPS GTG8 | 2.0 | FALSE |  | 2026-12-27T20:00:00+00:00 | 2027-01-04T10:00:00+00:00 | 2026-12-28T04:00:00+08:00 | 2027-01-04T18:00:00+08:00 |  |  |  |  | 182.00 | GTG8 BSI GTG8 Filter C/O GTG8 Evap Media C/O | Swap GTG7 to GTG8 to align to maintenance requirements |  | [{"equipmentGUID": "", "code": "UTLGENGTG8 YMPS", "name": "Generation: YMPS GTG8", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | f5401de2-23e5-49c7-bb6c-e952898b6f2a | McCubbin, Rob (RTIO) | Scheduled |  | Australia/Perth
68558 | 2025-07-30T03:51:12.8148963+00:00 | 2025-07-30T11:51:12.8148963+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2025-10-27T07:58:11.5477163+00:00 | 2025-10-27T15:58:11.5477163+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 264529 | TRUE | TRUE | 2025-10-27T07:58:11.5477163+00:00 | 2025-10-27T15:58:11.5477163+08:00 | #68558 - PPT: 186hrs - STK4P CORROSION REPAIRS | 4.0 | FALSE |  | 2026-12-06T04:00:00+00:00 | 2026-12-13T22:00:00+00:00 | 2026-12-06T12:00:00+08:00 | 2026-12-14T06:00:00+08:00 |  |  |  |  | 186.00 | Additional shut to repair SDNs and RMP defects on STK4P Contact Pete Corcoran P ¦ 089183 7095 e ¦ peter.corcoran@riotinto.com | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "23fbb7dd-a5b2-423e-99aa-100480c6af0d", "emailAddress": "peter.corcoran@riotinto.com", "displayName": "Peter Corcoran"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | PPT | Australia/Perth
68497 | 2025-07-17T02:40:32.4832094+00:00 | 2025-07-17T10:40:32.4832094+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-10-08T03:32:36.4832928+00:00 | 2025-10-08T11:32:36.4832928+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 246411 | TRUE | TRUE | 2025-10-08T03:32:36.4832928+00:00 | 2025-10-08T11:32:36.4832928+08:00 | #68497 - NBWT: 6hrs - PC7 ROD CRUSHER | 2.0 | TRUE |  | 2027-01-02T22:00:00+00:00 | 2027-01-03T04:00:00+00:00 | 2027-01-03T06:00:00+08:00 | 2027-01-03T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | NBWT | Australia/Perth
68496 | 2025-07-17T02:40:32.0591304+00:00 | 2025-07-17T10:40:32.0591304+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-10-08T03:32:37.1420618+00:00 | 2025-10-08T11:32:37.1420618+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 246413 | TRUE | TRUE | 2025-10-08T03:32:37.1420618+00:00 | 2025-10-08T11:32:37.1420618+08:00 | #68496 - NBWT: 6hrs - PC7 ROD CRUSHER | 2.0 | TRUE |  | 2026-12-26T22:00:00+00:00 | 2026-12-27T04:00:00+00:00 | 2026-12-27T06:00:00+08:00 | 2026-12-27T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | NBWT | Australia/Perth
68495 | 2025-07-17T02:40:31.6675491+00:00 | 2025-07-17T10:40:31.6675491+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-10-08T03:32:37.8096747+00:00 | 2025-10-08T11:32:37.8096747+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 246415 | TRUE | TRUE | 2025-10-08T03:32:37.8096747+00:00 | 2025-10-08T11:32:37.8096747+08:00 | #68495 - NBWT: 6hrs - PC7 ROD CRUSHER | 2.0 | TRUE |  | 2026-12-19T22:00:00+00:00 | 2026-12-20T04:00:00+00:00 | 2026-12-20T06:00:00+08:00 | 2026-12-20T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | NBWT | Australia/Perth
68483 | 2025-07-17T02:40:27.1174212+00:00 | 2025-07-17T10:40:27.1174212+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-10-08T03:32:38.5046822+00:00 | 2025-10-08T11:32:38.5046822+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 246417 | TRUE | TRUE | 2025-10-08T03:32:38.5046822+00:00 | 2025-10-08T11:32:38.5046822+08:00 | #68483 - NBWT: 108hrs - PC7 ROD CRUSHER | 2.0 | TRUE |  | 2026-12-09T22:00:00+00:00 | 2026-12-14T10:00:00+00:00 | 2026-12-10T06:00:00+08:00 | 2026-12-14T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | NBWT | Australia/Perth
67847 | 2025-06-19T13:21:46.5679284+00:00 | 2025-06-19T21:21:46.5679284+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-10T00:04:51.943444+00:00 | 2025-11-10T08:04:51.943444+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 273652 | TRUE | TRUE | 2025-11-10T00:04:51.943444+00:00 | 2025-11-10T08:04:51.943444+08:00 | #67847 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 3.0 | TRUE |  | 2026-12-06T02:00:00+00:00 | 2026-12-06T05:00:00+00:00 | 2026-12-06T10:00:00+08:00 | 2026-12-06T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop, Additional Info: 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance | IAM Refresh - Overrides |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | YAN | Australia/Perth
67848 | 2025-06-19T13:21:47.0717592+00:00 | 2025-06-19T21:21:47.0717592+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2025-11-10T00:04:55.2121373+00:00 | 2025-11-10T08:04:55.2121373+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 273655 | TRUE | TRUE | 2025-11-10T00:04:55.2121373+00:00 | 2025-11-10T08:04:55.2121373+08:00 | #67848 - YAN: 3hrs - LOOP PLANT PIT STOP & YCV215 INSPECTION | 4.0 | TRUE |  | 2026-12-20T02:00:00+00:00 | 2026-12-20T05:00:00+00:00 | 2026-12-20T10:00:00+08:00 | 2026-12-20T13:00:00+08:00 |  |  |  |  | 3.00 | 3hr Loop Plant Pit Stop, Additional Info: 3hr Loop Plant Pit Stop for Idler C/O's & minimal Maintenance | IAM Refresh - Overrides |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | YAN | Australia/Perth
44421 | 2021-11-25T02:57:03+00:00 | 2021-11-25T10:57:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-13T07:12:16.0648977+00:00 | 2025-10-13T15:12:16.0648977+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 253556 | TRUE | TRUE | 2025-10-13T07:12:16.0648977+00:00 | 2025-10-13T15:12:16.0648977+08:00 | #44421 - PPT: 106hrs - CAR DUMPER: PPT 3P | 11.0 | TRUE |  | 2026-12-14T10:00:00+00:00 | 2026-12-18T20:00:00+00:00 | 2026-12-14T18:00:00+08:00 | 2026-12-19T04:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | PPT | Australia/Perth
39789 | 2021-01-20T02:55:26+00:00 | 2021-01-20T10:55:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-27T05:07:53.0242497+00:00 | 2025-10-27T13:07:53.0242497+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 264454 | TRUE | TRUE | 2025-10-27T05:07:53.0242497+00:00 | 2025-10-27T13:07:53.0242497+08:00 | #39789 - EII: 96hrs - RECLAIMER: EII 2E | 3.0 | FALSE |  | 2026-12-08T16:00:00+00:00 | 2026-12-12T16:00:00+00:00 | 2026-12-09T00:00:00+08:00 | 2026-12-13T00:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "d1f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC2E", "name": "Reclaimer: EII 2E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abdd04b9-8dea-4d9f-a600-932dd15efab7", "emailAddress": "Dan.Abrahamson@riotinto.com", "displayName": "Dan Abrahamson"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | EII | Australia/Perth
40385 | 2021-02-24T07:07:59+00:00 | 2021-02-24T15:07:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-27T07:58:29.9839377+00:00 | 2025-10-27T15:58:29.9839377+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 264548 | TRUE | TRUE | 2025-10-27T07:58:29.9839377+00:00 | 2025-10-27T15:58:29.9839377+08:00 | #40385 - PPT: 106hrs - STACKER: PPT 4P | 7.0 | FALSE |  | 2026-12-13T22:00:00+00:00 | 2026-12-18T08:00:00+00:00 | 2026-12-14T06:00:00+08:00 | 2026-12-18T16:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | PPT | Australia/Perth
39819 | 2021-01-20T04:45:18+00:00 | 2021-01-20T12:45:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2025-10-21T01:09:54.1478106+00:00 | 2025-10-21T09:09:54.1478106+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 261387 | TRUE | TRUE | 2025-10-21T01:09:54.1478106+00:00 | 2025-10-21T09:09:54.1478106+08:00 | #39819 - EII: 80hrs - CONVEYOR: EII 10E | 2.0 | FALSE |  | 2026-12-07T06:00:00+00:00 | 2026-12-10T14:00:00+00:00 | 2026-12-07T14:00:00+08:00 | 2026-12-10T22:00:00+08:00 |  |  |  |  | 80.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "75bc9cce-242f-44ec-8ed3-7158f993005f", "emailAddress": "Jesse.Cunningham@riotinto.com", "displayName": "Cunningham, Jesse (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83689, "shutVersionId": 334230, "title": "#83689 - EII: 88hrs - CONVEYOR: EII 10E & STOCKPILE: EII 10.2", "startDatetimeUTC": "2026-12-06T22:00:00+00:00", "endDatetimeUTC": "2026-12-10T14:00:00+00:00"}}] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | EII | Australia/Perth
52434 | 2022-11-07T05:47:16+00:00 | 2022-11-07T13:47:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-0000000006e4", "displayName": "Duane Evans"} | 2026-10-20T02:39:38.3162398+00:00 | 2026-10-20T10:39:38.3162398+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 336205 | TRUE | TRUE | 2026-10-20T02:39:38.3162398+00:00 | 2026-10-20T10:39:38.3162398+08:00 | #52434 - CLA: 300hrs - RCL1 BUCKET WHEEL C/O | 10.3 | FALSE |  | 2027-04-18T04:00:00+00:00 | 2027-04-30T16:00:00+00:00 | 2027-04-18T12:00:00+08:00 | 2027-05-01T00:00:00+08:00 |  |  |  |  | 300.00 | Proposed Bucket Wheel Change Out Condition based |  |  | [{"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}] | [] | [] | [{"name": "Bucket Wheel Changeout"}] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLA | Australia/Perth
38926 | 2020-12-18T03:58:59+00:00 | 2020-12-18T11:58:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-17T05:49:42.0169498+00:00 | 2025-10-17T13:49:42.0169498+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 260166 | TRUE | TRUE | 2025-10-17T05:49:42.0169498+00:00 | 2025-10-17T13:49:42.0169498+08:00 | #38926 - CLB: 120hrs - SCREENHOUSE: CLB 05 OUTLOADING | 4.0 | FALSE |  | 2026-12-07T10:00:00+00:00 | 2026-12-12T10:00:00+00:00 | 2026-12-07T18:00:00+08:00 | 2026-12-12T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "7e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "CLBSCH05", "name": "Screenhouse: CLB 05 Outloading", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLB | Australia/Perth
38736 | 2020-12-18T03:37:12+00:00 | 2020-12-18T11:37:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-17T05:49:47.670592+00:00 | 2025-10-17T13:49:47.670592+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 260171 | TRUE | TRUE | 2025-10-17T05:49:47.670592+00:00 | 2025-10-17T13:49:47.670592+08:00 | #38736 - CLB: 120hrs - BERTH: CLB 06 | 4.0 | FALSE |  | 2026-12-07T10:00:00+00:00 | 2026-12-12T10:00:00+00:00 | 2026-12-07T18:00:00+08:00 | 2026-12-12T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "", "code": "CLBBTH06", "name": "Berth: CLB 06", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLB | Australia/Perth
38717 | 2020-12-18T03:36:41+00:00 | 2020-12-18T11:36:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-17T05:49:49.9830715+00:00 | 2025-10-17T13:49:49.9830715+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 260173 | TRUE | TRUE | 2025-10-17T05:49:49.9830715+00:00 | 2025-10-17T13:49:49.9830715+08:00 | #38717 - CLB: 120hrs - BERTH: CLB 05 | 4.0 | FALSE |  | 2026-12-07T10:00:00+00:00 | 2026-12-12T10:00:00+00:00 | 2026-12-07T18:00:00+08:00 | 2026-12-12T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "", "code": "CLBBTH05", "name": "Berth: CLB 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "abefcdab-0000-0000-0000-0000000002b7", "emailAddress": "Conor.O'Brien@riotinto.com", "displayName": "Conor O'Brien"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLB | Australia/Perth
38945 | 2020-12-18T03:59:29+00:00 | 2020-12-18T11:59:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2025-10-13T07:21:57.3944654+00:00 | 2025-10-13T15:21:57.3944654+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 253613 | TRUE | TRUE | 2025-10-13T07:21:57.3944654+00:00 | 2025-10-13T15:21:57.3944654+08:00 | #38945 - CLB: 120hrs - SHIPLOADER: CLB 11C | 4.0 | TRUE |  | 2026-12-07T10:00:00+00:00 | 2026-12-12T10:00:00+00:00 | 2026-12-07T18:00:00+08:00 | 2026-12-12T18:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | IAM Refresh - Manual Overrides |  | [{"equipmentGUID": "f9f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSLD11C", "name": "Shiploader: CLB 11C", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLB | Australia/Perth
43832 | 2021-11-11T06:01:09+00:00 | 2021-11-11T14:01:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000b08", "displayName": "Jenny Anderson"} | 2026-08-28T05:18:28.7942084+00:00 | 2026-08-28T13:18:28.7942084+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 332135 | TRUE | TRUE | 2026-08-28T05:18:28.7942084+00:00 | 2026-08-28T13:18:28.7942084+08:00 | #43832 - CLB: 12hrs - ILSUB01 SHUT (CD5/ST11/ST12/RF) | 6.1 | TRUE |  | 2027-09-06T22:00:00+00:00 | 2027-09-07T10:00:00+00:00 | 2027-09-07T06:00:00+08:00 | 2027-09-07T18:00:00+08:00 |  |  |  |  | 12.00 | Inload SUB 1 Electrical Shut - 12hrs Additional Info: Substation Shuts will be completed on a 26 weekly cycleTrack maintenance aligned to CLB yard 8hrs 19/02/2022 (please consider if shut was to move) |  | SCBI2733 | [{"equipmentGUID": "b53cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCD5C", "name": "Car Dumper: CLB 5C", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "bdf8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBSUBIL01", "name": "Substation: CLB Inloading 01", "assetClass": {"name": "Substation"}}, {"equipmentGUID": "dcf7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV853", "name": "Conveyor: CLB 853 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "3b40f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBCV861", "name": "Conveyor: CLB 861 Fines Return", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "bd22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST11", "name": "Stacker: CLB 11", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "7c387af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO01", "name": "Bin: CLB Screenhouse 05 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "102d7af1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO02", "name": "Bin: CLB Screenhouse 05 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7b2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO03", "name": "Bin: CLB Screenhouse 05 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "a53aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO04", "name": "Bin: CLB Screenhouse 05 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "090591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO05", "name": "Bin: CLB Screenhouse 05 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "000a91f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH05PO06", "name": "Bin: CLB Screenhouse 05 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "610091f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO01", "name": "Bin: CLB Screenhouse 06 Position 01", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "792591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO02", "name": "Bin: CLB Screenhouse 06 Position 02", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "7c2591f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO03", "name": "Bin: CLB Screenhouse 06 Position 03", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "0dcf80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO04", "name": "Bin: CLB Screenhouse 06 Position 04", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "88cd80f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO05", "name": "Bin: CLB Screenhouse 06 Position 05", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "3b2aa7f1-4a8c-ee11-a847-000d3acacefd", "code": "CLBBNSCH06PO06", "name": "Bin: CLB Screenhouse 06 Position 06", "assetClass": {"name": "Bin"}}, {"equipmentGUID": "", "code": "CLBSCH05LM", "name": "Screenhouse: CLB 05 Lump Module", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "", "code": "CLBSCH06LM", "name": "Screenhouse: CLB 06 Lump Module", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e3df37-61c1-4ca6-b6d0-9c0f25bdd249", "emailAddress": "Justin.Hewson@riotinto.com", "displayName": "Hewson, Justin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | CLB | Australia/Perth
54970 | 2023-04-19T00:21:44+00:00 | 2023-04-19T08:21:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-08T03:51:56.6538859+00:00 | 2025-10-08T11:51:56.6538859+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 246995 | TRUE | TRUE | 2025-10-08T03:51:56.6538859+00:00 | 2025-10-08T11:51:56.6538859+08:00 | #54970 - MDO: 24hrs - PLANT: MDO | 6.0 | TRUE |  | 2026-12-18T16:00:00+00:00 | 2026-12-19T16:00:00+00:00 | 2026-12-19T00:00:00+08:00 | 2026-12-20T00:00:00+08:00 |  |  |  |  | 24.00 | MDO PLT Pitstop for screen panel change out, urgent works and 6wkly stat inspections. | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "6c17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MDOPLT", "name": "Plant: MDO", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "c13d3e8a-78b6-450f-a80f-c153f2bf53a4", "emailAddress": "Miriam.Williams@riotinto.com", "displayName": "Miriam Williams"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "d913b999-4544-41f0-b973-51fd1889e474", "emailAddress": "Alexis.Wood@riotinto.com", "displayName": "Wood, Alexis (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | MDO | Australia/Perth
44927 | 2021-11-30T08:19:31+00:00 | 2021-11-30T16:19:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-08T04:11:03.4253435+00:00 | 2025-10-08T12:11:03.4253435+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 247188 | TRUE | TRUE | 2025-10-08T04:11:03.4253435+00:00 | 2025-10-08T12:11:03.4253435+08:00 | #44927 - MTP: 66hrs - TRAIN LOADOUT: MTP LOADOUT TUNNEL 01 | 5.0 | TRUE |  | 2026-12-02T11:00:00+00:00 | 2026-12-05T05:00:00+00:00 | 2026-12-02T19:00:00+08:00 | 2026-12-05T13:00:00+08:00 |  |  |  |  | 66.00 | TLO1 shut | IAM Refresh - Mines 08-10-2025 |  | [{"equipmentGUID": "b5d7495f-678b-ee11-a847-000d3acacefd", "code": "MTPTLOLOT01", "name": "Train Loadout: MTP Loadout Tunnel 01", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | MTP | Australia/Perth
44345 | 2021-11-24T07:44:55+00:00 | 2021-11-24T15:44:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-11T03:18:35.3209416+00:00 | 2026-09-11T11:18:35.3209416+08:00 | {"principalGUID": "f6a6f93b-c954-43b1-8963-ec26e3158aaa", "displayName": "Jude, William (RTIO)"} | {"name": "Fixed Plant"} | 333355 | TRUE | TRUE | 2026-09-11T03:18:35.3209416+00:00 | 2026-09-11T11:18:35.3209416+08:00 | #44345 - HD4: 12hrs - HD4 PLT - SPRINT SHUT | 11.1 | TRUE |  | 2027-01-12T22:00:00+00:00 | 2027-01-13T10:00:00+00:00 | 2027-01-13T06:00:00+08:00 | 2027-01-13T18:00:00+08:00 |  |  |  |  | 12.00 | HD4 Plant Sprint Shut |  |  | [{"equipmentGUID": "c65a111b-5a28-ef11-a84d-000d3acacefd", "code": "HD4PLT", "name": "Plant: HD4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0478dbbd-2634-4fad-9717-390205517a5e", "emailAddress": "Fatima.Afifah@riotinto.com", "displayName": "Afifah, Fatima (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | f6a6f93b-c954-43b1-8963-ec26e3158aaa | Jude, William (RTIO) | Scheduled | HD4 | Australia/Perth
44822 | 2021-11-30T03:40:21+00:00 | 2021-11-30T11:40:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T07:22:52.6361195+00:00 | 2026-07-03T15:22:52.6361195+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 329374 | TRUE | TRUE | 2026-07-03T07:22:52.6361195+00:00 | 2026-07-03T15:22:52.6361195+08:00 | #44822 - PDO: 336hrs - FIXED PLANT | 10.0 | TRUE |  | 2027-04-07T10:00:00+00:00 | 2027-04-21T10:00:00+00:00 | 2027-04-07T18:00:00+08:00 | 2027-04-21T18:00:00+08:00 |  |  |  |  | 336.00 | TLO Shut SI Scope | Maintain IAM linkages | 44822 | [{"equipmentGUID": "67f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PDOTLO", "name": "Train Loadout: PDO", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "2d43f963-33f9-4dd5-ba1e-e6a77488b003", "emailAddress": "MARIANO.MARIANO@riotinto.com", "displayName": "MARIANO, MARIANO (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "db5c6791-78aa-4ff8-ac71-8c15a9c3d7d2", "emailAddress": "Ashwin.Nair@riotinto.com", "displayName": "Nair, Ashwin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [{"name": "TLO Major Works"}] | [{"code": "P-0504886", "name": "PBO SI Remediation - Phase III", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "336"}] | [] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | PDO | Australia/Perth
67874 | 2025-06-19T13:28:57.3821236+00:00 | 2025-06-19T21:28:57.3821236+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T01:55:58.037491+00:00 | 2026-01-09T09:55:58.037491+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283619 | TRUE | TRUE | 2026-01-09T01:55:58.037491+00:00 | 2026-01-09T09:55:58.037491+08:00 | #67874 - YAN: 12hrs - RECLAIMER: YAN 02 | 3.0 | FALSE |  | 2026-12-06T16:00:00+00:00 | 2026-12-07T04:00:00+00:00 | 2026-12-07T00:00:00+08:00 | 2026-12-07T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection | IAM Refresh |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | YAN | Australia/Perth
67820 | 2025-06-19T13:12:44.1105156+00:00 | 2025-06-19T21:12:44.1105156+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T01:55:58.6294169+00:00 | 2026-01-09T09:55:58.6294169+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283621 | TRUE | TRUE | 2026-01-09T01:55:58.6294169+00:00 | 2026-01-09T09:55:58.6294169+08:00 | #67820 - YAN: 12hrs - RECLAIMER: YAN 01 | 3.0 | FALSE |  | 2026-12-13T16:00:00+00:00 | 2026-12-14T04:00:00+00:00 | 2026-12-14T00:00:00+08:00 | 2026-12-14T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection | IAM Refresh |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | YAN | Australia/Perth
67875 | 2025-06-19T13:28:57.8641332+00:00 | 2025-06-19T21:28:57.8641332+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T01:55:59.1871674+00:00 | 2026-01-09T09:55:59.1871674+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283623 | TRUE | TRUE | 2026-01-09T01:55:59.1871674+00:00 | 2026-01-09T09:55:59.1871674+08:00 | #67875 - YAN: 12hrs - RECLAIMER: YAN 02 | 3.0 | FALSE |  | 2026-12-20T16:00:00+00:00 | 2026-12-21T04:00:00+00:00 | 2026-12-21T00:00:00+08:00 | 2026-12-21T12:00:00+08:00 |  |  |  |  | 12.00 | YRC02 2WK Bucket & Chute Stop Inspection | IAM Refresh |  | [{"equipmentGUID": "ab28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC02", "name": "Reclaimer: YAN 02", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d26d788a-87bd-429b-82a9-441dbcf43610", "emailAddress": "Allen.James@riotinto.com", "displayName": "Allen James"}}] | [] | [] | [] | [] | [] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | YAN | Australia/Perth
67821 | 2025-06-19T13:12:44.5670679+00:00 | 2025-06-19T21:12:44.5670679+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T01:55:59.7296867+00:00 | 2026-01-09T09:55:59.7296867+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283625 | TRUE | TRUE | 2026-01-09T01:55:59.7296867+00:00 | 2026-01-09T09:55:59.7296867+08:00 | #67821 - YAN: 12hrs - RECLAIMER: YAN 01 | 3.0 | FALSE |  | 2026-12-27T16:00:00+00:00 | 2026-12-28T04:00:00+00:00 | 2026-12-28T00:00:00+08:00 | 2026-12-28T12:00:00+08:00 |  |  |  |  | 12.00 | YRC01 2WK Bucket & Chute Stop Inspection | IAM Refresh |  | [{"equipmentGUID": "fff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANRC01", "name": "Reclaimer: YAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "add75b33-9e32-4b2b-8f4c-986ea6966ce0", "emailAddress": "Danny.Clark@riotinto.com", "displayName": "Danny Clark"}}] | [] | [] | [] | [] | [] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | YAN | Australia/Perth
67902 | 2025-06-23T08:25:56.0913112+00:00 | 2025-06-23T16:25:56.0913112+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T02:50:20.8796021+00:00 | 2026-01-09T10:50:20.8796021+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283628 | TRUE | TRUE | 2026-01-09T02:50:20.8796021+00:00 | 2026-01-09T10:50:20.8796021+08:00 | #67902 - YAN: 12hrs - YAN LOOP PLANT | 4.0 | TRUE |  | 2026-12-02T22:00:00+00:00 | 2026-12-03T10:00:00+00:00 | 2026-12-03T06:00:00+08:00 | 2026-12-03T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's | IAM Refresh |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Site Constraint | YAN | Australia/Perth
67894 | 2025-06-23T08:23:56.9911467+00:00 | 2025-06-23T16:23:56.9911467+08:00 | {"principalGUID": "ed8648ca-ebc6-4536-bb85-49ad6324f770", "displayName": "Boyd, Malcolm (RTIO)"} | 2026-01-09T02:50:21.5851584+00:00 | 2026-01-09T10:50:21.5851584+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 283629 | TRUE | TRUE | 2026-01-09T02:50:21.5851584+00:00 | 2026-01-09T10:50:21.5851584+08:00 | #67894 - YAN: 12hrs - YAN LOOP PLANT | 4.0 | TRUE |  | 2026-12-01T22:00:00+00:00 | 2026-12-02T10:00:00+00:00 | 2026-12-02T06:00:00+08:00 | 2026-12-02T18:00:00+08:00 |  |  |  |  | 12.00 | 12hr - Loop Screen Outage 1 Plant to run at 50% for Screen Panel C/O's | IAM Refresh |  | [{"equipmentGUID": "6117ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT02", "name": "Plant: YAN 02 (Wet)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "2a386e14-9e80-ef11-a853-000d3acacefd", "code": "YANPLTLOOP", "name": "Plant: YAN Loop", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "6317ee47-4b9a-ee11-a847-000d3acacefd", "code": "YANPLT03", "name": "Plant: YAN 03 (JSE)", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "44eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ201", "name": "Crusher - Primary: YAN Primary Sizer 201 Plant 02 ", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "4e6ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "YANPCSSZ301", "name": "Crusher - Primary: YAN Primary Sizer 301 Plant 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "216c5942-335b-447b-879c-75a2bf3ab531", "emailAddress": "Luke.Davies2@riotinto.com", "displayName": "Luke Davies"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Site Constraint | YAN | Australia/Perth
82949 | 2026-06-23T23:30:39.2501169+00:00 | 2026-06-24T07:30:39.2501169+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | 2026-06-25T05:29:03.0985116+00:00 | 2026-06-25T13:29:03.0985116+08:00 | {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "displayName": "Iglio, Francesco (RTIO)"} | {"name": "Fixed Plant"} | 328459 | TRUE | TRUE | 2026-06-25T05:29:03.0985116+00:00 | 2026-06-25T13:29:03.0985116+08:00 | #82949 - BM2: 8735hrs - B2 CARE AND MAINTENANCE | 1.0 | TRUE |  | 2026-12-31T17:00:00+00:00 | 2027-12-30T16:00:00+00:00 | 2027-01-01T01:00:00+08:00 | 2027-12-31T00:00:00+08:00 |  |  |  |  | 8735.00 | B2 care and maintenance |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "a531f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0220", "name": "Crusher - Secondary: BM2 0220 No. 1", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "1346f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0320", "name": "Crusher - Secondary: BM2 0320 No. 2", "assetClass": {"name": "Crusher - Secondary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "05d900c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2AF0110", "name": "Apron Feeder: BM2 0110", "assetClass": {"name": "Apron Feeder"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "467cfd02-b2a6-45b8-ba65-ef08b4d136fe", "emailAddress": "Francesco.Iglio@riotinto.com", "displayName": "Iglio, Francesco (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 467cfd02-b2a6-45b8-ba65-ef08b4d136fe | Iglio, Francesco (RTIO) | Scheduled | BM2 | Australia/Perth
73002 | 2025-11-07T00:33:39.7627574+00:00 | 2025-11-07T08:33:39.7627574+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:20:40.3692608+00:00 | 2026-10-06T08:20:40.3692608+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335339 | TRUE | TRUE | 2026-10-06T00:20:40.3692608+00:00 | 2026-10-06T08:20:40.3692608+08:00 | #73002 - BM4: 24hrs - SCREEN: BM4 403 VIBRATING | 2.0 | FALSE |  | 2028-01-29T10:00:00+00:00 | 2028-01-30T10:00:00+00:00 | 2028-01-29T18:00:00+08:00 | 2028-01-30T18:00:00+08:00 |  |  |  |  | 24.00 | BSC403 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "9fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC403", "name": "Screen: BM4 403 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72971 | 2025-11-07T00:01:13.8444074+00:00 | 2025-11-07T08:01:13.8444074+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:20:54.2330728+00:00 | 2026-10-06T08:20:54.2330728+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335340 | TRUE | TRUE | 2026-10-06T00:20:54.2330728+00:00 | 2026-10-06T08:20:54.2330728+08:00 | #72971 - BM4: 24hrs - SCREEN: BM4 402 VIBRATING | 2.0 | FALSE |  | 2028-01-28T10:00:00+00:00 | 2028-01-29T10:00:00+00:00 | 2028-01-28T18:00:00+08:00 | 2028-01-29T18:00:00+08:00 |  |  |  |  | 24.00 | BSC402 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "94d400c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC402", "name": "Screen: BM4 402 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72940 | 2025-11-06T23:24:12.8130708+00:00 | 2025-11-07T07:24:12.8130708+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:21:07.9732243+00:00 | 2026-10-06T08:21:07.9732243+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335341 | TRUE | TRUE | 2026-10-06T00:21:07.9732243+00:00 | 2026-10-06T08:21:07.9732243+08:00 | #72940 - BM4: 24hrs - SCREEN: BM4 401 VIBRATING | 2.0 | FALSE |  | 2028-01-27T10:00:00+00:00 | 2028-01-28T10:00:00+00:00 | 2028-01-27T18:00:00+08:00 | 2028-01-28T18:00:00+08:00 |  |  |  |  | 24.00 | BSC401 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "ce3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC401", "name": "Screen: BM4 401 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73133 | 2025-11-07T03:51:08.4400739+00:00 | 2025-11-07T11:51:08.4400739+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:56:15.8661205+00:00 | 2026-10-06T08:56:15.8661205+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335350 | TRUE | TRUE | 2026-10-06T00:56:15.8661205+00:00 | 2026-10-06T08:56:15.8661205+08:00 | #73133 - BM4: 24hrs - SCREEN: BM4 406 VIBRATING | 2.0 | FALSE |  | 2027-11-27T10:00:00+00:00 | 2027-11-28T10:00:00+00:00 | 2027-11-27T18:00:00+08:00 | 2027-11-28T18:00:00+08:00 |  |  |  |  | 24.00 | BSC406 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "00eae8bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC406", "name": "Screen: BM4 406 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73061 | 2025-11-07T02:03:37.6409202+00:00 | 2025-11-07T10:03:37.6409202+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:56:29.5637388+00:00 | 2026-10-06T08:56:29.5637388+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335351 | TRUE | TRUE | 2026-10-06T00:56:29.5637388+00:00 | 2026-10-06T08:56:29.5637388+08:00 | #73061 - BM4: 24hrs - SCREEN: BM4 405 VIBRATING | 2.0 | FALSE |  | 2027-11-26T10:00:00+00:00 | 2027-11-27T10:00:00+00:00 | 2027-11-26T18:00:00+08:00 | 2027-11-27T18:00:00+08:00 |  |  |  |  | 24.00 | BSC405 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "a273fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC405", "name": "Screen: BM4 405 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73031 | 2025-11-07T01:28:29.8305937+00:00 | 2025-11-07T09:28:29.8305937+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:56:41.2710788+00:00 | 2026-10-06T08:56:41.2710788+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335352 | TRUE | TRUE | 2026-10-06T00:56:41.2710788+00:00 | 2026-10-06T08:56:41.2710788+08:00 | #73031 - BM4: 24hrs - SCREEN: BM4 404 VIBRATING | 2.0 | FALSE |  | 2027-11-25T10:00:00+00:00 | 2027-11-26T10:00:00+00:00 | 2027-11-25T18:00:00+08:00 | 2027-11-26T18:00:00+08:00 |  |  |  |  | 24.00 | BSC404 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "f260fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC404", "name": "Screen: BM4 404 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73001 | 2025-11-07T00:33:06.396667+00:00 | 2025-11-07T08:33:06.396667+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:56:53.9067921+00:00 | 2026-10-06T08:56:53.9067921+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335353 | TRUE | TRUE | 2026-10-06T00:56:53.9067921+00:00 | 2026-10-06T08:56:53.9067921+08:00 | #73001 - BM4: 24hrs - SCREEN: BM4 403 VIBRATING | 2.0 | FALSE |  | 2027-09-25T10:00:00+00:00 | 2027-09-26T10:00:00+00:00 | 2027-09-25T18:00:00+08:00 | 2027-09-26T18:00:00+08:00 |  |  |  |  | 24.00 | BSC403 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "9fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC403", "name": "Screen: BM4 403 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72970 | 2025-11-07T00:00:40.1484666+00:00 | 2025-11-07T08:00:40.1484666+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:57:06.1487275+00:00 | 2026-10-06T08:57:06.1487275+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335354 | TRUE | TRUE | 2026-10-06T00:57:06.1487275+00:00 | 2026-10-06T08:57:06.1487275+08:00 | #72970 - BM4: 24hrs - SCREEN: BM4 402 VIBRATING | 2.0 | FALSE |  | 2027-09-24T10:00:00+00:00 | 2027-09-25T10:00:00+00:00 | 2027-09-24T18:00:00+08:00 | 2027-09-25T18:00:00+08:00 |  |  |  |  | 24.00 | BSC402 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "94d400c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC402", "name": "Screen: BM4 402 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72939 | 2025-11-06T23:23:12.6824429+00:00 | 2025-11-07T07:23:12.6824429+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-10-06T00:57:18.6633935+00:00 | 2026-10-06T08:57:18.6633935+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 335355 | TRUE | TRUE | 2026-10-06T00:57:18.6633935+00:00 | 2026-10-06T08:57:18.6633935+08:00 | #72939 - BM4: 24hrs - SCREEN: BM4 401 VIBRATING | 2.0 | FALSE |  | 2027-09-23T10:00:00+00:00 | 2027-09-24T10:00:00+00:00 | 2027-09-23T18:00:00+08:00 | 2027-09-24T18:00:00+08:00 |  |  |  |  | 24.00 | BSC401 Screen Panel Change Out Top and Bottom Deck C/O | Re-align with frequency change |  | [{"equipmentGUID": "ce3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC401", "name": "Screen: BM4 401 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72870 | 2025-11-05T02:17:09.47428+00:00 | 2025-11-05T10:17:09.47428+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-11-10T06:35:40.5440138+00:00 | 2025-11-10T14:35:40.5440138+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 273712 | TRUE | TRUE | 2025-11-10T06:35:40.5440138+00:00 | 2025-11-10T14:35:40.5440138+08:00 | #72870 - BM4: 147hrs - CRUSHER - SECONDARY: BM4 302 | 1.0 | FALSE |  | 2026-12-09T19:00:00+00:00 | 2026-12-15T22:00:00+00:00 | 2026-12-10T03:00:00+08:00 | 2026-12-16T06:00:00+08:00 |  |  |  |  | 147.00 | BCC302 147hr Modular Shut |  |  | [{"equipmentGUID": "e25bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SCS302", "name": "Crusher - Secondary: BM4 302", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a4a6f5e6-f840-45ca-949b-1a838b5d2879", "emailAddress": "James.A.Ferguson@riotinto.com", "displayName": "Ferguson, James (RTIOEP)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7b7dc951-de55-4ed2-b5e2-3eea47d28065", "emailAddress": "Dean.Prescott@riotinto.com", "displayName": "Prescott, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72877 | 2025-11-05T07:53:17.6758285+00:00 | 2025-11-05T15:53:17.6758285+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T07:58:51.3800579+00:00 | 2025-12-10T15:58:51.3800579+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 281423 | TRUE | TRUE | 2025-12-10T07:58:51.3800579+00:00 | 2025-12-10T15:58:51.3800579+08:00 | #72877 - BM4: 147hrs - CRUSHER - SECONDARY: BM4 302 | 1.0 | FALSE |  | 2027-12-08T19:00:00+00:00 | 2027-12-14T22:00:00+00:00 | 2027-12-09T03:00:00+08:00 | 2027-12-15T06:00:00+08:00 |  |  |  |  | 147.00 | BCC302 147hr Modular Shut |  |  | [{"equipmentGUID": "e25bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SCS302", "name": "Crusher - Secondary: BM4 302", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a4a6f5e6-f840-45ca-949b-1a838b5d2879", "emailAddress": "James.A.Ferguson@riotinto.com", "displayName": "Ferguson, James (RTIOEP)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7b7dc951-de55-4ed2-b5e2-3eea47d28065", "emailAddress": "Dean.Prescott@riotinto.com", "displayName": "Prescott, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72876 | 2025-11-05T07:51:23.52592+00:00 | 2025-11-05T15:51:23.52592+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T07:58:52.188154+00:00 | 2025-12-10T15:58:52.188154+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 281424 | TRUE | TRUE | 2025-12-10T07:58:52.188154+00:00 | 2025-12-10T15:58:52.188154+08:00 | #72876 - BM4: 147hrs - CRUSHER - SECONDARY: BM4 301 | 1.0 | FALSE |  | 2027-09-08T19:00:00+00:00 | 2027-09-14T22:00:00+00:00 | 2027-09-09T03:00:00+08:00 | 2027-09-15T06:00:00+08:00 |  |  |  |  | 147.00 | BCC301 147hr Modular Shut |  |  | [{"equipmentGUID": "2132f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SCS301", "name": "Crusher - Secondary: BM4 301", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a4a6f5e6-f840-45ca-949b-1a838b5d2879", "emailAddress": "James.A.Ferguson@riotinto.com", "displayName": "Ferguson, James (RTIOEP)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7b7dc951-de55-4ed2-b5e2-3eea47d28065", "emailAddress": "Dean.Prescott@riotinto.com", "displayName": "Prescott, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72872 | 2025-11-05T02:26:33.3186643+00:00 | 2025-11-05T10:26:33.3186643+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T07:58:53.6504753+00:00 | 2025-12-10T15:58:53.6504753+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 281426 | TRUE | TRUE | 2025-12-10T07:58:53.6504753+00:00 | 2025-12-10T15:58:53.6504753+08:00 | #72872 - BM4: 147hrs - CRUSHER - SECONDARY: BM4 302 | 1.0 | FALSE |  | 2027-06-09T19:00:00+00:00 | 2027-06-15T22:00:00+00:00 | 2027-06-10T03:00:00+08:00 | 2027-06-16T06:00:00+08:00 |  |  |  |  | 147.00 | BCC302 147hr Modular Shut |  |  | [{"equipmentGUID": "e25bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SCS302", "name": "Crusher - Secondary: BM4 302", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a4a6f5e6-f840-45ca-949b-1a838b5d2879", "emailAddress": "James.A.Ferguson@riotinto.com", "displayName": "Ferguson, James (RTIOEP)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7b7dc951-de55-4ed2-b5e2-3eea47d28065", "emailAddress": "Dean.Prescott@riotinto.com", "displayName": "Prescott, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72871 | 2025-11-05T02:24:58.2946602+00:00 | 2025-11-05T10:24:58.2946602+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T07:58:54.3494479+00:00 | 2025-12-10T15:58:54.3494479+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 281427 | TRUE | TRUE | 2025-12-10T07:58:54.3494479+00:00 | 2025-12-10T15:58:54.3494479+08:00 | #72871 - BM4: 147hrs - CRUSHER - SECONDARY: BM4 301 | 1.0 | FALSE |  | 2027-03-10T19:00:00+00:00 | 2027-03-16T22:00:00+00:00 | 2027-03-11T03:00:00+08:00 | 2027-03-17T06:00:00+08:00 |  |  |  |  | 147.00 | BCC301 147hr Modular Shut |  |  | [{"equipmentGUID": "2132f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SCS301", "name": "Crusher - Secondary: BM4 301", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "emailAddress": "Glenn.Hall@riotinto.com", "displayName": "Hall, Glenn (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a4a6f5e6-f840-45ca-949b-1a838b5d2879", "emailAddress": "James.A.Ferguson@riotinto.com", "displayName": "Ferguson, James (RTIOEP)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7b7dc951-de55-4ed2-b5e2-3eea47d28065", "emailAddress": "Dean.Prescott@riotinto.com", "displayName": "Prescott, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73130 | 2025-11-07T03:48:43.8150111+00:00 | 2025-11-07T11:48:43.8150111+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:47.2221501+00:00 | 2026-04-08T10:53:47.2221501+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324657 | TRUE | TRUE | 2026-04-08T02:53:47.2221501+00:00 | 2026-04-08T10:53:47.2221501+08:00 | #73130 - BM4: 28hrs - SCREEN: BM4 406 VIBRATING | 2.0 | FALSE |  | 2027-07-24T10:00:00+00:00 | 2027-07-25T14:00:00+00:00 | 2027-07-24T18:00:00+08:00 | 2027-07-25T22:00:00+08:00 |  |  |  |  | 28.00 | BSC406 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "00eae8bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC406", "name": "Screen: BM4 406 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73058 | 2025-11-07T02:01:34.2702863+00:00 | 2025-11-07T10:01:34.2702863+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:47.3910201+00:00 | 2026-04-08T10:53:47.3910201+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324658 | TRUE | TRUE | 2026-04-08T02:53:47.3910201+00:00 | 2026-04-08T10:53:47.3910201+08:00 | #73058 - BM4: 24hrs - SCREEN: BM4 405 VIBRATING | 2.0 | FALSE |  | 2027-07-23T10:00:00+00:00 | 2027-07-24T10:00:00+00:00 | 2027-07-23T18:00:00+08:00 | 2027-07-24T18:00:00+08:00 |  |  |  |  | 24.00 | BSC405 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "a273fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC405", "name": "Screen: BM4 405 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73029 | 2025-11-07T01:17:09.8713261+00:00 | 2025-11-07T09:17:09.8713261+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:47.5541574+00:00 | 2026-04-08T10:53:47.5541574+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324659 | TRUE | TRUE | 2026-04-08T02:53:47.5541574+00:00 | 2026-04-08T10:53:47.5541574+08:00 | #73029 - BM4: 27hrs - SCREEN: BM4 404 VIBRATING | 2.0 | FALSE |  | 2027-07-22T07:00:00+00:00 | 2027-07-23T10:00:00+00:00 | 2027-07-22T15:00:00+08:00 | 2027-07-23T18:00:00+08:00 |  |  |  |  | 27.00 | BSC404 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "f260fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC404", "name": "Screen: BM4 404 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73000 | 2025-11-07T00:32:16.4725205+00:00 | 2025-11-07T08:32:16.4725205+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:47.715919+00:00 | 2026-04-08T10:53:47.715919+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324660 | TRUE | TRUE | 2026-04-08T02:53:47.715919+00:00 | 2026-04-08T10:53:47.715919+08:00 | #73000 - BM4: 28hrs - SCREEN: BM4 403 VIBRATING | 2.0 | FALSE |  | 2027-05-22T10:00:00+00:00 | 2027-05-23T14:00:00+00:00 | 2027-05-22T18:00:00+08:00 | 2027-05-23T22:00:00+08:00 |  |  |  |  | 28.00 | BSC403 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "9fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC403", "name": "Screen: BM4 403 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72969 | 2025-11-06T23:59:55.7452132+00:00 | 2025-11-07T07:59:55.7452132+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:47.8798887+00:00 | 2026-04-08T10:53:47.8798887+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324661 | TRUE | TRUE | 2026-04-08T02:53:47.8798887+00:00 | 2026-04-08T10:53:47.8798887+08:00 | #72969 - BM4: 24hrs - SCREEN: BM4 402 VIBRATING | 2.0 | FALSE |  | 2027-05-21T10:00:00+00:00 | 2027-05-22T10:00:00+00:00 | 2027-05-21T18:00:00+08:00 | 2027-05-22T18:00:00+08:00 |  |  |  |  | 24.00 | BSC402 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "94d400c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC402", "name": "Screen: BM4 402 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72938 | 2025-11-06T23:22:03.4021025+00:00 | 2025-11-07T07:22:03.4021025+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:48.0367763+00:00 | 2026-04-08T10:53:48.0367763+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324662 | TRUE | TRUE | 2026-04-08T02:53:48.0367763+00:00 | 2026-04-08T10:53:48.0367763+08:00 | #72938 - BM4: 26hrs - SCREEN: BM4 401 VIBRATING | 2.0 | FALSE |  | 2027-05-20T08:00:00+00:00 | 2027-05-21T10:00:00+00:00 | 2027-05-20T16:00:00+08:00 | 2027-05-21T18:00:00+08:00 |  |  |  |  | 26.00 | BSC401 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "ce3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC401", "name": "Screen: BM4 401 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
82117 | 2026-03-29T03:59:51.3199848+00:00 | 2026-03-29T11:59:51.3199848+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:48.2120561+00:00 | 2026-04-08T10:53:48.2120561+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324663 | TRUE | TRUE | 2026-04-08T02:53:48.2120561+00:00 | 2026-04-08T10:53:48.2120561+08:00 | #82117 - BM4: 72hrs - SCREEN: BM4 403 VIBRATING | 1.0 | FALSE |  | 2027-02-17T10:00:00+00:00 | 2027-02-20T10:00:00+00:00 | 2027-02-17T18:00:00+08:00 | 2027-02-20T18:00:00+08:00 |  |  |  |  | 72.00 | BSC403 Vib Screen C/O |  |  | [{"equipmentGUID": "9fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC403", "name": "Screen: BM4 403 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
82116 | 2026-03-29T03:53:35.4689627+00:00 | 2026-03-29T11:53:35.4689627+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:48.3694314+00:00 | 2026-04-08T10:53:48.3694314+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324664 | TRUE | TRUE | 2026-04-08T02:53:48.3694314+00:00 | 2026-04-08T10:53:48.3694314+08:00 | #82116 - BM4: 72hrs - SCREEN: BM4 401 VIBRATING | 1.0 | FALSE |  | 2027-01-20T10:00:00+00:00 | 2027-01-23T10:00:00+00:00 | 2027-01-20T18:00:00+08:00 | 2027-01-23T18:00:00+08:00 |  |  |  |  | 72.00 | BSC401 Vib Screen C/O |  |  | [{"equipmentGUID": "ce3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC401", "name": "Screen: BM4 401 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72998 | 2025-11-07T00:30:50.7458367+00:00 | 2025-11-07T08:30:50.7458367+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:48.5347654+00:00 | 2026-04-08T10:53:48.5347654+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324665 | TRUE | TRUE | 2026-04-08T02:53:48.5347654+00:00 | 2026-04-08T10:53:48.5347654+08:00 | #72998 - BM4: 27hrs - SCREEN: BM4 403 VIBRATING | 2.0 | FALSE |  | 2027-01-16T07:00:00+00:00 | 2027-01-17T10:00:00+00:00 | 2027-01-16T15:00:00+08:00 | 2027-01-17T18:00:00+08:00 |  |  |  |  | 27.00 | BSC403 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "9fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC403", "name": "Screen: BM4 403 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
72967 | 2025-11-06T23:57:35.567828+00:00 | 2025-11-07T07:57:35.567828+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2026-04-08T02:53:48.7134125+00:00 | 2026-04-08T10:53:48.7134125+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 324666 | TRUE | TRUE | 2026-04-08T02:53:48.7134125+00:00 | 2026-04-08T10:53:48.7134125+08:00 | #72967 - BM4: 29hrs - SCREEN: BM4 402 VIBRATING | 2.0 | FALSE |  | 2027-01-15T02:00:00+00:00 | 2027-01-16T07:00:00+00:00 | 2027-01-15T10:00:00+08:00 | 2027-01-16T15:00:00+08:00 |  |  |  |  | 29.00 | BSC402 Screen Panel Change Out Top and Bottom Deck C/O | Change required due to Panel C/O frequency change |  | [{"equipmentGUID": "94d400c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC402", "name": "Screen: BM4 402 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73131 | 2025-11-07T03:49:41.0099005+00:00 | 2025-11-07T11:49:41.0099005+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T05:13:33.5799425+00:00 | 2025-12-10T13:13:33.5799425+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 280408 | TRUE | TRUE | 2025-12-10T05:13:33.5799425+00:00 | 2025-12-10T13:13:33.5799425+08:00 | #73131 - BM4: 24hrs - SCREEN: BM4 406 VIBRATING | 1.0 | FALSE |  | 2027-03-21T10:00:00+00:00 | 2027-03-22T10:00:00+00:00 | 2027-03-21T18:00:00+08:00 | 2027-03-22T18:00:00+08:00 |  |  |  |  | 24.00 | BSC406 Screen Panel Change Out Top and Bottom Deck C/O |  |  | [{"equipmentGUID": "00eae8bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC406", "name": "Screen: BM4 406 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73059 | 2025-11-07T02:02:17.3447678+00:00 | 2025-11-07T10:02:17.3447678+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T05:14:06.3415094+00:00 | 2025-12-10T13:14:06.3415094+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 280436 | TRUE | TRUE | 2025-12-10T05:14:06.3415094+00:00 | 2025-12-10T13:14:06.3415094+08:00 | #73059 - BM4: 24hrs - SCREEN: BM4 405 VIBRATING | 1.0 | FALSE |  | 2027-03-20T10:00:00+00:00 | 2027-03-21T10:00:00+00:00 | 2027-03-20T18:00:00+08:00 | 2027-03-21T18:00:00+08:00 |  |  |  |  | 24.00 | BSC405 Screen Panel Change Out Top and Bottom Deck C/O |  |  | [{"equipmentGUID": "a273fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC405", "name": "Screen: BM4 405 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73030 | 2025-11-07T01:17:52.6949045+00:00 | 2025-11-07T09:17:52.6949045+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | 2025-12-10T05:14:39.4494148+00:00 | 2025-12-10T13:14:39.4494148+08:00 | {"principalGUID": "ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb", "displayName": "Hall, Glenn (RTIO)"} | {"name": "Fixed Plant"} | 280463 | TRUE | TRUE | 2025-12-10T05:14:39.4494148+00:00 | 2025-12-10T13:14:39.4494148+08:00 | #73030 - BM4: 24hrs - SCREEN: BM4 404 VIBRATING | 1.0 | FALSE |  | 2027-03-19T10:00:00+00:00 | 2027-03-20T10:00:00+00:00 | 2027-03-19T18:00:00+08:00 | 2027-03-20T18:00:00+08:00 |  |  |  |  | 24.00 | BSC404 Screen Panel Change Out Top and Bottom Deck C/O |  |  | [{"equipmentGUID": "f260fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4SC404", "name": "Screen: BM4 404 Vibrating ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "baeb91fb-2e86-4c78-ba7f-2cc8e663b27f", "emailAddress": "Mark.Cole@riotinto.com", "displayName": "Mark Cole"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "26e4e99f-b055-4595-8380-9183aa4599d3", "emailAddress": "Ben.Burfitt@riotinto.com", "displayName": "Burfitt, Ben (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | ee0ecf65-4e64-4e01-b5e3-f16d0226c4fb | Hall, Glenn (RTIO) | Scheduled | BM4 | Australia/Perth
73075 | 2025-11-07T02:51:20.1563071+00:00 | 2025-11-07T10:51:20.1563071+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-12-09T07:43:00.3853683+00:00 | 2025-12-09T15:43:00.3853683+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 280223 | TRUE | TRUE | 2025-12-09T07:43:00.3853683+00:00 | 2025-12-09T15:43:00.3853683+08:00 | #73075 - BM2: 12hrs - PLANT: BM2 | 1.0 | TRUE |  | 2027-04-22T22:00:00+00:00 | 2027-04-23T10:00:00+00:00 | 2027-04-23T06:00:00+08:00 | 2027-04-23T18:00:00+08:00 |  |  |  |  | 12.00 | Annual CAPD Testing on Stackers |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
73086 | 2025-11-07T02:51:22.6103771+00:00 | 2025-11-07T10:51:22.6103771+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-12-09T07:43:07.2336403+00:00 | 2025-12-09T15:43:07.2336403+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 280233 | TRUE | TRUE | 2025-12-09T07:43:07.2336403+00:00 | 2025-12-09T15:43:07.2336403+08:00 | #73086 - BM2: 12hrs - TRAIN LOADOUT: BM2 | 1.0 | TRUE |  | 2027-04-22T22:00:00+00:00 | 2027-04-23T10:00:00+00:00 | 2027-04-23T06:00:00+08:00 | 2027-04-23T18:00:00+08:00 |  |  |  |  | 12.00 | Annual CAPD Testing on Stackers |  |  | [{"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
81853 | 2026-03-19T23:52:06.6234934+00:00 | 2026-03-20T07:52:06.6234934+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T23:52:07.0477169+00:00 | 2026-03-20T07:52:07.0477169+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322473 | TRUE | TRUE | 2026-03-19T23:52:07.0477169+00:00 | 2026-03-20T07:52:07.0477169+08:00 | #81853 - NBWT: 108hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-12-15T22:00:00+00:00 | 2027-12-20T10:00:00+00:00 | 2027-12-16T06:00:00+08:00 | 2027-12-20T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81854 | 2026-03-19T23:52:06.6236511+00:00 | 2026-03-20T07:52:06.6236511+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T23:52:07.0477226+00:00 | 2026-03-20T07:52:07.0477226+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322474 | TRUE | TRUE | 2026-03-19T23:52:07.0477226+00:00 | 2026-03-20T07:52:07.0477226+08:00 | #81854 - NBWT: 108hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-09-15T22:00:00+00:00 | 2027-09-20T10:00:00+00:00 | 2027-09-16T06:00:00+08:00 | 2027-09-20T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81855 | 2026-03-19T23:52:06.6236587+00:00 | 2026-03-20T07:52:06.6236587+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T23:52:07.0477232+00:00 | 2026-03-20T07:52:07.0477232+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322475 | TRUE | TRUE | 2026-03-19T23:52:07.0477232+00:00 | 2026-03-20T07:52:07.0477232+08:00 | #81855 - NBWT: 108hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-06-16T22:00:00+00:00 | 2027-06-21T10:00:00+00:00 | 2027-06-17T06:00:00+08:00 | 2027-06-21T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81856 | 2026-03-19T23:52:06.6236673+00:00 | 2026-03-20T07:52:06.6236673+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T23:52:07.0477237+00:00 | 2026-03-20T07:52:07.0477237+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322476 | TRUE | TRUE | 2026-03-19T23:52:07.0477237+00:00 | 2026-03-20T07:52:07.0477237+08:00 | #81856 - NBWT: 108hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2027-03-18T22:00:00+00:00 | 2027-03-23T10:00:00+00:00 | 2027-03-19T06:00:00+08:00 | 2027-03-23T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
76382 | 2026-02-25T05:37:30.7144376+00:00 | 2026-02-25T13:37:30.7144376+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-10T02:26:32.7959066+00:00 | 2026-03-10T10:26:32.7959066+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 320819 | TRUE | TRUE | 2026-03-10T02:26:32.7959066+00:00 | 2026-03-10T10:26:32.7959066+08:00 | #76382 - BM2: 4hrs - CRUSHER - PRIMARY: BM2 01 & PLANT: BM2 | 1.0 | TRUE |  | 2027-09-08T11:30:00+00:00 | 2027-09-08T15:30:00+00:00 | 2027-09-08T19:30:00+08:00 | 2027-09-08T23:30:00+08:00 |  |  |  |  | 4.00 | belt re-tension required post shut. |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
76380 | 2026-02-25T05:32:39.4296585+00:00 | 2026-02-25T13:32:39.4296585+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-10T02:26:41.3433058+00:00 | 2026-03-10T10:26:41.3433058+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 320854 | TRUE | TRUE | 2026-03-10T02:26:41.3433058+00:00 | 2026-03-10T10:26:41.3433058+08:00 | #76380 - BM2: 4hrs - CRUSHER - PRIMARY: BM2 01 & PLANT: BM2 | 1.0 | TRUE |  | 2027-03-10T11:30:00+00:00 | 2027-03-10T15:30:00+00:00 | 2027-03-10T19:30:00+08:00 | 2027-03-10T23:30:00+08:00 |  |  |  |  | 4.00 | Post shut belt re-tension is required |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
76381 | 2026-02-25T05:33:41.911949+00:00 | 2026-02-25T13:33:41.911949+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-10T02:26:41.6023106+00:00 | 2026-03-10T10:26:41.6023106+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 320855 | TRUE | TRUE | 2026-03-10T02:26:41.6023106+00:00 | 2026-03-10T10:26:41.6023106+08:00 | #76381 - BM2: 4hrs - CRUSHER - PRIMARY: BM2 01 & PLANT: BM2 | 1.0 | TRUE |  | 2027-06-09T11:30:00+00:00 | 2027-06-09T15:30:00+00:00 | 2027-06-09T19:30:00+08:00 | 2027-06-09T23:30:00+08:00 |  |  |  |  | 4.00 | post shut belt re-tension required |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
76383 | 2026-02-25T05:37:31.4875922+00:00 | 2026-02-25T13:37:31.4875922+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-10T02:26:41.8854648+00:00 | 2026-03-10T10:26:41.8854648+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 320856 | TRUE | TRUE | 2026-03-10T02:26:41.8854648+00:00 | 2026-03-10T10:26:41.8854648+08:00 | #76383 - BM2: 4hrs - CRUSHER - PRIMARY: BM2 01 & PLANT: BM2 | 1.0 | TRUE |  | 2027-12-08T11:30:00+00:00 | 2027-12-08T15:30:00+00:00 | 2027-12-08T19:30:00+08:00 | 2027-12-08T23:30:00+08:00 |  |  |  |  | 4.00 | belt re-tension required post shut. |  |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
75981 | 2026-02-25T02:28:48.2867551+00:00 | 2026-02-25T10:28:48.2867551+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-10T02:26:42.7495584+00:00 | 2026-03-10T10:26:42.7495584+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 320859 | TRUE | TRUE | 2026-03-10T02:26:42.7495584+00:00 | 2026-03-10T10:26:42.7495584+08:00 | #75981 - BM2: 12hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-08-30T22:00:00+00:00 | 2027-08-31T10:00:00+00:00 | 2027-08-31T06:00:00+08:00 | 2027-08-31T18:00:00+08:00 |  |  |  |  | 12.00 | Jaw Crusher Liner Rotation - Loosen Crusher Bolts 24Hrs Pre-Shut |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
81768 | 2026-03-19T09:37:42.0465713+00:00 | 2026-03-19T17:37:42.0465713+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.475254+00:00 | 2026-03-19T18:18:17.475254+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322295 | TRUE | TRUE | 2026-03-19T10:18:17.475254+00:00 | 2026-03-19T18:18:17.475254+08:00 | #81768 - NBWT: 96hrs - CRUSHER - SECONDARY: NBWT 2301 | 2.0 | FALSE |  | 2027-01-20T22:00:00+00:00 | 2027-01-24T22:00:00+00:00 | 2027-01-21T06:00:00+08:00 | 2027-01-25T06:00:00+08:00 |  |  |  |  | 96.00 | CS2301 Secondary Crusher Rebuild 10% SOP Impact | Uploaded into the incorrect week |  | [{"equipmentGUID": "1227f0bf-7c7b-ee11-a846-000d3acacefd", "code": "NBWTSCS2301", "name": "Crusher - Secondary: NBWT 2301", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0e355955-835a-4fc6-a831-eea7d0ba7935", "emailAddress": "Andrew.Saunders2@riotinto.com", "displayName": "Saunders, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81769 | 2026-03-19T09:37:42.1517189+00:00 | 2026-03-19T17:37:42.1517189+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.475258+00:00 | 2026-03-19T18:18:17.475258+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322296 | TRUE | TRUE | 2026-03-19T10:18:17.475258+00:00 | 2026-03-19T18:18:17.475258+08:00 | #81769 - NBWT: 4hrs - PLANT: NBWT | 2.0 | TRUE |  | 2027-01-20T22:00:00+00:00 | 2027-01-21T02:00:00+00:00 | 2027-01-21T06:00:00+08:00 | 2027-01-21T10:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 | Uploaded into the incorrect week |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81771 | 2026-03-19T09:37:42.1519597+00:00 | 2026-03-19T17:37:42.1519597+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.4752586+00:00 | 2026-03-19T18:18:17.4752586+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322297 | TRUE | TRUE | 2026-03-19T10:18:17.4752586+00:00 | 2026-03-19T18:18:17.4752586+08:00 | #81771 - NBWT: 96hrs - CRUSHER - SECONDARY: NBWT 2301 | 2.0 | FALSE |  | 2027-07-21T22:00:00+00:00 | 2027-07-25T22:00:00+00:00 | 2027-07-22T06:00:00+08:00 | 2027-07-26T06:00:00+08:00 |  |  |  |  | 96.00 | CS2301 Secondary Crusher Rebuild 10% SOP Impact | Uploaded into the incorrect week |  | [{"equipmentGUID": "1227f0bf-7c7b-ee11-a846-000d3acacefd", "code": "NBWTSCS2301", "name": "Crusher - Secondary: NBWT 2301", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81772 | 2026-03-19T09:37:42.1520328+00:00 | 2026-03-19T17:37:42.1520328+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.4752589+00:00 | 2026-03-19T18:18:17.4752589+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322298 | TRUE | TRUE | 2026-03-19T10:18:17.4752589+00:00 | 2026-03-19T18:18:17.4752589+08:00 | #81772 - NBWT: 4hrs - PLANT: NBWT | 2.0 | TRUE |  | 2027-07-21T22:00:00+00:00 | 2027-07-22T02:00:00+00:00 | 2027-07-22T06:00:00+08:00 | 2027-07-22T10:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 | Uploaded into the incorrect week |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81774 | 2026-03-19T09:37:42.152173+00:00 | 2026-03-19T17:37:42.152173+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.4752606+00:00 | 2026-03-19T18:18:17.4752606+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322299 | TRUE | TRUE | 2026-03-19T10:18:17.4752606+00:00 | 2026-03-19T18:18:17.4752606+08:00 | #81774 - NBWT: 96hrs - CRUSHER - SECONDARY: NBWT 2301 | 2.0 | FALSE |  | 2028-01-19T22:00:00+00:00 | 2028-01-23T22:00:00+00:00 | 2028-01-20T06:00:00+08:00 | 2028-01-24T06:00:00+08:00 |  |  |  |  | 96.00 | CS2301 Secondary Crusher Rebuild 10% SOP Impact | Uploaded into the incorrect week |  | [{"equipmentGUID": "1227f0bf-7c7b-ee11-a846-000d3acacefd", "code": "NBWTSCS2301", "name": "Crusher - Secondary: NBWT 2301", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81775 | 2026-03-19T09:37:42.1522534+00:00 | 2026-03-19T17:37:42.1522534+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T10:18:17.475263+00:00 | 2026-03-19T18:18:17.475263+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322300 | TRUE | TRUE | 2026-03-19T10:18:17.475263+00:00 | 2026-03-19T18:18:17.475263+08:00 | #81775 - NBWT: 4hrs - PLANT: NBWT | 2.0 | TRUE |  | 2028-01-19T22:00:00+00:00 | 2028-01-20T02:00:00+00:00 | 2028-01-20T06:00:00+08:00 | 2028-01-20T10:00:00+08:00 |  |  |  |  | 4.00 | Spile Bar Outage Secondary Crusher CS2301 | Uploaded into the incorrect week |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81831 | 2026-03-19T22:32:19.647503+00:00 | 2026-03-20T06:32:19.647503+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T22:32:20.3808358+00:00 | 2026-03-20T06:32:20.3808358+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322399 | TRUE | TRUE | 2026-03-19T22:32:20.3808358+00:00 | 2026-03-20T06:32:20.3808358+08:00 | #81831 - NBWT: 96hrs - CRUSHER - SECONDARY: NBWT 2302 | 1.0 | FALSE |  | 2027-04-21T22:00:00+00:00 | 2027-04-25T22:00:00+00:00 | 2027-04-22T06:00:00+08:00 | 2027-04-26T06:00:00+08:00 |  |  |  |  | 96.00 | CS2302 Secondary Crusher Rebuild 10% SOP Impact |  |  | [{"equipmentGUID": "062cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "NBWTSCS2302", "name": "Crusher - Secondary: NBWT 2302", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
81832 | 2026-03-19T22:32:19.7495846+00:00 | 2026-03-20T06:32:19.7495846+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-03-19T22:32:20.3808424+00:00 | 2026-03-20T06:32:20.3808424+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322400 | TRUE | TRUE | 2026-03-19T22:32:20.3808424+00:00 | 2026-03-20T06:32:20.3808424+08:00 | #81832 - NBWT: 96hrs - CRUSHER - SECONDARY: NBWT 2302 | 1.0 | FALSE |  | 2027-10-20T22:00:00+00:00 | 2027-10-24T22:00:00+00:00 | 2027-10-21T06:00:00+08:00 | 2027-10-25T06:00:00+08:00 |  |  |  |  | 96.00 | CS2302 Secondary Crusher Rebuild 10% SOP Impact |  |  | [{"equipmentGUID": "062cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "NBWTSCS2302", "name": "Crusher - Secondary: NBWT 2302", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84461 | 2026-10-09T04:39:21.2615822+00:00 | 2026-10-09T12:39:21.2615822+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:43.4382691+00:00 | 2026-10-12T14:57:43.4382691+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335825 | TRUE | TRUE | 2026-10-12T06:57:43.4382691+00:00 | 2026-10-12T14:57:43.4382691+08:00 | #84461 - NBWT: 4hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-05T23:30:00+00:00 | 2027-10-06T03:30:00+00:00 | 2027-10-06T07:30:00+08:00 | 2027-10-06T11:30:00+08:00 |  |  |  |  | 4.00 | Crusher CS2121 needs to have spider assembly bolts re-tensioned 48 hours post feed on and then again 144hours (6days) after feed on. this outage is for the re-tension 144 hour post feed on. |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83132, "shutVersionId": 329745, "title": "#83132 - NBWT: 250hrs - CRUSHER - PRIMARY: SGE 02", "startDatetimeUTC": "2027-09-16T11:30:00+00:00", "endDatetimeUTC": "2027-09-26T21:30:00+00:00"}}] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84460 | 2026-10-09T04:28:03.632585+00:00 | 2026-10-09T12:28:03.632585+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:43.6021192+00:00 | 2026-10-12T14:57:43.6021192+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335826 | TRUE | TRUE | 2026-10-12T06:57:43.6021192+00:00 | 2026-10-12T14:57:43.6021192+08:00 | #84460 - NBWT: 4hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-28T23:30:00+00:00 | 2027-09-29T03:30:00+00:00 | 2027-09-29T07:30:00+08:00 | 2027-09-29T11:30:00+08:00 |  |  |  |  | 4.00 | Crusher CS2121 needs to have spider assembly bolts re-tensioned 48 hours after the feed comes back on as per OEM requirements. |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83132, "shutVersionId": 329745, "title": "#83132 - NBWT: 250hrs - CRUSHER - PRIMARY: SGE 02", "startDatetimeUTC": "2027-09-16T11:30:00+00:00", "endDatetimeUTC": "2027-09-26T21:30:00+00:00"}}] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84229 | 2026-10-09T03:24:18.3785281+00:00 | 2026-10-09T11:24:18.3785281+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:43.7282616+00:00 | 2026-10-12T14:57:43.7282616+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335827 | TRUE | TRUE | 2026-10-12T06:57:43.7282616+00:00 | 2026-10-12T14:57:43.7282616+08:00 | #84229 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-20T00:00:00+00:00 | 2027-12-20T03:00:00+00:00 | 2027-12-20T08:00:00+08:00 | 2027-12-20T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84228 | 2026-10-09T03:24:18.3784758+00:00 | 2026-10-09T11:24:18.3784758+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:43.8613721+00:00 | 2026-10-12T14:57:43.8613721+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335828 | TRUE | TRUE | 2026-10-12T06:57:43.8613721+00:00 | 2026-10-12T14:57:43.8613721+08:00 | #84228 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-06T00:00:00+00:00 | 2027-12-06T03:00:00+00:00 | 2027-12-06T08:00:00+08:00 | 2027-12-06T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84226 | 2026-10-09T03:24:18.378365+00:00 | 2026-10-09T11:24:18.378365+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:43.9915812+00:00 | 2026-10-12T14:57:43.9915812+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335829 | TRUE | TRUE | 2026-10-12T06:57:43.9915812+00:00 | 2026-10-12T14:57:43.9915812+08:00 | #84226 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-08T00:00:00+00:00 | 2027-11-08T03:00:00+00:00 | 2027-11-08T08:00:00+08:00 | 2027-11-08T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84227 | 2026-10-09T03:24:18.3784193+00:00 | 2026-10-09T11:24:18.3784193+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.1319044+00:00 | 2026-10-12T14:57:44.1319044+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335830 | TRUE | TRUE | 2026-10-12T06:57:44.1319044+00:00 | 2026-10-12T14:57:44.1319044+08:00 | #84227 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-22T00:00:00+00:00 | 2027-11-22T03:00:00+00:00 | 2027-11-22T08:00:00+08:00 | 2027-11-22T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84224 | 2026-10-09T03:24:18.3782304+00:00 | 2026-10-09T11:24:18.3782304+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.264689+00:00 | 2026-10-12T14:57:44.264689+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335831 | TRUE | TRUE | 2026-10-12T06:57:44.264689+00:00 | 2026-10-12T14:57:44.264689+08:00 | #84224 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-11T00:00:00+00:00 | 2027-10-11T03:00:00+00:00 | 2027-10-11T08:00:00+08:00 | 2027-10-11T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84225 | 2026-10-09T03:24:18.3783035+00:00 | 2026-10-09T11:24:18.3783035+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.4050732+00:00 | 2026-10-12T14:57:44.4050732+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335832 | TRUE | TRUE | 2026-10-12T06:57:44.4050732+00:00 | 2026-10-12T14:57:44.4050732+08:00 | #84225 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-25T00:00:00+00:00 | 2027-10-25T03:00:00+00:00 | 2027-10-25T08:00:00+08:00 | 2027-10-25T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84223 | 2026-10-09T03:24:18.3781782+00:00 | 2026-10-09T11:24:18.3781782+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.5508967+00:00 | 2026-10-12T14:57:44.5508967+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335833 | TRUE | TRUE | 2026-10-12T06:57:44.5508967+00:00 | 2026-10-12T14:57:44.5508967+08:00 | #84223 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-27T00:00:00+00:00 | 2027-09-27T03:00:00+00:00 | 2027-09-27T08:00:00+08:00 | 2027-09-27T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84222 | 2026-10-09T03:24:18.3781232+00:00 | 2026-10-09T11:24:18.3781232+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.6932763+00:00 | 2026-10-12T14:57:44.6932763+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335834 | TRUE | TRUE | 2026-10-12T06:57:44.6932763+00:00 | 2026-10-12T14:57:44.6932763+08:00 | #84222 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-13T00:00:00+00:00 | 2027-09-13T03:00:00+00:00 | 2027-09-13T08:00:00+08:00 | 2027-09-13T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84221 | 2026-10-09T03:24:18.3780707+00:00 | 2026-10-09T11:24:18.3780707+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.8379453+00:00 | 2026-10-12T14:57:44.8379453+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335835 | TRUE | TRUE | 2026-10-12T06:57:44.8379453+00:00 | 2026-10-12T14:57:44.8379453+08:00 | #84221 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-30T00:00:00+00:00 | 2027-08-30T03:00:00+00:00 | 2027-08-30T08:00:00+08:00 | 2027-08-30T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84220 | 2026-10-09T03:24:18.3780169+00:00 | 2026-10-09T11:24:18.3780169+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:44.9779408+00:00 | 2026-10-12T14:57:44.9779408+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335836 | TRUE | TRUE | 2026-10-12T06:57:44.9779408+00:00 | 2026-10-12T14:57:44.9779408+08:00 | #84220 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-16T00:00:00+00:00 | 2027-08-16T03:00:00+00:00 | 2027-08-16T08:00:00+08:00 | 2027-08-16T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84219 | 2026-10-09T03:24:18.3779587+00:00 | 2026-10-09T11:24:18.3779587+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.1146701+00:00 | 2026-10-12T14:57:45.1146701+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335837 | TRUE | TRUE | 2026-10-12T06:57:45.1146701+00:00 | 2026-10-12T14:57:45.1146701+08:00 | #84219 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-02T00:00:00+00:00 | 2027-08-02T03:00:00+00:00 | 2027-08-02T08:00:00+08:00 | 2027-08-02T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84218 | 2026-10-09T03:24:18.3778977+00:00 | 2026-10-09T11:24:18.3778977+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.2669016+00:00 | 2026-10-12T14:57:45.2669016+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335838 | TRUE | TRUE | 2026-10-12T06:57:45.2669016+00:00 | 2026-10-12T14:57:45.2669016+08:00 | #84218 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-19T00:00:00+00:00 | 2027-07-19T03:00:00+00:00 | 2027-07-19T08:00:00+08:00 | 2027-07-19T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84217 | 2026-10-09T03:24:18.3778181+00:00 | 2026-10-09T11:24:18.3778181+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.4241555+00:00 | 2026-10-12T14:57:45.4241555+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335839 | TRUE | TRUE | 2026-10-12T06:57:45.4241555+00:00 | 2026-10-12T14:57:45.4241555+08:00 | #84217 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-05T00:00:00+00:00 | 2027-07-05T03:00:00+00:00 | 2027-07-05T08:00:00+08:00 | 2027-07-05T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84216 | 2026-10-09T03:24:18.3777332+00:00 | 2026-10-09T11:24:18.3777332+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.5785657+00:00 | 2026-10-12T14:57:45.5785657+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335840 | TRUE | TRUE | 2026-10-12T06:57:45.5785657+00:00 | 2026-10-12T14:57:45.5785657+08:00 | #84216 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-21T00:00:00+00:00 | 2027-06-21T03:00:00+00:00 | 2027-06-21T08:00:00+08:00 | 2027-06-21T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84215 | 2026-10-09T03:24:18.3776007+00:00 | 2026-10-09T11:24:18.3776007+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.7272379+00:00 | 2026-10-12T14:57:45.7272379+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335841 | TRUE | TRUE | 2026-10-12T06:57:45.7272379+00:00 | 2026-10-12T14:57:45.7272379+08:00 | #84215 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-07T00:00:00+00:00 | 2027-06-07T03:00:00+00:00 | 2027-06-07T08:00:00+08:00 | 2027-06-07T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84214 | 2026-10-09T03:24:18.3774549+00:00 | 2026-10-09T11:24:18.3774549+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:45.8758747+00:00 | 2026-10-12T14:57:45.8758747+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335842 | TRUE | TRUE | 2026-10-12T06:57:45.8758747+00:00 | 2026-10-12T14:57:45.8758747+08:00 | #84214 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-24T00:00:00+00:00 | 2027-05-24T03:00:00+00:00 | 2027-05-24T08:00:00+08:00 | 2027-05-24T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84213 | 2026-10-09T03:24:18.3774001+00:00 | 2026-10-09T11:24:18.3774001+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.0355353+00:00 | 2026-10-12T14:57:46.0355353+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335843 | TRUE | TRUE | 2026-10-12T06:57:46.0355353+00:00 | 2026-10-12T14:57:46.0355353+08:00 | #84213 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-10T00:00:00+00:00 | 2027-05-10T03:00:00+00:00 | 2027-05-10T08:00:00+08:00 | 2027-05-10T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84212 | 2026-10-09T03:24:18.3773461+00:00 | 2026-10-09T11:24:18.3773461+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.1836326+00:00 | 2026-10-12T14:57:46.1836326+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335844 | TRUE | TRUE | 2026-10-12T06:57:46.1836326+00:00 | 2026-10-12T14:57:46.1836326+08:00 | #84212 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-26T00:00:00+00:00 | 2027-04-26T03:00:00+00:00 | 2027-04-26T08:00:00+08:00 | 2027-04-26T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84211 | 2026-10-09T03:24:18.3772898+00:00 | 2026-10-09T11:24:18.3772898+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.3540978+00:00 | 2026-10-12T14:57:46.3540978+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335845 | TRUE | TRUE | 2026-10-12T06:57:46.3540978+00:00 | 2026-10-12T14:57:46.3540978+08:00 | #84211 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-12T00:00:00+00:00 | 2027-04-12T03:00:00+00:00 | 2027-04-12T08:00:00+08:00 | 2027-04-12T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84210 | 2026-10-09T03:24:18.3772347+00:00 | 2026-10-09T11:24:18.3772347+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.5272226+00:00 | 2026-10-12T14:57:46.5272226+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335846 | TRUE | TRUE | 2026-10-12T06:57:46.5272226+00:00 | 2026-10-12T14:57:46.5272226+08:00 | #84210 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-29T00:00:00+00:00 | 2027-03-29T03:00:00+00:00 | 2027-03-29T08:00:00+08:00 | 2027-03-29T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84209 | 2026-10-09T03:24:18.377176+00:00 | 2026-10-09T11:24:18.377176+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.6933186+00:00 | 2026-10-12T14:57:46.6933186+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335847 | TRUE | TRUE | 2026-10-12T06:57:46.6933186+00:00 | 2026-10-12T14:57:46.6933186+08:00 | #84209 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-15T00:00:00+00:00 | 2027-03-15T03:00:00+00:00 | 2027-03-15T08:00:00+08:00 | 2027-03-15T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84208 | 2026-10-09T03:24:18.377113+00:00 | 2026-10-09T11:24:18.377113+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:46.8551684+00:00 | 2026-10-12T14:57:46.8551684+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335848 | TRUE | TRUE | 2026-10-12T06:57:46.8551684+00:00 | 2026-10-12T14:57:46.8551684+08:00 | #84208 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-01T00:00:00+00:00 | 2027-03-01T03:00:00+00:00 | 2027-03-01T08:00:00+08:00 | 2027-03-01T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84207 | 2026-10-09T03:24:18.3770376+00:00 | 2026-10-09T11:24:18.3770376+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:47.0191994+00:00 | 2026-10-12T14:57:47.0191994+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335849 | TRUE | TRUE | 2026-10-12T06:57:47.0191994+00:00 | 2026-10-12T14:57:47.0191994+08:00 | #84207 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-15T00:00:00+00:00 | 2027-02-15T03:00:00+00:00 | 2027-02-15T08:00:00+08:00 | 2027-02-15T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84206 | 2026-10-09T03:24:18.3769509+00:00 | 2026-10-09T11:24:18.3769509+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:47.1901467+00:00 | 2026-10-12T14:57:47.1901467+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335850 | TRUE | TRUE | 2026-10-12T06:57:47.1901467+00:00 | 2026-10-12T14:57:47.1901467+08:00 | #84206 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-01T00:00:00+00:00 | 2027-02-01T03:00:00+00:00 | 2027-02-01T08:00:00+08:00 | 2027-02-01T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84205 | 2026-10-09T03:24:18.3767171+00:00 | 2026-10-09T11:24:18.3767171+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:47.3709524+00:00 | 2026-10-12T14:57:47.3709524+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335851 | TRUE | TRUE | 2026-10-12T06:57:47.3709524+00:00 | 2026-10-12T14:57:47.3709524+08:00 | #84205 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-18T00:00:00+00:00 | 2027-01-18T03:00:00+00:00 | 2027-01-18T08:00:00+08:00 | 2027-01-18T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
84204 | 2026-10-09T03:24:18.2743691+00:00 | 2026-10-09T11:24:18.2743691+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-10-12T06:57:47.5648466+00:00 | 2026-10-12T14:57:47.5648466+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335852 | TRUE | TRUE | 2026-10-12T06:57:47.5648466+00:00 | 2026-10-12T14:57:47.5648466+08:00 | #84204 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-04T00:00:00+00:00 | 2027-01-04T03:00:00+00:00 | 2027-01-04T08:00:00+08:00 | 2027-01-04T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "74df50eb-c552-4abe-ba03-360d81ab11f2", "emailAddress": "Adrian.challis@riotinto.com", "displayName": "Adrian Challis"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
68494 | 2025-07-17T02:40:31.2687067+00:00 | 2025-07-17T10:40:31.2687067+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2025-07-17T02:40:31.5032043+00:00 | 2025-07-17T10:40:31.5032043+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 242082 | TRUE | TRUE | 2025-07-17T02:40:31.5032043+00:00 | 2025-07-17T10:40:31.5032043+08:00 | #68494 - NBWT: 6hrs - PC7 ROD CRUSHER | 1.0 | TRUE |  | 2026-12-05T22:00:00+00:00 | 2026-12-06T04:00:00+00:00 | 2026-12-06T06:00:00+08:00 | 2026-12-06T12:00:00+08:00 |  |  |  |  | 6.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "8217ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPCS03", "name": "Crusher - Primary: NBWT 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6195fc57-9545-4c3a-9cb1-5ed8415353d7", "emailAddress": "Andrew.Black2@riotinto.com", "displayName": "Black, Andrew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
74632 | 2025-12-17T22:45:12.5870797+00:00 | 2025-12-18T06:45:12.5870797+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-03-20T01:01:54.3096774+00:00 | 2026-03-20T09:01:54.3096774+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322527 | TRUE | TRUE | 2026-03-20T01:01:54.3096774+00:00 | 2026-03-20T09:01:54.3096774+08:00 | #74632 - BM2: 4hrs - CRUSHER - PRIMARY: BM2 01 & PLANT: BM2 | 2.0 | TRUE |  | 2026-12-02T11:30:00+00:00 | 2026-12-02T15:30:00+00:00 | 2026-12-02T19:30:00+08:00 | 2026-12-02T23:30:00+08:00 |  |  |  |  | 4.00 | Belt Retention | Belt re-tenstion required on CR0110 drive belts and the STK002 conveyor belt 24hours after feed on. |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}, {"equipmentGUID": "5a65fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST01", "name": "Stacker: BM2 01 Fines ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "c243f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2ST02", "name": "Stacker: BM2 02 Lump ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44150, "shutVersionId": 283908, "title": "#44150 - BM2: 144hrs - PLANT: BM2", "startDatetimeUTC": "2026-02-25T11:30:00+00:00", "endDatetimeUTC": "2026-03-03T11:30:00+00:00"}}] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
73107 | 2025-11-07T02:51:26.6878748+00:00 | 2025-11-07T10:51:26.6878748+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-06-19T04:50:29.9849044+00:00 | 2026-06-19T12:50:29.9849044+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 328301 | TRUE | TRUE | 2026-06-19T04:50:29.9849044+00:00 | 2026-06-19T12:50:29.9849044+08:00 | #73107 - NBWT: 6hrs - TRAIN LOADOUT: NBWT | 2.0 | TRUE |  | 2027-04-12T22:00:00+00:00 | 2027-04-13T04:00:00+00:00 | 2027-04-13T06:00:00+08:00 | 2027-04-13T12:00:00+08:00 |  |  |  |  | 6.00 | Annual CAPD Testing on Reclaimer | Required On this day by site team. |  | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
73097 | 2025-11-07T02:51:24.6476783+00:00 | 2025-11-07T10:51:24.6476783+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | 2026-06-19T04:50:29.9849337+00:00 | 2026-06-19T12:50:29.9849337+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 328320 | TRUE | TRUE | 2026-06-19T04:50:29.9849337+00:00 | 2026-06-19T12:50:29.9849337+08:00 | #73097 - NBWT: 12hrs - PLANT: NBWT | 2.0 | TRUE |  | 2027-04-13T22:00:00+00:00 | 2027-04-14T10:00:00+00:00 | 2027-04-14T06:00:00+08:00 | 2027-04-14T18:00:00+08:00 |  |  |  |  | 12.00 | Annual CAPD Testing on Stackers | Required On this day by site team. |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
83126 | 2026-06-30T22:38:23.1080595+00:00 | 2026-07-01T06:38:23.1080595+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-10-06T00:11:45.5895598+00:00 | 2026-10-06T08:11:45.5895598+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335332 | TRUE | TRUE | 2026-10-06T00:11:45.5895598+00:00 | 2026-10-06T08:11:45.5895598+08:00 | #83126 - NBWT: 276hrs - CRUSHER - PRIMARY: NBWT 01 | 2.0 | TRUE |  | 2027-06-14T11:30:00+00:00 | 2027-06-25T23:30:00+00:00 | 2027-06-14T19:30:00+08:00 | 2027-06-26T07:30:00+08:00 |  |  |  |  | 276.00 | PC01 Apron Feeder Overhaul Vault Liners Crusher Maintenance Spider Assembly and Hydroset | There was an issue with crusher overhaul in week 37 2026 - this work will now impact the week 24 shut in 2027. to enable all work to occur the timing of PC1 needs to be extended forwards - see attached email from Shut supt for further details. | SHNP2624 | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}, {"name": "Crusher Overhaul"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
69644 | 2025-10-14T02:52:49.3864477+00:00 | 2025-10-14T10:52:49.3864477+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-02-23T01:32:08.7718082+00:00 | 2026-02-23T09:32:08.7718082+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 287734 | TRUE | TRUE | 2026-02-23T01:32:08.7718082+00:00 | 2026-02-23T09:32:08.7718082+08:00 | #69644 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0320 NO. 2 | 3.0 | TRUE |  | 2027-02-25T04:00:00+00:00 | 2027-02-28T10:00:00+00:00 | 2027-02-25T12:00:00+08:00 | 2027-02-28T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0320 Liners & Cylinders Additional Info: CR0320 Overhaul | Shutdowns were not aligned correctly - they needed to match 2026 sequence |  | [{"equipmentGUID": "1346f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0320", "name": "Crusher - Secondary: BM2 0320 No. 2", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
69646 | 2025-10-14T02:52:49.9469889+00:00 | 2025-10-14T10:52:49.9469889+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-02-23T01:32:09.5473552+00:00 | 2026-02-23T09:32:09.5473552+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 287735 | TRUE | TRUE | 2026-02-23T01:32:09.5473552+00:00 | 2026-02-23T09:32:09.5473552+08:00 | #69646 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0320 NO. 2 | 3.0 | TRUE |  | 2027-05-27T04:00:00+00:00 | 2027-05-30T10:00:00+00:00 | 2027-05-27T12:00:00+08:00 | 2027-05-30T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0320 Liners & Cylinders Additional Info: CR0320 Overhaul | Shutdowns were not aligned correctly - they needed to match 2026 sequence |  | [{"equipmentGUID": "1346f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0320", "name": "Crusher - Secondary: BM2 0320 No. 2", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
69648 | 2025-10-14T02:52:50.5655617+00:00 | 2025-10-14T10:52:50.5655617+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-02-23T01:32:10.3356401+00:00 | 2026-02-23T09:32:10.3356401+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 287736 | TRUE | TRUE | 2026-02-23T01:32:10.3356401+00:00 | 2026-02-23T09:32:10.3356401+08:00 | #69648 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0320 NO. 2 | 3.0 | TRUE |  | 2027-08-26T04:00:00+00:00 | 2027-08-29T10:00:00+00:00 | 2027-08-26T12:00:00+08:00 | 2027-08-29T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0320 Liners & Cylinders Additional Info: CR0320 Overhaul | Shutdowns were not aligned correctly - they needed to match 2026 sequence |  | [{"equipmentGUID": "1346f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0320", "name": "Crusher - Secondary: BM2 0320 No. 2", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
69650 | 2025-10-14T02:52:51.2039047+00:00 | 2025-10-14T10:52:51.2039047+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-02-23T01:32:11.1563464+00:00 | 2026-02-23T09:32:11.1563464+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 287737 | TRUE | TRUE | 2026-02-23T01:32:11.1563464+00:00 | 2026-02-23T09:32:11.1563464+08:00 | #69650 - BM2: 78hrs - CRUSHER - SECONDARY: BM2 0320 NO. 2 | 3.0 | TRUE |  | 2027-11-25T04:00:00+00:00 | 2027-11-28T10:00:00+00:00 | 2027-11-25T12:00:00+08:00 | 2027-11-28T18:00:00+08:00 |  |  |  |  | 78.00 | C/O Eljay CR0320 Liners & Cylinders Additional Info: CR0320 Overhaul | Shutdowns were not aligned correctly - they needed to match 2026 sequence |  | [{"equipmentGUID": "1346f6bf-7c7b-ee11-a846-000d3acacefd", "code": "BM2SCS0320", "name": "Crusher - Secondary: BM2 0320 No. 2", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "dd0ecd4e-867d-4d92-80ff-d7c3e31ada17", "emailAddress": "Scott.Kaye@riotinto.com", "displayName": "Kaye, Scott (RTIO)"}}] | [] | [] | [{"name": "Major Liner Changeout"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
45390 | 2021-12-13T08:26:34+00:00 | 2021-12-13T16:26:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-12-10T05:29:01.9354166+00:00 | 2025-12-10T13:29:01.9354166+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 280591 | TRUE | TRUE | 2025-12-10T05:29:01.9354166+00:00 | 2025-12-10T13:29:01.9354166+08:00 | #45390 - NBWT: 108hrs - MODULE - PLANT: NBWT 03 | 8.0 | TRUE |  | 2027-11-04T11:30:00+00:00 | 2027-11-08T23:30:00+00:00 | 2027-11-04T19:30:00+08:00 | 2027-11-09T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 3 maintenance | shut extension doesn't align with SAP change out requirement so doesn't need to be extended. |  | [{"equipmentGUID": "1814b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD03", "name": "Module - Plant: NBWT 03", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44156 | 2021-11-23T01:55:33+00:00 | 2021-11-23T09:55:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:30.2116552+00:00 | 2026-03-13T09:09:30.2116552+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321092 | TRUE | TRUE | 2026-03-13T01:09:30.2116552+00:00 | 2026-03-13T09:09:30.2116552+08:00 | #44156 - BM2: 144hrs - PLANT: BM2 | 9.0 | TRUE |  | 2027-06-02T11:30:00+00:00 | 2027-06-08T11:30:00+00:00 | 2027-06-02T19:30:00+08:00 | 2027-06-08T19:30:00+08:00 |  |  |  |  | 144.00 | TOTAL PLANT SHUT | Start time needed adjusting |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44130 | 2021-11-22T08:32:59+00:00 | 2021-11-22T16:32:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:30.5162051+00:00 | 2026-03-13T09:09:30.5162051+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321093 | TRUE | TRUE | 2026-03-13T01:09:30.5162051+00:00 | 2026-03-13T09:09:30.5162051+08:00 | #44130 - BM2: 144hrs - PLANT: BM2 | 9.0 | TRUE |  | 2027-03-03T11:30:00+00:00 | 2027-03-09T11:30:00+00:00 | 2027-03-03T19:30:00+08:00 | 2027-03-09T19:30:00+08:00 |  |  |  |  | 144.00 | TOTAL PLANT SHUT | Start time needed adjusting |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44162 | 2021-11-23T02:13:40+00:00 | 2021-11-23T10:13:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:30.649234+00:00 | 2026-03-13T09:09:30.649234+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321094 | TRUE | TRUE | 2026-03-13T01:09:30.649234+00:00 | 2026-03-13T09:09:30.649234+08:00 | #44162 - BM2: 144hrs - PLANT: BM2 | 10.0 | TRUE |  | 2027-09-01T11:30:00+00:00 | 2027-09-07T11:30:00+00:00 | 2027-09-01T19:30:00+08:00 | 2027-09-07T19:30:00+08:00 |  |  |  |  | 144.00 | TOTAL PLANT SHUT | Start time needed adjusting |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44133 | 2021-11-22T08:45:28+00:00 | 2021-11-22T16:45:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:30.7815395+00:00 | 2026-03-13T09:09:30.7815395+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321095 | TRUE | TRUE | 2026-03-13T01:09:30.7815395+00:00 | 2026-03-13T09:09:30.7815395+08:00 | #44133 - BM2: 144hrs - PLANT: BM2 | 9.0 | TRUE |  | 2027-12-01T11:30:00+00:00 | 2027-12-07T11:30:00+00:00 | 2027-12-01T19:30:00+08:00 | 2027-12-07T19:30:00+08:00 |  |  |  |  | 144.00 | TOTAL PLANT SHUT | Start time needed adjusting |  | [{"equipmentGUID": "6517ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2PLT", "name": "Plant: BM2", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44134 | 2021-11-22T08:46:28+00:00 | 2021-11-22T16:46:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:37.6183739+00:00 | 2026-03-13T09:09:37.6183739+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321128 | TRUE | TRUE | 2026-03-13T01:09:37.6183739+00:00 | 2026-03-13T09:09:37.6183739+08:00 | #44134 - BM2: 144hrs - TRAIN LOADOUT: BM2 | 10.0 | TRUE |  | 2027-03-03T11:30:00+00:00 | 2027-03-09T11:30:00+00:00 | 2027-03-03T19:30:00+08:00 | 2027-03-09T19:30:00+08:00 |  |  |  |  | 144.00 | TLO Shut | Hours requested to be 144 and start times needed to be changed to 730pm Wednesday to align with rosters |  | [{"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44161 | 2021-11-23T02:12:52+00:00 | 2021-11-23T10:12:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:37.8797178+00:00 | 2026-03-13T09:09:37.8797178+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321129 | TRUE | TRUE | 2026-03-13T01:09:37.8797178+00:00 | 2026-03-13T09:09:37.8797178+08:00 | #44161 - BM2: 144hrs - TRAIN LOADOUT: BM2 | 9.0 | TRUE |  | 2027-06-02T11:30:00+00:00 | 2027-06-08T11:30:00+00:00 | 2027-06-02T19:30:00+08:00 | 2027-06-08T19:30:00+08:00 |  |  |  |  | 144.00 | TLO Shut | Hours requested to be 144 and start times needed to be changed to 730pm Wednesday to align with rosters |  | [{"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44158 | 2021-11-23T01:56:14+00:00 | 2021-11-23T09:56:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:38.1737184+00:00 | 2026-03-13T09:09:38.1737184+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321130 | TRUE | TRUE | 2026-03-13T01:09:38.1737184+00:00 | 2026-03-13T09:09:38.1737184+08:00 | #44158 - BM2: 144hrs - TRAIN LOADOUT: BM2 | 10.0 | TRUE |  | 2027-09-01T11:30:00+00:00 | 2027-09-07T11:30:00+00:00 | 2027-09-01T19:30:00+08:00 | 2027-09-07T19:30:00+08:00 |  |  |  |  | 144.00 | TLO Shut | Hours requested to be 144 and start times needed to be changed to 730pm Wednesday to align with rosters |  | [{"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
44137 | 2021-11-22T08:49:28+00:00 | 2021-11-22T16:49:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T01:09:38.4289533+00:00 | 2026-03-13T09:09:38.4289533+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321131 | TRUE | TRUE | 2026-03-13T01:09:38.4289533+00:00 | 2026-03-13T09:09:38.4289533+08:00 | #44137 - BM2: 144hrs - TRAIN LOADOUT: BM2 | 10.0 | TRUE |  | 2027-12-01T11:30:00+00:00 | 2027-12-07T11:30:00+00:00 | 2027-12-01T19:30:00+08:00 | 2027-12-07T19:30:00+08:00 |  |  |  |  | 144.00 | TLO Shut | Hours requested to be 144 and start times needed to be changed to 730pm Wednesday to align with rosters |  | [{"equipmentGUID": "6617ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM2TLO", "name": "Train Loadout: BM2", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "emailAddress": "James.Murphy4@riotinto.com", "displayName": "Murphy, James (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | BM2 | Australia/Perth
45389 | 2021-12-13T08:26:30+00:00 | 2021-12-13T16:26:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T07:54:07.5680664+00:00 | 2026-03-13T15:54:07.5680664+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321240 | TRUE | TRUE | 2026-03-13T07:54:07.5680664+00:00 | 2026-03-13T15:54:07.5680664+08:00 | #45389 - NBWT: 108hrs - MODULE - PLANT: NBWT 04 | 8.0 | TRUE |  | 2027-08-05T17:30:00+00:00 | 2027-08-10T05:30:00+00:00 | 2027-08-06T01:30:00+08:00 | 2027-08-10T13:30:00+08:00 |  |  |  |  | 108.00 | Module 4 | This shut has been reduced as the filter belt was clashing with another filter belt task on module 1 and 2. shut 45387 will be extended to enable this change out. |  | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
41850 | 2021-05-26T01:52:59+00:00 | 2021-05-26T09:52:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T08:21:38.3008512+00:00 | 2026-03-13T16:21:38.3008512+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321245 | TRUE | TRUE | 2026-03-13T08:21:38.3008512+00:00 | 2026-03-13T16:21:38.3008512+08:00 | #41850 - NBWT: 144hrs - TRAIN LOADOUT: NBWT | 10.0 | TRUE |  | 2027-03-23T22:00:00+00:00 | 2027-03-29T22:00:00+00:00 | 2027-03-24T06:00:00+08:00 | 2027-03-30T06:00:00+08:00 |  |  |  |  | 144.00 | NBWT Train Load Out | Shut start time changed to align with IAM requirement and duration has been extended as per MOC 134422 | 12 | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11466cd8-5156-40eb-b22d-024eb82aa63f", "emailAddress": "Ric.lambert@riotinto.com", "displayName": "Ric Lambert"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44525 | 2021-11-25T03:30:16+00:00 | 2021-11-25T11:30:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T08:21:38.7646542+00:00 | 2026-03-13T16:21:38.7646542+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321247 | TRUE | TRUE | 2026-03-13T08:21:38.7646542+00:00 | 2026-03-13T16:21:38.7646542+08:00 | #44525 - NBWT: 144hrs - TRAIN LOADOUT: NBWT | 13.0 | TRUE |  | 2027-09-21T22:00:00+00:00 | 2027-09-27T22:00:00+00:00 | 2027-09-22T06:00:00+08:00 | 2027-09-28T06:00:00+08:00 |  |  |  |  | 144.00 | NBWT Train Load Out | Shut start time changed to align with IAM requirement and duration has been extended as per MOC 134422 | 38 | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44527 | 2021-11-25T03:30:20+00:00 | 2021-11-25T11:30:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-13T08:21:38.9869049+00:00 | 2026-03-13T16:21:38.9869049+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321248 | TRUE | TRUE | 2026-03-13T08:21:38.9869049+00:00 | 2026-03-13T16:21:38.9869049+08:00 | #44527 - NBWT: 144hrs - TRAIN LOADOUT: NBWT | 8.0 | TRUE |  | 2027-12-21T22:00:00+00:00 | 2027-12-27T22:00:00+00:00 | 2027-12-22T06:00:00+08:00 | 2027-12-28T06:00:00+08:00 |  |  |  |  | 144.00 | NBWT Train Load Out | Shut start time changed to align with IAM requirement and duration has been extended as per MOC 134422 | 51 | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
45342 | 2021-12-13T08:25:14+00:00 | 2021-12-13T16:25:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-17T07:11:22.4094809+00:00 | 2026-03-17T15:11:22.4094809+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321463 | TRUE | TRUE | 2026-03-17T07:11:22.4094809+00:00 | 2026-03-17T15:11:22.4094809+08:00 | #45342 - NBWT: 108hrs - MODULE - PLANT: NBWT 01 | 9.0 | TRUE |  | 2027-04-29T11:30:00+00:00 | 2027-05-03T23:30:00+00:00 | 2027-04-29T19:30:00+08:00 | 2027-05-04T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 1 maintenance | shut start date was incorrect |  | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44501 | 2021-11-25T03:29:36+00:00 | 2021-11-25T11:29:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-17T07:11:24.7204584+00:00 | 2026-03-17T15:11:24.7204584+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321475 | TRUE | TRUE | 2026-03-17T07:11:24.7204584+00:00 | 2026-03-17T15:11:24.7204584+08:00 | #44501 - NBWT: 144hrs - PLANT: NBWT | 9.0 | TRUE |  | 2027-12-15T11:30:00+00:00 | 2027-12-21T11:30:00+00:00 | 2027-12-15T19:30:00+08:00 | 2027-12-21T19:30:00+08:00 |  |  |  |  | 144.00 | NBWT Plant shut | Duration has not changed - Start time and start day have been adjusted to suit IAM scheduled |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44505 | 2021-11-25T03:29:41+00:00 | 2021-11-25T11:29:41+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-18T00:03:51.2234683+00:00 | 2026-03-18T08:03:51.2234683+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 321791 | TRUE | TRUE | 2026-03-18T00:03:51.2234683+00:00 | 2026-03-18T08:03:51.2234683+08:00 | #44505 - NBWT: 144hrs - PLANT: NBWT | 12.1 | TRUE |  | 2027-03-17T11:30:00+00:00 | 2027-03-23T11:30:00+00:00 | 2027-03-17T19:30:00+08:00 | 2027-03-23T19:30:00+08:00 |  |  |  |  | 144.00 | NBWT Plant shut |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83141, "shutVersionId": 329529, "title": "#83141 - NBWT: 6hrs - PLANT: NBWT", "startDatetimeUTC": "2027-06-27T23:30:00+00:00", "endDatetimeUTC": "2027-06-28T05:30:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 83142, "shutVersionId": 329530, "title": "#83142 - NBWT: 6hrs - PLANT: NBWT", "startDatetimeUTC": "2027-09-27T23:30:00+00:00", "endDatetimeUTC": "2027-09-28T05:30:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 83143, "shutVersionId": 329531, "title": "#83143 - NBWT: 6hrs - PLANT: NBWT", "startDatetimeUTC": "2027-12-23T23:30:00+00:00", "endDatetimeUTC": "2027-12-24T05:30:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 83140, "shutVersionId": 329532, "title": "#83140 - NBWT: 6hrs - PLANT: NBWT", "startDatetimeUTC": "2027-03-25T23:30:00+00:00", "endDatetimeUTC": "2027-03-26T05:30:00+00:00"}}] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
45391 | 2021-12-13T08:26:35+00:00 | 2021-12-13T16:26:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-19T08:05:27.7555204+00:00 | 2026-03-19T16:05:27.7555204+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322096 | TRUE | TRUE | 2026-03-19T08:05:27.7555204+00:00 | 2026-03-19T16:05:27.7555204+08:00 | #45391 - NBWT: 108hrs - MODULE - PLANT: NBWT 04 | 8.0 | TRUE |  | 2027-11-04T17:30:00+00:00 | 2027-11-09T05:30:00+00:00 | 2027-11-05T01:30:00+08:00 | 2027-11-09T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 4 maintenance | Making in line with standard module shut of 108 hours. |  | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
45386 | 2021-12-13T08:26:25+00:00 | 2021-12-13T16:26:25+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-19T08:05:27.7555206+00:00 | 2026-03-19T16:05:27.7555206+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322097 | TRUE | TRUE | 2026-03-19T08:05:27.7555206+00:00 | 2026-03-19T16:05:27.7555206+08:00 | #45386 - NBWT: 108hrs - MODULE - PLANT: NBWT 03 | 8.0 | TRUE |  | 2027-05-06T11:30:00+00:00 | 2027-05-10T23:30:00+00:00 | 2027-05-06T19:30:00+08:00 | 2027-05-11T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 3 maintenance | Making in line with standard module shut of 108 hours. |  | [{"equipmentGUID": "1814b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD03", "name": "Module - Plant: NBWT 03", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
45347 | 2021-12-13T08:25:20+00:00 | 2021-12-13T16:25:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-19T08:17:52.7300483+00:00 | 2026-03-19T16:17:52.7300483+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 322112 | TRUE | TRUE | 2026-03-19T08:17:52.7300483+00:00 | 2026-03-19T16:17:52.7300483+08:00 | #45347 - NBWT: 108hrs - MODULE - PLANT: NBWT 02 | 9.0 | TRUE |  | 2027-10-28T17:30:00+00:00 | 2027-11-02T05:30:00+00:00 | 2027-10-29T01:30:00+08:00 | 2027-11-02T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 2 maintenance | Reducing to line up with standard moduole 108 hour shuts. |  | [{"equipmentGUID": "1714b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD02", "name": "Module - Plant: NBWT 02", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44523 | 2021-11-25T03:30:11+00:00 | 2021-11-25T11:30:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-22T07:15:06.8475786+00:00 | 2026-07-22T15:15:06.8475786+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 330264 | TRUE | TRUE | 2026-07-22T07:15:06.8475786+00:00 | 2026-07-22T15:15:06.8475786+08:00 | #44523 - NBWT: 192hrs - TRAIN LOADOUT: NBWT | 12.0 | TRUE |  | 2027-06-22T22:00:00+00:00 | 2027-06-30T22:00:00+00:00 | 2027-06-23T06:00:00+08:00 | 2027-07-01T06:00:00+08:00 |  |  |  |  | 192.00 | NBWT Train Load Out Reclaimer Luff cylinder Replacement | Balanced Machine SME, Michael Tailor has suggest that the Luff Cylinders on the Nammuldi reclaimer needs to be replaced in 2027. | 25 | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44570 | 2021-11-25T03:31:33+00:00 | 2021-11-25T11:31:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:50:37.9215149+00:00 | 2026-10-02T14:50:37.9215149+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335046 | TRUE | TRUE | 2026-10-02T06:50:37.9215149+00:00 | 2026-10-02T14:50:37.9215149+08:00 | #44570 - NBWT: 108hrs - CRUSHER - PRIMARY: SGE 02 | 8.0 | TRUE |  | 2027-02-04T11:30:00+00:00 | 2027-02-08T23:30:00+00:00 | 2027-02-04T19:30:00+08:00 | 2027-02-09T07:30:00+08:00 |  |  |  |  | 108.00 | PC02 Shut | Comments - Shut Supt Andrew Saunders "SGE needs to be 108 hrs, that was part of our operating strategy with commissioning and tool time not being sufficient through the mod shuts, if single line mods goes ahead SGE will always be linked to a module" |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
44572 | 2021-11-25T03:31:35+00:00 | 2021-11-25T11:31:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:50:38.2088776+00:00 | 2026-10-02T14:50:38.2088776+08:00 | {"principalGUID": "4ccec04b-6933-40a4-ba67-f806f098c657", "displayName": "Murphy, James (RTIO)"} | {"name": "Fixed Plant"} | 335047 | TRUE | TRUE | 2026-10-02T06:50:38.2088776+00:00 | 2026-10-02T14:50:38.2088776+08:00 | #44572 - NBWT: 108hrs - CRUSHER - PRIMARY: SGE 02 | 6.0 | TRUE |  | 2027-08-05T11:30:00+00:00 | 2027-08-09T23:30:00+00:00 | 2027-08-05T19:30:00+08:00 | 2027-08-10T07:30:00+08:00 |  |  |  |  | 108.00 | PC02 Shut | Comments - Shut Supt Andrew Saunders "SGE needs to be 108 hrs, that was part of our operating strategy with commissioning and tool time not being sufficient through the mod shuts, if single line mods goes ahead SGE will always be linked to a module" |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | 4ccec04b-6933-40a4-ba67-f806f098c657 | Murphy, James (RTIO) | Scheduled | NBWT | Australia/Perth
69741 | 2025-10-15T00:56:04.6477759+00:00 | 2025-10-15T08:56:04.6477759+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-08-10T05:09:05.1774465+00:00 | 2026-08-10T13:09:05.1774465+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330992 | TRUE | TRUE | 2026-08-10T05:09:05.1774465+00:00 | 2026-08-10T13:09:05.1774465+08:00 | #69741 - MTP: 88hrs - CONVEYOR: MTP 24M | 2.0 | FALSE |  | 2026-12-27T20:00:00+00:00 | 2026-12-31T12:00:00+00:00 | 2026-12-28T04:00:00+08:00 | 2026-12-31T20:00:00+08:00 |  |  |  |  | 88.00 | 24M Module Maintenance | Structural works under conveyor length |  | [{"equipmentGUID": "b43ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV24M", "name": "Conveyor: MTP 24M", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
70575 | 2025-10-15T05:59:06.8795301+00:00 | 2025-10-15T13:59:06.8795301+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2025-10-20T00:43:27.0590368+00:00 | 2025-10-20T08:43:27.0590368+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 260768 | TRUE | TRUE | 2025-10-20T00:43:27.0590368+00:00 | 2025-10-20T08:43:27.0590368+08:00 | #70575 - MTP: 39hrs - SCREEN: MTP FINAL PRODUCT NO. 7 | 2.0 | FALSE |  | 2027-01-01T20:00:00+00:00 | 2027-01-03T11:00:00+00:00 | 2027-01-02T04:00:00+08:00 | 2027-01-03T19:00:00+08:00 |  |  |  |  | 39.00 | 7FPS Module Maintenance | Correcting date error |  | [{"equipmentGUID": "c808f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC7FPS", "name": "Screen: MTP Final Product No. 7 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82737 | 2026-06-02T05:50:46.7681262+00:00 | 2026-06-02T13:50:46.7681262+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-09-15T01:07:59.3653104+00:00 | 2026-09-15T09:07:59.3653104+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 333404 | TRUE | TRUE | 2026-09-15T01:07:59.3653104+00:00 | 2026-09-15T09:07:59.3653104+08:00 | #82737 - MTP: 92hrs - 88STK MODULE | 1.1 | FALSE |  | 2027-02-08T16:00:00+00:00 | 2027-02-12T12:00:00+00:00 | 2027-02-09T00:00:00+08:00 | 2027-02-12T20:00:00+08:00 |  |  |  |  | 92.00 | 88STK Module Maintenance P-0504955 – TP Overhead Protection Project 88STK Tripper Guard Install Project Contact: Lionel Koh (Lionel.Koh@riotinto.com) |  |  | [{"equipmentGUID": "b858fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST88", "name": "Stacker: MTP 88 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
68970 | 2025-09-05T05:16:57.8912976+00:00 | 2025-09-05T13:16:57.8912976+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-09-10T01:23:16.9692412+00:00 | 2026-09-10T09:23:16.9692412+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 333310 | TRUE | TRUE | 2026-09-10T01:23:16.9692412+00:00 | 2026-09-10T09:23:16.9692412+08:00 | #68970 - MTP: 84hrs - CONVEYOR: MTP 16C | 2.0 | FALSE |  | 2026-12-29T22:00:00+00:00 | 2027-01-02T10:00:00+00:00 | 2026-12-30T06:00:00+08:00 | 2027-01-02T18:00:00+08:00 |  |  |  |  | 84.00 | 16C Modular Maintenance | Work scope change for HSECAM |  | [{"equipmentGUID": "", "code": "MTPCV16C", "name": "Conveyor: MTP 16C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82121 | 2026-03-30T22:32:52.0258366+00:00 | 2026-03-31T06:32:52.0258366+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-05-07T06:53:03.7080212+00:00 | 2026-05-07T14:53:03.7080212+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 326130 | TRUE | TRUE | 2026-05-07T06:53:03.7080212+00:00 | 2026-05-07T14:53:03.7080212+08:00 | #82121 - MTP: 6hrs - 42BWR PROCESS INSPECTION | 1.0 | TRUE |  | 2026-12-09T11:00:00+00:00 | 2026-12-09T17:00:00+00:00 | 2026-12-09T19:00:00+08:00 | 2026-12-10T01:00:00+08:00 |  |  |  |  | 6.00 | Mechanical 42BWR Inspection Process Off |  |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "85e100c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPRC42", "name": "Reclaimer: MTP 42", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82724 | 2026-06-02T05:50:46.7679654+00:00 | 2026-06-02T13:50:46.7679654+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-24T02:26:35.2040679+00:00 | 2026-06-24T10:26:35.2040679+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 328429 | TRUE | TRUE | 2026-06-24T02:26:35.2040679+00:00 | 2026-06-24T10:26:35.2040679+08:00 | #82724 - MTP: 116hrs - W&S MODULE 3 | 2.0 | FALSE |  | 2027-01-15T16:00:00+00:00 | 2027-01-20T12:00:00+00:00 | 2027-01-16T00:00:00+08:00 | 2027-01-20T20:00:00+08:00 |  |  |  |  | 116.00 | W&S Module 3 Maintenance Underpan replacement on Primary Screen | Underpan replacement on Primary Screen |  | [{"equipmentGUID": "61efe581-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD03", "name": "Screen: MTP Wash & Screen Module 03", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82662 | 2026-06-02T03:13:23.6609101+00:00 | 2026-06-02T11:13:23.6609101+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:39.4846985+00:00 | 2026-06-08T07:54:39.4846985+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327427 | TRUE | TRUE | 2026-06-07T23:54:39.4846985+00:00 | 2026-06-08T07:54:39.4846985+08:00 | #82662 - MTP: 172hrs - CYCLONE 1 MODULE | 1.0 | FALSE |  | 2027-01-26T11:00:00+00:00 | 2027-02-02T15:00:00+00:00 | 2027-01-26T19:00:00+08:00 | 2027-02-02T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 1 Module Maintenance |  |  | [{"equipmentGUID": "909b68e0-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD01", "name": "Cyclone: MTP Module 01", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82661 | 2026-06-02T03:13:23.6609022+00:00 | 2026-06-02T11:13:23.6609022+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:40.2239064+00:00 | 2026-06-08T07:54:40.2239064+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327428 | TRUE | TRUE | 2026-06-07T23:54:40.2239064+00:00 | 2026-06-08T07:54:40.2239064+08:00 | #82661 - MTP: 42hrs - 71C MODULE | 1.0 | FALSE |  | 2027-07-15T18:00:00+00:00 | 2027-07-17T12:00:00+00:00 | 2027-07-16T02:00:00+08:00 | 2027-07-17T20:00:00+08:00 |  |  |  |  | 42.00 | 71C Module Maintenance |  |  | [{"equipmentGUID": "5570fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV71C", "name": "Conveyor: MTP 71C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82660 | 2026-06-02T03:13:23.6608929+00:00 | 2026-06-02T11:13:23.6608929+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:40.9527719+00:00 | 2026-06-08T07:54:40.9527719+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327429 | TRUE | TRUE | 2026-06-07T23:54:40.9527719+00:00 | 2026-06-08T07:54:40.9527719+08:00 | #82660 - MTP: 42hrs - 71C MODULE | 1.0 | FALSE |  | 2027-01-14T18:00:00+00:00 | 2027-01-16T12:00:00+00:00 | 2027-01-15T02:00:00+08:00 | 2027-01-16T20:00:00+08:00 |  |  |  |  | 42.00 | 71C Module Maintenance |  |  | [{"equipmentGUID": "5570fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV71C", "name": "Conveyor: MTP 71C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82659 | 2026-06-02T03:13:23.660864+00:00 | 2026-06-02T11:13:23.660864+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:41.6728232+00:00 | 2026-06-08T07:54:41.6728232+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327430 | TRUE | TRUE | 2026-06-07T23:54:41.6728232+00:00 | 2026-06-08T07:54:41.6728232+08:00 | #82659 - MTP: 44hrs - P252 MODULE | 1.0 | FALSE |  | 2027-07-13T16:00:00+00:00 | 2027-07-15T12:00:00+00:00 | 2027-07-14T00:00:00+08:00 | 2027-07-15T20:00:00+08:00 |  |  |  |  | 44.00 | P252 Module Maintenance |  |  | [{"equipmentGUID": "da3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP252", "name": "Pump: MTP 252 Spirals Cyclone Feed 02", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82658 | 2026-06-02T03:13:23.6608545+00:00 | 2026-06-02T11:13:23.6608545+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:42.3617848+00:00 | 2026-06-08T07:54:42.3617848+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327431 | TRUE | TRUE | 2026-06-07T23:54:42.3617848+00:00 | 2026-06-08T07:54:42.3617848+08:00 | #82658 - MTP: 44hrs - P252 MODULE | 1.0 | FALSE |  | 2027-01-12T16:00:00+00:00 | 2027-01-14T12:00:00+00:00 | 2027-01-13T00:00:00+08:00 | 2027-01-14T20:00:00+08:00 |  |  |  |  | 44.00 | P252 Module Maintenance |  |  | [{"equipmentGUID": "da3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP252", "name": "Pump: MTP 252 Spirals Cyclone Feed 02", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82657 | 2026-06-02T03:13:23.6608302+00:00 | 2026-06-02T11:13:23.6608302+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:43.1236906+00:00 | 2026-06-08T07:54:43.1236906+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327432 | TRUE | TRUE | 2026-06-07T23:54:43.1236906+00:00 | 2026-06-08T07:54:43.1236906+08:00 | #82657 - MTP: 44hrs - P251 MODULE | 1.0 | FALSE |  | 2027-07-11T16:00:00+00:00 | 2027-07-13T12:00:00+00:00 | 2027-07-12T00:00:00+08:00 | 2027-07-13T20:00:00+08:00 |  |  |  |  | 44.00 | P251 Module Maintenance |  |  | [{"equipmentGUID": "a00bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP251", "name": "Pump: MTP 251 Spirals Cyclone Feed 01", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82656 | 2026-06-02T03:13:23.6603483+00:00 | 2026-06-02T11:13:23.6603483+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:43.8599271+00:00 | 2026-06-08T07:54:43.8599271+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327433 | TRUE | TRUE | 2026-06-07T23:54:43.8599271+00:00 | 2026-06-08T07:54:43.8599271+08:00 | #82656 - MTP: 44hrs - P251 MODULE | 1.0 | FALSE |  | 2027-01-10T16:00:00+00:00 | 2027-01-12T12:00:00+00:00 | 2027-01-11T00:00:00+08:00 | 2027-01-12T20:00:00+08:00 |  |  |  |  | 44.00 | P251 Module Maintenance |  |  | [{"equipmentGUID": "a00bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP251", "name": "Pump: MTP 251 Spirals Cyclone Feed 01", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
68827 | 2025-09-05T02:35:00.4609525+00:00 | 2025-09-05T10:35:00.4609525+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-10-20T02:18:38.9378296+00:00 | 2025-10-20T10:18:38.9378296+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 260788 | TRUE | TRUE | 2025-10-20T02:18:38.9378296+00:00 | 2025-10-20T10:18:38.9378296+08:00 | #68827 - MTP: 92hrs - CRUSHER - SECONDARY: MTP 05 LOW GRADE | 4.0 | FALSE |  | 2026-12-14T16:00:00+00:00 | 2026-12-18T12:00:00+00:00 | 2026-12-15T00:00:00+08:00 | 2026-12-18T20:00:00+08:00 |  |  |  |  | 92.00 | 5CCT Module Maintenance | Correcting date error |  | [{"equipmentGUID": "4cf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS05", "name": "Crusher - Secondary: MTP 05 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "9d3595e7-5258-4113-83da-60aee539f6ec", "emailAddress": "jean.vanwijk@riotinto.com", "displayName": "Van Wijk, Jean (RTA)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82672 | 2026-06-02T03:13:23.6610005+00:00 | 2026-06-02T11:13:23.6610005+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:31.8698856+00:00 | 2026-06-08T07:54:31.8698856+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327416 | TRUE | TRUE | 2026-06-07T23:54:31.8698856+00:00 | 2026-06-08T07:54:31.8698856+08:00 | #82672 - MTP: 124hrs - SPIRALS 3 MODULE | 1.0 | FALSE |  | 2027-02-03T11:00:00+00:00 | 2027-02-08T15:00:00+00:00 | 2027-02-03T19:00:00+08:00 | 2027-02-08T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 3 Module Maintenance |  |  | [{"equipmentGUID": "53121ca8-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD03", "name": "Spirals: MTP Module 03", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82673 | 2026-06-02T03:13:23.6610088+00:00 | 2026-06-02T11:13:23.6610088+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:32.5577622+00:00 | 2026-06-08T07:54:32.5577622+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327417 | TRUE | TRUE | 2026-06-07T23:54:32.5577622+00:00 | 2026-06-08T07:54:32.5577622+08:00 | #82673 - MTP: 124hrs - SPIRALS 3 MODULE | 1.0 | FALSE |  | 2027-08-04T11:00:00+00:00 | 2027-08-09T15:00:00+00:00 | 2027-08-04T19:00:00+08:00 | 2027-08-09T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 3 Module Maintenance |  |  | [{"equipmentGUID": "53121ca8-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD03", "name": "Spirals: MTP Module 03", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82671 | 2026-06-02T03:13:23.6609916+00:00 | 2026-06-02T11:13:23.6609916+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:33.2383655+00:00 | 2026-06-08T07:54:33.2383655+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327418 | TRUE | TRUE | 2026-06-07T23:54:33.2383655+00:00 | 2026-06-08T07:54:33.2383655+08:00 | #82671 - MTP: 124hrs - SPIRALS 2 MODULE | 1.0 | FALSE |  | 2027-11-29T11:00:00+00:00 | 2027-12-04T15:00:00+00:00 | 2027-11-29T19:00:00+08:00 | 2027-12-04T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 2 Module Maintenance |  |  | [{"equipmentGUID": "bd470ca1-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD02", "name": "Spirals: MTP Module 02", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82670 | 2026-06-02T03:13:23.6609811+00:00 | 2026-06-02T11:13:23.6609811+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:33.9196893+00:00 | 2026-06-08T07:54:33.9196893+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327419 | TRUE | TRUE | 2026-06-07T23:54:33.9196893+00:00 | 2026-06-08T07:54:33.9196893+08:00 | #82670 - MTP: 124hrs - SPIRALS 2 MODULE | 1.0 | FALSE |  | 2027-05-30T11:00:00+00:00 | 2027-06-04T15:00:00+00:00 | 2027-05-30T19:00:00+08:00 | 2027-06-04T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 2 Module Maintenance |  |  | [{"equipmentGUID": "bd470ca1-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD02", "name": "Spirals: MTP Module 02", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82669 | 2026-06-02T03:13:23.6609708+00:00 | 2026-06-02T11:13:23.6609708+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:34.5947426+00:00 | 2026-06-08T07:54:34.5947426+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327420 | TRUE | TRUE | 2026-06-07T23:54:34.5947426+00:00 | 2026-06-08T07:54:34.5947426+08:00 | #82669 - MTP: 124hrs - SPIRALS 1 MODULE | 1.0 | FALSE |  | 2027-10-07T11:00:00+00:00 | 2027-10-12T15:00:00+00:00 | 2027-10-07T19:00:00+08:00 | 2027-10-12T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 1 Module Maintenance |  |  | [{"equipmentGUID": "8d052a97-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD01", "name": "Spirals: MTP Module 01", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82668 | 2026-06-02T03:13:23.660963+00:00 | 2026-06-02T11:13:23.660963+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:35.2860126+00:00 | 2026-06-08T07:54:35.2860126+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327421 | TRUE | TRUE | 2026-06-07T23:54:35.2860126+00:00 | 2026-06-08T07:54:35.2860126+08:00 | #82668 - MTP: 124hrs - SPIRALS 1 MODULE | 1.0 | FALSE |  | 2027-04-08T11:00:00+00:00 | 2027-04-13T15:00:00+00:00 | 2027-04-08T19:00:00+08:00 | 2027-04-13T23:00:00+08:00 |  |  |  |  | 124.00 | Spirals 1 Module Maintenance |  |  | [{"equipmentGUID": "8d052a97-7580-ef11-a853-000d3acacefd", "code": "MTPSPIMOD01", "name": "Spirals: MTP Module 01", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82666 | 2026-06-02T03:13:23.6609458+00:00 | 2026-06-02T11:13:23.6609458+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:35.9642161+00:00 | 2026-06-08T07:54:35.9642161+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327422 | TRUE | TRUE | 2026-06-07T23:54:35.9642161+00:00 | 2026-06-08T07:54:35.9642161+08:00 | #82666 - MTP: 172hrs - CYCLONE 3 MODULE | 1.0 | FALSE |  | 2027-03-30T11:00:00+00:00 | 2027-04-06T15:00:00+00:00 | 2027-03-30T19:00:00+08:00 | 2027-04-06T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 3 Module Maintenance |  |  | [{"equipmentGUID": "850018f6-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD03", "name": "Cyclone: MTP Module 03", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82667 | 2026-06-02T03:13:23.6609537+00:00 | 2026-06-02T11:13:23.6609537+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:36.7071655+00:00 | 2026-06-08T07:54:36.7071655+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327423 | TRUE | TRUE | 2026-06-07T23:54:36.7071655+00:00 | 2026-06-08T07:54:36.7071655+08:00 | #82667 - MTP: 172hrs - CYCLONE 3 MODULE | 1.0 | FALSE |  | 2027-09-28T11:00:00+00:00 | 2027-10-05T15:00:00+00:00 | 2027-09-28T19:00:00+08:00 | 2027-10-05T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 3 Module Maintenance |  |  | [{"equipmentGUID": "850018f6-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD03", "name": "Cyclone: MTP Module 03", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82665 | 2026-06-02T03:13:23.6609355+00:00 | 2026-06-02T11:13:23.6609355+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:37.4315561+00:00 | 2026-06-08T07:54:37.4315561+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327424 | TRUE | TRUE | 2026-06-07T23:54:37.4315561+00:00 | 2026-06-08T07:54:37.4315561+08:00 | #82665 - MTP: 172hrs - CYCLONE 2 MODULE | 1.0 | FALSE |  | 2027-10-14T11:00:00+00:00 | 2027-10-21T15:00:00+00:00 | 2027-10-14T19:00:00+08:00 | 2027-10-21T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 2 Module Maintenance |  |  | [{"equipmentGUID": "25fbd9e8-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD02", "name": "Cyclone: MTP Module 02", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82664 | 2026-06-02T03:13:23.6609275+00:00 | 2026-06-02T11:13:23.6609275+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:38.1115442+00:00 | 2026-06-08T07:54:38.1115442+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327425 | TRUE | TRUE | 2026-06-07T23:54:38.1115442+00:00 | 2026-06-08T07:54:38.1115442+08:00 | #82664 - MTP: 172hrs - CYCLONE 2 MODULE | 1.0 | FALSE |  | 2027-04-15T11:00:00+00:00 | 2027-04-22T15:00:00+00:00 | 2027-04-15T19:00:00+08:00 | 2027-04-22T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 2 Module Maintenance |  |  | [{"equipmentGUID": "25fbd9e8-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD02", "name": "Cyclone: MTP Module 02", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82663 | 2026-06-02T03:13:23.6609199+00:00 | 2026-06-02T11:13:23.6609199+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:38.8073601+00:00 | 2026-06-08T07:54:38.8073601+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327426 | TRUE | TRUE | 2026-06-07T23:54:38.8073601+00:00 | 2026-06-08T07:54:38.8073601+08:00 | #82663 - MTP: 172hrs - CYCLONE 1 MODULE | 1.0 | FALSE |  | 2027-07-27T11:00:00+00:00 | 2027-08-03T15:00:00+00:00 | 2027-07-27T19:00:00+08:00 | 2027-08-03T23:00:00+08:00 |  |  |  |  | 172.00 | Cyclone 1 Module Maintenance |  |  | [{"equipmentGUID": "909b68e0-0c89-ef11-a853-000d3acacefd", "code": "MTPCYMOD01", "name": "Cyclone: MTP Module 01", "assetClass": {"name": "Cyclone"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82704 | 2026-06-02T05:50:46.7677716+00:00 | 2026-06-02T13:50:46.7677716+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-10T05:08:41.9213173+00:00 | 2026-08-10T13:08:41.9213173+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330991 | TRUE | TRUE | 2026-08-10T05:08:41.9213173+00:00 | 2026-08-10T13:08:41.9213173+08:00 | #82704 - MTP: 88hrs - 31M CONVEYOR MODULE | 2.0 | FALSE |  | 2027-03-14T20:00:00+00:00 | 2027-03-18T12:00:00+00:00 | 2027-03-15T04:00:00+08:00 | 2027-03-18T20:00:00+08:00 |  |  |  |  | 88.00 | 31M Module Maintenance | Structural work under conveyor length |  | [{"equipmentGUID": "a8ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV31M", "name": "Conveyor: MTP 31M", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
83680 | 2026-08-11T23:35:20.2486169+00:00 | 2026-08-12T07:35:20.2486169+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-18T04:23:46.980837+00:00 | 2026-08-18T12:23:46.980837+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 331384 | TRUE | TRUE | 2026-08-18T04:23:46.980837+00:00 | 2026-08-18T12:23:46.980837+08:00 | #83680 - MTP: 121hrs - W&S MOD 5 POSTSHUT TRIPLE CHUTE C/O | 1.0 | FALSE |  | 2027-05-15T11:00:00+00:00 | 2027-05-20T12:00:00+00:00 | 2027-05-15T19:00:00+08:00 | 2027-05-20T20:00:00+08:00 |  |  |  |  | 121.00 | W&S Module 5, Triple chute C/O, Post Low Grade Shutdown works Install Primary Screen (AURY), Install Underpan, Install Dewatering Launder, Install 3-way Post shut from the triple chute installs for 20c, 22C and 24C conveyors |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "390dba50-1ed6-4ddd-8496-5659f095f8e1", "emailAddress": "Ursula.Tovey@riotinto.com", "displayName": "Ursula Tovey"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44956, "shutVersionId": 327782, "title": "#44956 - MTP: 264hrs - PLANT: MTP LOW GRADE", "startDatetimeUTC": "2027-05-04T11:00:00+00:00", "endDatetimeUTC": "2027-05-15T11:00:00+00:00"}}] | [{"name": "Other"}] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
83679 | 2026-08-11T23:23:48.8415694+00:00 | 2026-08-12T07:23:48.8415694+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-18T04:23:47.236466+00:00 | 2026-08-18T12:23:47.236466+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 331385 | TRUE | TRUE | 2026-08-18T04:23:47.236466+00:00 | 2026-08-18T12:23:47.236466+08:00 | #83679 - MTP: 135hrs - W&S MOD 5 PRESHUT TRIPLE CHUTE C/O | 1.0 | FALSE |  | 2027-04-28T20:00:00+00:00 | 2027-05-04T11:00:00+00:00 | 2027-04-29T04:00:00+08:00 | 2027-05-04T19:00:00+08:00 |  |  |  |  | 135.00 | W&S Module 5, Triple chute C/O, Pre Low Grade shut works Remove primary screen, Underpan, 3-Way and Dewatering Launder ready for the triple chute to be replace to 20C, 22C and 24C conveyors |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "390dba50-1ed6-4ddd-8496-5659f095f8e1", "emailAddress": "Ursula.Tovey@riotinto.com", "displayName": "Ursula Tovey"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44956, "shutVersionId": 327782, "title": "#44956 - MTP: 264hrs - PLANT: MTP LOW GRADE", "startDatetimeUTC": "2027-05-04T11:00:00+00:00", "endDatetimeUTC": "2027-05-15T11:00:00+00:00"}}] | [{"name": "Other"}] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82802 | 2026-06-02T07:14:46.267176+00:00 | 2026-06-02T15:14:46.267176+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:34.6660744+00:00 | 2026-06-08T07:53:34.6660744+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327298 | TRUE | TRUE | 2026-06-07T23:53:34.6660744+00:00 | 2026-06-08T07:53:34.6660744+08:00 | #82802 - MTP: 68hrs - 1TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-12-31T16:00:00+00:00 | 2028-01-03T12:00:00+00:00 | 2028-01-01T00:00:00+08:00 | 2028-01-03T20:00:00+08:00 |  |  |  |  | 68.00 | 1TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "7734f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS01", "name": "Crusher - Tertiary: MTP 01 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82800 | 2026-06-02T07:14:46.2671516+00:00 | 2026-06-02T15:14:46.2671516+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:34.914738+00:00 | 2026-06-08T07:53:34.914738+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327299 | TRUE | TRUE | 2026-06-07T23:53:34.914738+00:00 | 2026-06-08T07:53:34.914738+08:00 | #82800 - MTP: 68hrs - 1TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-07-02T16:00:00+00:00 | 2027-07-05T12:00:00+00:00 | 2027-07-03T00:00:00+08:00 | 2027-07-05T20:00:00+08:00 |  |  |  |  | 68.00 | 1TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "7734f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS01", "name": "Crusher - Tertiary: MTP 01 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82801 | 2026-06-02T07:14:46.2671638+00:00 | 2026-06-02T15:14:46.2671638+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:35.1875195+00:00 | 2026-06-08T07:53:35.1875195+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327300 | TRUE | TRUE | 2026-06-07T23:53:35.1875195+00:00 | 2026-06-08T07:53:35.1875195+08:00 | #82801 - MTP: 68hrs - 1TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-10-01T16:00:00+00:00 | 2027-10-04T12:00:00+00:00 | 2027-10-02T00:00:00+08:00 | 2027-10-04T20:00:00+08:00 |  |  |  |  | 68.00 | 1TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "7734f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS01", "name": "Crusher - Tertiary: MTP 01 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82799 | 2026-06-02T07:14:46.2671375+00:00 | 2026-06-02T15:14:46.2671375+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:35.4319006+00:00 | 2026-06-08T07:53:35.4319006+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327301 | TRUE | TRUE | 2026-06-07T23:53:35.4319006+00:00 | 2026-06-08T07:53:35.4319006+08:00 | #82799 - MTP: 68hrs - 1TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-04-02T16:00:00+00:00 | 2027-04-05T12:00:00+00:00 | 2027-04-03T00:00:00+08:00 | 2027-04-05T20:00:00+08:00 |  |  |  |  | 68.00 | 1TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "7734f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS01", "name": "Crusher - Tertiary: MTP 01 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82798 | 2026-06-02T07:14:46.2671256+00:00 | 2026-06-02T15:14:46.2671256+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:35.6897213+00:00 | 2026-06-08T07:53:35.6897213+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327302 | TRUE | TRUE | 2026-06-07T23:53:35.6897213+00:00 | 2026-06-08T07:53:35.6897213+08:00 | #82798 - MTP: 39hrs - 15FPS MODULE | 1.0 | FALSE |  | 2027-11-19T20:00:00+00:00 | 2027-11-21T11:00:00+00:00 | 2027-11-20T04:00:00+08:00 | 2027-11-21T19:00:00+08:00 |  |  |  |  | 39.00 | 15FPS Module Maintenance |  |  | [{"equipmentGUID": "1567fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC15FPS", "name": "Screen: MTP Final Product No. 15", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82797 | 2026-06-02T07:14:46.2671135+00:00 | 2026-06-02T15:14:46.2671135+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:35.9331038+00:00 | 2026-06-08T07:53:35.9331038+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327303 | TRUE | TRUE | 2026-06-07T23:53:35.9331038+00:00 | 2026-06-08T07:53:35.9331038+08:00 | #82797 - MTP: 39hrs - 15FPS MODULE | 1.0 | FALSE |  | 2027-08-20T20:00:00+00:00 | 2027-08-22T11:00:00+00:00 | 2027-08-21T04:00:00+08:00 | 2027-08-22T19:00:00+08:00 |  |  |  |  | 39.00 | 15FPS Module Maintenance |  |  | [{"equipmentGUID": "1567fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC15FPS", "name": "Screen: MTP Final Product No. 15", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82796 | 2026-06-02T07:14:46.2671+00:00 | 2026-06-02T15:14:46.2671+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:36.1838493+00:00 | 2026-06-08T07:53:36.1838493+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327304 | TRUE | TRUE | 2026-06-07T23:53:36.1838493+00:00 | 2026-06-08T07:53:36.1838493+08:00 | #82796 - MTP: 39hrs - 15FPS MODULE | 1.0 | FALSE |  | 2027-05-21T20:00:00+00:00 | 2027-05-23T11:00:00+00:00 | 2027-05-22T04:00:00+08:00 | 2027-05-23T19:00:00+08:00 |  |  |  |  | 39.00 | 15FPS Module Maintenance |  |  | [{"equipmentGUID": "1567fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC15FPS", "name": "Screen: MTP Final Product No. 15", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82795 | 2026-06-02T07:14:46.2670884+00:00 | 2026-06-02T15:14:46.2670884+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:36.4358459+00:00 | 2026-06-08T07:53:36.4358459+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327305 | TRUE | TRUE | 2026-06-07T23:53:36.4358459+00:00 | 2026-06-08T07:53:36.4358459+08:00 | #82795 - MTP: 39hrs - 15FPS MODULE | 1.0 | FALSE |  | 2027-02-19T20:00:00+00:00 | 2027-02-21T11:00:00+00:00 | 2027-02-20T04:00:00+08:00 | 2027-02-21T19:00:00+08:00 |  |  |  |  | 39.00 | 15FPS Module Maintenance |  |  | [{"equipmentGUID": "1567fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC15FPS", "name": "Screen: MTP Final Product No. 15", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82794 | 2026-06-02T07:14:46.2670764+00:00 | 2026-06-02T15:14:46.2670764+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:36.6907984+00:00 | 2026-06-08T07:53:36.6907984+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327306 | TRUE | TRUE | 2026-06-07T23:53:36.6907984+00:00 | 2026-06-08T07:53:36.6907984+08:00 | #82794 - MTP: 39hrs - 14FPS MODULE | 1.0 | FALSE |  | 2027-10-29T20:00:00+00:00 | 2027-10-31T11:00:00+00:00 | 2027-10-30T04:00:00+08:00 | 2027-10-31T19:00:00+08:00 |  |  |  |  | 39.00 | 14FPS Module Maintenance |  |  | [{"equipmentGUID": "1bffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC14FPS", "name": "Screen: MTP Final Product No. 14", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82792 | 2026-06-02T07:14:46.2670506+00:00 | 2026-06-02T15:14:46.2670506+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:36.9634842+00:00 | 2026-06-08T07:53:36.9634842+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327307 | TRUE | TRUE | 2026-06-07T23:53:36.9634842+00:00 | 2026-06-08T07:53:36.9634842+08:00 | #82792 - MTP: 39hrs - 14FPS MODULE | 1.0 | FALSE |  | 2027-04-30T20:00:00+00:00 | 2027-05-02T11:00:00+00:00 | 2027-05-01T04:00:00+08:00 | 2027-05-02T19:00:00+08:00 |  |  |  |  | 39.00 | 14FPS Module Maintenance |  |  | [{"equipmentGUID": "1bffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC14FPS", "name": "Screen: MTP Final Product No. 14", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82793 | 2026-06-02T07:14:46.2670627+00:00 | 2026-06-02T15:14:46.2670627+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:37.2240886+00:00 | 2026-06-08T07:53:37.2240886+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327308 | TRUE | TRUE | 2026-06-07T23:53:37.2240886+00:00 | 2026-06-08T07:53:37.2240886+08:00 | #82793 - MTP: 39hrs - 14FPS MODULE | 1.0 | FALSE |  | 2027-07-30T20:00:00+00:00 | 2027-08-01T11:00:00+00:00 | 2027-07-31T04:00:00+08:00 | 2027-08-01T19:00:00+08:00 |  |  |  |  | 39.00 | 14FPS Module Maintenance |  |  | [{"equipmentGUID": "1bffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC14FPS", "name": "Screen: MTP Final Product No. 14", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82779 | 2026-06-02T07:14:46.2668869+00:00 | 2026-06-02T15:14:46.2668869+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:41.3793499+00:00 | 2026-06-08T07:53:41.3793499+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327320 | TRUE | TRUE | 2026-06-07T23:53:41.3793499+00:00 | 2026-06-08T07:53:41.3793499+08:00 | #82779 - MTP: 39hrs - 11FPS MODULE | 1.0 | FALSE |  | 2027-02-02T20:00:00+00:00 | 2027-02-04T11:00:00+00:00 | 2027-02-03T04:00:00+08:00 | 2027-02-04T19:00:00+08:00 |  |  |  |  | 39.00 | 11FPS Module Maintenance |  |  | [{"equipmentGUID": "e86afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC11FPS", "name": "Screen: MTP Final Product No. 11 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82780 | 2026-06-02T07:14:46.2669005+00:00 | 2026-06-02T15:14:46.2669005+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:41.6843559+00:00 | 2026-06-08T07:53:41.6843559+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327321 | TRUE | TRUE | 2026-06-07T23:53:41.6843559+00:00 | 2026-06-08T07:53:41.6843559+08:00 | #82780 - MTP: 39hrs - 11FPS MODULE | 1.0 | FALSE |  | 2027-05-03T20:00:00+00:00 | 2027-05-05T11:00:00+00:00 | 2027-05-04T04:00:00+08:00 | 2027-05-05T19:00:00+08:00 |  |  |  |  | 39.00 | 11FPS Module Maintenance |  |  | [{"equipmentGUID": "e86afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC11FPS", "name": "Screen: MTP Final Product No. 11 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82778 | 2026-06-02T07:14:46.266875+00:00 | 2026-06-02T15:14:46.266875+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:41.9887703+00:00 | 2026-06-08T07:53:41.9887703+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327322 | TRUE | TRUE | 2026-06-07T23:53:41.9887703+00:00 | 2026-06-08T07:53:41.9887703+08:00 | #82778 - MTP: 39hrs - 10FPS MODULE | 1.0 | FALSE |  | 2027-12-14T20:00:00+00:00 | 2027-12-16T11:00:00+00:00 | 2027-12-15T04:00:00+08:00 | 2027-12-16T19:00:00+08:00 |  |  |  |  | 39.00 | 10FPS Module Maintenance |  |  | [{"equipmentGUID": "4146f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC10FPS", "name": "Screen: MTP Final Product No. 10 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82777 | 2026-06-02T07:14:46.266863+00:00 | 2026-06-02T15:14:46.266863+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:42.3001318+00:00 | 2026-06-08T07:53:42.3001318+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327323 | TRUE | TRUE | 2026-06-07T23:53:42.3001318+00:00 | 2026-06-08T07:53:42.3001318+08:00 | #82777 - MTP: 39hrs - 10FPS MODULE | 1.0 | FALSE |  | 2027-09-14T20:00:00+00:00 | 2027-09-16T11:00:00+00:00 | 2027-09-15T04:00:00+08:00 | 2027-09-16T19:00:00+08:00 |  |  |  |  | 39.00 | 10FPS Module Maintenance |  |  | [{"equipmentGUID": "4146f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC10FPS", "name": "Screen: MTP Final Product No. 10 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82776 | 2026-06-02T07:14:46.2668488+00:00 | 2026-06-02T15:14:46.2668488+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:42.6208219+00:00 | 2026-06-08T07:53:42.6208219+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327324 | TRUE | TRUE | 2026-06-07T23:53:42.6208219+00:00 | 2026-06-08T07:53:42.6208219+08:00 | #82776 - MTP: 39hrs - 10FPS MODULE | 1.0 | FALSE |  | 2027-06-15T20:00:00+00:00 | 2027-06-17T11:00:00+00:00 | 2027-06-16T04:00:00+08:00 | 2027-06-17T19:00:00+08:00 |  |  |  |  | 39.00 | 10FPS Module Maintenance |  |  | [{"equipmentGUID": "4146f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC10FPS", "name": "Screen: MTP Final Product No. 10 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82775 | 2026-06-02T07:14:46.2668368+00:00 | 2026-06-02T15:14:46.2668368+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:42.9514806+00:00 | 2026-06-08T07:53:42.9514806+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327325 | TRUE | TRUE | 2026-06-07T23:53:42.9514806+00:00 | 2026-06-08T07:53:42.9514806+08:00 | #82775 - MTP: 39hrs - 10FPS MODULE | 1.0 | FALSE |  | 2027-03-16T20:00:00+00:00 | 2027-03-18T11:00:00+00:00 | 2027-03-17T04:00:00+08:00 | 2027-03-18T19:00:00+08:00 |  |  |  |  | 39.00 | 10FPS Module Maintenance |  |  | [{"equipmentGUID": "4146f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC10FPS", "name": "Screen: MTP Final Product No. 10 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82774 | 2026-06-02T07:14:46.2668245+00:00 | 2026-06-02T15:14:46.2668245+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:43.2873887+00:00 | 2026-06-08T07:53:43.2873887+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327326 | TRUE | TRUE | 2026-06-07T23:53:43.2873887+00:00 | 2026-06-08T07:53:43.2873887+08:00 | #82774 - MTP: 39hrs - 9FPS MODULE | 1.0 | FALSE |  | 2027-12-25T20:00:00+00:00 | 2027-12-27T11:00:00+00:00 | 2027-12-26T04:00:00+08:00 | 2027-12-27T19:00:00+08:00 |  |  |  |  | 39.00 | 9FPS Module Maintenance |  |  | [{"equipmentGUID": "4bdd00c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC9FPS", "name": "Screen: MTP Final Product No. 9 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82773 | 2026-06-02T07:14:46.2668099+00:00 | 2026-06-02T15:14:46.2668099+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:43.639249+00:00 | 2026-06-08T07:53:43.639249+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327327 | TRUE | TRUE | 2026-06-07T23:53:43.639249+00:00 | 2026-06-08T07:53:43.639249+08:00 | #82773 - MTP: 39hrs - 9FPS MODULE | 1.0 | FALSE |  | 2027-09-25T20:00:00+00:00 | 2027-09-27T11:00:00+00:00 | 2027-09-26T04:00:00+08:00 | 2027-09-27T19:00:00+08:00 |  |  |  |  | 39.00 | 9FPS Module Maintenance |  |  | [{"equipmentGUID": "4bdd00c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC9FPS", "name": "Screen: MTP Final Product No. 9 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82772 | 2026-06-02T07:14:46.2667959+00:00 | 2026-06-02T15:14:46.2667959+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:43.9801233+00:00 | 2026-06-08T07:53:43.9801233+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327328 | TRUE | TRUE | 2026-06-07T23:53:43.9801233+00:00 | 2026-06-08T07:53:43.9801233+08:00 | #82772 - MTP: 39hrs - 9FPS MODULE | 1.0 | FALSE |  | 2027-06-26T20:00:00+00:00 | 2027-06-28T11:00:00+00:00 | 2027-06-27T04:00:00+08:00 | 2027-06-28T19:00:00+08:00 |  |  |  |  | 39.00 | 9FPS Module Maintenance |  |  | [{"equipmentGUID": "4bdd00c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC9FPS", "name": "Screen: MTP Final Product No. 9 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82771 | 2026-06-02T07:14:46.2667778+00:00 | 2026-06-02T15:14:46.2667778+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:44.3323707+00:00 | 2026-06-08T07:53:44.3323707+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327329 | TRUE | TRUE | 2026-06-07T23:53:44.3323707+00:00 | 2026-06-08T07:53:44.3323707+08:00 | #82771 - MTP: 39hrs - 9FPS MODULE | 1.0 | FALSE |  | 2027-03-27T20:00:00+00:00 | 2027-03-29T11:00:00+00:00 | 2027-03-28T04:00:00+08:00 | 2027-03-29T19:00:00+08:00 |  |  |  |  | 39.00 | 9FPS Module Maintenance |  |  | [{"equipmentGUID": "4bdd00c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC9FPS", "name": "Screen: MTP Final Product No. 9 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82770 | 2026-06-02T07:14:46.2667613+00:00 | 2026-06-02T15:14:46.2667613+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:44.6732624+00:00 | 2026-06-08T07:53:44.6732624+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327330 | TRUE | TRUE | 2026-06-07T23:53:44.6732624+00:00 | 2026-06-08T07:53:44.6732624+08:00 | #82770 - MTP: 39hrs - 8FPS MODULE | 1.0 | FALSE |  | 2027-11-12T20:00:00+00:00 | 2027-11-14T11:00:00+00:00 | 2027-11-13T04:00:00+08:00 | 2027-11-14T19:00:00+08:00 |  |  |  |  | 39.00 | 8FPS Module Maintenance |  |  | [{"equipmentGUID": "c926f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC8FPS", "name": "Screen: MTP Final Product No. 8 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82769 | 2026-06-02T07:14:46.2667478+00:00 | 2026-06-02T15:14:46.2667478+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:45.0261016+00:00 | 2026-06-08T07:53:45.0261016+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327331 | TRUE | TRUE | 2026-06-07T23:53:45.0261016+00:00 | 2026-06-08T07:53:45.0261016+08:00 | #82769 - MTP: 39hrs - 8FPS MODULE | 1.0 | FALSE |  | 2027-08-13T20:00:00+00:00 | 2027-08-15T11:00:00+00:00 | 2027-08-14T04:00:00+08:00 | 2027-08-15T19:00:00+08:00 |  |  |  |  | 39.00 | 8FPS Module Maintenance |  |  | [{"equipmentGUID": "c926f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC8FPS", "name": "Screen: MTP Final Product No. 8 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82699 | 2026-06-02T05:50:46.7677268+00:00 | 2026-06-02T13:50:46.7677268+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:15.3274301+00:00 | 2026-06-08T07:54:15.3274301+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327390 | TRUE | TRUE | 2026-06-07T23:54:15.3274301+00:00 | 2026-06-08T07:54:15.3274301+08:00 | #82699 - MTP: 92hrs - C8 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-06-03T16:00:00+00:00 | 2027-06-07T12:00:00+00:00 | 2027-06-04T00:00:00+08:00 | 2027-06-07T20:00:00+08:00 |  |  |  |  | 92.00 | C8 Module Maintenance |  |  | [{"equipmentGUID": "c632f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS08", "name": "Crusher - Tertiary: MTP 08 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82698 | 2026-06-02T05:50:46.7677191+00:00 | 2026-06-02T13:50:46.7677191+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:15.9075082+00:00 | 2026-06-08T07:54:15.9075082+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327391 | TRUE | TRUE | 2026-06-07T23:54:15.9075082+00:00 | 2026-06-08T07:54:15.9075082+08:00 | #82698 - MTP: 92hrs - C8 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-03-03T16:00:00+00:00 | 2027-03-07T12:00:00+00:00 | 2027-03-04T00:00:00+08:00 | 2027-03-07T20:00:00+08:00 |  |  |  |  | 92.00 | C8 Module Maintenance |  |  | [{"equipmentGUID": "c632f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS08", "name": "Crusher - Tertiary: MTP 08 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82696 | 2026-06-02T05:50:46.7677016+00:00 | 2026-06-02T13:50:46.7677016+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:16.4793784+00:00 | 2026-06-08T07:54:16.4793784+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327392 | TRUE | TRUE | 2026-06-07T23:54:16.4793784+00:00 | 2026-06-08T07:54:16.4793784+08:00 | #82696 - MTP: 92hrs - C7 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-08-22T16:00:00+00:00 | 2027-08-26T12:00:00+00:00 | 2027-08-23T00:00:00+08:00 | 2027-08-26T20:00:00+08:00 |  |  |  |  | 92.00 | C7 Module Maintenance |  |  | [{"equipmentGUID": "36d500c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS07", "name": "Crusher - Tertiary: MTP 07 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82697 | 2026-06-02T05:50:46.7677093+00:00 | 2026-06-02T13:50:46.7677093+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:17.0780364+00:00 | 2026-06-08T07:54:17.0780364+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327393 | TRUE | TRUE | 2026-06-07T23:54:17.0780364+00:00 | 2026-06-08T07:54:17.0780364+08:00 | #82697 - MTP: 92hrs - C7 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-11-25T16:00:00+00:00 | 2027-11-29T12:00:00+00:00 | 2027-11-26T00:00:00+08:00 | 2027-11-29T20:00:00+08:00 |  |  |  |  | 92.00 | C7 Module Maintenance |  |  | [{"equipmentGUID": "36d500c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS07", "name": "Crusher - Tertiary: MTP 07 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82695 | 2026-06-02T05:50:46.7676936+00:00 | 2026-06-02T13:50:46.7676936+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:17.6833292+00:00 | 2026-06-08T07:54:17.6833292+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327394 | TRUE | TRUE | 2026-06-07T23:54:17.6833292+00:00 | 2026-06-08T07:54:17.6833292+08:00 | #82695 - MTP: 92hrs - C7 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-05-24T16:00:00+00:00 | 2027-05-28T12:00:00+00:00 | 2027-05-25T00:00:00+08:00 | 2027-05-28T20:00:00+08:00 |  |  |  |  | 92.00 | C7 Module Maintenance |  |  | [{"equipmentGUID": "36d500c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS07", "name": "Crusher - Tertiary: MTP 07 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82694 | 2026-06-02T05:50:46.7676832+00:00 | 2026-06-02T13:50:46.7676832+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:18.2936865+00:00 | 2026-06-08T07:54:18.2936865+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327395 | TRUE | TRUE | 2026-06-07T23:54:18.2936865+00:00 | 2026-06-08T07:54:18.2936865+08:00 | #82694 - MTP: 92hrs - C7 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-02-22T16:00:00+00:00 | 2027-02-26T12:00:00+00:00 | 2027-02-23T00:00:00+08:00 | 2027-02-26T20:00:00+08:00 |  |  |  |  | 92.00 | C7 Module Maintenance |  |  | [{"equipmentGUID": "36d500c0-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS07", "name": "Crusher - Tertiary: MTP 07 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82693 | 2026-06-02T05:50:46.767675+00:00 | 2026-06-02T13:50:46.767675+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:18.8902767+00:00 | 2026-06-08T07:54:18.8902767+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327396 | TRUE | TRUE | 2026-06-07T23:54:18.8902767+00:00 | 2026-06-08T07:54:18.8902767+08:00 | #82693 - MTP: 92hrs - 5 CIRCUIT MODULE | 1.0 | FALSE |  | 2027-12-20T16:00:00+00:00 | 2027-12-24T12:00:00+00:00 | 2027-12-21T00:00:00+08:00 | 2027-12-24T20:00:00+08:00 |  |  |  |  | 92.00 | 5CCT Module Maintenance |  |  | [{"equipmentGUID": "4cf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS05", "name": "Crusher - Secondary: MTP 05 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82692 | 2026-06-02T05:50:46.7676671+00:00 | 2026-06-02T13:50:46.7676671+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:19.4856228+00:00 | 2026-06-08T07:54:19.4856228+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327397 | TRUE | TRUE | 2026-06-07T23:54:19.4856228+00:00 | 2026-06-08T07:54:19.4856228+08:00 | #82692 - MTP: 92hrs - 5 CIRCUIT MODULE | 1.0 | FALSE |  | 2027-09-15T16:00:00+00:00 | 2027-09-19T12:00:00+00:00 | 2027-09-16T00:00:00+08:00 | 2027-09-19T20:00:00+08:00 |  |  |  |  | 92.00 | 5CCT Module Maintenance |  |  | [{"equipmentGUID": "4cf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS05", "name": "Crusher - Secondary: MTP 05 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82689 | 2026-06-02T05:50:46.7676384+00:00 | 2026-06-02T13:50:46.7676384+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:21.3329853+00:00 | 2026-06-08T07:54:21.3329853+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327400 | TRUE | TRUE | 2026-06-07T23:54:21.3329853+00:00 | 2026-06-08T07:54:21.3329853+08:00 | #82689 - MTP: 92hrs - 6 CIRCUIT MODULE | 1.0 | FALSE |  | 2027-11-21T16:00:00+00:00 | 2027-11-25T12:00:00+00:00 | 2027-11-22T00:00:00+08:00 | 2027-11-25T20:00:00+08:00 |  |  |  |  | 92.00 | 6CCT Module Maintenance |  |  | [{"equipmentGUID": "95e5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS06", "name": "Crusher - Secondary: MTP 06 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82686 | 2026-06-02T05:50:46.7671385+00:00 | 2026-06-02T13:50:46.7671385+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:23.2371734+00:00 | 2026-06-08T07:54:23.2371734+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327403 | TRUE | TRUE | 2026-06-07T23:54:23.2371734+00:00 | 2026-06-08T07:54:23.2371734+08:00 | #82686 - MTP: 92hrs - 6 CIRCUIT MODULE | 1.0 | FALSE |  | 2027-02-17T16:00:00+00:00 | 2027-02-21T12:00:00+00:00 | 2027-02-18T00:00:00+08:00 | 2027-02-21T20:00:00+08:00 |  |  |  |  | 92.00 | 6CCT Module Maintenance |  |  | [{"equipmentGUID": "95e5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS06", "name": "Crusher - Secondary: MTP 06 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82685 | 2026-06-02T03:13:23.6611172+00:00 | 2026-06-02T11:13:23.6611172+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:23.8878178+00:00 | 2026-06-08T07:54:23.8878178+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327404 | TRUE | TRUE | 2026-06-07T23:54:23.8878178+00:00 | 2026-06-08T07:54:23.8878178+08:00 | #82685 - MTP: 172hrs - DRUM 2 MODULE | 1.0 | FALSE |  | 2027-10-24T11:00:00+00:00 | 2027-10-31T15:00:00+00:00 | 2027-10-24T19:00:00+08:00 | 2027-10-31T23:00:00+08:00 |  |  |  |  | 172.00 | Drum 2 Module Maintetance |  |  | [{"equipmentGUID": "8817ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM02", "name": "Drum: MTP Module 02", "assetClass": {"name": "Drum"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82814 | 2026-06-02T07:14:46.2673295+00:00 | 2026-06-02T15:14:46.2673295+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:31.7980658+00:00 | 2026-06-08T07:53:31.7980658+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327286 | TRUE | TRUE | 2026-06-07T23:53:31.7980658+00:00 | 2026-06-08T07:53:31.7980658+08:00 | #82814 - MTP: 68hrs - 4TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-10-16T16:00:00+00:00 | 2027-10-19T12:00:00+00:00 | 2027-10-17T00:00:00+08:00 | 2027-10-19T20:00:00+08:00 |  |  |  |  | 68.00 | 4TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "e05ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS04", "name": "Crusher - Tertiary: MTP 04 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82813 | 2026-06-02T07:14:46.2673175+00:00 | 2026-06-02T15:14:46.2673175+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:32.1121544+00:00 | 2026-06-08T07:53:32.1121544+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327287 | TRUE | TRUE | 2026-06-07T23:53:32.1121544+00:00 | 2026-06-08T07:53:32.1121544+08:00 | #82813 - MTP: 68hrs - 4TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-07-18T16:00:00+00:00 | 2027-07-21T12:00:00+00:00 | 2027-07-19T00:00:00+08:00 | 2027-07-21T20:00:00+08:00 |  |  |  |  | 68.00 | 4TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "e05ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS04", "name": "Crusher - Tertiary: MTP 04 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82812 | 2026-06-02T07:14:46.2673041+00:00 | 2026-06-02T15:14:46.2673041+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:32.3120601+00:00 | 2026-06-08T07:53:32.3120601+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327288 | TRUE | TRUE | 2026-06-07T23:53:32.3120601+00:00 | 2026-06-08T07:53:32.3120601+08:00 | #82812 - MTP: 68hrs - 4TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-04-17T16:00:00+00:00 | 2027-04-20T12:00:00+00:00 | 2027-04-18T00:00:00+08:00 | 2027-04-20T20:00:00+08:00 |  |  |  |  | 68.00 | 4TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "e05ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS04", "name": "Crusher - Tertiary: MTP 04 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82809 | 2026-06-02T07:14:46.267266+00:00 | 2026-06-02T15:14:46.267266+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:32.7372667+00:00 | 2026-06-08T07:53:32.7372667+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327290 | TRUE | TRUE | 2026-06-07T23:53:32.7372667+00:00 | 2026-06-08T07:53:32.7372667+08:00 | #82809 - MTP: 68hrs - 3TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-08-05T16:00:00+00:00 | 2027-08-08T12:00:00+00:00 | 2027-08-06T00:00:00+08:00 | 2027-08-08T20:00:00+08:00 |  |  |  |  | 68.00 | 3TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "4d37f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS03", "name": "Crusher - Tertiary: MTP 03 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82810 | 2026-06-02T07:14:46.2672777+00:00 | 2026-06-02T15:14:46.2672777+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:32.9482615+00:00 | 2026-06-08T07:53:32.9482615+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327291 | TRUE | TRUE | 2026-06-07T23:53:32.9482615+00:00 | 2026-06-08T07:53:32.9482615+08:00 | #82810 - MTP: 68hrs - 3TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-11-04T16:00:00+00:00 | 2027-11-07T12:00:00+00:00 | 2027-11-05T00:00:00+08:00 | 2027-11-07T20:00:00+08:00 |  |  |  |  | 68.00 | 3TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "4d37f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS03", "name": "Crusher - Tertiary: MTP 03 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82808 | 2026-06-02T07:14:46.2672537+00:00 | 2026-06-02T15:14:46.2672537+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:33.1772597+00:00 | 2026-06-08T07:53:33.1772597+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327292 | TRUE | TRUE | 2026-06-07T23:53:33.1772597+00:00 | 2026-06-08T07:53:33.1772597+08:00 | #82808 - MTP: 68hrs - 3TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-05-06T16:00:00+00:00 | 2027-05-09T12:00:00+00:00 | 2027-05-07T00:00:00+08:00 | 2027-05-09T20:00:00+08:00 |  |  |  |  | 68.00 | 3TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "4d37f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS03", "name": "Crusher - Tertiary: MTP 03 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82807 | 2026-06-02T07:14:46.2672405+00:00 | 2026-06-02T15:14:46.2672405+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:33.4116215+00:00 | 2026-06-08T07:53:33.4116215+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327293 | TRUE | TRUE | 2026-06-07T23:53:33.4116215+00:00 | 2026-06-08T07:53:33.4116215+08:00 | #82807 - MTP: 68hrs - 3TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-02-05T16:00:00+00:00 | 2027-02-08T12:00:00+00:00 | 2027-02-06T00:00:00+08:00 | 2027-02-08T20:00:00+08:00 |  |  |  |  | 68.00 | 3TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "4d37f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS03", "name": "Crusher - Tertiary: MTP 03 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82806 | 2026-06-02T07:14:46.2672286+00:00 | 2026-06-02T15:14:46.2672286+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:33.6733573+00:00 | 2026-06-08T07:53:33.6733573+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327294 | TRUE | TRUE | 2026-06-07T23:53:33.6733573+00:00 | 2026-06-08T07:53:33.6733573+08:00 | #82806 - MTP: 68hrs - 2TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-11-15T16:00:00+00:00 | 2027-11-18T12:00:00+00:00 | 2027-11-16T00:00:00+08:00 | 2027-11-18T20:00:00+08:00 |  |  |  |  | 68.00 | 2TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "71eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS02", "name": "Crusher - Tertiary: MTP 02 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82805 | 2026-06-02T07:14:46.2672137+00:00 | 2026-06-02T15:14:46.2672137+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:33.9373452+00:00 | 2026-06-08T07:53:33.9373452+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327295 | TRUE | TRUE | 2026-06-07T23:53:33.9373452+00:00 | 2026-06-08T07:53:33.9373452+08:00 | #82805 - MTP: 68hrs - 2TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-08-16T16:00:00+00:00 | 2027-08-19T12:00:00+00:00 | 2027-08-17T00:00:00+08:00 | 2027-08-19T20:00:00+08:00 |  |  |  |  | 68.00 | 2TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "71eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS02", "name": "Crusher - Tertiary: MTP 02 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82804 | 2026-06-02T07:14:46.2672017+00:00 | 2026-06-02T15:14:46.2672017+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:34.175122+00:00 | 2026-06-08T07:53:34.175122+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327296 | TRUE | TRUE | 2026-06-07T23:53:34.175122+00:00 | 2026-06-08T07:53:34.175122+08:00 | #82804 - MTP: 68hrs - 2TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-05-17T16:00:00+00:00 | 2027-05-20T12:00:00+00:00 | 2027-05-18T00:00:00+08:00 | 2027-05-20T20:00:00+08:00 |  |  |  |  | 68.00 | 2TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "71eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS02", "name": "Crusher - Tertiary: MTP 02 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82803 | 2026-06-02T07:14:46.26719+00:00 | 2026-06-02T15:14:46.26719+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:34.4105129+00:00 | 2026-06-08T07:53:34.4105129+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327297 | TRUE | TRUE | 2026-06-07T23:53:34.4105129+00:00 | 2026-06-08T07:53:34.4105129+08:00 | #82803 - MTP: 68hrs - 2TC TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-02-15T16:00:00+00:00 | 2027-02-18T12:00:00+00:00 | 2027-02-16T00:00:00+08:00 | 2027-02-18T20:00:00+08:00 |  |  |  |  | 68.00 | 2TC Tert Crusher Module Maintenance |  |  | [{"equipmentGUID": "71eee8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS02", "name": "Crusher - Tertiary: MTP 02 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82791 | 2026-06-02T07:14:46.2670386+00:00 | 2026-06-02T15:14:46.2670386+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:37.5313002+00:00 | 2026-06-08T07:53:37.5313002+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327309 | TRUE | TRUE | 2026-06-07T23:53:37.5313002+00:00 | 2026-06-08T07:53:37.5313002+08:00 | #82791 - MTP: 39hrs - 14FPS MODULE | 1.0 | FALSE |  | 2027-01-29T20:00:00+00:00 | 2027-01-31T11:00:00+00:00 | 2027-01-30T04:00:00+08:00 | 2027-01-31T19:00:00+08:00 |  |  |  |  | 39.00 | 14FPS Module Maintenance |  |  | [{"equipmentGUID": "1bffe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC14FPS", "name": "Screen: MTP Final Product No. 14", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82790 | 2026-06-02T07:14:46.2670251+00:00 | 2026-06-02T15:14:46.2670251+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:37.8229447+00:00 | 2026-06-08T07:53:37.8229447+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327310 | TRUE | TRUE | 2026-06-07T23:53:37.8229447+00:00 | 2026-06-08T07:53:37.8229447+08:00 | #82790 - MTP: 39hrs - 13FPS MODULE | 1.0 | FALSE |  | 2027-12-28T20:00:00+00:00 | 2027-12-30T11:00:00+00:00 | 2027-12-29T04:00:00+08:00 | 2027-12-30T19:00:00+08:00 |  |  |  |  | 39.00 | 13FPS Module Maintenance |  |  | [{"equipmentGUID": "8856fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC13FPS", "name": "Screen: MTP Final Product No. 13", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82789 | 2026-06-02T07:14:46.267013+00:00 | 2026-06-02T15:14:46.267013+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:38.1754971+00:00 | 2026-06-08T07:53:38.1754971+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327311 | TRUE | TRUE | 2026-06-07T23:53:38.1754971+00:00 | 2026-06-08T07:53:38.1754971+08:00 | #82789 - MTP: 39hrs - 13FPS MODULE | 1.0 | FALSE |  | 2027-09-28T20:00:00+00:00 | 2027-09-30T11:00:00+00:00 | 2027-09-29T04:00:00+08:00 | 2027-09-30T19:00:00+08:00 |  |  |  |  | 39.00 | 13FPS Module Maintenance |  |  | [{"equipmentGUID": "8856fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC13FPS", "name": "Screen: MTP Final Product No. 13", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82788 | 2026-06-02T07:14:46.2670011+00:00 | 2026-06-02T15:14:46.2670011+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:38.5012929+00:00 | 2026-06-08T07:53:38.5012929+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327312 | TRUE | TRUE | 2026-06-07T23:53:38.5012929+00:00 | 2026-06-08T07:53:38.5012929+08:00 | #82788 - MTP: 39hrs - 13FPS MODULE | 1.0 | FALSE |  | 2027-06-29T20:00:00+00:00 | 2027-07-01T11:00:00+00:00 | 2027-06-30T04:00:00+08:00 | 2027-07-01T19:00:00+08:00 |  |  |  |  | 39.00 | 13FPS Module Maintenance |  |  | [{"equipmentGUID": "8856fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC13FPS", "name": "Screen: MTP Final Product No. 13", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82787 | 2026-06-02T07:14:46.2669879+00:00 | 2026-06-02T15:14:46.2669879+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:38.8231709+00:00 | 2026-06-08T07:53:38.8231709+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327313 | TRUE | TRUE | 2026-06-07T23:53:38.8231709+00:00 | 2026-06-08T07:53:38.8231709+08:00 | #82787 - MTP: 39hrs - 13FPS MODULE | 1.0 | FALSE |  | 2027-03-30T20:00:00+00:00 | 2027-04-01T11:00:00+00:00 | 2027-03-31T04:00:00+08:00 | 2027-04-01T19:00:00+08:00 |  |  |  |  | 39.00 | 13FPS Module Maintenance |  |  | [{"equipmentGUID": "8856fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC13FPS", "name": "Screen: MTP Final Product No. 13", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82786 | 2026-06-02T07:14:46.266976+00:00 | 2026-06-02T15:14:46.266976+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:39.1515999+00:00 | 2026-06-08T07:53:39.1515999+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327314 | TRUE | TRUE | 2026-06-07T23:53:39.1515999+00:00 | 2026-06-08T07:53:39.1515999+08:00 | #82786 - MTP: 39hrs - 12FPS MODULE | 1.0 | FALSE |  | 2027-11-22T20:00:00+00:00 | 2027-11-24T11:00:00+00:00 | 2027-11-23T04:00:00+08:00 | 2027-11-24T19:00:00+08:00 |  |  |  |  | 39.00 | 12FPS Module Maintenance |  |  | [{"equipmentGUID": "e575fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC12FPS", "name": "Screen: MTP Final Product No. 12 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82785 | 2026-06-02T07:14:46.2669641+00:00 | 2026-06-02T15:14:46.2669641+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:39.5005415+00:00 | 2026-06-08T07:53:39.5005415+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327315 | TRUE | TRUE | 2026-06-07T23:53:39.5005415+00:00 | 2026-06-08T07:53:39.5005415+08:00 | #82785 - MTP: 39hrs - 12FPS MODULE | 1.0 | FALSE |  | 2027-08-23T20:00:00+00:00 | 2027-08-25T11:00:00+00:00 | 2027-08-24T04:00:00+08:00 | 2027-08-25T19:00:00+08:00 |  |  |  |  | 39.00 | 12FPS Module Maintenance |  |  | [{"equipmentGUID": "e575fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC12FPS", "name": "Screen: MTP Final Product No. 12 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82784 | 2026-06-02T07:14:46.2669503+00:00 | 2026-06-02T15:14:46.2669503+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:39.8878446+00:00 | 2026-06-08T07:53:39.8878446+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327316 | TRUE | TRUE | 2026-06-07T23:53:39.8878446+00:00 | 2026-06-08T07:53:39.8878446+08:00 | #82784 - MTP: 39hrs - 12FPS MODULE | 1.0 | FALSE |  | 2027-05-24T20:00:00+00:00 | 2027-05-26T11:00:00+00:00 | 2027-05-25T04:00:00+08:00 | 2027-05-26T19:00:00+08:00 |  |  |  |  | 39.00 | 12FPS Module Maintenance |  |  | [{"equipmentGUID": "e575fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC12FPS", "name": "Screen: MTP Final Product No. 12 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82783 | 2026-06-02T07:14:46.2669384+00:00 | 2026-06-02T15:14:46.2669384+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:40.4804107+00:00 | 2026-06-08T07:53:40.4804107+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327317 | TRUE | TRUE | 2026-06-07T23:53:40.4804107+00:00 | 2026-06-08T07:53:40.4804107+08:00 | #82783 - MTP: 39hrs - 12FPS MODULE | 1.0 | FALSE |  | 2027-02-22T20:00:00+00:00 | 2027-02-24T11:00:00+00:00 | 2027-02-23T04:00:00+08:00 | 2027-02-24T19:00:00+08:00 |  |  |  |  | 39.00 | 12FPS Module Maintenance |  |  | [{"equipmentGUID": "e575fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC12FPS", "name": "Screen: MTP Final Product No. 12 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82782 | 2026-06-02T07:14:46.2669261+00:00 | 2026-06-02T15:14:46.2669261+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:40.7681949+00:00 | 2026-06-08T07:53:40.7681949+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327318 | TRUE | TRUE | 2026-06-07T23:53:40.7681949+00:00 | 2026-06-08T07:53:40.7681949+08:00 | #82782 - MTP: 39hrs - 11FPS MODULE | 1.0 | FALSE |  | 2027-11-01T20:00:00+00:00 | 2027-11-03T11:00:00+00:00 | 2027-11-02T04:00:00+08:00 | 2027-11-03T19:00:00+08:00 |  |  |  |  | 39.00 | 11FPS Module Maintenance |  |  | [{"equipmentGUID": "e86afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC11FPS", "name": "Screen: MTP Final Product No. 11 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82781 | 2026-06-02T07:14:46.2669125+00:00 | 2026-06-02T15:14:46.2669125+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:41.0649373+00:00 | 2026-06-08T07:53:41.0649373+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327319 | TRUE | TRUE | 2026-06-07T23:53:41.0649373+00:00 | 2026-06-08T07:53:41.0649373+08:00 | #82781 - MTP: 39hrs - 11FPS MODULE | 1.0 | FALSE |  | 2027-08-02T20:00:00+00:00 | 2027-08-04T11:00:00+00:00 | 2027-08-03T04:00:00+08:00 | 2027-08-04T19:00:00+08:00 |  |  |  |  | 39.00 | 11FPS Module Maintenance |  |  | [{"equipmentGUID": "e86afbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC11FPS", "name": "Screen: MTP Final Product No. 11 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82768 | 2026-06-02T07:14:46.2667321+00:00 | 2026-06-02T15:14:46.2667321+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:45.3834531+00:00 | 2026-06-08T07:53:45.3834531+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327332 | TRUE | TRUE | 2026-06-07T23:53:45.3834531+00:00 | 2026-06-08T07:53:45.3834531+08:00 | #82768 - MTP: 39hrs - 8FPS MODULE | 1.0 | FALSE |  | 2027-05-14T20:00:00+00:00 | 2027-05-16T11:00:00+00:00 | 2027-05-15T04:00:00+08:00 | 2027-05-16T19:00:00+08:00 |  |  |  |  | 39.00 | 8FPS Module Maintenance |  |  | [{"equipmentGUID": "c926f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC8FPS", "name": "Screen: MTP Final Product No. 8 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82767 | 2026-06-02T07:14:46.2667167+00:00 | 2026-06-02T15:14:46.2667167+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:45.733405+00:00 | 2026-06-08T07:53:45.733405+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327333 | TRUE | TRUE | 2026-06-07T23:53:45.733405+00:00 | 2026-06-08T07:53:45.733405+08:00 | #82767 - MTP: 39hrs - 8FPS MODULE | 1.0 | FALSE |  | 2027-02-12T20:00:00+00:00 | 2027-02-14T11:00:00+00:00 | 2027-02-13T04:00:00+08:00 | 2027-02-14T19:00:00+08:00 |  |  |  |  | 39.00 | 8FPS Module Maintenance |  |  | [{"equipmentGUID": "c926f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC8FPS", "name": "Screen: MTP Final Product No. 8 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82766 | 2026-06-02T07:14:46.2667044+00:00 | 2026-06-02T15:14:46.2667044+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:46.1006389+00:00 | 2026-06-08T07:53:46.1006389+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327334 | TRUE | TRUE | 2026-06-07T23:53:46.1006389+00:00 | 2026-06-08T07:53:46.1006389+08:00 | #82766 - MTP: 39hrs - 7FPS MODULE | 1.0 | FALSE |  | 2027-10-08T20:00:00+00:00 | 2027-10-10T11:00:00+00:00 | 2027-10-09T04:00:00+08:00 | 2027-10-10T19:00:00+08:00 |  |  |  |  | 39.00 | 7FPS Module Maintenance |  |  | [{"equipmentGUID": "c808f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC7FPS", "name": "Screen: MTP Final Product No. 7 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82765 | 2026-06-02T07:14:46.2666897+00:00 | 2026-06-02T15:14:46.2666897+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:46.4550603+00:00 | 2026-06-08T07:53:46.4550603+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327335 | TRUE | TRUE | 2026-06-07T23:53:46.4550603+00:00 | 2026-06-08T07:53:46.4550603+08:00 | #82765 - MTP: 39hrs - 7FPS MODULE | 1.0 | FALSE |  | 2027-07-09T20:00:00+00:00 | 2027-07-11T11:00:00+00:00 | 2027-07-10T04:00:00+08:00 | 2027-07-11T19:00:00+08:00 |  |  |  |  | 39.00 | 7FPS Module Maintenance |  |  | [{"equipmentGUID": "c808f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC7FPS", "name": "Screen: MTP Final Product No. 7 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82764 | 2026-06-02T07:14:46.2666762+00:00 | 2026-06-02T15:14:46.2666762+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:46.8483317+00:00 | 2026-06-08T07:53:46.8483317+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327336 | TRUE | TRUE | 2026-06-07T23:53:46.8483317+00:00 | 2026-06-08T07:53:46.8483317+08:00 | #82764 - MTP: 39hrs - 7FPS MODULE | 1.0 | FALSE |  | 2027-04-09T20:00:00+00:00 | 2027-04-11T11:00:00+00:00 | 2027-04-10T04:00:00+08:00 | 2027-04-11T19:00:00+08:00 |  |  |  |  | 39.00 | 7FPS Module Maintenance |  |  | [{"equipmentGUID": "c808f0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC7FPS", "name": "Screen: MTP Final Product No. 7 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82763 | 2026-06-02T07:14:46.2666647+00:00 | 2026-06-02T15:14:46.2666647+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:47.2043434+00:00 | 2026-06-08T07:53:47.2043434+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327337 | TRUE | TRUE | 2026-06-07T23:53:47.2043434+00:00 | 2026-06-08T07:53:47.2043434+08:00 | #82763 - MTP: 39hrs - 6FPS MODULE | 1.0 | FALSE |  | 2027-10-26T20:00:00+00:00 | 2027-10-28T11:00:00+00:00 | 2027-10-27T04:00:00+08:00 | 2027-10-28T19:00:00+08:00 |  |  |  |  | 39.00 | 6FPS Module Maintenance |  |  | [{"equipmentGUID": "5ff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC6FPS", "name": "Screen: MTP Final Product No. 6 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82762 | 2026-06-02T07:14:46.2666529+00:00 | 2026-06-02T15:14:46.2666529+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:47.5845144+00:00 | 2026-06-08T07:53:47.5845144+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327338 | TRUE | TRUE | 2026-06-07T23:53:47.5845144+00:00 | 2026-06-08T07:53:47.5845144+08:00 | #82762 - MTP: 39hrs - 6FPS MODULE | 1.0 | FALSE |  | 2027-07-27T20:00:00+00:00 | 2027-07-29T11:00:00+00:00 | 2027-07-28T04:00:00+08:00 | 2027-07-29T19:00:00+08:00 |  |  |  |  | 39.00 | 6FPS Module Maintenance |  |  | [{"equipmentGUID": "5ff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC6FPS", "name": "Screen: MTP Final Product No. 6 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82761 | 2026-06-02T07:14:46.2666394+00:00 | 2026-06-02T15:14:46.2666394+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:47.9744522+00:00 | 2026-06-08T07:53:47.9744522+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327339 | TRUE | TRUE | 2026-06-07T23:53:47.9744522+00:00 | 2026-06-08T07:53:47.9744522+08:00 | #82761 - MTP: 39hrs - 6FPS MODULE | 1.0 | FALSE |  | 2027-04-26T20:00:00+00:00 | 2027-04-28T11:00:00+00:00 | 2027-04-27T04:00:00+08:00 | 2027-04-28T19:00:00+08:00 |  |  |  |  | 39.00 | 6FPS Module Maintenance |  |  | [{"equipmentGUID": "5ff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC6FPS", "name": "Screen: MTP Final Product No. 6 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82760 | 2026-06-02T07:14:46.2666264+00:00 | 2026-06-02T15:14:46.2666264+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:48.3490634+00:00 | 2026-06-08T07:53:48.3490634+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327340 | TRUE | TRUE | 2026-06-07T23:53:48.3490634+00:00 | 2026-06-08T07:53:48.3490634+08:00 | #82760 - MTP: 39hrs - 6FPS MODULE | 1.0 | FALSE |  | 2027-01-26T20:00:00+00:00 | 2027-01-28T11:00:00+00:00 | 2027-01-27T04:00:00+08:00 | 2027-01-28T19:00:00+08:00 |  |  |  |  | 39.00 | 6FPS Module Maintenance |  |  | [{"equipmentGUID": "5ff1e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC6FPS", "name": "Screen: MTP Final Product No. 6 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82759 | 2026-06-02T07:14:46.2666141+00:00 | 2026-06-02T15:14:46.2666141+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:48.728485+00:00 | 2026-06-08T07:53:48.728485+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327341 | TRUE | TRUE | 2026-06-07T23:53:48.728485+00:00 | 2026-06-08T07:53:48.728485+08:00 | #82759 - MTP: 39hrs - 5FPS MODULE | 1.0 | FALSE |  | 2027-12-22T20:00:00+00:00 | 2027-12-24T11:00:00+00:00 | 2027-12-23T04:00:00+08:00 | 2027-12-24T19:00:00+08:00 |  |  |  |  | 39.00 | 5FPS Module Maintenance |  |  | [{"equipmentGUID": "3636f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC5FPS", "name": "Screen: MTP Final Product No. 5 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82758 | 2026-06-02T07:14:46.2666003+00:00 | 2026-06-02T15:14:46.2666003+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:49.1209875+00:00 | 2026-06-08T07:53:49.1209875+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327342 | TRUE | TRUE | 2026-06-07T23:53:49.1209875+00:00 | 2026-06-08T07:53:49.1209875+08:00 | #82758 - MTP: 39hrs - 5FPS MODULE | 1.0 | FALSE |  | 2027-09-22T20:00:00+00:00 | 2027-09-24T11:00:00+00:00 | 2027-09-23T04:00:00+08:00 | 2027-09-24T19:00:00+08:00 |  |  |  |  | 39.00 | 5FPS Module Maintenance |  |  | [{"equipmentGUID": "3636f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC5FPS", "name": "Screen: MTP Final Product No. 5 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82757 | 2026-06-02T07:14:46.2665882+00:00 | 2026-06-02T15:14:46.2665882+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:49.5001445+00:00 | 2026-06-08T07:53:49.5001445+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327343 | TRUE | TRUE | 2026-06-07T23:53:49.5001445+00:00 | 2026-06-08T07:53:49.5001445+08:00 | #82757 - MTP: 39hrs - 5FPS MODULE | 1.0 | FALSE |  | 2027-06-23T20:00:00+00:00 | 2027-06-25T11:00:00+00:00 | 2027-06-24T04:00:00+08:00 | 2027-06-25T19:00:00+08:00 |  |  |  |  | 39.00 | 5FPS Module Maintenance |  |  | [{"equipmentGUID": "3636f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC5FPS", "name": "Screen: MTP Final Product No. 5 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82756 | 2026-06-02T07:14:46.2665757+00:00 | 2026-06-02T15:14:46.2665757+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:49.8876255+00:00 | 2026-06-08T07:53:49.8876255+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327344 | TRUE | TRUE | 2026-06-07T23:53:49.8876255+00:00 | 2026-06-08T07:53:49.8876255+08:00 | #82756 - MTP: 39hrs - 5FPS MODULE | 1.0 | FALSE |  | 2027-03-24T20:00:00+00:00 | 2027-03-26T11:00:00+00:00 | 2027-03-25T04:00:00+08:00 | 2027-03-26T19:00:00+08:00 |  |  |  |  | 39.00 | 5FPS Module Maintenance |  |  | [{"equipmentGUID": "3636f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC5FPS", "name": "Screen: MTP Final Product No. 5 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82755 | 2026-06-02T07:14:46.2665611+00:00 | 2026-06-02T15:14:46.2665611+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:50.3033986+00:00 | 2026-06-08T07:53:50.3033986+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327345 | TRUE | TRUE | 2026-06-07T23:53:50.3033986+00:00 | 2026-06-08T07:53:50.3033986+08:00 | #82755 - MTP: 39hrs - 4FPS MODULE | 1.0 | FALSE |  | 2027-11-25T20:00:00+00:00 | 2027-11-27T11:00:00+00:00 | 2027-11-26T04:00:00+08:00 | 2027-11-27T19:00:00+08:00 |  |  |  |  | 39.00 | 4FPS Module Maintenance |  |  | [{"equipmentGUID": "b668fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC4FPS", "name": "Screen: MTP Final Product No. 4 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82754 | 2026-06-02T07:14:46.2665491+00:00 | 2026-06-02T15:14:46.2665491+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:50.7076006+00:00 | 2026-06-08T07:53:50.7076006+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327346 | TRUE | TRUE | 2026-06-07T23:53:50.7076006+00:00 | 2026-06-08T07:53:50.7076006+08:00 | #82754 - MTP: 39hrs - 4FPS MODULE | 1.0 | FALSE |  | 2027-08-26T20:00:00+00:00 | 2027-08-28T11:00:00+00:00 | 2027-08-27T04:00:00+08:00 | 2027-08-28T19:00:00+08:00 |  |  |  |  | 39.00 | 4FPS Module Maintenance |  |  | [{"equipmentGUID": "b668fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC4FPS", "name": "Screen: MTP Final Product No. 4 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82752 | 2026-06-02T07:14:46.2665127+00:00 | 2026-06-02T15:14:46.2665127+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:51.1077975+00:00 | 2026-06-08T07:53:51.1077975+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327347 | TRUE | TRUE | 2026-06-07T23:53:51.1077975+00:00 | 2026-06-08T07:53:51.1077975+08:00 | #82752 - MTP: 39hrs - 4FPS MODULE | 1.0 | FALSE |  | 2027-02-25T20:00:00+00:00 | 2027-02-27T11:00:00+00:00 | 2027-02-26T04:00:00+08:00 | 2027-02-27T19:00:00+08:00 |  |  |  |  | 39.00 | 4FPS Module Maintenance |  |  | [{"equipmentGUID": "b668fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC4FPS", "name": "Screen: MTP Final Product No. 4 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82753 | 2026-06-02T07:14:46.2665265+00:00 | 2026-06-02T15:14:46.2665265+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:51.5134394+00:00 | 2026-06-08T07:53:51.5134394+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327348 | TRUE | TRUE | 2026-06-07T23:53:51.5134394+00:00 | 2026-06-08T07:53:51.5134394+08:00 | #82753 - MTP: 39hrs - 4FPS MODULE | 1.0 | FALSE |  | 2027-05-27T20:00:00+00:00 | 2027-05-29T11:00:00+00:00 | 2027-05-28T04:00:00+08:00 | 2027-05-29T19:00:00+08:00 |  |  |  |  | 39.00 | 4FPS Module Maintenance |  |  | [{"equipmentGUID": "b668fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC4FPS", "name": "Screen: MTP Final Product No. 4 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82751 | 2026-06-02T07:14:46.266501+00:00 | 2026-06-02T15:14:46.266501+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:51.9254584+00:00 | 2026-06-08T07:53:51.9254584+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327349 | TRUE | TRUE | 2026-06-07T23:53:51.9254584+00:00 | 2026-06-08T07:53:51.9254584+08:00 | #82751 - MTP: 39hrs - 3FPS MODULE | 1.0 | FALSE |  | 2027-10-14T20:00:00+00:00 | 2027-10-16T11:00:00+00:00 | 2027-10-15T04:00:00+08:00 | 2027-10-16T19:00:00+08:00 |  |  |  |  | 39.00 | 3FPS Module Maintenance |  |  | [{"equipmentGUID": "58fbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC3FPS", "name": "Screen: MTP Final Product No. 3 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82750 | 2026-06-02T07:14:46.2664888+00:00 | 2026-06-02T15:14:46.2664888+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:52.3300334+00:00 | 2026-06-08T07:53:52.3300334+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327350 | TRUE | TRUE | 2026-06-07T23:53:52.3300334+00:00 | 2026-06-08T07:53:52.3300334+08:00 | #82750 - MTP: 39hrs - 3FPS MODULE | 1.0 | FALSE |  | 2027-07-15T20:00:00+00:00 | 2027-07-17T11:00:00+00:00 | 2027-07-16T04:00:00+08:00 | 2027-07-17T19:00:00+08:00 |  |  |  |  | 39.00 | 3FPS Module Maintenance |  |  | [{"equipmentGUID": "58fbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC3FPS", "name": "Screen: MTP Final Product No. 3 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82749 | 2026-06-02T07:14:46.2664748+00:00 | 2026-06-02T15:14:46.2664748+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:52.7523852+00:00 | 2026-06-08T07:53:52.7523852+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327351 | TRUE | TRUE | 2026-06-07T23:53:52.7523852+00:00 | 2026-06-08T07:53:52.7523852+08:00 | #82749 - MTP: 39hrs - 3FPS MODULE | 1.0 | FALSE |  | 2027-04-14T20:00:00+00:00 | 2027-04-16T11:00:00+00:00 | 2027-04-15T04:00:00+08:00 | 2027-04-16T19:00:00+08:00 |  |  |  |  | 39.00 | 3FPS Module Maintenance |  |  | [{"equipmentGUID": "58fbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC3FPS", "name": "Screen: MTP Final Product No. 3 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82748 | 2026-06-02T07:14:46.2664613+00:00 | 2026-06-02T15:14:46.2664613+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:53.1688534+00:00 | 2026-06-08T07:53:53.1688534+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327352 | TRUE | TRUE | 2026-06-07T23:53:53.1688534+00:00 | 2026-06-08T07:53:53.1688534+08:00 | #82748 - MTP: 39hrs - 3FPS MODULE | 1.0 | FALSE |  | 2027-01-14T20:00:00+00:00 | 2027-01-16T11:00:00+00:00 | 2027-01-15T04:00:00+08:00 | 2027-01-16T19:00:00+08:00 |  |  |  |  | 39.00 | 3FPS Module Maintenance |  |  | [{"equipmentGUID": "58fbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC3FPS", "name": "Screen: MTP Final Product No. 3 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82747 | 2026-06-02T07:14:46.2664448+00:00 | 2026-06-02T15:14:46.2664448+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:53.5839178+00:00 | 2026-06-08T07:53:53.5839178+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327353 | TRUE | TRUE | 2026-06-07T23:53:53.5839178+00:00 | 2026-06-08T07:53:53.5839178+08:00 | #82747 - MTP: 39hrs - 2FPS MODULE | 1.0 | FALSE |  | 2027-10-11T20:00:00+00:00 | 2027-10-13T11:00:00+00:00 | 2027-10-12T04:00:00+08:00 | 2027-10-13T19:00:00+08:00 |  |  |  |  | 39.00 | 2FPS Module Maintenance |  |  | [{"equipmentGUID": "7524f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC2FPS", "name": "Screen: MTP Final Product No. 2 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82746 | 2026-06-02T07:14:46.266431+00:00 | 2026-06-02T15:14:46.266431+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:53.9994138+00:00 | 2026-06-08T07:53:53.9994138+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327354 | TRUE | TRUE | 2026-06-07T23:53:53.9994138+00:00 | 2026-06-08T07:53:53.9994138+08:00 | #82746 - MTP: 39hrs - 2FPS MODULE | 1.0 | FALSE |  | 2027-07-12T20:00:00+00:00 | 2027-07-14T11:00:00+00:00 | 2027-07-13T04:00:00+08:00 | 2027-07-14T19:00:00+08:00 |  |  |  |  | 39.00 | 2FPS Module Maintenance |  |  | [{"equipmentGUID": "7524f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC2FPS", "name": "Screen: MTP Final Product No. 2 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82745 | 2026-06-02T07:14:46.2663951+00:00 | 2026-06-02T15:14:46.2663951+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:54.4200675+00:00 | 2026-06-08T07:53:54.4200675+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327355 | TRUE | TRUE | 2026-06-07T23:53:54.4200675+00:00 | 2026-06-08T07:53:54.4200675+08:00 | #82745 - MTP: 39hrs - 2FPS MODULE | 1.0 | FALSE |  | 2027-04-11T20:00:00+00:00 | 2027-04-13T11:00:00+00:00 | 2027-04-12T04:00:00+08:00 | 2027-04-13T19:00:00+08:00 |  |  |  |  | 39.00 | 2FPS Module Maintenance |  |  | [{"equipmentGUID": "7524f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC2FPS", "name": "Screen: MTP Final Product No. 2 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82736 | 2026-06-02T05:50:46.7681157+00:00 | 2026-06-02T13:50:46.7681157+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:56.6736246+00:00 | 2026-06-08T07:53:56.6736246+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327357 | TRUE | TRUE | 2026-06-07T23:53:56.6736246+00:00 | 2026-06-08T07:53:56.6736246+08:00 | #82736 - MTP: 92hrs - 93STK MODULE | 1.0 | FALSE |  | 2028-01-03T16:00:00+00:00 | 2028-01-07T12:00:00+00:00 | 2028-01-04T00:00:00+08:00 | 2028-01-07T20:00:00+08:00 |  |  |  |  | 92.00 | 93STK Module Maintenance |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82731 | 2026-06-02T05:50:46.7680237+00:00 | 2026-06-02T13:50:46.7680237+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:57.9711261+00:00 | 2026-06-08T07:53:57.9711261+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327358 | TRUE | TRUE | 2026-06-07T23:53:57.9711261+00:00 | 2026-06-08T07:53:57.9711261+08:00 | #82731 - MTP: 92hrs - W&S MODULE 6 | 1.0 | FALSE |  | 2027-09-24T16:00:00+00:00 | 2027-09-28T12:00:00+00:00 | 2027-09-25T00:00:00+08:00 | 2027-09-28T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 6 Maintenance |  |  | [{"equipmentGUID": "7571e0a4-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD06", "name": "Screen: MTP Wash & Screen Module 06", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82730 | 2026-06-02T05:50:46.768014+00:00 | 2026-06-02T13:50:46.768014+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:58.438905+00:00 | 2026-06-08T07:53:58.438905+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327359 | TRUE | TRUE | 2026-06-07T23:53:58.438905+00:00 | 2026-06-08T07:53:58.438905+08:00 | #82730 - MTP: 92hrs - W&S MODULE 6 | 1.0 | FALSE |  | 2027-03-26T16:00:00+00:00 | 2027-03-30T12:00:00+00:00 | 2027-03-27T00:00:00+08:00 | 2027-03-30T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 6 Maintenance |  |  | [{"equipmentGUID": "7571e0a4-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD06", "name": "Screen: MTP Wash & Screen Module 06", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82729 | 2026-06-02T05:50:46.768006+00:00 | 2026-06-02T13:50:46.768006+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:58.9033706+00:00 | 2026-06-08T07:53:58.9033706+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327360 | TRUE | TRUE | 2026-06-07T23:53:58.9033706+00:00 | 2026-06-08T07:53:58.9033706+08:00 | #82729 - MTP: 92hrs - W&S MODULE 5 | 1.0 | FALSE |  | 2027-09-06T16:00:00+00:00 | 2027-09-10T12:00:00+00:00 | 2027-09-07T00:00:00+08:00 | 2027-09-10T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 5 Maintenance |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82728 | 2026-06-02T05:50:46.7679984+00:00 | 2026-06-02T13:50:46.7679984+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:59.3575946+00:00 | 2026-06-08T07:53:59.3575946+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327361 | TRUE | TRUE | 2026-06-07T23:53:59.3575946+00:00 | 2026-06-08T07:53:59.3575946+08:00 | #82728 - MTP: 92hrs - W&S MODULE 5 | 1.0 | FALSE |  | 2027-03-09T16:00:00+00:00 | 2027-03-13T12:00:00+00:00 | 2027-03-10T00:00:00+08:00 | 2027-03-13T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 5 Maintenance |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82727 | 2026-06-02T05:50:46.7679893+00:00 | 2026-06-02T13:50:46.7679893+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:53:59.8302109+00:00 | 2026-06-08T07:53:59.8302109+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327362 | TRUE | TRUE | 2026-06-07T23:53:59.8302109+00:00 | 2026-06-08T07:53:59.8302109+08:00 | #82727 - MTP: 92hrs - W&S MODULE 4 | 1.0 | FALSE |  | 2027-08-26T16:00:00+00:00 | 2027-08-30T12:00:00+00:00 | 2027-08-27T00:00:00+08:00 | 2027-08-30T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 4 Maintenance |  |  | [{"equipmentGUID": "a6dee187-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD04", "name": "Screen: MTP Wash & Screen Module 04", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82726 | 2026-06-02T05:50:46.7679818+00:00 | 2026-06-02T13:50:46.7679818+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:00.6182532+00:00 | 2026-06-08T07:54:00.6182532+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327363 | TRUE | TRUE | 2026-06-07T23:54:00.6182532+00:00 | 2026-06-08T07:54:00.6182532+08:00 | #82726 - MTP: 92hrs - W&S MODULE 4 | 1.0 | FALSE |  | 2027-02-26T16:00:00+00:00 | 2027-03-02T12:00:00+00:00 | 2027-02-27T00:00:00+08:00 | 2027-03-02T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 4 Maintenance |  |  | [{"equipmentGUID": "a6dee187-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD04", "name": "Screen: MTP Wash & Screen Module 04", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82725 | 2026-06-02T05:50:46.7679741+00:00 | 2026-06-02T13:50:46.7679741+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:01.1569731+00:00 | 2026-06-08T07:54:01.1569731+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327364 | TRUE | TRUE | 2026-06-07T23:54:01.1569731+00:00 | 2026-06-08T07:54:01.1569731+08:00 | #82725 - MTP: 116hrs - W&S MODULE 3 | 1.0 | FALSE |  | 2027-07-14T16:00:00+00:00 | 2027-07-19T12:00:00+00:00 | 2027-07-15T00:00:00+08:00 | 2027-07-19T20:00:00+08:00 |  |  |  |  | 116.00 | W&S Module 3 Maintenance |  |  | [{"equipmentGUID": "61efe581-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD03", "name": "Screen: MTP Wash & Screen Module 03", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82723 | 2026-06-02T05:50:46.767958+00:00 | 2026-06-02T13:50:46.767958+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:02.2072441+00:00 | 2026-06-08T07:54:02.2072441+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327366 | TRUE | TRUE | 2026-06-07T23:54:02.2072441+00:00 | 2026-06-08T07:54:02.2072441+08:00 | #82723 - MTP: 92hrs - W&S MODULE 2 | 1.0 | FALSE |  | 2027-12-08T16:00:00+00:00 | 2027-12-12T12:00:00+00:00 | 2027-12-09T00:00:00+08:00 | 2027-12-12T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 2 Maintenance |  |  | [{"equipmentGUID": "83318e78-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD02", "name": "Screen: MTP Wash & Screen Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82722 | 2026-06-02T05:50:46.7679504+00:00 | 2026-06-02T13:50:46.7679504+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:02.6766246+00:00 | 2026-06-08T07:54:02.6766246+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327367 | TRUE | TRUE | 2026-06-07T23:54:02.6766246+00:00 | 2026-06-08T07:54:02.6766246+08:00 | #82722 - MTP: 92hrs - W&S MODULE 2 | 1.0 | FALSE |  | 2027-06-07T16:00:00+00:00 | 2027-06-11T12:00:00+00:00 | 2027-06-08T00:00:00+08:00 | 2027-06-11T20:00:00+08:00 |  |  |  |  | 92.00 | W&S Module 2 Maintenance |  |  | [{"equipmentGUID": "83318e78-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD02", "name": "Screen: MTP Wash & Screen Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82721 | 2026-06-02T05:50:46.7679412+00:00 | 2026-06-02T13:50:46.7679412+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:03.1660369+00:00 | 2026-06-08T07:54:03.1660369+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327368 | TRUE | TRUE | 2026-06-07T23:54:03.1660369+00:00 | 2026-06-08T07:54:03.1660369+08:00 | #82721 - MTP: 212hrs - W&S MODULE 1 | 1.0 | FALSE |  | 2027-07-20T16:00:00+00:00 | 2027-07-29T12:00:00+00:00 | 2027-07-21T00:00:00+08:00 | 2027-07-29T20:00:00+08:00 |  |  |  |  | 212.00 | W&S Module 1 Maintenance |  |  | [{"equipmentGUID": "0f91deaf-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD01", "name": "Screen: MTP Wash & Screen Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82720 | 2026-06-02T05:50:46.7679337+00:00 | 2026-06-02T13:50:46.7679337+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:03.6894497+00:00 | 2026-06-08T07:54:03.6894497+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327369 | TRUE | TRUE | 2026-06-07T23:54:03.6894497+00:00 | 2026-06-08T07:54:03.6894497+08:00 | #82720 - MTP: 116hrs - W&S MODULE 1 | 1.0 | FALSE |  | 2027-01-21T16:00:00+00:00 | 2027-01-26T12:00:00+00:00 | 2027-01-22T00:00:00+08:00 | 2027-01-26T20:00:00+08:00 |  |  |  |  | 116.00 | W&S Module 1 Maintenance |  |  | [{"equipmentGUID": "0f91deaf-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD01", "name": "Screen: MTP Wash & Screen Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82719 | 2026-06-02T05:50:46.7679247+00:00 | 2026-06-02T13:50:46.7679247+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:04.2100588+00:00 | 2026-06-08T07:54:04.2100588+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327370 | TRUE | TRUE | 2026-06-07T23:54:04.2100588+00:00 | 2026-06-08T07:54:04.2100588+08:00 | #82719 - MTP: 14hrs - W&S MODULE 6 PITSTOP | 1.0 | FALSE |  | 2027-12-31T20:00:00+00:00 | 2028-01-01T10:00:00+00:00 | 2028-01-01T04:00:00+08:00 | 2028-01-01T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 6 Pitstop |  |  | [{"equipmentGUID": "7571e0a4-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD06", "name": "Screen: MTP Wash & Screen Module 06", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82718 | 2026-06-02T05:50:46.7679163+00:00 | 2026-06-02T13:50:46.7679163+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:04.7237539+00:00 | 2026-06-08T07:54:04.7237539+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327371 | TRUE | TRUE | 2026-06-07T23:54:04.7237539+00:00 | 2026-06-08T07:54:04.7237539+08:00 | #82718 - MTP: 14hrs - W&S MODULE 6 PITSTOP | 1.0 | FALSE |  | 2027-07-02T20:00:00+00:00 | 2027-07-03T10:00:00+00:00 | 2027-07-03T04:00:00+08:00 | 2027-07-03T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 6 Pitstop |  |  | [{"equipmentGUID": "7571e0a4-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD06", "name": "Screen: MTP Wash & Screen Module 06", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82717 | 2026-06-02T05:50:46.7679089+00:00 | 2026-06-02T13:50:46.7679089+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:05.2544466+00:00 | 2026-06-08T07:54:05.2544466+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327372 | TRUE | TRUE | 2026-06-07T23:54:05.2544466+00:00 | 2026-06-08T07:54:05.2544466+08:00 | #82717 - MTP: 14hrs - W&S MODULE 5 PITSTOP | 1.0 | FALSE |  | 2027-12-12T20:00:00+00:00 | 2027-12-13T10:00:00+00:00 | 2027-12-13T04:00:00+08:00 | 2027-12-13T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 5 Pitstop |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82715 | 2026-06-02T05:50:46.7678903+00:00 | 2026-06-02T13:50:46.7678903+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:05.7607233+00:00 | 2026-06-08T07:54:05.7607233+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327373 | TRUE | TRUE | 2026-06-07T23:54:05.7607233+00:00 | 2026-06-08T07:54:05.7607233+08:00 | #82715 - MTP: 14hrs - W&S MODULE 4 PITSTOP | 1.0 | FALSE |  | 2027-11-28T20:00:00+00:00 | 2027-11-29T10:00:00+00:00 | 2027-11-29T04:00:00+08:00 | 2027-11-29T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 4 Pitstop |  |  | [{"equipmentGUID": "a6dee187-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD04", "name": "Screen: MTP Wash & Screen Module 04", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82716 | 2026-06-02T05:50:46.7678997+00:00 | 2026-06-02T13:50:46.7678997+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:06.3046794+00:00 | 2026-06-08T07:54:06.3046794+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327374 | TRUE | TRUE | 2026-06-07T23:54:06.3046794+00:00 | 2026-06-08T07:54:06.3046794+08:00 | #82716 - MTP: 14hrs - W&S MODULE 5 PITSTOP | 1.0 | FALSE |  | 2027-06-12T20:00:00+00:00 | 2027-06-13T10:00:00+00:00 | 2027-06-13T04:00:00+08:00 | 2027-06-13T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 5 Pitstop |  |  | [{"equipmentGUID": "eb978292-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD05", "name": "Screen: MTP Wash & Screen Module 05", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82714 | 2026-06-02T05:50:46.7678779+00:00 | 2026-06-02T13:50:46.7678779+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:06.8605127+00:00 | 2026-06-08T07:54:06.8605127+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327375 | TRUE | TRUE | 2026-06-07T23:54:06.8605127+00:00 | 2026-06-08T07:54:06.8605127+08:00 | #82714 - MTP: 14hrs - W&S MODULE 4 PITSTOP | 1.0 | FALSE |  | 2027-05-29T20:00:00+00:00 | 2027-05-30T10:00:00+00:00 | 2027-05-30T04:00:00+08:00 | 2027-05-30T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 4 Pitstop |  |  | [{"equipmentGUID": "a6dee187-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD04", "name": "Screen: MTP Wash & Screen Module 04", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82713 | 2026-06-02T05:50:46.7678664+00:00 | 2026-06-02T13:50:46.7678664+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:07.4334803+00:00 | 2026-06-08T07:54:07.4334803+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327376 | TRUE | TRUE | 2026-06-07T23:54:07.4334803+00:00 | 2026-06-08T07:54:07.4334803+08:00 | #82713 - MTP: 14hrs - W&S MODULE 3 PITSTOP | 1.0 | FALSE |  | 2027-10-13T20:00:00+00:00 | 2027-10-14T10:00:00+00:00 | 2027-10-14T04:00:00+08:00 | 2027-10-14T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 3 Pitstop |  |  | [{"equipmentGUID": "61efe581-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD03", "name": "Screen: MTP Wash & Screen Module 03", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82712 | 2026-06-02T05:50:46.7678588+00:00 | 2026-06-02T13:50:46.7678588+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:07.9723421+00:00 | 2026-06-08T07:54:07.9723421+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327377 | TRUE | TRUE | 2026-06-07T23:54:07.9723421+00:00 | 2026-06-08T07:54:07.9723421+08:00 | #82712 - MTP: 14hrs - W&S MODULE 3 PITSTOP | 1.0 | FALSE |  | 2027-04-14T20:00:00+00:00 | 2027-04-15T10:00:00+00:00 | 2027-04-15T04:00:00+08:00 | 2027-04-15T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 3 Pitstop |  |  | [{"equipmentGUID": "61efe581-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD03", "name": "Screen: MTP Wash & Screen Module 03", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82710 | 2026-06-02T05:50:46.767836+00:00 | 2026-06-02T13:50:46.767836+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:08.521656+00:00 | 2026-06-08T07:54:08.521656+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327378 | TRUE | TRUE | 2026-06-07T23:54:08.521656+00:00 | 2026-06-08T07:54:08.521656+08:00 | #82710 - MTP: 14hrs - W&S MODULE 2 PITSTOP | 1.0 | FALSE |  | 2027-03-07T20:00:00+00:00 | 2027-03-08T10:00:00+00:00 | 2027-03-08T04:00:00+08:00 | 2027-03-08T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 2 Pitstop |  |  | [{"equipmentGUID": "83318e78-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD02", "name": "Screen: MTP Wash & Screen Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82711 | 2026-06-02T05:50:46.7678463+00:00 | 2026-06-02T13:50:46.7678463+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:09.1026177+00:00 | 2026-06-08T07:54:09.1026177+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327379 | TRUE | TRUE | 2026-06-07T23:54:09.1026177+00:00 | 2026-06-08T07:54:09.1026177+08:00 | #82711 - MTP: 14hrs - W&S MODULE 2 PITSTOP | 1.0 | FALSE |  | 2027-09-05T20:00:00+00:00 | 2027-09-06T10:00:00+00:00 | 2027-09-06T04:00:00+08:00 | 2027-09-06T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 2 Pitstop |  |  | [{"equipmentGUID": "83318e78-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD02", "name": "Screen: MTP Wash & Screen Module 02", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82709 | 2026-06-02T05:50:46.767828+00:00 | 2026-06-02T13:50:46.767828+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:09.6366038+00:00 | 2026-06-08T07:54:09.6366038+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327380 | TRUE | TRUE | 2026-06-07T23:54:09.6366038+00:00 | 2026-06-08T07:54:09.6366038+08:00 | #82709 - MTP: 14hrs - W&S MODULE 1 PITSTOP | 1.0 | FALSE |  | 2027-10-23T20:00:00+00:00 | 2027-10-24T10:00:00+00:00 | 2027-10-24T04:00:00+08:00 | 2027-10-24T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 1 Pitstop |  |  | [{"equipmentGUID": "0f91deaf-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD01", "name": "Screen: MTP Wash & Screen Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82708 | 2026-06-02T05:50:46.7678186+00:00 | 2026-06-02T13:50:46.7678186+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:10.1750206+00:00 | 2026-06-08T07:54:10.1750206+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327381 | TRUE | TRUE | 2026-06-07T23:54:10.1750206+00:00 | 2026-06-08T07:54:10.1750206+08:00 | #82708 - MTP: 14hrs - W&S MODULE 1 PITSTOP | 1.0 | FALSE |  | 2027-04-24T20:00:00+00:00 | 2027-04-25T10:00:00+00:00 | 2027-04-25T04:00:00+08:00 | 2027-04-25T18:00:00+08:00 |  |  |  |  | 14.00 | W&S Module 1 Pitstop |  |  | [{"equipmentGUID": "0f91deaf-0586-ef11-a853-000d3acacefd", "code": "MTPSCWSCMOD01", "name": "Screen: MTP Wash & Screen Module 01", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82707 | 2026-06-02T05:50:46.767811+00:00 | 2026-06-02T13:50:46.767811+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:10.7659464+00:00 | 2026-06-08T07:54:10.7659464+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327382 | TRUE | TRUE | 2026-06-07T23:54:10.7659464+00:00 | 2026-06-08T07:54:10.7659464+08:00 | #82707 - MTP: 36hrs - 16C CONVEYOR MODULE | 1.0 | FALSE |  | 2027-12-30T22:00:00+00:00 | 2028-01-01T10:00:00+00:00 | 2027-12-31T06:00:00+08:00 | 2028-01-01T18:00:00+08:00 |  |  |  |  | 36.00 | 16C Modular Maintenance |  |  | [{"equipmentGUID": "", "code": "MTPCV16C", "name": "Conveyor: MTP 16C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82706 | 2026-06-02T05:50:46.767794+00:00 | 2026-06-02T13:50:46.767794+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:11.316662+00:00 | 2026-06-08T07:54:11.316662+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327383 | TRUE | TRUE | 2026-06-07T23:54:11.316662+00:00 | 2026-06-08T07:54:11.316662+08:00 | #82706 - MTP: 36hrs - 16C CONVEYOR MODULE | 1.0 | FALSE |  | 2027-06-29T22:00:00+00:00 | 2027-07-01T10:00:00+00:00 | 2027-06-30T06:00:00+08:00 | 2027-07-01T18:00:00+08:00 |  |  |  |  | 36.00 | 16C Modular Maintenance |  |  | [{"equipmentGUID": "", "code": "MTPCV16C", "name": "Conveyor: MTP 16C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82705 | 2026-06-02T05:50:46.7677799+00:00 | 2026-06-02T13:50:46.7677799+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:11.9037031+00:00 | 2026-06-08T07:54:11.9037031+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327384 | TRUE | TRUE | 2026-06-07T23:54:11.9037031+00:00 | 2026-06-08T07:54:11.9037031+08:00 | #82705 - MTP: 40hrs - 31M CONVEYOR MODULE | 1.0 | FALSE |  | 2027-09-12T20:00:00+00:00 | 2027-09-14T12:00:00+00:00 | 2027-09-13T04:00:00+08:00 | 2027-09-14T20:00:00+08:00 |  |  |  |  | 40.00 | 31M Module Maintenance |  |  | [{"equipmentGUID": "a8ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV31M", "name": "Conveyor: MTP 31M", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82703 | 2026-06-02T05:50:46.7677633+00:00 | 2026-06-02T13:50:46.7677633+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:13.0098819+00:00 | 2026-06-08T07:54:13.0098819+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327386 | TRUE | TRUE | 2026-06-07T23:54:13.0098819+00:00 | 2026-06-08T07:54:13.0098819+08:00 | #82703 - MTP: 40hrs - 24M CONVEYOR MODULE | 1.0 | FALSE |  | 2027-12-28T20:00:00+00:00 | 2027-12-30T12:00:00+00:00 | 2027-12-29T04:00:00+08:00 | 2027-12-30T20:00:00+08:00 |  |  |  |  | 40.00 | 24M Module Maintenance |  |  | [{"equipmentGUID": "b43ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV24M", "name": "Conveyor: MTP 24M", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82701 | 2026-06-02T05:50:46.7677462+00:00 | 2026-06-02T13:50:46.7677462+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:13.5648095+00:00 | 2026-06-08T07:54:13.5648095+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327387 | TRUE | TRUE | 2026-06-07T23:54:13.5648095+00:00 | 2026-06-08T07:54:13.5648095+08:00 | #82701 - MTP: 92hrs - C8 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-12-04T16:00:00+00:00 | 2027-12-08T12:00:00+00:00 | 2027-12-05T00:00:00+08:00 | 2027-12-08T20:00:00+08:00 |  |  |  |  | 92.00 | C8 Module Maintenance |  |  | [{"equipmentGUID": "c632f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS08", "name": "Crusher - Tertiary: MTP 08 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82702 | 2026-06-02T05:50:46.7677537+00:00 | 2026-06-02T13:50:46.7677537+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:14.1420715+00:00 | 2026-06-08T07:54:14.1420715+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327388 | TRUE | TRUE | 2026-06-07T23:54:14.1420715+00:00 | 2026-06-08T07:54:14.1420715+08:00 | #82702 - MTP: 40hrs - 24M CONVEYOR MODULE | 1.0 | FALSE |  | 2027-06-27T20:00:00+00:00 | 2027-06-29T12:00:00+00:00 | 2027-06-28T04:00:00+08:00 | 2027-06-29T20:00:00+08:00 |  |  |  |  | 40.00 | 24M Module Maintenance |  |  | [{"equipmentGUID": "b43ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV24M", "name": "Conveyor: MTP 24M", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82700 | 2026-06-02T05:50:46.7677363+00:00 | 2026-06-02T13:50:46.7677363+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:14.7230551+00:00 | 2026-06-08T07:54:14.7230551+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327389 | TRUE | TRUE | 2026-06-07T23:54:14.7230551+00:00 | 2026-06-08T07:54:14.7230551+08:00 | #82700 - MTP: 92hrs - C8 TERTIARY CRUSHER MODULE | 1.0 | FALSE |  | 2027-08-31T16:00:00+00:00 | 2027-09-04T12:00:00+00:00 | 2027-09-01T00:00:00+08:00 | 2027-09-04T20:00:00+08:00 |  |  |  |  | 92.00 | C8 Module Maintenance |  |  | [{"equipmentGUID": "c632f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS08", "name": "Crusher - Tertiary: MTP 08 Low Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82684 | 2026-06-02T03:13:23.6611081+00:00 | 2026-06-02T11:13:23.6611081+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:24.5527744+00:00 | 2026-06-08T07:54:24.5527744+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327405 | TRUE | TRUE | 2026-06-07T23:54:24.5527744+00:00 | 2026-06-08T07:54:24.5527744+08:00 | #82684 - MTP: 172hrs - DRUM 2 MODULE | 1.0 | FALSE |  | 2027-04-25T11:00:00+00:00 | 2027-05-02T15:00:00+00:00 | 2027-04-25T19:00:00+08:00 | 2027-05-02T23:00:00+08:00 |  |  |  |  | 172.00 | Drum 2 Module Maintetance |  |  | [{"equipmentGUID": "8817ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM02", "name": "Drum: MTP Module 02", "assetClass": {"name": "Drum"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82682 | 2026-06-02T03:13:23.6610898+00:00 | 2026-06-02T11:13:23.6610898+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:25.1697742+00:00 | 2026-06-08T07:54:25.1697742+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327406 | TRUE | TRUE | 2026-06-07T23:54:25.1697742+00:00 | 2026-06-08T07:54:25.1697742+08:00 | #82682 - MTP: 172hrs - DRUM 1 MODULE | 1.0 | FALSE |  | 2027-06-14T11:00:00+00:00 | 2027-06-21T15:00:00+00:00 | 2027-06-14T19:00:00+08:00 | 2027-06-21T23:00:00+08:00 |  |  |  |  | 172.00 | Drum 1 Module Maintenance |  |  | [{"equipmentGUID": "8f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM01", "name": "Drum: MTP Module 01", "assetClass": {"name": "Drum"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82683 | 2026-06-02T03:13:23.6611001+00:00 | 2026-06-02T11:13:23.6611001+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:25.8565608+00:00 | 2026-06-08T07:54:25.8565608+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327407 | TRUE | TRUE | 2026-06-07T23:54:25.8565608+00:00 | 2026-06-08T07:54:25.8565608+08:00 | #82683 - MTP: 172hrs - DRUM 1 MODULE | 1.0 | FALSE |  | 2027-12-13T11:00:00+00:00 | 2027-12-20T15:00:00+00:00 | 2027-12-13T19:00:00+08:00 | 2027-12-20T23:00:00+08:00 |  |  |  |  | 172.00 | Drum 1 Module Maintenance |  |  | [{"equipmentGUID": "8f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM01", "name": "Drum: MTP Module 01", "assetClass": {"name": "Drum"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82681 | 2026-06-02T03:13:23.6610794+00:00 | 2026-06-02T11:13:23.6610794+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:26.5302621+00:00 | 2026-06-08T07:54:26.5302621+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327408 | TRUE | TRUE | 2026-06-07T23:54:26.5302621+00:00 | 2026-06-08T07:54:26.5302621+08:00 | #82681 - MTP: 196hrs - DRUM 0 MODULE | 1.0 | FALSE |  | 2027-08-10T11:00:00+00:00 | 2027-08-18T15:00:00+00:00 | 2027-08-10T19:00:00+08:00 | 2027-08-18T23:00:00+08:00 |  |  |  |  | 196.00 | Drum 0 Module Maintenance |  |  | [{"equipmentGUID": "8e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM0", "name": "Drum: MTP Module 0", "assetClass": {"name": "Drum"}}, {"equipmentGUID": "760cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV22C", "name": "Conveyor: MTP 22C", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "e030f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV23C", "name": "Conveyor: MTP 23C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82680 | 2026-06-02T03:13:23.6610704+00:00 | 2026-06-02T11:13:23.6610704+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:27.2129566+00:00 | 2026-06-08T07:54:27.2129566+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327409 | TRUE | TRUE | 2026-06-07T23:54:27.2129566+00:00 | 2026-06-08T07:54:27.2129566+08:00 | #82680 - MTP: 196hrs - DRUM 0 MODULE | 1.0 | FALSE |  | 2027-02-09T11:00:00+00:00 | 2027-02-17T15:00:00+00:00 | 2027-02-09T19:00:00+08:00 | 2027-02-17T23:00:00+08:00 |  |  |  |  | 196.00 | Drum 0 Module Maintenance |  |  | [{"equipmentGUID": "8e17ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPDM0", "name": "Drum: MTP Module 0", "assetClass": {"name": "Drum"}}, {"equipmentGUID": "760cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV22C", "name": "Conveyor: MTP 22C", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "e030f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV23C", "name": "Conveyor: MTP 23C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82679 | 2026-06-02T03:13:23.6610585+00:00 | 2026-06-02T11:13:23.6610585+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:27.8562593+00:00 | 2026-06-08T07:54:27.8562593+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327410 | TRUE | TRUE | 2026-06-07T23:54:27.8562593+00:00 | 2026-06-08T07:54:27.8562593+08:00 | #82679 - MTP: 44hrs - 72C MODULE | 1.0 | FALSE |  | 2027-12-26T16:00:00+00:00 | 2027-12-28T12:00:00+00:00 | 2027-12-27T00:00:00+08:00 | 2027-12-28T20:00:00+08:00 |  |  |  |  | 44.00 | 72C Module Maintenance |  |  | [{"equipmentGUID": "0e27f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV72C", "name": "Conveyor: MTP 72C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82678 | 2026-06-02T03:13:23.6610507+00:00 | 2026-06-02T11:13:23.6610507+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:28.545278+00:00 | 2026-06-08T07:54:28.545278+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327411 | TRUE | TRUE | 2026-06-07T23:54:28.545278+00:00 | 2026-06-08T07:54:28.545278+08:00 | #82678 - MTP: 44hrs - 72C MODULE | 1.0 | FALSE |  | 2027-06-25T16:00:00+00:00 | 2027-06-27T12:00:00+00:00 | 2027-06-26T00:00:00+08:00 | 2027-06-27T20:00:00+08:00 |  |  |  |  | 44.00 | 72C Module Maintenance |  |  | [{"equipmentGUID": "0e27f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPCV72C", "name": "Conveyor: MTP 72C", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82677 | 2026-06-02T03:13:23.6610429+00:00 | 2026-06-02T11:13:23.6610429+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:29.211164+00:00 | 2026-06-08T07:54:29.211164+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327412 | TRUE | TRUE | 2026-06-07T23:54:29.211164+00:00 | 2026-06-08T07:54:29.211164+08:00 | #82677 - MTP: 44hrs - P253 MODULE | 1.0 | FALSE |  | 2027-09-22T16:00:00+00:00 | 2027-09-24T12:00:00+00:00 | 2027-09-23T00:00:00+08:00 | 2027-09-24T20:00:00+08:00 |  |  |  |  | 44.00 | P253 Module Maintenance |  |  | [{"equipmentGUID": "a9ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP253", "name": "Pump: MTP 253 Spirals Cyclone Feed 03", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82676 | 2026-06-02T03:13:23.6610336+00:00 | 2026-06-02T11:13:23.6610336+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:29.8903834+00:00 | 2026-06-08T07:54:29.8903834+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327413 | TRUE | TRUE | 2026-06-07T23:54:29.8903834+00:00 | 2026-06-08T07:54:29.8903834+08:00 | #82676 - MTP: 44hrs - P253 MODULE | 1.0 | FALSE |  | 2027-03-23T16:00:00+00:00 | 2027-03-25T12:00:00+00:00 | 2027-03-24T00:00:00+08:00 | 2027-03-25T20:00:00+08:00 |  |  |  |  | 44.00 | P253 Module Maintenance |  |  | [{"equipmentGUID": "a9ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPPMP253", "name": "Pump: MTP 253 Spirals Cyclone Feed 03", "assetClass": {"name": "Pump"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82674 | 2026-06-02T03:13:23.6610184+00:00 | 2026-06-02T11:13:23.6610184+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:30.5444263+00:00 | 2026-06-08T07:54:30.5444263+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327414 | TRUE | TRUE | 2026-06-07T23:54:30.5444263+00:00 | 2026-06-08T07:54:30.5444263+08:00 | #82674 - MTP: 44hrs - SPIRALS 4 MODULE | 1.0 | FALSE |  | 2027-03-21T16:00:00+00:00 | 2027-03-23T12:00:00+00:00 | 2027-03-22T00:00:00+08:00 | 2027-03-23T20:00:00+08:00 |  |  |  |  | 44.00 | Spirals 4 Module Maintenance |  |  | [{"equipmentGUID": "850c1b40-d965-ef11-a852-000d3acacefd", "code": "MTPSPIMOD04", "name": "Spirals: MTP Module 04", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82675 | 2026-06-02T03:13:23.6610262+00:00 | 2026-06-02T11:13:23.6610262+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-06-07T23:54:31.2038649+00:00 | 2026-06-08T07:54:31.2038649+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 327415 | TRUE | TRUE | 2026-06-07T23:54:31.2038649+00:00 | 2026-06-08T07:54:31.2038649+08:00 | #82675 - MTP: 44hrs - SPIRALS 4 MODULE | 1.0 | FALSE |  | 2027-09-20T16:00:00+00:00 | 2027-09-22T12:00:00+00:00 | 2027-09-21T00:00:00+08:00 | 2027-09-22T20:00:00+08:00 |  |  |  |  | 44.00 | Spirals 4 Module Maintenance |  |  | [{"equipmentGUID": "850c1b40-d965-ef11-a852-000d3acacefd", "code": "MTPSPIMOD04", "name": "Spirals: MTP Module 04", "assetClass": {"name": "Spirals"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "82d63fcf-4f74-45a5-9428-e719a4a4ad54", "emailAddress": "Rikki.Sturzaker@riotinto.com", "displayName": "Sturzaker, Rikki (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82688 | 2026-06-02T05:50:46.767628+00:00 | 2026-06-02T13:50:46.767628+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-05T03:21:27.8816957+00:00 | 2026-08-05T11:21:27.8816957+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330856 | TRUE | TRUE | 2026-08-05T03:21:27.8816957+00:00 | 2026-08-05T11:21:27.8816957+08:00 | #82688 - MTP: 164hrs - 6 CIRCUIT MODULE | 2.0 | FALSE |  | 2027-08-18T16:00:00+00:00 | 2027-08-25T12:00:00+00:00 | 2027-08-19T00:00:00+08:00 | 2027-08-25T20:00:00+08:00 |  |  |  |  | 164.00 | 6CCT Module Maintenance | Apron Feeder complete upper chute liner replacement |  | [{"equipmentGUID": "95e5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS06", "name": "Crusher - Secondary: MTP 06 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82691 | 2026-06-02T05:50:46.7676577+00:00 | 2026-06-02T13:50:46.7676577+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-05T03:21:28.0472779+00:00 | 2026-08-05T11:21:28.0472779+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330857 | TRUE | TRUE | 2026-08-05T03:21:28.0472779+00:00 | 2026-08-05T11:21:28.0472779+08:00 | #82691 - MTP: 164hrs - 5 CIRCUIT MODULE | 2.0 | FALSE |  | 2027-06-21T16:00:00+00:00 | 2027-06-28T12:00:00+00:00 | 2027-06-22T00:00:00+08:00 | 2027-06-28T20:00:00+08:00 |  |  |  |  | 164.00 | 5CCT Module Maintenance | Apron feeder complete upper chute liner replacement |  | [{"equipmentGUID": "4cf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS05", "name": "Crusher - Secondary: MTP 05 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82687 | 2026-06-02T05:50:46.7676057+00:00 | 2026-06-02T13:50:46.7676057+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-05T03:21:28.2576973+00:00 | 2026-08-05T11:21:28.2576973+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330858 | TRUE | TRUE | 2026-08-05T03:21:28.2576973+00:00 | 2026-08-05T11:21:28.2576973+08:00 | #82687 - MTP: 164hrs - 6 CIRCUIT MODULE | 2.0 | FALSE |  | 2027-05-19T16:00:00+00:00 | 2027-05-26T12:00:00+00:00 | 2027-05-20T00:00:00+08:00 | 2027-05-26T20:00:00+08:00 |  |  |  |  | 164.00 | 6CCT Module Maintenance | Apron feeder complete upper chute liners to be replaced |  | [{"equipmentGUID": "95e5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS06", "name": "Crusher - Secondary: MTP 06 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82690 | 2026-06-02T05:50:46.7676493+00:00 | 2026-06-02T13:50:46.7676493+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-08-05T03:21:28.4452095+00:00 | 2026-08-05T11:21:28.4452095+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 330859 | TRUE | TRUE | 2026-08-05T03:21:28.4452095+00:00 | 2026-08-05T11:21:28.4452095+08:00 | #82690 - MTP: 164hrs - 5 CIRCUIT MODULE | 2.0 | FALSE |  | 2027-03-17T16:00:00+00:00 | 2027-03-24T12:00:00+00:00 | 2027-03-18T00:00:00+08:00 | 2027-03-24T20:00:00+08:00 |  |  |  |  | 164.00 | 5CCT Module Maintenance | Apron feeder complete upper chute liners to be replaced |  | [{"equipmentGUID": "4cf6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSCS05", "name": "Crusher - Secondary: MTP 05 Low Grade", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "cfe60bb3-09e5-413b-86f1-b44a52eab139", "emailAddress": "Ben.Logan@riotinto.com", "displayName": "Ben Logan"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0ea9fbf2-4fcd-467a-b13b-60e712d13f7b", "emailAddress": "Tayne.Cunningham@riotinto.com", "displayName": "Tayne Cunningham"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82743 | 2026-06-02T05:50:46.7681757+00:00 | 2026-06-02T13:50:46.7681757+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:34.559799+00:00 | 2026-07-03T09:21:34.559799+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329291 | TRUE | TRUE | 2026-07-03T01:21:34.559799+00:00 | 2026-07-03T09:21:34.559799+08:00 | #82743 - MTP: 92hrs - 15STK MODULE | 1.0 | FALSE |  | 2027-10-19T16:00:00+00:00 | 2027-10-23T12:00:00+00:00 | 2027-10-20T00:00:00+08:00 | 2027-10-23T20:00:00+08:00 |  |  |  |  | 92.00 | 15STK Module Maintenance |  |  | [{"equipmentGUID": "bf2bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST15", "name": "Stacker: MTP 15 Lump", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82742 | 2026-06-02T05:50:46.7681665+00:00 | 2026-06-02T13:50:46.7681665+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:34.750062+00:00 | 2026-07-03T09:21:34.750062+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329292 | TRUE | TRUE | 2026-07-03T01:21:34.750062+00:00 | 2026-07-03T09:21:34.750062+08:00 | #82742 - MTP: 140hrs - 15STK MODULE | 1.0 | FALSE |  | 2027-04-20T16:00:00+00:00 | 2027-04-26T12:00:00+00:00 | 2027-04-21T00:00:00+08:00 | 2027-04-26T20:00:00+08:00 |  |  |  |  | 140.00 | 15STK Module Maintenance |  |  | [{"equipmentGUID": "bf2bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST15", "name": "Stacker: MTP 15 Lump", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82741 | 2026-06-02T05:50:46.7681591+00:00 | 2026-06-02T13:50:46.7681591+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:34.9346747+00:00 | 2026-07-03T09:21:34.9346747+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329293 | TRUE | TRUE | 2026-07-03T01:21:34.9346747+00:00 | 2026-07-03T09:21:34.9346747+08:00 | #82741 - MTP: 92hrs - 88STK MODULE | 1.0 | FALSE |  | 2027-11-08T16:00:00+00:00 | 2027-11-12T12:00:00+00:00 | 2027-11-09T00:00:00+08:00 | 2027-11-12T20:00:00+08:00 |  |  |  |  | 92.00 | 88STK Module Maintenance |  |  | [{"equipmentGUID": "b858fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST88", "name": "Stacker: MTP 88 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82740 | 2026-06-02T05:50:46.7681513+00:00 | 2026-06-02T13:50:46.7681513+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:35.1577501+00:00 | 2026-07-03T09:21:35.1577501+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329294 | TRUE | TRUE | 2026-07-03T01:21:35.1577501+00:00 | 2026-07-03T09:21:35.1577501+08:00 | #82740 - MTP: 12hrs - 88STK MODULE RMP WASH DOWN | 1.0 | FALSE |  | 2027-11-07T22:00:00+00:00 | 2027-11-08T10:00:00+00:00 | 2027-11-08T06:00:00+08:00 | 2027-11-08T18:00:00+08:00 |  |  |  |  | 12.00 | 88STK Module RMP Wash Down |  |  | [{"equipmentGUID": "b858fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST88", "name": "Stacker: MTP 88 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82738 | 2026-06-02T05:50:46.768134+00:00 | 2026-06-02T13:50:46.768134+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:35.3662891+00:00 | 2026-07-03T09:21:35.3662891+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329295 | TRUE | TRUE | 2026-07-03T01:21:35.3662891+00:00 | 2026-07-03T09:21:35.3662891+08:00 | #82738 - MTP: 92hrs - 88STK MODULE | 1.0 | FALSE |  | 2027-05-10T16:00:00+00:00 | 2027-05-14T12:00:00+00:00 | 2027-05-11T00:00:00+08:00 | 2027-05-14T20:00:00+08:00 |  |  |  |  | 92.00 | 88STK Module Maintenance |  |  | [{"equipmentGUID": "b858fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST88", "name": "Stacker: MTP 88 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82739 | 2026-06-02T05:50:46.7681422+00:00 | 2026-06-02T13:50:46.7681422+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:35.5890275+00:00 | 2026-07-03T09:21:35.5890275+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329296 | TRUE | TRUE | 2026-07-03T01:21:35.5890275+00:00 | 2026-07-03T09:21:35.5890275+08:00 | #82739 - MTP: 92hrs - 88STK MODULE | 1.0 | FALSE |  | 2027-08-09T16:00:00+00:00 | 2027-08-13T12:00:00+00:00 | 2027-08-10T00:00:00+08:00 | 2027-08-13T20:00:00+08:00 |  |  |  |  | 92.00 | 88STK Module Maintenance |  |  | [{"equipmentGUID": "b858fbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST88", "name": "Stacker: MTP 88 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82735 | 2026-06-02T05:50:46.7680984+00:00 | 2026-06-02T13:50:46.7680984+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:35.9991913+00:00 | 2026-07-03T09:21:35.9991913+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329298 | TRUE | TRUE | 2026-07-03T01:21:35.9991913+00:00 | 2026-07-03T09:21:35.9991913+08:00 | #82735 - MTP: 92hrs - 93STK MODULE | 1.0 | FALSE |  | 2027-10-04T16:00:00+00:00 | 2027-10-08T12:00:00+00:00 | 2027-10-05T00:00:00+08:00 | 2027-10-08T20:00:00+08:00 |  |  |  |  | 92.00 | 93STK Module Maintenance |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82733 | 2026-06-02T05:50:46.7680401+00:00 | 2026-06-02T13:50:46.7680401+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:36.2423941+00:00 | 2026-07-03T09:21:36.2423941+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329299 | TRUE | TRUE | 2026-07-03T01:21:36.2423941+00:00 | 2026-07-03T09:21:36.2423941+08:00 | #82733 - MTP: 92hrs - 93STK MODULE | 1.0 | FALSE |  | 2027-04-05T16:00:00+00:00 | 2027-04-09T12:00:00+00:00 | 2027-04-06T00:00:00+08:00 | 2027-04-09T20:00:00+08:00 |  |  |  |  | 92.00 | 93STK Module Maintenance |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82734 | 2026-06-02T05:50:46.7680495+00:00 | 2026-06-02T13:50:46.7680495+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:36.4712959+00:00 | 2026-07-03T09:21:36.4712959+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329300 | TRUE | TRUE | 2026-07-03T01:21:36.4712959+00:00 | 2026-07-03T09:21:36.4712959+08:00 | #82734 - MTP: 92hrs - 93STK MODULE | 1.0 | FALSE |  | 2027-07-05T16:00:00+00:00 | 2027-07-09T12:00:00+00:00 | 2027-07-06T00:00:00+08:00 | 2027-07-09T20:00:00+08:00 |  |  |  |  | 92.00 | 93STK Module Maintenance |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82732 | 2026-06-02T05:50:46.7680315+00:00 | 2026-06-02T13:50:46.7680315+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-07-03T01:21:36.6848832+00:00 | 2026-07-03T09:21:36.6848832+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 329301 | TRUE | TRUE | 2026-07-03T01:21:36.6848832+00:00 | 2026-07-03T09:21:36.6848832+08:00 | #82732 - MTP: 12hrs - 93STK MODULE RMP WASH DOWN | 1.0 | FALSE |  | 2027-04-04T22:00:00+00:00 | 2027-04-05T10:00:00+00:00 | 2027-04-05T06:00:00+08:00 | 2027-04-05T18:00:00+08:00 |  |  |  |  | 12.00 | 93STK Module RMP Wash Down |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
68812 | 2025-09-05T02:10:13.9070689+00:00 | 2025-09-05T10:10:13.9070689+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2025-09-22T02:51:46.2472096+00:00 | 2025-09-22T10:51:46.2472096+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | {"name": "Fixed Plant"} | 244551 | TRUE | TRUE | 2025-09-22T02:51:46.2472096+00:00 | 2025-09-22T10:51:46.2472096+08:00 | #68812 - MTP: 92hrs - STACKER: MTP 93 FINES | 1.0 | FALSE |  | 2026-12-28T16:00:00+00:00 | 2027-01-01T12:00:00+00:00 | 2026-12-29T00:00:00+08:00 | 2027-01-01T20:00:00+08:00 |  |  |  |  | 92.00 | 93STK Module Maintenance |  |  | [{"equipmentGUID": "ac38f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPST93", "name": "Stacker: MTP 93 Fines", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "emailAddress": "Bradley.Sheehan@riotinto.com", "displayName": "Sheehan, Bradley (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 6640c1ce-a2a1-478a-b24b-1a8441afb962 | Sheehan, Bradley (RTIO) | Scheduled | MTP | Australia/Perth
82644 | 2026-06-01T04:53:18.6024225+00:00 | 2026-06-01T12:53:18.6024225+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-08-10T02:13:39.3445252+00:00 | 2026-08-10T10:13:39.3445252+08:00 | {"principalGUID": "dd09e12b-f64d-488c-b551-87e8c1ac7b2f", "displayName": "Jeffs, Ross (RTIO)"} | {"name": "Fixed Plant"} | 330966 | TRUE | TRUE | 2026-08-10T02:13:39.3445252+00:00 | 2026-08-10T10:13:39.3445252+08:00 | #82644 - WAN: 24hrs - TRAIN LOADOUT: WAN | 2.0 | TRUE |  | 2027-02-28T16:00:00+00:00 | 2027-03-01T16:00:00+00:00 | 2027-03-01T00:00:00+08:00 | 2027-03-02T00:00:00+08:00 |  |  |  |  | 24.00 | Reclaimer Bucket C/O | Was supposed to commence at Midnight for Wash and Isolations to allow 6am Maintenance Start |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "d616f0bf-7c7b-ee11-a846-000d3acacefd", "code": "WANRC01", "name": "Reclaimer: WAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "fd9465b1-6644-4d4c-916b-34added2dd50", "emailAddress": "Samuel.Thorne@riotinto.com", "displayName": "Thorne, Samuel (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | dd09e12b-f64d-488c-b551-87e8c1ac7b2f | Jeffs, Ross (RTIO) | Scheduled | WAN | Australia/Perth
82645 | 2026-06-01T04:53:19.2080378+00:00 | 2026-06-01T12:53:19.2080378+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-08-10T02:13:39.6323538+00:00 | 2026-08-10T10:13:39.6323538+08:00 | {"principalGUID": "dd09e12b-f64d-488c-b551-87e8c1ac7b2f", "displayName": "Jeffs, Ross (RTIO)"} | {"name": "Fixed Plant"} | 330967 | TRUE | TRUE | 2026-08-10T02:13:39.6323538+00:00 | 2026-08-10T10:13:39.6323538+08:00 | #82645 - WAN: 24hrs - TRAIN LOADOUT: WAN | 2.0 | TRUE |  | 2027-05-30T16:00:00+00:00 | 2027-05-31T16:00:00+00:00 | 2027-05-31T00:00:00+08:00 | 2027-06-01T00:00:00+08:00 |  |  |  |  | 24.00 | Reclaimer Bucket C/O | Was supposed to commence at Midnight for Wash and Isolations to allow 6am Maintenance Start |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "d616f0bf-7c7b-ee11-a846-000d3acacefd", "code": "WANRC01", "name": "Reclaimer: WAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "fd9465b1-6644-4d4c-916b-34added2dd50", "emailAddress": "Samuel.Thorne@riotinto.com", "displayName": "Thorne, Samuel (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | dd09e12b-f64d-488c-b551-87e8c1ac7b2f | Jeffs, Ross (RTIO) | Scheduled | WAN | Australia/Perth
82646 | 2026-06-01T04:53:19.3874024+00:00 | 2026-06-01T12:53:19.3874024+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-08-10T02:13:39.8228104+00:00 | 2026-08-10T10:13:39.8228104+08:00 | {"principalGUID": "dd09e12b-f64d-488c-b551-87e8c1ac7b2f", "displayName": "Jeffs, Ross (RTIO)"} | {"name": "Fixed Plant"} | 330968 | TRUE | TRUE | 2026-08-10T02:13:39.8228104+00:00 | 2026-08-10T10:13:39.8228104+08:00 | #82646 - WAN: 24hrs - TRAIN LOADOUT: WAN | 2.0 | TRUE |  | 2027-08-29T16:00:00+00:00 | 2027-08-30T16:00:00+00:00 | 2027-08-30T00:00:00+08:00 | 2027-08-31T00:00:00+08:00 |  |  |  |  | 24.00 | Reclaimer Bucket C/O | Was supposed to commence at Midnight for Wash and Isolations to allow 6am Maintenance Start |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "d616f0bf-7c7b-ee11-a846-000d3acacefd", "code": "WANRC01", "name": "Reclaimer: WAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "fd9465b1-6644-4d4c-916b-34added2dd50", "emailAddress": "Samuel.Thorne@riotinto.com", "displayName": "Thorne, Samuel (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | dd09e12b-f64d-488c-b551-87e8c1ac7b2f | Jeffs, Ross (RTIO) | Scheduled | WAN | Australia/Perth
82647 | 2026-06-01T04:53:19.567325+00:00 | 2026-06-01T12:53:19.567325+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-08-10T02:13:40.0458746+00:00 | 2026-08-10T10:13:40.0458746+08:00 | {"principalGUID": "dd09e12b-f64d-488c-b551-87e8c1ac7b2f", "displayName": "Jeffs, Ross (RTIO)"} | {"name": "Fixed Plant"} | 330969 | TRUE | TRUE | 2026-08-10T02:13:40.0458746+00:00 | 2026-08-10T10:13:40.0458746+08:00 | #82647 - WAN: 24hrs - TRAIN LOADOUT: WAN | 2.0 | TRUE |  | 2027-11-28T16:00:00+00:00 | 2027-11-29T16:00:00+00:00 | 2027-11-29T00:00:00+08:00 | 2027-11-30T00:00:00+08:00 |  |  |  |  | 24.00 | Reclaimer Bucket C/O | Was supposed to commence at Midnight for Wash and Isolations to allow 6am Maintenance Start |  | [{"equipmentGUID": "c7fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "WANTLO", "name": "Train Loadout: WAN", "assetClass": {"name": "Train Loadout"}}, {"equipmentGUID": "d616f0bf-7c7b-ee11-a846-000d3acacefd", "code": "WANRC01", "name": "Reclaimer: WAN 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "fd9465b1-6644-4d4c-916b-34added2dd50", "emailAddress": "Samuel.Thorne@riotinto.com", "displayName": "Thorne, Samuel (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | dd09e12b-f64d-488c-b551-87e8c1ac7b2f | Jeffs, Ross (RTIO) | Scheduled | WAN | Australia/Perth
83995 | 2026-09-25T02:38:46.7330537+00:00 | 2026-09-25T10:38:46.7330537+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | 2026-10-02T06:34:08.0460531+00:00 | 2026-10-02T14:34:08.0460531+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335023 | TRUE | TRUE | 2026-10-02T06:34:08.0460531+00:00 | 2026-10-02T14:34:08.0460531+08:00 | #83995 - RVA: 24hrs - RVA SCREEN PANEL SPRINT | 1.0 | TRUE |  | 2027-01-04T16:00:00+00:00 | 2027-01-05T16:00:00+00:00 | 2027-01-05T00:00:00+08:00 | 2027-01-06T00:00:00+08:00 |  |  |  |  | 24.00 | Inspect wet plant screen panels and change Ad-hoc as required. |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "31cead4c-692a-4b59-bd32-1db808cf6367", "emailAddress": "jayden.dadleh@riotinto.com", "displayName": "Dadleh, Jayden (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "emailAddress": "Ailsa.Azizah@riotinto.com", "displayName": "Azizah, Ailsa (RTA)"}}] | [] | [] | [] | [] | [] | Approved | Create | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
83994 | 2026-09-25T02:30:17.1340323+00:00 | 2026-09-25T10:30:17.1340323+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | 2026-10-02T06:34:08.2254872+00:00 | 2026-10-02T14:34:08.2254872+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335024 | TRUE | TRUE | 2026-10-02T06:34:08.2254872+00:00 | 2026-10-02T14:34:08.2254872+08:00 | #83994 - RVA: 24hrs - RVA SCREEN PANEL SPRINT | 1.0 | TRUE |  | 2027-10-04T16:00:00+00:00 | 2027-10-05T16:00:00+00:00 | 2027-10-05T00:00:00+08:00 | 2027-10-06T00:00:00+08:00 |  |  |  |  | 24.00 | Inspect wet plant screen panels and change Ad-hoc as required. |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "31cead4c-692a-4b59-bd32-1db808cf6367", "emailAddress": "jayden.dadleh@riotinto.com", "displayName": "Dadleh, Jayden (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "emailAddress": "Ailsa.Azizah@riotinto.com", "displayName": "Azizah, Ailsa (RTA)"}}] | [] | [] | [] | [] | [] | Approved | Create | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
83993 | 2026-09-25T02:28:39.9768296+00:00 | 2026-09-25T10:28:39.9768296+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | 2026-10-02T06:34:08.4068748+00:00 | 2026-10-02T14:34:08.4068748+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335025 | TRUE | TRUE | 2026-10-02T06:34:08.4068748+00:00 | 2026-10-02T14:34:08.4068748+08:00 | #83993 - RVA: 24hrs - RVA SCREEN PANEL SPRINT | 1.0 | TRUE |  | 2027-07-05T16:00:00+00:00 | 2027-07-06T16:00:00+00:00 | 2027-07-06T00:00:00+08:00 | 2027-07-07T00:00:00+08:00 |  |  |  |  | 24.00 | Inspect wet plant screen panels and change Ad-hoc as required. |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "31cead4c-692a-4b59-bd32-1db808cf6367", "emailAddress": "jayden.dadleh@riotinto.com", "displayName": "Dadleh, Jayden (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "emailAddress": "Ailsa.Azizah@riotinto.com", "displayName": "Azizah, Ailsa (RTA)"}}] | [] | [] | [] | [] | [] | Approved | Create | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
83107 | 2026-06-29T23:27:12.2335535+00:00 | 2026-06-30T07:27:12.2335535+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | 2026-08-03T04:14:25.2734592+00:00 | 2026-08-03T12:14:25.2734592+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 330727 | TRUE | TRUE | 2026-08-03T04:14:25.2734592+00:00 | 2026-08-03T12:14:25.2734592+08:00 | #83107 - RVA: 132hrs - PLANT: RVA WET & TRAIN LOADOUT: RVA | 1.0 | TRUE |  | 2027-08-12T03:00:00+00:00 | 2027-08-17T15:00:00+00:00 | 2027-08-12T11:00:00+08:00 | 2027-08-17T23:00:00+08:00 |  |  |  |  | 132.00 | TLO Stockpiling Dozing Outage. |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "4227f6bf-7c7b-ee11-a846-000d3acacefd", "code": "RVATLO", "name": "Train Loadout: RVA", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Dozing"}] | Approved | Create | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Site Constraint | RVA | Australia/Perth
83992 | 2026-09-25T02:25:57.6994788+00:00 | 2026-09-25T10:25:57.6994788+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | 2026-10-02T06:34:08.5930616+00:00 | 2026-10-02T14:34:08.5930616+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335026 | TRUE | TRUE | 2026-10-02T06:34:08.5930616+00:00 | 2026-10-02T14:34:08.5930616+08:00 | #83992 - RVA: 24hrs - RVA SCREEN PANEL SPRINT | 1.0 | TRUE |  | 2027-04-05T16:00:00+00:00 | 2027-04-06T16:00:00+00:00 | 2027-04-06T00:00:00+08:00 | 2027-04-07T00:00:00+08:00 |  |  |  |  | 24.00 | Inspect wet plant screen panels and change Ad-hoc as required. |  |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "31cead4c-692a-4b59-bd32-1db808cf6367", "emailAddress": "jayden.dadleh@riotinto.com", "displayName": "Dadleh, Jayden (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "emailAddress": "Ailsa.Azizah@riotinto.com", "displayName": "Azizah, Ailsa (RTA)"}}] | [] | [] | [] | [] | [] | Approved | Create | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
82178 | 2026-04-09T05:15:29.7252035+00:00 | 2026-04-09T13:15:29.7252035+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-07-29T08:39:23.1018054+00:00 | 2026-07-29T16:39:23.1018054+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 330560 | TRUE | TRUE | 2026-07-29T08:39:23.1018054+00:00 | 2026-07-29T16:39:23.1018054+08:00 | #82178 - RVJ: 462hrs - PP1 SIZER PROJECT | 2.0 | TRUE |  | 2027-01-05T21:00:00+00:00 | 2027-01-25T03:00:00+00:00 | 2027-01-06T05:00:00+08:00 | 2027-01-25T11:00:00+08:00 |  |  |  |  | 462.00 | PP1 Sizer Project - Placeholder o Electrical & instrumentation scope  Removal of redundant cables  Electrical disconnection of AFD1 & Head Chute sensors  Removal of 127-DB-04, FMB 05, FMB 08  SUBSTATION J5 MODIFICATION + CABLE TERMINATION  Re-Installation of 127-DB-04, FMB 05, FMB 08 proprietary equipment  Installation of new cables from PP1 JB's TBC to field locations  Termination of Electrical enclosures and proprietary equipment  Testing of installed cables and equipment / completion of ITR's o Structural Works  Remove Existing Sizer Feed Chute RL 163.130  Deconstruct Existing Sizer Middle Feed Chute  Modify Hydraulic/Lube/Conduit Routes for Structure Upgrades  Install Short Column on South Angle Brace  Modify Existing Upper Sizer Feed Chute  Deconstruct Sizer Platform @ RL 160.580  Install New Module 5/6 Platform Connections RL 160.580  Install New Sizer Platform & Tower RL 151 - 160.5  Sizer Replacement  Modify Davit Crane & Rock Breaker Column Supports  Install Structure @ RL 160.580 Sizer Platform  Install Structural Support Steel for Sizer Feed Chute RL 163.500 o Commissioning | no conflicts between work fronts during the proposed shutdown window, All disciplines are aligned on the sequence and duration of activities. The schedule has been developed by Monos in close collaboration with key vendors (MMD and Tasman Power). |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "00e7d21c-57a7-445f-87a1-a7672499ad87", "emailAddress": "Allen.Matemerah@riotinto.com", "displayName": "Matemerah, Allen (RTIO-GUIDANTGLOBAL)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44665, "shutVersionId": 283101, "title": "#44665 - RVJ: 120hrs - PLANT: RVJ 01", "startDatetimeUTC": "2027-01-05T21:00:00+00:00", "endDatetimeUTC": "2027-01-10T21:00:00+00:00"}}] | [{"name": "Project Interactions"}] | [{"code": "P-0603646", "name": "PP1 Sizer project", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "315"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44723 | 2021-11-26T04:26:47+00:00 | 2021-11-26T12:26:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-31T06:40:56.7034904+00:00 | 2026-07-31T14:40:56.7034904+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 330682 | TRUE | TRUE | 2026-07-31T06:40:56.7034904+00:00 | 2026-07-31T14:40:56.7034904+08:00 | #44723 - RVA: 269hrs - PLANT: RVA WET | 12.0 | TRUE |  | 2027-08-12T03:00:00+00:00 | 2027-08-23T08:00:00+00:00 | 2027-08-12T11:00:00+08:00 | 2027-08-23T16:00:00+08:00 |  |  |  |  | 269.00 | RVA WET PLANT SHUT C/O Apron Feeder Components AF2401 | Mesa A week 34 shut and dozing constraint forward 5 days to better align to the CLA shut |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44704 | 2021-11-26T04:26:17+00:00 | 2021-11-26T12:26:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-10T05:57:50.3858115+00:00 | 2026-06-10T13:57:50.3858115+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 327608 | TRUE | TRUE | 2026-06-10T05:57:50.3858115+00:00 | 2026-06-10T13:57:50.3858115+08:00 | #44704 - RVA: 132hrs - TRAIN LOADOUT: RVA | 8.2 | TRUE |  | 2027-11-20T15:00:00+00:00 | 2027-11-26T03:00:00+00:00 | 2027-11-20T23:00:00+08:00 | 2027-11-26T11:00:00+08:00 |  |  |  |  | 132.00 | RVA TLO SHUT |  |  | [{"equipmentGUID": "4227f6bf-7c7b-ee11-a846-000d3acacefd", "code": "RVATLO", "name": "Train Loadout: RVA", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "132"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44703 | 2021-11-26T04:26:16+00:00 | 2021-11-26T12:26:16+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-10T05:58:45.2827419+00:00 | 2026-06-10T13:58:45.2827419+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 327610 | TRUE | TRUE | 2026-06-10T05:58:45.2827419+00:00 | 2026-06-10T13:58:45.2827419+08:00 | #44703 - RVA: 257hrs - TLO STOCKPILE REMOVED | 7.6 | TRUE |  | 2027-08-17T15:00:00+00:00 | 2027-08-28T08:00:00+00:00 | 2027-08-17T23:00:00+08:00 | 2027-08-28T16:00:00+08:00 |  |  |  |  | 257.00 | RVA TLO SHUT C/O Gate1 Guillotine Assembly 10YR TL101 C/O Gate4 Guillotine Assembly 10YR TL101 |  |  | [{"equipmentGUID": "4227f6bf-7c7b-ee11-a846-000d3acacefd", "code": "RVATLO", "name": "Train Loadout: RVA", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [{"name": "TLO Major Works"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "257"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44702 | 2021-11-26T04:26:12+00:00 | 2021-11-26T12:26:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-10T05:59:39.2541571+00:00 | 2026-06-10T13:59:39.2541571+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 327612 | TRUE | TRUE | 2026-06-10T05:59:39.2541571+00:00 | 2026-06-10T13:59:39.2541571+08:00 | #44702 - RVA: 132hrs - TRAIN LOADOUT: RVA | 7.2 | TRUE |  | 2027-05-22T15:00:00+00:00 | 2027-05-28T03:00:00+00:00 | 2027-05-22T23:00:00+08:00 | 2027-05-28T11:00:00+08:00 |  |  |  |  | 132.00 | RVA TLO SHUT |  |  | [{"equipmentGUID": "4227f6bf-7c7b-ee11-a846-000d3acacefd", "code": "RVATLO", "name": "Train Loadout: RVA", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "132"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44621 | 2021-11-25T04:05:14+00:00 | 2021-11-25T12:05:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-10T06:07:00.2930817+00:00 | 2026-06-10T14:07:00.2930817+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 327624 | TRUE | TRUE | 2026-06-10T06:07:00.2930817+00:00 | 2026-06-10T14:07:00.2930817+08:00 | #44621 - RVJ: 257hrs - TRAIN LOADOUT: RVJ | 7.4 | TRUE |  | 2027-08-18T03:00:00+00:00 | 2027-08-28T20:00:00+00:00 | 2027-08-18T11:00:00+08:00 | 2027-08-29T04:00:00+08:00 |  |  |  |  | 257.00 | Standard TLO shut C/O Apron Feeder Components TLOAF01 C/O Apron Feeder Components TLOAF02 |  |  | [{"equipmentGUID": "691af0bf-7c7b-ee11-a846-000d3acacefd", "code": "RVJTLO", "name": "Train Loadout: RVJ", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "257"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44620 | 2021-11-25T04:05:11+00:00 | 2021-11-25T12:05:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-09T05:52:00.172905+00:00 | 2026-10-09T13:52:00.172905+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335760 | TRUE | TRUE | 2026-10-09T05:52:00.172905+00:00 | 2026-10-09T13:52:00.172905+08:00 | #44620 - RVJ: 120hrs - TRAIN LOADOUT: RVJ | 8.0 | TRUE |  | 2027-05-22T03:00:00+00:00 | 2027-05-27T03:00:00+00:00 | 2027-05-22T11:00:00+08:00 | 2027-05-27T11:00:00+08:00 |  |  |  |  | 120.00 | RVJ TLO SHUT | 24 hr TLO extension request to align outage with PP3 outage 120 hours to maximize tool time as TLO offline due to PP3 outage and no direct tipping permission. Adhoc requests for 2027 and a further request and MOC to request permanent change 2028. |  | [{"equipmentGUID": "691af0bf-7c7b-ee11-a846-000d3acacefd", "code": "RVJTLO", "name": "Train Loadout: RVJ", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "96"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44622 | 2021-11-25T04:05:14+00:00 | 2021-11-25T12:05:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-09T05:52:00.7108085+00:00 | 2026-10-09T13:52:00.7108085+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335761 | TRUE | TRUE | 2026-10-09T05:52:00.7108085+00:00 | 2026-10-09T13:52:00.7108085+08:00 | #44622 - RVJ: 120hrs - TRAIN LOADOUT: RVJ | 8.0 | TRUE |  | 2027-11-21T03:00:00+00:00 | 2027-11-26T03:00:00+00:00 | 2027-11-21T11:00:00+08:00 | 2027-11-26T11:00:00+08:00 |  |  |  |  | 120.00 | RVJ TLO SHUT | 24 hr TLO extension request to align outage with PP3 outage 120 hours to maximize tool time as TLO offline due to PP3 outage and no direct tipping permission. Adhoc requests for 2027 and a further request and MOC to request permanent change 2028. |  | [{"equipmentGUID": "691af0bf-7c7b-ee11-a846-000d3acacefd", "code": "RVJTLO", "name": "Train Loadout: RVJ", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "d8ef2c32-6742-48a8-9e85-4edcc57c271a", "emailAddress": "Jessica.Young@riotinto.com", "displayName": "Young, Jessica (RTA-CHANDLERMACLEOD)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "96"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44619 | 2021-11-25T04:05:10+00:00 | 2021-11-25T12:05:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-09T05:52:00.9418444+00:00 | 2026-10-09T13:52:00.9418444+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 335762 | TRUE | TRUE | 2026-10-09T05:52:00.9418444+00:00 | 2026-10-09T13:52:00.9418444+08:00 | #44619 - RVJ: 120hrs - TRAIN LOADOUT: RVJ | 8.0 | TRUE |  | 2027-02-21T03:00:00+00:00 | 2027-02-26T03:00:00+00:00 | 2027-02-21T11:00:00+08:00 | 2027-02-26T11:00:00+08:00 |  |  |  |  | 120.00 | RVJ TLO SHUT | 24 hr TLO extension request to align outage with PP3 outage 120 hours to maximize tool time as TLO offline due to PP3 outage and no direct tipping permission. Adhoc requests for 2027 and a further request and MOC to request permanent change 2028. |  | [{"equipmentGUID": "691af0bf-7c7b-ee11-a846-000d3acacefd", "code": "RVJTLO", "name": "Train Loadout: RVJ", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [] | [] | [] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
54619 | 2023-03-13T11:45:31+00:00 | 2023-03-13T19:45:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-10T07:31:59.198999+00:00 | 2026-06-10T15:31:59.198999+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 327652 | TRUE | TRUE | 2026-06-10T07:31:59.198999+00:00 | 2026-06-10T15:31:59.198999+08:00 | #54619 - RVJ: 120hrs - PLANT: RVJ 01 | 6.2 | TRUE |  | 2027-04-06T21:00:00+00:00 | 2027-04-11T21:00:00+00:00 | 2027-04-07T05:00:00+08:00 | 2027-04-12T05:00:00+08:00 |  |  |  |  | 120.00 | PP1 Shut |  |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "00e7d21c-57a7-445f-87a1-a7672499ad87", "emailAddress": "Allen.Matemerah@riotinto.com", "displayName": "Matemerah, Allen (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0603646", "name": "Mesa J FXP SZ01 Upgrade", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44692 | 2021-11-26T04:24:51+00:00 | 2021-11-26T12:24:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-10T02:29:29.2461246+00:00 | 2026-03-10T10:29:29.2461246+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 320889 | TRUE | TRUE | 2026-03-10T02:29:29.2461246+00:00 | 2026-03-10T10:29:29.2461246+08:00 | #44692 - RVJ: 120hrs - PLANT: RVJ 02 | 8.0 | TRUE |  | 2027-04-07T21:00:00+00:00 | 2027-04-12T21:00:00+00:00 | 2027-04-08T05:00:00+08:00 | 2027-04-13T05:00:00+08:00 |  |  |  |  | 120.00 | PP2 IAM Maintenance Thickener maintenance | AF02 C/O has been moved to Wk27 2026, extension no longer required, duration updated to standard IAM |  | [{"equipmentGUID": "6f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT02", "name": "Plant: RVJ 02", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [] | [{"name": "Thickener Maintenance"}] | [] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44748 | 2021-11-26T11:05:19+00:00 | 2021-11-26T19:05:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-03-10T02:41:20.030607+00:00 | 2026-03-10T10:41:20.030607+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 320915 | TRUE | TRUE | 2026-03-10T02:41:20.030607+00:00 | 2026-03-10T10:41:20.030607+08:00 | #44748 - RVJ: 120hrs - PLANT: RVJ 03 | 12.1 | TRUE |  | 2027-05-22T03:00:00+00:00 | 2027-05-27T03:00:00+00:00 | 2027-05-22T11:00:00+08:00 | 2027-05-27T11:00:00+08:00 |  |  |  |  | 120.00 | PP3 SHUT |  |  | [{"equipmentGUID": "7217ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT03", "name": "Plant: RVJ 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [] | [] | [] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44749 | 2021-11-26T11:06:22+00:00 | 2021-11-26T19:06:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:15:23.9530007+00:00 | 2026-09-30T15:15:23.9530007+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334675 | TRUE | TRUE | 2026-09-30T07:15:23.9530007+00:00 | 2026-09-30T15:15:23.9530007+08:00 | #44749 - RVJ: 245hrs - PLANT: RVJ 03 | 8.3 | TRUE |  | 2027-08-18T03:00:00+00:00 | 2027-08-28T08:00:00+00:00 | 2027-08-18T11:00:00+08:00 | 2027-08-28T16:00:00+08:00 |  |  |  |  | 245.00 | PP3 SHUT C/O SIZER SHAFTS 156WK SZ03 |  |  | [{"equipmentGUID": "7217ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT03", "name": "Plant: RVJ 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Sizer Shafts"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "245"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44691 | 2021-11-26T04:24:51+00:00 | 2021-11-26T12:24:51+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:18:33.6172108+00:00 | 2026-09-30T15:18:33.6172108+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334677 | TRUE | TRUE | 2026-09-30T07:18:33.6172108+00:00 | 2026-09-30T15:18:33.6172108+08:00 | #44691 - RVJ: 120hrs - PLANT: RVJ 02 | 7.2 | TRUE |  | 2027-01-07T00:00:00+00:00 | 2027-01-12T00:00:00+00:00 | 2027-01-07T08:00:00+08:00 | 2027-01-12T08:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance C/O Conveyor Belt PP2 CV03B |  |  | [{"equipmentGUID": "6f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT02", "name": "Plant: RVJ 02", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44669 | 2021-11-26T04:24:12+00:00 | 2021-11-26T12:24:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:20:18.1240562+00:00 | 2026-09-30T15:20:18.1240562+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334678 | TRUE | TRUE | 2026-09-30T07:20:18.1240562+00:00 | 2026-09-30T15:20:18.1240562+08:00 | #44669 - RVJ: 120hrs - PLANT: RVJ 01 | 9.3 | TRUE |  | 2027-07-06T21:00:00+00:00 | 2027-07-11T21:00:00+00:00 | 2027-07-07T05:00:00+08:00 | 2027-07-12T05:00:00+08:00 |  |  |  |  | 120.00 | RVJ PLT1 SHUT C/O Conveyor Belt PP1 CV03A |  |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44693 | 2021-11-26T04:24:52+00:00 | 2021-11-26T12:24:52+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:21:00.426747+00:00 | 2026-09-30T15:21:00.426747+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334679 | TRUE | TRUE | 2026-09-30T07:21:00.426747+00:00 | 2026-09-30T15:21:00.426747+08:00 | #44693 - RVJ: 120hrs - PLANT: RVJ 02 | 8.3 | TRUE |  | 2027-07-07T21:00:00+00:00 | 2027-07-12T21:00:00+00:00 | 2027-07-08T05:00:00+08:00 | 2027-07-13T05:00:00+08:00 |  |  |  |  | 120.00 | PP2 Shut C/O Conveyor Belt PP2 CV02B |  |  | [{"equipmentGUID": "6f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT02", "name": "Plant: RVJ 02", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
54620 | 2023-03-13T11:57:54+00:00 | 2023-03-13T19:57:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:22:45.8001541+00:00 | 2026-09-30T15:22:45.8001541+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334681 | TRUE | TRUE | 2026-09-30T07:22:45.8001541+00:00 | 2026-09-30T15:22:45.8001541+08:00 | #54620 - RVJ: 120hrs - PLANT: RVJ 01 | 6.3 | TRUE |  | 2027-10-05T21:00:00+00:00 | 2027-10-10T21:00:00+00:00 | 2027-10-06T05:00:00+08:00 | 2027-10-11T05:00:00+08:00 |  |  |  |  | 120.00 | PP1 Shut C/O Conveyor Belt PP1 CV02A |  |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44694 | 2021-11-26T04:24:56+00:00 | 2021-11-26T12:24:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-30T07:23:28.6860492+00:00 | 2026-09-30T15:23:28.6860492+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334682 | TRUE | TRUE | 2026-09-30T07:23:28.6860492+00:00 | 2026-09-30T15:23:28.6860492+08:00 | #44694 - RVJ: 120hrs - PLANT: RVJ 02 | 8.3 | TRUE |  | 2027-10-06T21:00:00+00:00 | 2027-10-11T21:00:00+00:00 | 2027-10-07T05:00:00+08:00 | 2027-10-12T05:00:00+08:00 |  |  |  |  | 120.00 | PP2 Shut C/O Conveyor Belt PP2 CV05B |  |  | [{"equipmentGUID": "6f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT02", "name": "Plant: RVJ 02", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Conveyor Belt Changeout"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44673 | 2021-11-26T04:24:21+00:00 | 2021-11-26T12:24:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T02:43:26.3974322+00:00 | 2026-09-29T10:43:26.3974322+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334181 | TRUE | TRUE | 2026-09-29T02:43:26.3974322+00:00 | 2026-09-29T10:43:26.3974322+08:00 | #44673 - RVJ: 120hrs - PLANT: RVJ 01 | 9.2 | TRUE |  | 2028-01-04T21:00:00+00:00 | 2028-01-09T21:00:00+00:00 | 2028-01-05T05:00:00+08:00 | 2028-01-10T05:00:00+08:00 |  |  |  |  | 120.00 | PP1 Shut |  |  | [{"equipmentGUID": "7117ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT01", "name": "Plant: RVJ 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44695 | 2021-11-26T04:24:56+00:00 | 2021-11-26T12:24:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:05:45.3527626+00:00 | 2026-09-29T11:05:45.3527626+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334186 | TRUE | TRUE | 2026-09-29T03:05:45.3527626+00:00 | 2026-09-29T11:05:45.3527626+08:00 | #44695 - RVJ: 120hrs - PLANT: RVJ 02 | 6.2 | TRUE |  | 2028-01-05T21:00:00+00:00 | 2028-01-10T21:00:00+00:00 | 2028-01-06T05:00:00+08:00 | 2028-01-11T05:00:00+08:00 |  |  |  |  | 120.00 | PP2 Shut |  |  | [{"equipmentGUID": "6f17ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT02", "name": "Plant: RVJ 02", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44697 | 2021-11-26T04:26:08+00:00 | 2021-11-26T12:26:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:10:24.7084769+00:00 | 2026-09-29T11:10:24.7084769+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334190 | TRUE | TRUE | 2026-09-29T03:10:24.7084769+00:00 | 2026-09-29T11:10:24.7084769+08:00 | #44697 - RVA: 144hrs - PLANT: RVA DRY | 7.4 | TRUE |  | 2027-02-20T03:00:00+00:00 | 2027-02-26T03:00:00+00:00 | 2027-02-20T11:00:00+08:00 | 2027-02-26T11:00:00+08:00 |  |  |  |  | 144.00 | RVA PLANT SHUT |  |  | [{"equipmentGUID": "7417ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLT", "name": "Plant: RVA Dry", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "144"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44698 | 2021-11-26T04:26:08+00:00 | 2021-11-26T12:26:08+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:12:36.3554515+00:00 | 2026-09-29T11:12:36.3554515+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334191 | TRUE | TRUE | 2026-09-29T03:12:36.3554515+00:00 | 2026-09-29T11:12:36.3554515+08:00 | #44698 - RVA: 144hrs - PLANT: RVA DRY | 7.2 | TRUE |  | 2027-05-22T03:00:00+00:00 | 2027-05-28T03:00:00+00:00 | 2027-05-22T11:00:00+08:00 | 2027-05-28T11:00:00+08:00 |  |  |  |  | 144.00 | RVA PLANT SHUT |  |  | [{"equipmentGUID": "7417ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLT", "name": "Plant: RVA Dry", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 73431, "shutVersionId": 276682, "title": "#73431 - SYSTEM: 22hrs - SOFTWARE: HME FRONTRUNNER DISPATCH", "startDatetimeUTC": "2027-05-17T20:00:00+00:00", "endDatetimeUTC": "2027-05-18T18:00:00+00:00"}}] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "144"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44699 | 2021-11-26T04:26:09+00:00 | 2021-11-26T12:26:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:13:39.2081861+00:00 | 2026-09-29T11:13:39.2081861+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334192 | TRUE | TRUE | 2026-09-29T03:13:39.2081861+00:00 | 2026-09-29T11:13:39.2081861+08:00 | #44699 - RVA: 269hrs - PLANT: RVA DRY | 8.1 | TRUE |  | 2027-08-12T03:00:00+00:00 | 2027-08-23T08:00:00+00:00 | 2027-08-12T11:00:00+08:00 | 2027-08-23T16:00:00+08:00 |  |  |  |  | 269.00 | RVA PLANT SHUT |  |  | [{"equipmentGUID": "7417ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLT", "name": "Plant: RVA Dry", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "269"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44701 | 2021-11-26T04:26:12+00:00 | 2021-11-26T12:26:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:15:41.7079941+00:00 | 2026-09-29T11:15:41.7079941+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334194 | TRUE | TRUE | 2026-09-29T03:15:41.7079941+00:00 | 2026-09-29T11:15:41.7079941+08:00 | #44701 - RVA: 132hrs - TRAIN LOADOUT: RVA | 7.2 | TRUE |  | 2027-02-20T15:00:00+00:00 | 2027-02-26T03:00:00+00:00 | 2027-02-20T23:00:00+08:00 | 2027-02-26T11:00:00+08:00 |  |  |  |  | 132.00 | RVA TLO SHUT |  |  | [{"equipmentGUID": "4227f6bf-7c7b-ee11-a846-000d3acacefd", "code": "RVATLO", "name": "Train Loadout: RVA", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "132"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
44750 | 2021-11-26T11:07:22+00:00 | 2021-11-26T19:07:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-29T03:22:54.7750555+00:00 | 2026-09-29T11:22:54.7750555+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334196 | TRUE | TRUE | 2026-09-29T03:22:54.7750555+00:00 | 2026-09-29T11:22:54.7750555+08:00 | #44750 - RVJ: 120hrs - PLANT: RVJ 03 | 8.2 | TRUE |  | 2027-11-21T03:00:00+00:00 | 2027-11-26T03:00:00+00:00 | 2027-11-21T11:00:00+08:00 | 2027-11-26T11:00:00+08:00 |  |  |  |  | 120.00 | PP3 SHUT |  |  | [{"equipmentGUID": "7217ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVJPLT03", "name": "Plant: RVJ 03", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "5e2d3e7c-7baa-4695-b252-afa5c081f04d", "emailAddress": "Amy.Lopresti@riotinto.com", "displayName": "Amy Lopresti"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVJ | Australia/Perth
44700 | 2021-11-26T04:26:11+00:00 | 2021-11-26T12:26:11+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-01T04:41:38.3107405+00:00 | 2026-10-01T12:41:38.3107405+08:00 | {"principalGUID": "9b97eafe-fc36-4281-b0d7-bea7e4b0613e", "displayName": "Collins, Suzanne (RTIO)"} | {"name": "Fixed Plant"} | 334813 | TRUE | TRUE | 2026-10-01T04:41:38.3107405+00:00 | 2026-10-01T12:41:38.3107405+08:00 | #44700 - RVA: 144hrs - PLANT: RVA DRY | 7.3 | TRUE |  | 2027-11-20T03:00:00+00:00 | 2027-11-26T03:00:00+00:00 | 2027-11-20T11:00:00+08:00 | 2027-11-26T11:00:00+08:00 |  |  |  |  | 144.00 | RVA PLANT SHUT C/O Prim Sizer Shafts&Liners 52WK CR101 |  |  | [{"equipmentGUID": "7417ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLT", "name": "Plant: RVA Dry", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "d2af849a-3e87-428c-94e6-3b0f8f30a953", "emailAddress": "Matthew.Sexton2@riotinto.com", "displayName": "Sexton, Matthew J (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "81a2043e-425d-4047-9f25-dde824bf0482", "emailAddress": "Daniel.Coyne2@riotinto.com", "displayName": "Coyne, Daniel (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Sizer Shafts"}] | [{"code": "P-0603386", "name": "Robe Valley SI Remediation", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "144"}] | [] | Approved | Update | 9b97eafe-fc36-4281-b0d7-bea7e4b0613e | Collins, Suzanne (RTIO) | Scheduled | RVA | Australia/Perth
82856 | 2026-06-08T01:14:30.5127602+00:00 | 2026-06-08T09:14:30.5127602+08:00 | {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "displayName": "Bouyer, Scott (RTIO)"} | 2026-06-15T01:59:47.5532798+00:00 | 2026-06-15T09:59:47.5532798+08:00 | {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "displayName": "Bouyer, Scott (RTIO)"} | {"name": "Fixed Plant"} | 327906 | TRUE | TRUE | 2026-06-15T01:59:47.5532798+00:00 | 2026-06-15T09:59:47.5532798+08:00 | #82856 - PPT: 130hrs - PPSS - REC2P SMPT STRUCTURAL MODIFICATIONS | 1.0 | FALSE |  | 2028-01-02T22:00:00+00:00 | 2028-01-08T08:00:00+00:00 | 2028-01-03T06:00:00+08:00 | 2028-01-08T16:00:00+08:00 |  |  |  |  | 130.00 | PPSS - REC2P SMPT Structural Modifications Bechtel/DHHI to complete SMPT Structural mods to strengthen the machine for removal in major shut |  |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "emailAddress": "Scott.Bouyer@riotinto.com", "displayName": "Bouyer, Scott (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 45706, "shutVersionId": 275119, "title": "#45706 - PPT: 130hrs - RECLAIMER: PPT 2P ", "startDatetimeUTC": "2028-01-02T22:00:00+00:00", "endDatetimeUTC": "2028-01-08T08:00:00+00:00"}}] | [{"name": "Reclaimer Replacement"}] | [{"code": "P-0505178", "name": "Parker Point Stockyard Sustaining", "projectTeam": {"name": "D&T"}, "totalProjectTime": "130"}] | [] | Approved | Create | 9674c013-0b77-4a25-b794-5b4a8c769734 | Bouyer, Scott (RTIO) | Major Projects | PPT | Australia/Perth
82853 | 2026-06-08T00:51:09.6309602+00:00 | 2026-06-08T08:51:09.6309602+08:00 | {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "displayName": "Bouyer, Scott (RTIO)"} | 2026-09-17T03:01:27.1530351+00:00 | 2026-09-17T11:01:27.1530351+08:00 | {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "displayName": "Bouyer, Scott (RTIO)"} | {"name": "Fixed Plant"} | 333475 | TRUE | TRUE | 2026-09-17T03:01:27.1530351+00:00 | 2026-09-17T11:01:27.1530351+08:00 | #82853 - PPT: 56hrs - PPSS - REC3P SMPT STRUCTURAL MODIFICATIONS | 2.0 | FALSE |  | 2026-11-28T14:00:00+00:00 | 2026-11-30T22:00:00+00:00 | 2026-11-28T22:00:00+08:00 | 2026-12-01T06:00:00+08:00 |  |  |  |  | 56.00 | PPSS - REC3P SMPT Structural Modifications Bechtel/DHHI to complete SMPT Structural mods to strengthen the machine for removal in major shut | Reduced to match actual tool time duration supplied by bechtel |  | [{"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "emailAddress": "Scott.Bouyer@riotinto.com", "displayName": "Bouyer, Scott (RTIO)"}}] | [] | [] | [{"name": "Reclaimer Replacement"}] | [{"code": "P-0505178", "name": "Parker Point Stockyard Sustaining", "projectTeam": {"name": "D&T"}, "totalProjectTime": "212"}] | [] | Approved | Update | 9674c013-0b77-4a25-b794-5b4a8c769734 | Bouyer, Scott (RTIO) | Major Projects | PPT | Australia/Perth
83373 | 2026-07-02T05:55:49.5824503+00:00 | 2026-07-02T13:55:49.5824503+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-10-14T07:24:26.5049875+00:00 | 2026-10-14T15:24:26.5049875+08:00 | {"principalGUID": "15eb755a-292d-4f05-8f1e-d051748ec64c", "displayName": "Chen, Nicholas (RTIO)"} | {"name": "HME"} | 335893 | TRUE | TRUE | 2026-10-14T07:24:26.5049875+00:00 | 2026-10-14T15:24:26.5049875+08:00 | #83373 - HD4: 336hrs - 07D336 KOMATSU WA1200-6 WHEEL LOADER | 2.0 | FALSE |  | 2027-06-12T04:00:00+00:00 | 2027-06-26T04:00:00+00:00 | 2027-06-12T12:00:00+08:00 | 2027-06-26T12:00:00+08:00 |  |  |  |  | 336.00 | 14,000hr Shut | updated to match CAT3 labour tracker | SLD33627 | [{"equipmentGUID": "77f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07D336", "name": "07D336 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 15eb755a-292d-4f05-8f1e-d051748ec64c | Chen, Nicholas (RTIO) | Scheduled | HD4 | Australia/Perth |  | L-East
82811 | 2026-06-02T07:14:46.2672924+00:00 | 2026-06-02T15:14:46.2672924+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-09-01T04:17:49.8421802+00:00 | 2026-09-01T12:17:49.8421802+08:00 | {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "displayName": "Butler, Gavin J (RTIO)"} | {"name": "Fixed Plant"} | 332395 | TRUE | TRUE | 2026-09-01T04:17:49.8421802+00:00 | 2026-09-01T12:17:49.8421802+08:00 | #82811 - MTP: 63hrs - CRUSHER - TERTIARY: MTP 04 HIGH GRADE | 2.0 | FALSE |  | 2027-01-10T20:00:00+00:00 | 2027-01-13T11:00:00+00:00 | 2027-01-11T04:00:00+08:00 | 2027-01-13T19:00:00+08:00 |  |  |  |  | 63.00 | 4TC Tert Crusher Module Maintenance | moved out of PC2 shut window due to no labor to complete 4tc module during shut |  | [{"equipmentGUID": "e05ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "MTPTCS04", "name": "Crusher - Tertiary: MTP 04 High Grade", "assetClass": {"name": "Crusher - Tertiary"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 91f19e83-3976-47ce-8fc2-c65d56349520 | Butler, Gavin J (RTIO) | Scheduled | MTP | Australia/Perth
82744 | 2026-06-02T07:14:46.2660154+00:00 | 2026-06-02T15:14:46.2660154+08:00 | {"principalGUID": "6640c1ce-a2a1-478a-b24b-1a8441afb962", "displayName": "Sheehan, Bradley (RTIO)"} | 2026-09-01T04:17:50.0826605+00:00 | 2026-09-01T12:17:50.0826605+08:00 | {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "displayName": "Butler, Gavin J (RTIO)"} | {"name": "Fixed Plant"} | 332396 | TRUE | TRUE | 2026-09-01T04:17:50.0826605+00:00 | 2026-09-01T12:17:50.0826605+08:00 | #82744 - MTP: 39hrs - SCREEN: MTP FINAL PRODUCT NO. 2 | 2.0 | FALSE |  | 2027-01-07T20:00:00+00:00 | 2027-01-09T11:00:00+00:00 | 2027-01-08T04:00:00+08:00 | 2027-01-09T19:00:00+08:00 |  |  |  |  | 39.00 | 2FPS Module Maintenance | Moved to allow work to be moved out of PC2 Shut window |  | [{"equipmentGUID": "7524f6bf-7c7b-ee11-a846-000d3acacefd", "code": "MTPSC2FPS", "name": "Screen: MTP Final Product No. 2 ", "assetClass": {"name": "Screen"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "cc0a438f-131b-4c36-bd20-a0a3440dbd94", "emailAddress": "Patrick.Dempsey@riotinto.com", "displayName": "Patrick Dempsey"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "4d353443-3820-4dec-a234-dac72e0262d6", "emailAddress": "Matthew.Delaporte@riotinto.com", "displayName": "Matt Delaporte"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aa0a1aa3-3389-40aa-a983-f97f9cbbf651", "emailAddress": "CraigHugo@riotinto.com", "displayName": "Craig Hugo"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "91f19e83-3976-47ce-8fc2-c65d56349520", "emailAddress": "Gavin.Butler3@riotinto.com", "displayName": "Butler, Gavin J (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "87f38a72-0576-4261-8bb8-2f76c636b8dd", "emailAddress": "Colin.Rowe-Platts@riotinto.com", "displayName": "Rowe-Platts, Colin (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 91f19e83-3976-47ce-8fc2-c65d56349520 | Butler, Gavin J (RTIO) | Scheduled | MTP | Australia/Perth
84495 | 2026-10-16T08:27:20.0441161+00:00 | 2026-10-16T16:27:20.0441161+08:00 | {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "displayName": "Cross, Dylan (RTIO)"} | 2026-10-19T00:44:38.0342823+00:00 | 2026-10-19T08:44:38.0342823+08:00 | {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "displayName": "Cross, Dylan (RTIO)"} | {"name": "Fixed Plant"} | 336186 | TRUE | TRUE | 2026-10-19T00:44:38.0342823+00:00 | 2026-10-19T08:44:38.0342823+08:00 | #84495 - CLA: 336hrs - CONVEYOR: CLA SFP187 & RECLAIMER: CLA 01 | 1.0 | FALSE |  | 2027-01-14T16:00:00+00:00 | 2027-01-28T16:00:00+00:00 | 2027-01-15T00:00:00+08:00 | 2027-01-29T00:00:00+08:00 |  |  |  |  | 336.00 | RCL1 Slew Bearing Change Out. |  |  | [{"equipmentGUID": "3c05f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP187", "name": "Conveyor: CLA SFP187", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "emailAddress": "Dylan.Cross@riotinto.com", "displayName": "Dylan Cross"}}] | [] | [] | [] | [] | [] | Approved | Create | 8fff3db1-9fd4-4b41-ae45-d570bd95aded | Cross, Dylan (RTIO) | Scheduled | CLA | Australia/Perth
68521 | 2025-07-22T03:05:27.31554+00:00 | 2025-07-22T11:05:27.31554+08:00 | {"principalGUID": "695d1fc5-b511-459e-b9e2-ec5f66214672", "displayName": "Boskell, Ray (RTIO)"} | 2026-10-20T05:57:11.1704406+00:00 | 2026-10-20T13:57:11.1704406+08:00 | {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "displayName": "Cross, Dylan (RTIO)"} | {"name": "Fixed Plant"} | 336224 | TRUE | TRUE | 2026-10-20T05:57:11.1704406+00:00 | 2026-10-20T13:57:11.1704406+08:00 | #68521 - CLA: 174hrs - STK4 DUAL LUFF CYLINDER C/O | 4.0 | FALSE |  | 2027-04-18T16:00:00+00:00 | 2027-04-25T22:00:00+00:00 | 2027-04-19T00:00:00+08:00 | 2027-04-26T06:00:00+08:00 |  |  |  |  | 174.00 | STK4 Dual Luff Cylinder replacement - Site Major Work Planning team COMP Project | Moving to week 16 as slew bear change out on RCL1 taking priority in week 3 | SCAY2703 | [{"equipmentGUID": "3c05f0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLACVSFP187", "name": "Conveyor: CLA SFP187", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "e21df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLAST04", "name": "Stacker: CLA 04", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "a71df0bf-7c7b-ee11-a846-000d3acacefd", "code": "CLARC01", "name": "Reclaimer: CLA 01", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "3fbab50d-fe77-4934-a097-9472f7ad657e", "emailAddress": "Brian.Kimber@riotinto.com", "displayName": "Brian Kimber"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "83d85889-ca8b-420f-bf73-2882d9c306b7", "emailAddress": "Shaun.Adamson@riotinto.com", "displayName": "Shaun Adamson"}}] | [] | [] | [{"name": "Luff Cylinder Changeout"}] | [] | [] | Approved | Update | 8fff3db1-9fd4-4b41-ae45-d570bd95aded | Cross, Dylan (RTIO) | Scheduled | CLA | Australia/Perth
67449 | 2025-05-16T04:20:39.9778877+00:00 | 2025-05-16T12:20:39.9778877+08:00 | {"principalGUID": "0f0244bb-49eb-4831-b9b7-551f4ce8bc12", "displayName": "Burgess, Natasha (RTIO)"} | 2026-10-07T23:48:33.4175738+00:00 | 2026-10-08T07:48:33.4175738+08:00 | {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "displayName": "Cross, Dylan (RTIO)"} | {"name": "Fixed Plant"} | 335445 | TRUE | TRUE | 2026-10-07T23:48:33.4175738+00:00 | 2026-10-08T07:48:33.4175738+08:00 | #67449 - CLB: 5hrs - ST12 BOGIE ACOUSTICS | 2.0 | FALSE |  | 2027-01-01T23:00:00+00:00 | 2027-01-02T04:00:00+00:00 | 2027-01-02T07:00:00+08:00 | 2027-01-02T12:00:00+08:00 |  |  |  |  | 5.00 | Cmon ST12 Bogie Acoustics On - Maintenance Plan - 1692560. Flexible on date. Planned for a week after the shut for each stacker so any faults can be picked up before the next. Con Mon would prefer it Tuesday to Thursday but flexible with the weeks. | moving away from STK13 |  | [{"equipmentGUID": "a551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST12", "name": "Stacker: CLB 12", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "75bc9cce-242f-44ec-8ed3-7158f993005f", "emailAddress": "Jesse.Cunningham@riotinto.com", "displayName": "Cunningham, Jesse (RTIO)"}}, {"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "0f0244bb-49eb-4831-b9b7-551f4ce8bc12", "emailAddress": "Natasha.Burgess@riotinto.com", "displayName": "Natasha Burgess"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f57138d4-f059-400c-8e76-8e065eb0e0ec", "emailAddress": "Brad.Ross3@riotinto.com", "displayName": "Ross, Brad M (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 8fff3db1-9fd4-4b41-ae45-d570bd95aded | Cross, Dylan (RTIO) | Scheduled | CLB | Australia/Perth
39040 | 2020-12-18T04:04:34+00:00 | 2020-12-18T12:04:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000507", "displayName": "Owen Walpole"} | 2026-10-07T23:48:21.1945817+00:00 | 2026-10-08T07:48:21.1945817+08:00 | {"principalGUID": "8fff3db1-9fd4-4b41-ae45-d570bd95aded", "displayName": "Cross, Dylan (RTIO)"} | {"name": "Fixed Plant"} | 335444 | TRUE | TRUE | 2026-10-07T23:48:21.1945817+00:00 | 2026-10-08T07:48:21.1945817+08:00 | #39040 - CLB: 84hrs - STACKER: CLB 13 | 4.0 | FALSE |  | 2026-12-27T22:00:00+00:00 | 2026-12-31T10:00:00+00:00 | 2026-12-28T06:00:00+08:00 | 2026-12-31T18:00:00+08:00 |  |  |  |  | 84.00 | Standard IAM Maintenance | Moving work into Week 53 to better balance labour requirements over the Christmas period. |  | [{"equipmentGUID": "5437f6bf-7c7b-ee11-a846-000d3acacefd", "code": "CLBST13", "name": "Stacker: CLB 13", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7bf563f0-7567-4209-9a6e-fecb9e957300", "emailAddress": "David.clamp@riotinto.com", "displayName": "David Clamp"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aeb27b25-e369-45d7-aaa0-a38b45540933", "emailAddress": "Oli.McAllister@riotinto.com", "displayName": "Oli McAllister"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f4f20a82-1820-4708-87b6-43d6e0522099", "emailAddress": "Emma.Oakes@riotinto.com", "displayName": "Emma Oakes"}}] | [] | [] | [] | [] | [] | Approved | Update | 8fff3db1-9fd4-4b41-ae45-d570bd95aded | Cross, Dylan (RTIO) | Scheduled | CLB | Australia/Perth
41802 | 2021-05-26T00:54:54+00:00 | 2021-05-26T08:54:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-01-16T04:39:00.9326207+00:00 | 2026-01-16T12:39:00.9326207+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 283923 | TRUE | TRUE | 2026-01-16T04:39:00.9326207+00:00 | 2026-01-16T12:39:00.9326207+08:00 | #41802 - NBWT: 144hrs - TRAIN LOADOUT: NBWT | 11.0 | TRUE |  | 2026-12-15T22:00:00+00:00 | 2026-12-21T22:00:00+00:00 | 2026-12-16T06:00:00+08:00 | 2026-12-22T06:00:00+08:00 |  |  |  |  | 144.00 | NBWT Train Load Out | Align with Plant Shut for Time between Shutdowns |  | [{"equipmentGUID": "e7cf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTTLO", "name": "Train Loadout: NBWT", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "11466cd8-5156-40eb-b22d-024eb82aa63f", "emailAddress": "Ric.lambert@riotinto.com", "displayName": "Ric Lambert"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "18a19243-1b76-4ab3-b8a2-5a47d0dbff9d", "emailAddress": "Tristan.Raymer@riotinto.com", "displayName": "Tristan Raymer"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "60db32ae-d17c-419c-b83a-5437dee6cae8", "emailAddress": "Richard.Kerwick@riotinto.com", "displayName": "Richard Kerwick"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44573 | 2021-11-25T03:31:36+00:00 | 2021-11-25T11:31:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:24.849727+00:00 | 2026-07-07T10:50:24.849727+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329533 | TRUE | TRUE | 2026-07-07T02:50:24.849727+00:00 | 2026-07-07T10:50:24.849727+08:00 | #44573 - NBWT: 108hrs - CRUSHER - PRIMARY: SGE 02 | 7.0 | TRUE |  | 2027-11-04T11:30:00+00:00 | 2027-11-08T23:30:00+00:00 | 2027-11-04T19:30:00+08:00 | 2027-11-09T07:30:00+08:00 |  |  |  |  | 108.00 | PC02 Shut | 2027 MSF Updates | SHNM2744 | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44551 | 2021-11-25T03:31:00+00:00 | 2021-11-25T11:31:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:25.3644373+00:00 | 2026-07-07T10:50:25.3644373+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329534 | TRUE | TRUE | 2026-07-07T02:50:25.3644373+00:00 | 2026-07-07T10:50:25.3644373+08:00 | #44551 - NBWT: 108hrs - CRUSHER - PRIMARY: NBWT 01 | 7.0 | TRUE |  | 2027-10-28T11:30:00+00:00 | 2027-11-01T23:30:00+00:00 | 2027-10-28T19:30:00+08:00 | 2027-11-02T07:30:00+08:00 |  |  |  |  | 108.00 | PC01 shut | 2027 MSF Updates |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
45346 | 2021-12-13T08:25:20+00:00 | 2021-12-13T16:25:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:25.9030563+00:00 | 2026-07-07T10:50:25.9030563+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329535 | TRUE | TRUE | 2026-07-07T02:50:25.9030563+00:00 | 2026-07-07T10:50:25.9030563+08:00 | #45346 - NBWT: 108hrs - MODULE - PLANT: NBWT 01 | 7.0 | TRUE |  | 2027-10-28T11:30:00+00:00 | 2027-11-01T23:30:00+00:00 | 2027-10-28T19:30:00+08:00 | 2027-11-02T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 1 maintenance | 2027 MSF Updates |  | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
45344 | 2021-12-13T08:25:15+00:00 | 2021-12-13T16:25:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:27.5231318+00:00 | 2026-07-07T10:50:27.5231318+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329537 | TRUE | TRUE | 2026-07-07T02:50:27.5231318+00:00 | 2026-07-07T10:50:27.5231318+08:00 | #45344 - NBWT: 108hrs - MODULE - PLANT: NBWT 01 | 11.0 | TRUE |  | 2027-07-29T11:30:00+00:00 | 2027-08-02T23:30:00+00:00 | 2027-07-29T19:30:00+08:00 | 2027-08-03T07:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 1 maintenance | 2027 MSF Updates | SHNM2717 | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44506 | 2021-11-25T03:29:45+00:00 | 2021-11-25T11:29:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:29.261671+00:00 | 2026-07-07T10:50:29.261671+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329540 | TRUE | TRUE | 2026-07-07T02:50:29.261671+00:00 | 2026-07-07T10:50:29.261671+08:00 | #44506 - NBWT: 228hrs - PLANT: NBWT | 13.0 | TRUE |  | 2027-06-16T11:30:00+00:00 | 2027-06-25T23:30:00+00:00 | 2027-06-16T19:30:00+08:00 | 2027-06-26T07:30:00+08:00 |  |  |  |  | 228.00 | NBWT Plant shut - Apron Feeder Overhaul | 2027 MSF Updates - Apron Feeder Overhaul | SHNP2724 | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83133, "shutVersionId": 333409, "title": "#83133 - NBWT: 325hrs - MODULE - PLANT: NBWT 04", "startDatetimeUTC": "2027-06-16T11:30:00+00:00", "endDatetimeUTC": "2027-06-30T00:30:00+00:00"}}] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44571 | 2021-11-25T03:31:33+00:00 | 2021-11-25T11:31:33+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:29.9182883+00:00 | 2026-07-07T10:50:29.9182883+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329541 | TRUE | TRUE | 2026-07-07T02:50:29.9182883+00:00 | 2026-07-07T10:50:29.9182883+08:00 | #44571 - NBWT: 108hrs - CRUSHER - PRIMARY: SGE 02 | 10.0 | TRUE |  | 2027-05-06T11:30:00+00:00 | 2027-05-10T23:30:00+00:00 | 2027-05-06T19:30:00+08:00 | 2027-05-11T07:30:00+08:00 |  |  |  |  | 108.00 | PC02 STD Shutdown | MSF Updates 2027 |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
45387 | 2021-12-13T08:26:29+00:00 | 2021-12-13T16:26:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:30.5056183+00:00 | 2026-07-07T10:50:30.5056183+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329542 | TRUE | TRUE | 2026-07-07T02:50:30.5056183+00:00 | 2026-07-07T10:50:30.5056183+08:00 | #45387 - NBWT: 108hrs - MODULE - PLANT: NBWT 04 | 10.0 | TRUE |  | 2027-05-06T17:30:00+00:00 | 2027-05-11T05:30:00+00:00 | 2027-05-07T01:30:00+08:00 | 2027-05-11T13:30:00+08:00 |  |  |  |  | 108.00 | Standard Module 4 Shutdown | MSF Updates 2027 | SHNM2718 | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44549 | 2021-11-25T03:30:56+00:00 | 2021-11-25T11:30:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-07T02:50:31.0655946+00:00 | 2026-07-07T10:50:31.0655946+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329543 | TRUE | TRUE | 2026-07-07T02:50:31.0655946+00:00 | 2026-07-07T10:50:31.0655946+08:00 | #44549 - NBWT: 108hrs - CRUSHER - PRIMARY: NBWT 01 | 8.0 | TRUE |  | 2027-04-29T11:30:00+00:00 | 2027-05-03T23:30:00+00:00 | 2027-04-29T19:30:00+08:00 | 2027-05-04T07:30:00+08:00 |  |  |  |  | 108.00 | PC01 Shutdown - STD 108Hrs | MSF Updates 2027 |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44499 | 2021-11-25T03:29:31+00:00 | 2021-11-25T11:29:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-04T04:39:01.1761777+00:00 | 2026-06-04T12:39:01.1761777+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 327244 | TRUE | TRUE | 2026-06-04T04:39:01.1761777+00:00 | 2026-06-04T12:39:01.1761777+08:00 | #44499 - NBWT: 120hrs - PLANT: NBWT | 8.0 | TRUE |  | 2026-12-09T11:30:00+00:00 | 2026-12-14T11:30:00+00:00 | 2026-12-09T19:30:00+08:00 | 2026-12-14T19:30:00+08:00 |  |  |  |  | 120.00 | NBWT Plant shut | Update as per MSF Extensions to WK37 |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
44500 | 2021-11-25T03:29:35+00:00 | 2021-11-25T11:29:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-09T04:26:20.4227683+00:00 | 2026-07-09T12:26:20.4227683+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329746 | TRUE | TRUE | 2026-07-09T04:26:20.4227683+00:00 | 2026-07-09T12:26:20.4227683+08:00 | #44500 - NBWT: 228hrs - PLANT: NBWT | 9.0 | TRUE |  | 2027-09-16T11:30:00+00:00 | 2027-09-25T23:30:00+00:00 | 2027-09-16T19:30:00+08:00 | 2027-09-26T07:30:00+08:00 |  |  |  |  | 228.00 | NBWT Plant shut - AF2204 Overhaul / Retrofit | 2027 MSF Updates - Apron Feeder Overhaul |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83129, "shutVersionId": 333410, "title": "#83129 - NBWT: 325hrs - MODULE - PLANT: NBWT 01", "startDatetimeUTC": "2027-09-16T11:30:00+00:00", "endDatetimeUTC": "2027-09-30T00:30:00+00:00"}}] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
75409 | 2026-02-24T00:36:22.6190387+00:00 | 2026-02-24T08:36:22.6190387+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:04.5219676+00:00 | 2026-02-24T14:36:04.5219676+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288090 | TRUE | TRUE | 2026-02-24T06:36:04.5219676+00:00 | 2026-02-24T14:36:04.5219676+08:00 | #75409 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2026-12-04T01:00:00+00:00 | 2026-12-04T04:00:00+00:00 | 2026-12-04T09:00:00+08:00 | 2026-12-04T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75410 | 2026-02-24T00:36:23.0158699+00:00 | 2026-02-24T08:36:23.0158699+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:05.5013752+00:00 | 2026-02-24T14:36:05.5013752+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288091 | TRUE | TRUE | 2026-02-24T06:36:05.5013752+00:00 | 2026-02-24T14:36:05.5013752+08:00 | #75410 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2026-12-11T01:00:00+00:00 | 2026-12-11T04:00:00+00:00 | 2026-12-11T09:00:00+08:00 | 2026-12-11T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75411 | 2026-02-24T00:36:23.4128455+00:00 | 2026-02-24T08:36:23.4128455+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:06.4689868+00:00 | 2026-02-24T14:36:06.4689868+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288092 | TRUE | TRUE | 2026-02-24T06:36:06.4689868+00:00 | 2026-02-24T14:36:06.4689868+08:00 | #75411 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2026-12-18T01:00:00+00:00 | 2026-12-18T04:00:00+00:00 | 2026-12-18T09:00:00+08:00 | 2026-12-18T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75412 | 2026-02-24T00:36:23.8257699+00:00 | 2026-02-24T08:36:23.8257699+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:07.5180151+00:00 | 2026-02-24T14:36:07.5180151+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288093 | TRUE | TRUE | 2026-02-24T06:36:07.5180151+00:00 | 2026-02-24T14:36:07.5180151+08:00 | #75412 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2026-12-25T01:00:00+00:00 | 2026-12-25T04:00:00+00:00 | 2026-12-25T09:00:00+08:00 | 2026-12-25T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75413 | 2026-02-24T00:36:24.2277766+00:00 | 2026-02-24T08:36:24.2277766+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:08.4803841+00:00 | 2026-02-24T14:36:08.4803841+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288094 | TRUE | TRUE | 2026-02-24T06:36:08.4803841+00:00 | 2026-02-24T14:36:08.4803841+08:00 | #75413 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-01-01T01:00:00+00:00 | 2027-01-01T04:00:00+00:00 | 2027-01-01T09:00:00+08:00 | 2027-01-01T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75414 | 2026-02-24T00:36:24.648183+00:00 | 2026-02-24T08:36:24.648183+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:09.4890407+00:00 | 2026-02-24T14:36:09.4890407+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288095 | TRUE | TRUE | 2026-02-24T06:36:09.4890407+00:00 | 2026-02-24T14:36:09.4890407+08:00 | #75414 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-01-08T01:00:00+00:00 | 2027-01-08T04:00:00+00:00 | 2027-01-08T09:00:00+08:00 | 2027-01-08T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75415 | 2026-02-24T00:36:25.0613148+00:00 | 2026-02-24T08:36:25.0613148+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:10.4722174+00:00 | 2026-02-24T14:36:10.4722174+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288096 | TRUE | TRUE | 2026-02-24T06:36:10.4722174+00:00 | 2026-02-24T14:36:10.4722174+08:00 | #75415 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-01-15T01:00:00+00:00 | 2027-01-15T04:00:00+00:00 | 2027-01-15T09:00:00+08:00 | 2027-01-15T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75416 | 2026-02-24T00:36:25.4669692+00:00 | 2026-02-24T08:36:25.4669692+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:11.537148+00:00 | 2026-02-24T14:36:11.537148+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288097 | TRUE | TRUE | 2026-02-24T06:36:11.537148+00:00 | 2026-02-24T14:36:11.537148+08:00 | #75416 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-01-22T01:00:00+00:00 | 2027-01-22T04:00:00+00:00 | 2027-01-22T09:00:00+08:00 | 2027-01-22T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75417 | 2026-02-24T00:36:25.8778316+00:00 | 2026-02-24T08:36:25.8778316+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:12.553825+00:00 | 2026-02-24T14:36:12.553825+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288098 | TRUE | TRUE | 2026-02-24T06:36:12.553825+00:00 | 2026-02-24T14:36:12.553825+08:00 | #75417 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-01-29T01:00:00+00:00 | 2027-01-29T04:00:00+00:00 | 2027-01-29T09:00:00+08:00 | 2027-01-29T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75418 | 2026-02-24T00:36:26.2821736+00:00 | 2026-02-24T08:36:26.2821736+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:13.7683881+00:00 | 2026-02-24T14:36:13.7683881+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288099 | TRUE | TRUE | 2026-02-24T06:36:13.7683881+00:00 | 2026-02-24T14:36:13.7683881+08:00 | #75418 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-02-05T01:00:00+00:00 | 2027-02-05T04:00:00+00:00 | 2027-02-05T09:00:00+08:00 | 2027-02-05T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75419 | 2026-02-24T00:36:26.6935635+00:00 | 2026-02-24T08:36:26.6935635+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:14.8131601+00:00 | 2026-02-24T14:36:14.8131601+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288100 | TRUE | TRUE | 2026-02-24T06:36:14.8131601+00:00 | 2026-02-24T14:36:14.8131601+08:00 | #75419 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-02-12T01:00:00+00:00 | 2027-02-12T04:00:00+00:00 | 2027-02-12T09:00:00+08:00 | 2027-02-12T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75420 | 2026-02-24T00:36:27.1087447+00:00 | 2026-02-24T08:36:27.1087447+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:15.841251+00:00 | 2026-02-24T14:36:15.841251+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288101 | TRUE | TRUE | 2026-02-24T06:36:15.841251+00:00 | 2026-02-24T14:36:15.841251+08:00 | #75420 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-02-19T01:00:00+00:00 | 2027-02-19T04:00:00+00:00 | 2027-02-19T09:00:00+08:00 | 2027-02-19T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75421 | 2026-02-24T00:36:27.5192045+00:00 | 2026-02-24T08:36:27.5192045+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:16.9089028+00:00 | 2026-02-24T14:36:16.9089028+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288102 | TRUE | TRUE | 2026-02-24T06:36:16.9089028+00:00 | 2026-02-24T14:36:16.9089028+08:00 | #75421 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-02-26T01:00:00+00:00 | 2027-02-26T04:00:00+00:00 | 2027-02-26T09:00:00+08:00 | 2027-02-26T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75422 | 2026-02-24T00:36:27.9437777+00:00 | 2026-02-24T08:36:27.9437777+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:17.8935279+00:00 | 2026-02-24T14:36:17.8935279+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288103 | TRUE | TRUE | 2026-02-24T06:36:17.8935279+00:00 | 2026-02-24T14:36:17.8935279+08:00 | #75422 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-03-05T01:00:00+00:00 | 2027-03-05T04:00:00+00:00 | 2027-03-05T09:00:00+08:00 | 2027-03-05T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75423 | 2026-02-24T00:36:28.3671823+00:00 | 2026-02-24T08:36:28.3671823+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:18.910601+00:00 | 2026-02-24T14:36:18.910601+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288104 | TRUE | TRUE | 2026-02-24T06:36:18.910601+00:00 | 2026-02-24T14:36:18.910601+08:00 | #75423 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-03-12T01:00:00+00:00 | 2027-03-12T04:00:00+00:00 | 2027-03-12T09:00:00+08:00 | 2027-03-12T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75424 | 2026-02-24T00:36:28.7941735+00:00 | 2026-02-24T08:36:28.7941735+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:19.9080929+00:00 | 2026-02-24T14:36:19.9080929+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288105 | TRUE | TRUE | 2026-02-24T06:36:19.9080929+00:00 | 2026-02-24T14:36:19.9080929+08:00 | #75424 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-03-19T01:00:00+00:00 | 2027-03-19T04:00:00+00:00 | 2027-03-19T09:00:00+08:00 | 2027-03-19T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75425 | 2026-02-24T00:36:29.2150499+00:00 | 2026-02-24T08:36:29.2150499+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:20.8891754+00:00 | 2026-02-24T14:36:20.8891754+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288106 | TRUE | TRUE | 2026-02-24T06:36:20.8891754+00:00 | 2026-02-24T14:36:20.8891754+08:00 | #75425 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-03-26T01:00:00+00:00 | 2027-03-26T04:00:00+00:00 | 2027-03-26T09:00:00+08:00 | 2027-03-26T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75426 | 2026-02-24T00:36:29.6399806+00:00 | 2026-02-24T08:36:29.6399806+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:21.8843272+00:00 | 2026-02-24T14:36:21.8843272+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288107 | TRUE | TRUE | 2026-02-24T06:36:21.8843272+00:00 | 2026-02-24T14:36:21.8843272+08:00 | #75426 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-04-02T01:00:00+00:00 | 2027-04-02T04:00:00+00:00 | 2027-04-02T09:00:00+08:00 | 2027-04-02T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75427 | 2026-02-24T00:36:30.1061028+00:00 | 2026-02-24T08:36:30.1061028+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:22.9173069+00:00 | 2026-02-24T14:36:22.9173069+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288108 | TRUE | TRUE | 2026-02-24T06:36:22.9173069+00:00 | 2026-02-24T14:36:22.9173069+08:00 | #75427 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-04-09T01:00:00+00:00 | 2027-04-09T04:00:00+00:00 | 2027-04-09T09:00:00+08:00 | 2027-04-09T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75428 | 2026-02-24T00:36:30.5233297+00:00 | 2026-02-24T08:36:30.5233297+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:23.9115401+00:00 | 2026-02-24T14:36:23.9115401+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288109 | TRUE | TRUE | 2026-02-24T06:36:23.9115401+00:00 | 2026-02-24T14:36:23.9115401+08:00 | #75428 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-04-16T01:00:00+00:00 | 2027-04-16T04:00:00+00:00 | 2027-04-16T09:00:00+08:00 | 2027-04-16T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75429 | 2026-02-24T00:36:30.9847593+00:00 | 2026-02-24T08:36:30.9847593+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:24.9377478+00:00 | 2026-02-24T14:36:24.9377478+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288110 | TRUE | TRUE | 2026-02-24T06:36:24.9377478+00:00 | 2026-02-24T14:36:24.9377478+08:00 | #75429 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-04-23T01:00:00+00:00 | 2027-04-23T04:00:00+00:00 | 2027-04-23T09:00:00+08:00 | 2027-04-23T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75430 | 2026-02-24T00:36:31.4437859+00:00 | 2026-02-24T08:36:31.4437859+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:26.0465492+00:00 | 2026-02-24T14:36:26.0465492+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288111 | TRUE | TRUE | 2026-02-24T06:36:26.0465492+00:00 | 2026-02-24T14:36:26.0465492+08:00 | #75430 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-04-30T01:00:00+00:00 | 2027-04-30T04:00:00+00:00 | 2027-04-30T09:00:00+08:00 | 2027-04-30T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75431 | 2026-02-24T00:36:31.8793803+00:00 | 2026-02-24T08:36:31.8793803+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:27.2026952+00:00 | 2026-02-24T14:36:27.2026952+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288112 | TRUE | TRUE | 2026-02-24T06:36:27.2026952+00:00 | 2026-02-24T14:36:27.2026952+08:00 | #75431 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-05-07T01:00:00+00:00 | 2027-05-07T04:00:00+00:00 | 2027-05-07T09:00:00+08:00 | 2027-05-07T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75432 | 2026-02-24T00:36:32.3100964+00:00 | 2026-02-24T08:36:32.3100964+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:28.3042658+00:00 | 2026-02-24T14:36:28.3042658+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288113 | TRUE | TRUE | 2026-02-24T06:36:28.3042658+00:00 | 2026-02-24T14:36:28.3042658+08:00 | #75432 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-05-14T01:00:00+00:00 | 2027-05-14T04:00:00+00:00 | 2027-05-14T09:00:00+08:00 | 2027-05-14T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75433 | 2026-02-24T00:36:32.7615084+00:00 | 2026-02-24T08:36:32.7615084+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:29.335614+00:00 | 2026-02-24T14:36:29.335614+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288114 | TRUE | TRUE | 2026-02-24T06:36:29.335614+00:00 | 2026-02-24T14:36:29.335614+08:00 | #75433 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-05-21T01:00:00+00:00 | 2027-05-21T04:00:00+00:00 | 2027-05-21T09:00:00+08:00 | 2027-05-21T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75434 | 2026-02-24T00:36:33.2109296+00:00 | 2026-02-24T08:36:33.2109296+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:30.3786745+00:00 | 2026-02-24T14:36:30.3786745+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288115 | TRUE | TRUE | 2026-02-24T06:36:30.3786745+00:00 | 2026-02-24T14:36:30.3786745+08:00 | #75434 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-05-28T01:00:00+00:00 | 2027-05-28T04:00:00+00:00 | 2027-05-28T09:00:00+08:00 | 2027-05-28T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75435 | 2026-02-24T00:36:33.6314771+00:00 | 2026-02-24T08:36:33.6314771+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:31.4245883+00:00 | 2026-02-24T14:36:31.4245883+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288116 | TRUE | TRUE | 2026-02-24T06:36:31.4245883+00:00 | 2026-02-24T14:36:31.4245883+08:00 | #75435 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-06-04T01:00:00+00:00 | 2027-06-04T04:00:00+00:00 | 2027-06-04T09:00:00+08:00 | 2027-06-04T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75436 | 2026-02-24T00:36:34.0632432+00:00 | 2026-02-24T08:36:34.0632432+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:32.4592345+00:00 | 2026-02-24T14:36:32.4592345+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288117 | TRUE | TRUE | 2026-02-24T06:36:32.4592345+00:00 | 2026-02-24T14:36:32.4592345+08:00 | #75436 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-06-11T01:00:00+00:00 | 2027-06-11T04:00:00+00:00 | 2027-06-11T09:00:00+08:00 | 2027-06-11T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75437 | 2026-02-24T00:36:34.5132644+00:00 | 2026-02-24T08:36:34.5132644+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:33.5446637+00:00 | 2026-02-24T14:36:33.5446637+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288118 | TRUE | TRUE | 2026-02-24T06:36:33.5446637+00:00 | 2026-02-24T14:36:33.5446637+08:00 | #75437 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-06-18T01:00:00+00:00 | 2027-06-18T04:00:00+00:00 | 2027-06-18T09:00:00+08:00 | 2027-06-18T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75438 | 2026-02-24T00:36:34.9427356+00:00 | 2026-02-24T08:36:34.9427356+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:34.5636644+00:00 | 2026-02-24T14:36:34.5636644+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288119 | TRUE | TRUE | 2026-02-24T06:36:34.5636644+00:00 | 2026-02-24T14:36:34.5636644+08:00 | #75438 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-06-25T01:00:00+00:00 | 2027-06-25T04:00:00+00:00 | 2027-06-25T09:00:00+08:00 | 2027-06-25T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75439 | 2026-02-24T00:36:35.390139+00:00 | 2026-02-24T08:36:35.390139+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:35.5834284+00:00 | 2026-02-24T14:36:35.5834284+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288120 | TRUE | TRUE | 2026-02-24T06:36:35.5834284+00:00 | 2026-02-24T14:36:35.5834284+08:00 | #75439 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-07-02T01:00:00+00:00 | 2027-07-02T04:00:00+00:00 | 2027-07-02T09:00:00+08:00 | 2027-07-02T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75440 | 2026-02-24T00:36:35.8266744+00:00 | 2026-02-24T08:36:35.8266744+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:36.6146556+00:00 | 2026-02-24T14:36:36.6146556+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288121 | TRUE | TRUE | 2026-02-24T06:36:36.6146556+00:00 | 2026-02-24T14:36:36.6146556+08:00 | #75440 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-07-09T01:00:00+00:00 | 2027-07-09T04:00:00+00:00 | 2027-07-09T09:00:00+08:00 | 2027-07-09T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75441 | 2026-02-24T00:36:36.265708+00:00 | 2026-02-24T08:36:36.265708+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:37.6512914+00:00 | 2026-02-24T14:36:37.6512914+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288122 | TRUE | TRUE | 2026-02-24T06:36:37.6512914+00:00 | 2026-02-24T14:36:37.6512914+08:00 | #75441 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-07-16T01:00:00+00:00 | 2027-07-16T04:00:00+00:00 | 2027-07-16T09:00:00+08:00 | 2027-07-16T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75442 | 2026-02-24T00:36:36.7092899+00:00 | 2026-02-24T08:36:36.7092899+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:38.7005223+00:00 | 2026-02-24T14:36:38.7005223+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288123 | TRUE | TRUE | 2026-02-24T06:36:38.7005223+00:00 | 2026-02-24T14:36:38.7005223+08:00 | #75442 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-07-23T01:00:00+00:00 | 2027-07-23T04:00:00+00:00 | 2027-07-23T09:00:00+08:00 | 2027-07-23T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75443 | 2026-02-24T00:36:37.1646483+00:00 | 2026-02-24T08:36:37.1646483+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:39.7209864+00:00 | 2026-02-24T14:36:39.7209864+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288124 | TRUE | TRUE | 2026-02-24T06:36:39.7209864+00:00 | 2026-02-24T14:36:39.7209864+08:00 | #75443 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-07-30T01:00:00+00:00 | 2027-07-30T04:00:00+00:00 | 2027-07-30T09:00:00+08:00 | 2027-07-30T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75444 | 2026-02-24T00:36:37.6162905+00:00 | 2026-02-24T08:36:37.6162905+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:41.3997578+00:00 | 2026-02-24T14:36:41.3997578+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288125 | TRUE | TRUE | 2026-02-24T06:36:41.3997578+00:00 | 2026-02-24T14:36:41.3997578+08:00 | #75444 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-08-06T01:00:00+00:00 | 2027-08-06T04:00:00+00:00 | 2027-08-06T09:00:00+08:00 | 2027-08-06T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75445 | 2026-02-24T00:36:38.0542541+00:00 | 2026-02-24T08:36:38.0542541+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:42.4405822+00:00 | 2026-02-24T14:36:42.4405822+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288126 | TRUE | TRUE | 2026-02-24T06:36:42.4405822+00:00 | 2026-02-24T14:36:42.4405822+08:00 | #75445 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-08-13T01:00:00+00:00 | 2027-08-13T04:00:00+00:00 | 2027-08-13T09:00:00+08:00 | 2027-08-13T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75446 | 2026-02-24T00:36:38.5256385+00:00 | 2026-02-24T08:36:38.5256385+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:43.5084479+00:00 | 2026-02-24T14:36:43.5084479+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288127 | TRUE | TRUE | 2026-02-24T06:36:43.5084479+00:00 | 2026-02-24T14:36:43.5084479+08:00 | #75446 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-08-20T01:00:00+00:00 | 2027-08-20T04:00:00+00:00 | 2027-08-20T09:00:00+08:00 | 2027-08-20T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75447 | 2026-02-24T00:36:38.965564+00:00 | 2026-02-24T08:36:38.965564+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:44.6061444+00:00 | 2026-02-24T14:36:44.6061444+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288128 | TRUE | TRUE | 2026-02-24T06:36:44.6061444+00:00 | 2026-02-24T14:36:44.6061444+08:00 | #75447 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-08-27T01:00:00+00:00 | 2027-08-27T04:00:00+00:00 | 2027-08-27T09:00:00+08:00 | 2027-08-27T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75448 | 2026-02-24T00:36:39.4111771+00:00 | 2026-02-24T08:36:39.4111771+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:45.6630615+00:00 | 2026-02-24T14:36:45.6630615+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288129 | TRUE | TRUE | 2026-02-24T06:36:45.6630615+00:00 | 2026-02-24T14:36:45.6630615+08:00 | #75448 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-09-03T01:00:00+00:00 | 2027-09-03T04:00:00+00:00 | 2027-09-03T09:00:00+08:00 | 2027-09-03T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75449 | 2026-02-24T00:36:39.8450773+00:00 | 2026-02-24T08:36:39.8450773+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:46.720427+00:00 | 2026-02-24T14:36:46.720427+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288130 | TRUE | TRUE | 2026-02-24T06:36:46.720427+00:00 | 2026-02-24T14:36:46.720427+08:00 | #75449 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-09-10T01:00:00+00:00 | 2027-09-10T04:00:00+00:00 | 2027-09-10T09:00:00+08:00 | 2027-09-10T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75450 | 2026-02-24T00:36:40.2915321+00:00 | 2026-02-24T08:36:40.2915321+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:47.7713366+00:00 | 2026-02-24T14:36:47.7713366+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288131 | TRUE | TRUE | 2026-02-24T06:36:47.7713366+00:00 | 2026-02-24T14:36:47.7713366+08:00 | #75450 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-09-17T01:00:00+00:00 | 2027-09-17T04:00:00+00:00 | 2027-09-17T09:00:00+08:00 | 2027-09-17T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75451 | 2026-02-24T00:36:40.7290034+00:00 | 2026-02-24T08:36:40.7290034+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:48.845601+00:00 | 2026-02-24T14:36:48.845601+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288132 | TRUE | TRUE | 2026-02-24T06:36:48.845601+00:00 | 2026-02-24T14:36:48.845601+08:00 | #75451 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-09-24T01:00:00+00:00 | 2027-09-24T04:00:00+00:00 | 2027-09-24T09:00:00+08:00 | 2027-09-24T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75452 | 2026-02-24T00:36:41.1681593+00:00 | 2026-02-24T08:36:41.1681593+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:49.9099713+00:00 | 2026-02-24T14:36:49.9099713+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288133 | TRUE | TRUE | 2026-02-24T06:36:49.9099713+00:00 | 2026-02-24T14:36:49.9099713+08:00 | #75452 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-10-01T01:00:00+00:00 | 2027-10-01T04:00:00+00:00 | 2027-10-01T09:00:00+08:00 | 2027-10-01T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75453 | 2026-02-24T00:36:41.6102709+00:00 | 2026-02-24T08:36:41.6102709+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:51.0242462+00:00 | 2026-02-24T14:36:51.0242462+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288134 | TRUE | TRUE | 2026-02-24T06:36:51.0242462+00:00 | 2026-02-24T14:36:51.0242462+08:00 | #75453 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-10-08T01:00:00+00:00 | 2027-10-08T04:00:00+00:00 | 2027-10-08T09:00:00+08:00 | 2027-10-08T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75454 | 2026-02-24T00:36:42.0803442+00:00 | 2026-02-24T08:36:42.0803442+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:36:52.0867597+00:00 | 2026-02-24T14:36:52.0867597+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288135 | TRUE | TRUE | 2026-02-24T06:36:52.0867597+00:00 | 2026-02-24T14:36:52.0867597+08:00 | #75454 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-10-15T01:00:00+00:00 | 2027-10-15T04:00:00+00:00 | 2027-10-15T09:00:00+08:00 | 2027-10-15T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75455 | 2026-02-24T00:36:42.5384748+00:00 | 2026-02-24T08:36:42.5384748+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:50.0489849+00:00 | 2026-02-24T14:37:50.0489849+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288136 | TRUE | TRUE | 2026-02-24T06:37:50.0489849+00:00 | 2026-02-24T14:37:50.0489849+08:00 | #75455 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-10-22T01:00:00+00:00 | 2027-10-22T04:00:00+00:00 | 2027-10-22T09:00:00+08:00 | 2027-10-22T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75456 | 2026-02-24T00:36:43.0836615+00:00 | 2026-02-24T08:36:43.0836615+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:51.065146+00:00 | 2026-02-24T14:37:51.065146+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288137 | TRUE | TRUE | 2026-02-24T06:37:51.065146+00:00 | 2026-02-24T14:37:51.065146+08:00 | #75456 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-10-29T01:00:00+00:00 | 2027-10-29T04:00:00+00:00 | 2027-10-29T09:00:00+08:00 | 2027-10-29T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75457 | 2026-02-24T00:36:43.5387234+00:00 | 2026-02-24T08:36:43.5387234+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:52.0424129+00:00 | 2026-02-24T14:37:52.0424129+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288138 | TRUE | TRUE | 2026-02-24T06:37:52.0424129+00:00 | 2026-02-24T14:37:52.0424129+08:00 | #75457 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-11-05T01:00:00+00:00 | 2027-11-05T04:00:00+00:00 | 2027-11-05T09:00:00+08:00 | 2027-11-05T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75458 | 2026-02-24T00:36:43.9861178+00:00 | 2026-02-24T08:36:43.9861178+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:53.0233075+00:00 | 2026-02-24T14:37:53.0233075+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288139 | TRUE | TRUE | 2026-02-24T06:37:53.0233075+00:00 | 2026-02-24T14:37:53.0233075+08:00 | #75458 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-11-12T01:00:00+00:00 | 2027-11-12T04:00:00+00:00 | 2027-11-12T09:00:00+08:00 | 2027-11-12T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
83133 | 2026-06-30T22:50:35.467002+00:00 | 2026-07-01T06:50:35.467002+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-09-15T06:12:04.3071214+00:00 | 2026-09-15T14:12:04.3071214+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 333409 | TRUE | TRUE | 2026-09-15T06:12:04.3071214+00:00 | 2026-09-15T14:12:04.3071214+08:00 | #83133 - NBWT: 325hrs - MODULE - PLANT: NBWT 04 | 2.0 | TRUE |  | 2027-06-16T11:30:00+00:00 | 2027-06-30T00:30:00+00:00 | 2027-06-16T19:30:00+08:00 | 2027-06-30T08:30:00+08:00 |  |  |  |  | 325.00 | MOD 4 Shutdown - Filter Belt C/O | Filter Belt C/O Change Module 4 to be completed first in 2027 as per RE Recommendations No Change in SOP or Hours Required | SHNP2737 | [{"equipmentGUID": "1914b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD04", "name": "Module - Plant: NBWT 04", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44506, "shutVersionId": 329540, "title": "#44506 - NBWT: 228hrs - PLANT: NBWT", "startDatetimeUTC": "2027-06-16T11:30:00+00:00", "endDatetimeUTC": "2027-06-25T23:30:00+00:00"}}] | [{"name": "Belt Filter Changeout"}] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83129 | 2026-06-30T22:41:19.5046189+00:00 | 2026-07-01T06:41:19.5046189+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-09-15T06:12:04.470297+00:00 | 2026-09-15T14:12:04.470297+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 333410 | TRUE | TRUE | 2026-09-15T06:12:04.470297+00:00 | 2026-09-15T14:12:04.470297+08:00 | #83129 - NBWT: 325hrs - MODULE - PLANT: NBWT 01 | 2.0 | TRUE |  | 2027-09-16T11:30:00+00:00 | 2027-09-30T00:30:00+00:00 | 2027-09-16T19:30:00+08:00 | 2027-09-30T08:30:00+08:00 |  |  |  |  | 325.00 | MOD 1 Shutdown - Filter Belt C/O | Filter Belt C/O Change Module 4 to be completed first in 2027 as per RE Recommendations No Change in SOP or Hours Required | SHNP2724 | [{"equipmentGUID": "1614b296-1f82-ef11-a853-000d3acacefd", "code": "NBWTPLTMOD01", "name": "Module - Plant: NBWT 01", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44500, "shutVersionId": 329746, "title": "#44500 - NBWT: 228hrs - PLANT: NBWT", "startDatetimeUTC": "2027-09-16T11:30:00+00:00", "endDatetimeUTC": "2027-09-25T23:30:00+00:00"}}] | [{"name": "Belt Filter Changeout"}] | [] | [] | Approved | Update | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
70703 | 2025-10-16T01:32:28.3025971+00:00 | 2025-10-16T09:32:28.3025971+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2025-10-22T02:33:03.1600848+00:00 | 2025-10-22T10:33:03.1600848+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 262410 | TRUE | TRUE | 2025-10-22T02:33:03.1600848+00:00 | 2025-10-22T10:33:03.1600848+08:00 | #70703 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2026-12-21T00:00:00+00:00 | 2026-12-21T03:00:00+00:00 | 2026-12-21T08:00:00+08:00 | 2026-12-21T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
70702 | 2025-10-16T01:32:27.9252674+00:00 | 2025-10-16T09:32:27.9252674+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2025-10-22T02:33:03.7829659+00:00 | 2025-10-22T10:33:03.7829659+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 262411 | TRUE | TRUE | 2025-10-22T02:33:03.7829659+00:00 | 2025-10-22T10:33:03.7829659+08:00 | #70702 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2026-12-07T00:00:00+00:00 | 2026-12-07T03:00:00+00:00 | 2026-12-07T08:00:00+08:00 | 2026-12-07T11:00:00+08:00 |  |  |  |  | 3.00 | CV2122 Brake Pad Replacement |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83253 | 2026-07-01T00:34:08.9270248+00:00 | 2026-07-01T08:34:08.9270248+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:46.7674921+00:00 | 2026-07-07T10:49:46.7674921+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329423 | TRUE | TRUE | 2026-07-07T02:49:46.7674921+00:00 | 2026-07-07T10:49:46.7674921+08:00 | #83253 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-31T02:30:00+00:00 | 2027-12-31T05:30:00+00:00 | 2027-12-31T10:30:00+08:00 | 2027-12-31T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83252 | 2026-07-01T00:34:08.7631475+00:00 | 2026-07-01T08:34:08.7631475+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:46.9446259+00:00 | 2026-07-07T10:49:46.9446259+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329424 | TRUE | TRUE | 2026-07-07T02:49:46.9446259+00:00 | 2026-07-07T10:49:46.9446259+08:00 | #83252 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-24T02:30:00+00:00 | 2027-12-24T05:30:00+00:00 | 2027-12-24T10:30:00+08:00 | 2027-12-24T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83251 | 2026-07-01T00:34:08.5891809+00:00 | 2026-07-01T08:34:08.5891809+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:47.1133365+00:00 | 2026-07-07T10:49:47.1133365+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329425 | TRUE | TRUE | 2026-07-07T02:49:47.1133365+00:00 | 2026-07-07T10:49:47.1133365+08:00 | #83251 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-17T02:30:00+00:00 | 2027-12-17T05:30:00+00:00 | 2027-12-17T10:30:00+08:00 | 2027-12-17T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83250 | 2026-07-01T00:34:08.433957+00:00 | 2026-07-01T08:34:08.433957+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:47.2786266+00:00 | 2026-07-07T10:49:47.2786266+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329426 | TRUE | TRUE | 2026-07-07T02:49:47.2786266+00:00 | 2026-07-07T10:49:47.2786266+08:00 | #83250 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-10T02:30:00+00:00 | 2027-12-10T05:30:00+00:00 | 2027-12-10T10:30:00+08:00 | 2027-12-10T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83249 | 2026-07-01T00:34:08.2700332+00:00 | 2026-07-01T08:34:08.2700332+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:47.471891+00:00 | 2026-07-07T10:49:47.471891+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329427 | TRUE | TRUE | 2026-07-07T02:49:47.471891+00:00 | 2026-07-07T10:49:47.471891+08:00 | #83249 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-12-03T02:30:00+00:00 | 2027-12-03T05:30:00+00:00 | 2027-12-03T10:30:00+08:00 | 2027-12-03T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83248 | 2026-07-01T00:34:08.111345+00:00 | 2026-07-01T08:34:08.111345+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:47.674077+00:00 | 2026-07-07T10:49:47.674077+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329428 | TRUE | TRUE | 2026-07-07T02:49:47.674077+00:00 | 2026-07-07T10:49:47.674077+08:00 | #83248 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-26T02:30:00+00:00 | 2027-11-26T05:30:00+00:00 | 2027-11-26T10:30:00+08:00 | 2027-11-26T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83235 | 2026-07-01T00:34:05.7829032+00:00 | 2026-07-01T08:34:05.7829032+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:50.8073618+00:00 | 2026-07-07T10:49:50.8073618+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329441 | TRUE | TRUE | 2026-07-07T02:49:50.8073618+00:00 | 2026-07-07T10:49:50.8073618+08:00 | #83235 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-27T02:30:00+00:00 | 2027-08-27T05:30:00+00:00 | 2027-08-27T10:30:00+08:00 | 2027-08-27T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83234 | 2026-07-01T00:34:05.6300886+00:00 | 2026-07-01T08:34:05.6300886+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:51.0563625+00:00 | 2026-07-07T10:49:51.0563625+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329442 | TRUE | TRUE | 2026-07-07T02:49:51.0563625+00:00 | 2026-07-07T10:49:51.0563625+08:00 | #83234 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-20T02:30:00+00:00 | 2027-08-20T05:30:00+00:00 | 2027-08-20T10:30:00+08:00 | 2027-08-20T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83233 | 2026-07-01T00:34:05.4742183+00:00 | 2026-07-01T08:34:05.4742183+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:51.3081175+00:00 | 2026-07-07T10:49:51.3081175+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329443 | TRUE | TRUE | 2026-07-07T02:49:51.3081175+00:00 | 2026-07-07T10:49:51.3081175+08:00 | #83233 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-13T02:30:00+00:00 | 2027-08-13T05:30:00+00:00 | 2027-08-13T10:30:00+08:00 | 2027-08-13T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83232 | 2026-07-01T00:34:05.2909188+00:00 | 2026-07-01T08:34:05.2909188+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:51.5886057+00:00 | 2026-07-07T10:49:51.5886057+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329444 | TRUE | TRUE | 2026-07-07T02:49:51.5886057+00:00 | 2026-07-07T10:49:51.5886057+08:00 | #83232 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-08-06T02:30:00+00:00 | 2027-08-06T05:30:00+00:00 | 2027-08-06T10:30:00+08:00 | 2027-08-06T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83231 | 2026-07-01T00:34:05.1513402+00:00 | 2026-07-01T08:34:05.1513402+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:51.8592215+00:00 | 2026-07-07T10:49:51.8592215+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329445 | TRUE | TRUE | 2026-07-07T02:49:51.8592215+00:00 | 2026-07-07T10:49:51.8592215+08:00 | #83231 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-30T02:30:00+00:00 | 2027-07-30T05:30:00+00:00 | 2027-07-30T10:30:00+08:00 | 2027-07-30T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83230 | 2026-07-01T00:34:05.0170947+00:00 | 2026-07-01T08:34:05.0170947+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:52.1224467+00:00 | 2026-07-07T10:49:52.1224467+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329446 | TRUE | TRUE | 2026-07-07T02:49:52.1224467+00:00 | 2026-07-07T10:49:52.1224467+08:00 | #83230 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-23T02:30:00+00:00 | 2027-07-23T05:30:00+00:00 | 2027-07-23T10:30:00+08:00 | 2027-07-23T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83229 | 2026-07-01T00:34:04.8827588+00:00 | 2026-07-01T08:34:04.8827588+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:52.3830038+00:00 | 2026-07-07T10:49:52.3830038+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329447 | TRUE | TRUE | 2026-07-07T02:49:52.3830038+00:00 | 2026-07-07T10:49:52.3830038+08:00 | #83229 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-16T02:30:00+00:00 | 2027-07-16T05:30:00+00:00 | 2027-07-16T10:30:00+08:00 | 2027-07-16T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83228 | 2026-07-01T00:34:04.721382+00:00 | 2026-07-01T08:34:04.721382+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:52.6313809+00:00 | 2026-07-07T10:49:52.6313809+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329448 | TRUE | TRUE | 2026-07-07T02:49:52.6313809+00:00 | 2026-07-07T10:49:52.6313809+08:00 | #83228 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-09T02:30:00+00:00 | 2027-07-09T05:30:00+00:00 | 2027-07-09T10:30:00+08:00 | 2027-07-09T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83227 | 2026-07-01T00:34:04.5923678+00:00 | 2026-07-01T08:34:04.5923678+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:52.8998514+00:00 | 2026-07-07T10:49:52.8998514+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329449 | TRUE | TRUE | 2026-07-07T02:49:52.8998514+00:00 | 2026-07-07T10:49:52.8998514+08:00 | #83227 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-07-02T02:30:00+00:00 | 2027-07-02T05:30:00+00:00 | 2027-07-02T10:30:00+08:00 | 2027-07-02T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83226 | 2026-07-01T00:34:04.4568206+00:00 | 2026-07-01T08:34:04.4568206+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:53.1882436+00:00 | 2026-07-07T10:49:53.1882436+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329450 | TRUE | TRUE | 2026-07-07T02:49:53.1882436+00:00 | 2026-07-07T10:49:53.1882436+08:00 | #83226 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-25T02:30:00+00:00 | 2027-06-25T05:30:00+00:00 | 2027-06-25T10:30:00+08:00 | 2027-06-25T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83225 | 2026-07-01T00:34:04.312181+00:00 | 2026-07-01T08:34:04.312181+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:53.4485993+00:00 | 2026-07-07T10:49:53.4485993+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329451 | TRUE | TRUE | 2026-07-07T02:49:53.4485993+00:00 | 2026-07-07T10:49:53.4485993+08:00 | #83225 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-18T02:30:00+00:00 | 2027-06-18T05:30:00+00:00 | 2027-06-18T10:30:00+08:00 | 2027-06-18T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83224 | 2026-07-01T00:34:04.1755454+00:00 | 2026-07-01T08:34:04.1755454+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:53.7354357+00:00 | 2026-07-07T10:49:53.7354357+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329452 | TRUE | TRUE | 2026-07-07T02:49:53.7354357+00:00 | 2026-07-07T10:49:53.7354357+08:00 | #83224 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-11T02:30:00+00:00 | 2027-06-11T05:30:00+00:00 | 2027-06-11T10:30:00+08:00 | 2027-06-11T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83223 | 2026-07-01T00:34:04.0355726+00:00 | 2026-07-01T08:34:04.0355726+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:54.0102375+00:00 | 2026-07-07T10:49:54.0102375+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329453 | TRUE | TRUE | 2026-07-07T02:49:54.0102375+00:00 | 2026-07-07T10:49:54.0102375+08:00 | #83223 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-06-04T02:30:00+00:00 | 2027-06-04T05:30:00+00:00 | 2027-06-04T10:30:00+08:00 | 2027-06-04T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83222 | 2026-07-01T00:34:03.9048567+00:00 | 2026-07-01T08:34:03.9048567+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:54.2960949+00:00 | 2026-07-07T10:49:54.2960949+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329454 | TRUE | TRUE | 2026-07-07T02:49:54.2960949+00:00 | 2026-07-07T10:49:54.2960949+08:00 | #83222 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-28T02:30:00+00:00 | 2027-05-28T05:30:00+00:00 | 2027-05-28T10:30:00+08:00 | 2027-05-28T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83221 | 2026-07-01T00:34:03.7612625+00:00 | 2026-07-01T08:34:03.7612625+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:54.5930645+00:00 | 2026-07-07T10:49:54.5930645+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329455 | TRUE | TRUE | 2026-07-07T02:49:54.5930645+00:00 | 2026-07-07T10:49:54.5930645+08:00 | #83221 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-21T02:30:00+00:00 | 2027-05-21T05:30:00+00:00 | 2027-05-21T10:30:00+08:00 | 2027-05-21T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83220 | 2026-07-01T00:34:03.6271317+00:00 | 2026-07-01T08:34:03.6271317+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:54.9128749+00:00 | 2026-07-07T10:49:54.9128749+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329456 | TRUE | TRUE | 2026-07-07T02:49:54.9128749+00:00 | 2026-07-07T10:49:54.9128749+08:00 | #83220 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-14T02:30:00+00:00 | 2027-05-14T05:30:00+00:00 | 2027-05-14T10:30:00+08:00 | 2027-05-14T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83219 | 2026-07-01T00:34:03.5028109+00:00 | 2026-07-01T08:34:03.5028109+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:55.243055+00:00 | 2026-07-07T10:49:55.243055+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329457 | TRUE | TRUE | 2026-07-07T02:49:55.243055+00:00 | 2026-07-07T10:49:55.243055+08:00 | #83219 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-05-07T02:30:00+00:00 | 2027-05-07T05:30:00+00:00 | 2027-05-07T10:30:00+08:00 | 2027-05-07T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83218 | 2026-07-01T00:34:03.3650597+00:00 | 2026-07-01T08:34:03.3650597+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:55.563873+00:00 | 2026-07-07T10:49:55.563873+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329458 | TRUE | TRUE | 2026-07-07T02:49:55.563873+00:00 | 2026-07-07T10:49:55.563873+08:00 | #83218 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-30T02:30:00+00:00 | 2027-04-30T05:30:00+00:00 | 2027-04-30T10:30:00+08:00 | 2027-04-30T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83217 | 2026-07-01T00:34:03.2486019+00:00 | 2026-07-01T08:34:03.2486019+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:55.8854739+00:00 | 2026-07-07T10:49:55.8854739+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329459 | TRUE | TRUE | 2026-07-07T02:49:55.8854739+00:00 | 2026-07-07T10:49:55.8854739+08:00 | #83217 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-23T02:30:00+00:00 | 2027-04-23T05:30:00+00:00 | 2027-04-23T10:30:00+08:00 | 2027-04-23T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83216 | 2026-07-01T00:34:03.1302548+00:00 | 2026-07-01T08:34:03.1302548+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:56.174107+00:00 | 2026-07-07T10:49:56.174107+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329460 | TRUE | TRUE | 2026-07-07T02:49:56.174107+00:00 | 2026-07-07T10:49:56.174107+08:00 | #83216 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-16T02:30:00+00:00 | 2027-04-16T05:30:00+00:00 | 2027-04-16T10:30:00+08:00 | 2027-04-16T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83215 | 2026-07-01T00:34:02.9862608+00:00 | 2026-07-01T08:34:02.9862608+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:56.4635618+00:00 | 2026-07-07T10:49:56.4635618+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329461 | TRUE | TRUE | 2026-07-07T02:49:56.4635618+00:00 | 2026-07-07T10:49:56.4635618+08:00 | #83215 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-09T02:30:00+00:00 | 2027-04-09T05:30:00+00:00 | 2027-04-09T10:30:00+08:00 | 2027-04-09T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83214 | 2026-07-01T00:34:02.8611822+00:00 | 2026-07-01T08:34:02.8611822+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:56.7834421+00:00 | 2026-07-07T10:49:56.7834421+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329462 | TRUE | TRUE | 2026-07-07T02:49:56.7834421+00:00 | 2026-07-07T10:49:56.7834421+08:00 | #83214 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-04-02T02:30:00+00:00 | 2027-04-02T05:30:00+00:00 | 2027-04-02T10:30:00+08:00 | 2027-04-02T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83213 | 2026-07-01T00:34:02.7273285+00:00 | 2026-07-01T08:34:02.7273285+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:57.129444+00:00 | 2026-07-07T10:49:57.129444+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329463 | TRUE | TRUE | 2026-07-07T02:49:57.129444+00:00 | 2026-07-07T10:49:57.129444+08:00 | #83213 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-26T02:30:00+00:00 | 2027-03-26T05:30:00+00:00 | 2027-03-26T10:30:00+08:00 | 2027-03-26T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83212 | 2026-07-01T00:34:02.588668+00:00 | 2026-07-01T08:34:02.588668+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:57.4517096+00:00 | 2026-07-07T10:49:57.4517096+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329464 | TRUE | TRUE | 2026-07-07T02:49:57.4517096+00:00 | 2026-07-07T10:49:57.4517096+08:00 | #83212 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-19T02:30:00+00:00 | 2027-03-19T05:30:00+00:00 | 2027-03-19T10:30:00+08:00 | 2027-03-19T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83211 | 2026-07-01T00:34:02.4651918+00:00 | 2026-07-01T08:34:02.4651918+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:57.7789791+00:00 | 2026-07-07T10:49:57.7789791+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329465 | TRUE | TRUE | 2026-07-07T02:49:57.7789791+00:00 | 2026-07-07T10:49:57.7789791+08:00 | #83211 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-12T02:30:00+00:00 | 2027-03-12T05:30:00+00:00 | 2027-03-12T10:30:00+08:00 | 2027-03-12T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83210 | 2026-07-01T00:34:02.336595+00:00 | 2026-07-01T08:34:02.336595+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:58.1099463+00:00 | 2026-07-07T10:49:58.1099463+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329466 | TRUE | TRUE | 2026-07-07T02:49:58.1099463+00:00 | 2026-07-07T10:49:58.1099463+08:00 | #83210 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-03-05T02:30:00+00:00 | 2027-03-05T05:30:00+00:00 | 2027-03-05T10:30:00+08:00 | 2027-03-05T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83209 | 2026-07-01T00:34:02.2248203+00:00 | 2026-07-01T08:34:02.2248203+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:58.4393755+00:00 | 2026-07-07T10:49:58.4393755+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329467 | TRUE | TRUE | 2026-07-07T02:49:58.4393755+00:00 | 2026-07-07T10:49:58.4393755+08:00 | #83209 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-26T02:30:00+00:00 | 2027-02-26T05:30:00+00:00 | 2027-02-26T10:30:00+08:00 | 2027-02-26T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83208 | 2026-07-01T00:34:02.1109441+00:00 | 2026-07-01T08:34:02.1109441+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:58.7787055+00:00 | 2026-07-07T10:49:58.7787055+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329468 | TRUE | TRUE | 2026-07-07T02:49:58.7787055+00:00 | 2026-07-07T10:49:58.7787055+08:00 | #83208 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-19T02:30:00+00:00 | 2027-02-19T05:30:00+00:00 | 2027-02-19T10:30:00+08:00 | 2027-02-19T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83207 | 2026-07-01T00:34:01.9905085+00:00 | 2026-07-01T08:34:01.9905085+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:59.1080229+00:00 | 2026-07-07T10:49:59.1080229+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329469 | TRUE | TRUE | 2026-07-07T02:49:59.1080229+00:00 | 2026-07-07T10:49:59.1080229+08:00 | #83207 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-12T02:30:00+00:00 | 2027-02-12T05:30:00+00:00 | 2027-02-12T10:30:00+08:00 | 2027-02-12T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83206 | 2026-07-01T00:34:01.8686519+00:00 | 2026-07-01T08:34:01.8686519+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:59.47962+00:00 | 2026-07-07T10:49:59.47962+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329470 | TRUE | TRUE | 2026-07-07T02:49:59.47962+00:00 | 2026-07-07T10:49:59.47962+08:00 | #83206 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-02-05T02:30:00+00:00 | 2027-02-05T05:30:00+00:00 | 2027-02-05T10:30:00+08:00 | 2027-02-05T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83205 | 2026-07-01T00:34:01.7612778+00:00 | 2026-07-01T08:34:01.7612778+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:59.8299725+00:00 | 2026-07-07T10:49:59.8299725+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329471 | TRUE | TRUE | 2026-07-07T02:49:59.8299725+00:00 | 2026-07-07T10:49:59.8299725+08:00 | #83205 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-29T02:30:00+00:00 | 2027-01-29T05:30:00+00:00 | 2027-01-29T10:30:00+08:00 | 2027-01-29T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83204 | 2026-07-01T00:34:01.6467931+00:00 | 2026-07-01T08:34:01.6467931+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:00.4308406+00:00 | 2026-07-07T10:50:00.4308406+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329472 | TRUE | TRUE | 2026-07-07T02:50:00.4308406+00:00 | 2026-07-07T10:50:00.4308406+08:00 | #83204 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-22T02:30:00+00:00 | 2027-01-22T05:30:00+00:00 | 2027-01-22T10:30:00+08:00 | 2027-01-22T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83203 | 2026-07-01T00:34:01.5162805+00:00 | 2026-07-01T08:34:01.5162805+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:00.8973724+00:00 | 2026-07-07T10:50:00.8973724+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329473 | TRUE | TRUE | 2026-07-07T02:50:00.8973724+00:00 | 2026-07-07T10:50:00.8973724+08:00 | #83203 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-15T02:30:00+00:00 | 2027-01-15T05:30:00+00:00 | 2027-01-15T10:30:00+08:00 | 2027-01-15T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83202 | 2026-07-01T00:34:01.4052499+00:00 | 2026-07-01T08:34:01.4052499+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:01.3257301+00:00 | 2026-07-07T10:50:01.3257301+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329474 | TRUE | TRUE | 2026-07-07T02:50:01.3257301+00:00 | 2026-07-07T10:50:01.3257301+08:00 | #83202 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-08T02:30:00+00:00 | 2027-01-08T05:30:00+00:00 | 2027-01-08T10:30:00+08:00 | 2027-01-08T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83201 | 2026-07-01T00:34:00.9777955+00:00 | 2026-07-01T08:34:00.9777955+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:01.7710678+00:00 | 2026-07-07T10:50:01.7710678+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329475 | TRUE | TRUE | 2026-07-07T02:50:01.7710678+00:00 | 2026-07-07T10:50:01.7710678+08:00 | #83201 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-01-01T02:30:00+00:00 | 2027-01-01T05:30:00+00:00 | 2027-01-01T10:30:00+08:00 | 2027-01-01T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83200 | 2026-07-01T00:31:49.86498+00:00 | 2026-07-01T08:31:49.86498+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:02.1218897+00:00 | 2026-07-07T10:50:02.1218897+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329476 | TRUE | TRUE | 2026-07-07T02:50:02.1218897+00:00 | 2026-07-07T10:50:02.1218897+08:00 | #83200 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-12-30T23:30:00+00:00 | 2027-12-31T02:30:00+00:00 | 2027-12-31T07:30:00+08:00 | 2027-12-31T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83199 | 2026-07-01T00:31:49.6997502+00:00 | 2026-07-01T08:31:49.6997502+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:02.4625947+00:00 | 2026-07-07T10:50:02.4625947+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329477 | TRUE | TRUE | 2026-07-07T02:50:02.4625947+00:00 | 2026-07-07T10:50:02.4625947+08:00 | #83199 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-12-23T23:30:00+00:00 | 2027-12-24T02:30:00+00:00 | 2027-12-24T07:30:00+08:00 | 2027-12-24T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83198 | 2026-07-01T00:31:49.407563+00:00 | 2026-07-01T08:31:49.407563+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:02.818473+00:00 | 2026-07-07T10:50:02.818473+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329478 | TRUE | TRUE | 2026-07-07T02:50:02.818473+00:00 | 2026-07-07T10:50:02.818473+08:00 | #83198 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-12-16T23:30:00+00:00 | 2027-12-17T02:30:00+00:00 | 2027-12-17T07:30:00+08:00 | 2027-12-17T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83197 | 2026-07-01T00:31:49.2162984+00:00 | 2026-07-01T08:31:49.2162984+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:03.1452836+00:00 | 2026-07-07T10:50:03.1452836+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329479 | TRUE | TRUE | 2026-07-07T02:50:03.1452836+00:00 | 2026-07-07T10:50:03.1452836+08:00 | #83197 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-12-09T23:30:00+00:00 | 2027-12-10T02:30:00+00:00 | 2027-12-10T07:30:00+08:00 | 2027-12-10T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83196 | 2026-07-01T00:31:49.039232+00:00 | 2026-07-01T08:31:49.039232+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:03.4783645+00:00 | 2026-07-07T10:50:03.4783645+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329480 | TRUE | TRUE | 2026-07-07T02:50:03.4783645+00:00 | 2026-07-07T10:50:03.4783645+08:00 | #83196 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-12-02T23:30:00+00:00 | 2027-12-03T02:30:00+00:00 | 2027-12-03T07:30:00+08:00 | 2027-12-03T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83195 | 2026-07-01T00:31:48.8679115+00:00 | 2026-07-01T08:31:48.8679115+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:03.838189+00:00 | 2026-07-07T10:50:03.838189+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329481 | TRUE | TRUE | 2026-07-07T02:50:03.838189+00:00 | 2026-07-07T10:50:03.838189+08:00 | #83195 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-11-25T23:30:00+00:00 | 2027-11-26T02:30:00+00:00 | 2027-11-26T07:30:00+08:00 | 2027-11-26T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83194 | 2026-07-01T00:31:48.7019671+00:00 | 2026-07-01T08:31:48.7019671+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:04.1961472+00:00 | 2026-07-07T10:50:04.1961472+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329482 | TRUE | TRUE | 2026-07-07T02:50:04.1961472+00:00 | 2026-07-07T10:50:04.1961472+08:00 | #83194 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-11-18T23:30:00+00:00 | 2027-11-19T02:30:00+00:00 | 2027-11-19T07:30:00+08:00 | 2027-11-19T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83193 | 2026-07-01T00:31:48.5434637+00:00 | 2026-07-01T08:31:48.5434637+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:04.5323156+00:00 | 2026-07-07T10:50:04.5323156+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329483 | TRUE | TRUE | 2026-07-07T02:50:04.5323156+00:00 | 2026-07-07T10:50:04.5323156+08:00 | #83193 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-11-11T23:30:00+00:00 | 2027-11-12T02:30:00+00:00 | 2027-11-12T07:30:00+08:00 | 2027-11-12T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83192 | 2026-07-01T00:31:48.3809136+00:00 | 2026-07-01T08:31:48.3809136+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:04.9014125+00:00 | 2026-07-07T10:50:04.9014125+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329484 | TRUE | TRUE | 2026-07-07T02:50:04.9014125+00:00 | 2026-07-07T10:50:04.9014125+08:00 | #83192 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-11-04T23:30:00+00:00 | 2027-11-05T02:30:00+00:00 | 2027-11-05T07:30:00+08:00 | 2027-11-05T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83191 | 2026-07-01T00:31:48.2163675+00:00 | 2026-07-01T08:31:48.2163675+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:05.271709+00:00 | 2026-07-07T10:50:05.271709+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329485 | TRUE | TRUE | 2026-07-07T02:50:05.271709+00:00 | 2026-07-07T10:50:05.271709+08:00 | #83191 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-10-28T23:30:00+00:00 | 2027-10-29T02:30:00+00:00 | 2027-10-29T07:30:00+08:00 | 2027-10-29T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83190 | 2026-07-01T00:31:48.0606264+00:00 | 2026-07-01T08:31:48.0606264+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:05.6151014+00:00 | 2026-07-07T10:50:05.6151014+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329486 | TRUE | TRUE | 2026-07-07T02:50:05.6151014+00:00 | 2026-07-07T10:50:05.6151014+08:00 | #83190 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-10-21T23:30:00+00:00 | 2027-10-22T02:30:00+00:00 | 2027-10-22T07:30:00+08:00 | 2027-10-22T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83189 | 2026-07-01T00:31:47.8972637+00:00 | 2026-07-01T08:31:47.8972637+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:05.9462378+00:00 | 2026-07-07T10:50:05.9462378+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329487 | TRUE | TRUE | 2026-07-07T02:50:05.9462378+00:00 | 2026-07-07T10:50:05.9462378+08:00 | #83189 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-10-14T23:30:00+00:00 | 2027-10-15T02:30:00+00:00 | 2027-10-15T07:30:00+08:00 | 2027-10-15T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83188 | 2026-07-01T00:31:47.7375092+00:00 | 2026-07-01T08:31:47.7375092+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:06.2760714+00:00 | 2026-07-07T10:50:06.2760714+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329488 | TRUE | TRUE | 2026-07-07T02:50:06.2760714+00:00 | 2026-07-07T10:50:06.2760714+08:00 | #83188 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-10-07T23:30:00+00:00 | 2027-10-08T02:30:00+00:00 | 2027-10-08T07:30:00+08:00 | 2027-10-08T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83187 | 2026-07-01T00:31:47.5663921+00:00 | 2026-07-01T08:31:47.5663921+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:06.6209925+00:00 | 2026-07-07T10:50:06.6209925+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329489 | TRUE | TRUE | 2026-07-07T02:50:06.6209925+00:00 | 2026-07-07T10:50:06.6209925+08:00 | #83187 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-09-30T23:30:00+00:00 | 2027-10-01T02:30:00+00:00 | 2027-10-01T07:30:00+08:00 | 2027-10-01T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83186 | 2026-07-01T00:31:47.3941291+00:00 | 2026-07-01T08:31:47.3941291+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:06.9587281+00:00 | 2026-07-07T10:50:06.9587281+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329490 | TRUE | TRUE | 2026-07-07T02:50:06.9587281+00:00 | 2026-07-07T10:50:06.9587281+08:00 | #83186 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-09-23T23:30:00+00:00 | 2027-09-24T02:30:00+00:00 | 2027-09-24T07:30:00+08:00 | 2027-09-24T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83185 | 2026-07-01T00:31:47.2413313+00:00 | 2026-07-01T08:31:47.2413313+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:07.3236775+00:00 | 2026-07-07T10:50:07.3236775+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329491 | TRUE | TRUE | 2026-07-07T02:50:07.3236775+00:00 | 2026-07-07T10:50:07.3236775+08:00 | #83185 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-09-16T23:30:00+00:00 | 2027-09-17T02:30:00+00:00 | 2027-09-17T07:30:00+08:00 | 2027-09-17T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83184 | 2026-07-01T00:31:47.0902372+00:00 | 2026-07-01T08:31:47.0902372+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:07.6994181+00:00 | 2026-07-07T10:50:07.6994181+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329492 | TRUE | TRUE | 2026-07-07T02:50:07.6994181+00:00 | 2026-07-07T10:50:07.6994181+08:00 | #83184 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-09-09T23:30:00+00:00 | 2027-09-10T02:30:00+00:00 | 2027-09-10T07:30:00+08:00 | 2027-09-10T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83183 | 2026-07-01T00:31:46.9445551+00:00 | 2026-07-01T08:31:46.9445551+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:08.0768637+00:00 | 2026-07-07T10:50:08.0768637+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329493 | TRUE | TRUE | 2026-07-07T02:50:08.0768637+00:00 | 2026-07-07T10:50:08.0768637+08:00 | #83183 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-09-02T23:30:00+00:00 | 2027-09-03T02:30:00+00:00 | 2027-09-03T07:30:00+08:00 | 2027-09-03T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83182 | 2026-07-01T00:31:46.80027+00:00 | 2026-07-01T08:31:46.80027+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:08.4353727+00:00 | 2026-07-07T10:50:08.4353727+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329494 | TRUE | TRUE | 2026-07-07T02:50:08.4353727+00:00 | 2026-07-07T10:50:08.4353727+08:00 | #83182 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-08-26T23:30:00+00:00 | 2027-08-27T02:30:00+00:00 | 2027-08-27T07:30:00+08:00 | 2027-08-27T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83181 | 2026-07-01T00:31:46.6586752+00:00 | 2026-07-01T08:31:46.6586752+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:08.7959487+00:00 | 2026-07-07T10:50:08.7959487+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329495 | TRUE | TRUE | 2026-07-07T02:50:08.7959487+00:00 | 2026-07-07T10:50:08.7959487+08:00 | #83181 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-08-19T23:30:00+00:00 | 2027-08-20T02:30:00+00:00 | 2027-08-20T07:30:00+08:00 | 2027-08-20T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83180 | 2026-07-01T00:31:46.4154264+00:00 | 2026-07-01T08:31:46.4154264+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:09.1697474+00:00 | 2026-07-07T10:50:09.1697474+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329496 | TRUE | TRUE | 2026-07-07T02:50:09.1697474+00:00 | 2026-07-07T10:50:09.1697474+08:00 | #83180 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-08-12T23:30:00+00:00 | 2027-08-13T02:30:00+00:00 | 2027-08-13T07:30:00+08:00 | 2027-08-13T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83179 | 2026-07-01T00:31:46.2511521+00:00 | 2026-07-01T08:31:46.2511521+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:09.5508812+00:00 | 2026-07-07T10:50:09.5508812+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329497 | TRUE | TRUE | 2026-07-07T02:50:09.5508812+00:00 | 2026-07-07T10:50:09.5508812+08:00 | #83179 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-08-05T23:30:00+00:00 | 2027-08-06T02:30:00+00:00 | 2027-08-06T07:30:00+08:00 | 2027-08-06T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83178 | 2026-07-01T00:31:46.0960461+00:00 | 2026-07-01T08:31:46.0960461+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:09.9157521+00:00 | 2026-07-07T10:50:09.9157521+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329498 | TRUE | TRUE | 2026-07-07T02:50:09.9157521+00:00 | 2026-07-07T10:50:09.9157521+08:00 | #83178 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-29T23:30:00+00:00 | 2027-07-30T02:30:00+00:00 | 2027-07-30T07:30:00+08:00 | 2027-07-30T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83177 | 2026-07-01T00:31:45.9399455+00:00 | 2026-07-01T08:31:45.9399455+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:10.2987879+00:00 | 2026-07-07T10:50:10.2987879+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329499 | TRUE | TRUE | 2026-07-07T02:50:10.2987879+00:00 | 2026-07-07T10:50:10.2987879+08:00 | #83177 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-22T23:30:00+00:00 | 2027-07-23T02:30:00+00:00 | 2027-07-23T07:30:00+08:00 | 2027-07-23T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83176 | 2026-07-01T00:31:45.7851482+00:00 | 2026-07-01T08:31:45.7851482+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:10.6764893+00:00 | 2026-07-07T10:50:10.6764893+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329500 | TRUE | TRUE | 2026-07-07T02:50:10.6764893+00:00 | 2026-07-07T10:50:10.6764893+08:00 | #83176 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-15T23:30:00+00:00 | 2027-07-16T02:30:00+00:00 | 2027-07-16T07:30:00+08:00 | 2027-07-16T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83175 | 2026-07-01T00:31:45.6307194+00:00 | 2026-07-01T08:31:45.6307194+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:11.0897362+00:00 | 2026-07-07T10:50:11.0897362+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329501 | TRUE | TRUE | 2026-07-07T02:50:11.0897362+00:00 | 2026-07-07T10:50:11.0897362+08:00 | #83175 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-08T23:30:00+00:00 | 2027-07-09T02:30:00+00:00 | 2027-07-09T07:30:00+08:00 | 2027-07-09T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83174 | 2026-07-01T00:31:45.469554+00:00 | 2026-07-01T08:31:45.469554+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:11.469188+00:00 | 2026-07-07T10:50:11.469188+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329502 | TRUE | TRUE | 2026-07-07T02:50:11.469188+00:00 | 2026-07-07T10:50:11.469188+08:00 | #83174 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-07-01T23:30:00+00:00 | 2027-07-02T02:30:00+00:00 | 2027-07-02T07:30:00+08:00 | 2027-07-02T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83173 | 2026-07-01T00:31:45.3191792+00:00 | 2026-07-01T08:31:45.3191792+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:11.8524799+00:00 | 2026-07-07T10:50:11.8524799+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329503 | TRUE | TRUE | 2026-07-07T02:50:11.8524799+00:00 | 2026-07-07T10:50:11.8524799+08:00 | #83173 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-06-24T23:30:00+00:00 | 2027-06-25T02:30:00+00:00 | 2027-06-25T07:30:00+08:00 | 2027-06-25T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83172 | 2026-07-01T00:31:45.1682169+00:00 | 2026-07-01T08:31:45.1682169+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:12.2474794+00:00 | 2026-07-07T10:50:12.2474794+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329504 | TRUE | TRUE | 2026-07-07T02:50:12.2474794+00:00 | 2026-07-07T10:50:12.2474794+08:00 | #83172 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-06-17T23:30:00+00:00 | 2027-06-18T02:30:00+00:00 | 2027-06-18T07:30:00+08:00 | 2027-06-18T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83171 | 2026-07-01T00:31:45.0102225+00:00 | 2026-07-01T08:31:45.0102225+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:12.620586+00:00 | 2026-07-07T10:50:12.620586+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329505 | TRUE | TRUE | 2026-07-07T02:50:12.620586+00:00 | 2026-07-07T10:50:12.620586+08:00 | #83171 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-06-10T23:30:00+00:00 | 2027-06-11T02:30:00+00:00 | 2027-06-11T07:30:00+08:00 | 2027-06-11T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83170 | 2026-07-01T00:31:44.8666038+00:00 | 2026-07-01T08:31:44.8666038+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:12.993517+00:00 | 2026-07-07T10:50:12.993517+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329506 | TRUE | TRUE | 2026-07-07T02:50:12.993517+00:00 | 2026-07-07T10:50:12.993517+08:00 | #83170 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-06-03T23:30:00+00:00 | 2027-06-04T02:30:00+00:00 | 2027-06-04T07:30:00+08:00 | 2027-06-04T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83169 | 2026-07-01T00:31:44.7170524+00:00 | 2026-07-01T08:31:44.7170524+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:13.3895234+00:00 | 2026-07-07T10:50:13.3895234+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329507 | TRUE | TRUE | 2026-07-07T02:50:13.3895234+00:00 | 2026-07-07T10:50:13.3895234+08:00 | #83169 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-05-27T23:30:00+00:00 | 2027-05-28T02:30:00+00:00 | 2027-05-28T07:30:00+08:00 | 2027-05-28T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83168 | 2026-07-01T00:31:44.5818797+00:00 | 2026-07-01T08:31:44.5818797+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:13.7931778+00:00 | 2026-07-07T10:50:13.7931778+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329508 | TRUE | TRUE | 2026-07-07T02:50:13.7931778+00:00 | 2026-07-07T10:50:13.7931778+08:00 | #83168 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-05-20T23:30:00+00:00 | 2027-05-21T02:30:00+00:00 | 2027-05-21T07:30:00+08:00 | 2027-05-21T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83167 | 2026-07-01T00:31:44.4450378+00:00 | 2026-07-01T08:31:44.4450378+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:14.2289036+00:00 | 2026-07-07T10:50:14.2289036+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329509 | TRUE | TRUE | 2026-07-07T02:50:14.2289036+00:00 | 2026-07-07T10:50:14.2289036+08:00 | #83167 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-05-13T23:30:00+00:00 | 2027-05-14T02:30:00+00:00 | 2027-05-14T07:30:00+08:00 | 2027-05-14T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83166 | 2026-07-01T00:31:44.3030653+00:00 | 2026-07-01T08:31:44.3030653+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:14.6372013+00:00 | 2026-07-07T10:50:14.6372013+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329510 | TRUE | TRUE | 2026-07-07T02:50:14.6372013+00:00 | 2026-07-07T10:50:14.6372013+08:00 | #83166 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-05-06T23:30:00+00:00 | 2027-05-07T02:30:00+00:00 | 2027-05-07T07:30:00+08:00 | 2027-05-07T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83165 | 2026-07-01T00:31:44.1710028+00:00 | 2026-07-01T08:31:44.1710028+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:15.0547803+00:00 | 2026-07-07T10:50:15.0547803+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329511 | TRUE | TRUE | 2026-07-07T02:50:15.0547803+00:00 | 2026-07-07T10:50:15.0547803+08:00 | #83165 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-04-29T23:30:00+00:00 | 2027-04-30T02:30:00+00:00 | 2027-04-30T07:30:00+08:00 | 2027-04-30T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83164 | 2026-07-01T00:31:44.0398049+00:00 | 2026-07-01T08:31:44.0398049+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:15.4641709+00:00 | 2026-07-07T10:50:15.4641709+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329512 | TRUE | TRUE | 2026-07-07T02:50:15.4641709+00:00 | 2026-07-07T10:50:15.4641709+08:00 | #83164 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-04-22T23:30:00+00:00 | 2027-04-23T02:30:00+00:00 | 2027-04-23T07:30:00+08:00 | 2027-04-23T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83163 | 2026-07-01T00:31:43.9186983+00:00 | 2026-07-01T08:31:43.9186983+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:15.8861586+00:00 | 2026-07-07T10:50:15.8861586+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329513 | TRUE | TRUE | 2026-07-07T02:50:15.8861586+00:00 | 2026-07-07T10:50:15.8861586+08:00 | #83163 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-04-15T23:30:00+00:00 | 2027-04-16T02:30:00+00:00 | 2027-04-16T07:30:00+08:00 | 2027-04-16T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83162 | 2026-07-01T00:31:43.7920021+00:00 | 2026-07-01T08:31:43.7920021+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:16.275967+00:00 | 2026-07-07T10:50:16.275967+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329514 | TRUE | TRUE | 2026-07-07T02:50:16.275967+00:00 | 2026-07-07T10:50:16.275967+08:00 | #83162 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-04-08T23:30:00+00:00 | 2027-04-09T02:30:00+00:00 | 2027-04-09T07:30:00+08:00 | 2027-04-09T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83161 | 2026-07-01T00:31:43.6768067+00:00 | 2026-07-01T08:31:43.6768067+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:16.6845525+00:00 | 2026-07-07T10:50:16.6845525+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329515 | TRUE | TRUE | 2026-07-07T02:50:16.6845525+00:00 | 2026-07-07T10:50:16.6845525+08:00 | #83161 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-04-01T23:30:00+00:00 | 2027-04-02T02:30:00+00:00 | 2027-04-02T07:30:00+08:00 | 2027-04-02T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83160 | 2026-07-01T00:31:43.549541+00:00 | 2026-07-01T08:31:43.549541+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:17.132863+00:00 | 2026-07-07T10:50:17.132863+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329516 | TRUE | TRUE | 2026-07-07T02:50:17.132863+00:00 | 2026-07-07T10:50:17.132863+08:00 | #83160 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-03-25T23:30:00+00:00 | 2027-03-26T02:30:00+00:00 | 2027-03-26T07:30:00+08:00 | 2027-03-26T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83159 | 2026-07-01T00:31:43.4218883+00:00 | 2026-07-01T08:31:43.4218883+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:17.5543983+00:00 | 2026-07-07T10:50:17.5543983+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329517 | TRUE | TRUE | 2026-07-07T02:50:17.5543983+00:00 | 2026-07-07T10:50:17.5543983+08:00 | #83159 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-03-18T23:30:00+00:00 | 2027-03-19T02:30:00+00:00 | 2027-03-19T07:30:00+08:00 | 2027-03-19T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83158 | 2026-07-01T00:31:43.3002484+00:00 | 2026-07-01T08:31:43.3002484+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:17.9800902+00:00 | 2026-07-07T10:50:17.9800902+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329518 | TRUE | TRUE | 2026-07-07T02:50:17.9800902+00:00 | 2026-07-07T10:50:17.9800902+08:00 | #83158 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-03-11T23:30:00+00:00 | 2027-03-12T02:30:00+00:00 | 2027-03-12T07:30:00+08:00 | 2027-03-12T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83157 | 2026-07-01T00:31:43.1822578+00:00 | 2026-07-01T08:31:43.1822578+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:18.3882594+00:00 | 2026-07-07T10:50:18.3882594+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329519 | TRUE | TRUE | 2026-07-07T02:50:18.3882594+00:00 | 2026-07-07T10:50:18.3882594+08:00 | #83157 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-03-04T23:30:00+00:00 | 2027-03-05T02:30:00+00:00 | 2027-03-05T07:30:00+08:00 | 2027-03-05T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83156 | 2026-07-01T00:31:43.0685156+00:00 | 2026-07-01T08:31:43.0685156+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:18.7854246+00:00 | 2026-07-07T10:50:18.7854246+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329520 | TRUE | TRUE | 2026-07-07T02:50:18.7854246+00:00 | 2026-07-07T10:50:18.7854246+08:00 | #83156 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-02-25T23:30:00+00:00 | 2027-02-26T02:30:00+00:00 | 2027-02-26T07:30:00+08:00 | 2027-02-26T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83155 | 2026-07-01T00:31:42.9537116+00:00 | 2026-07-01T08:31:42.9537116+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:19.2382219+00:00 | 2026-07-07T10:50:19.2382219+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329521 | TRUE | TRUE | 2026-07-07T02:50:19.2382219+00:00 | 2026-07-07T10:50:19.2382219+08:00 | #83155 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-02-18T23:30:00+00:00 | 2027-02-19T02:30:00+00:00 | 2027-02-19T07:30:00+08:00 | 2027-02-19T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83154 | 2026-07-01T00:31:42.8394511+00:00 | 2026-07-01T08:31:42.8394511+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:19.6956404+00:00 | 2026-07-07T10:50:19.6956404+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329522 | TRUE | TRUE | 2026-07-07T02:50:19.6956404+00:00 | 2026-07-07T10:50:19.6956404+08:00 | #83154 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-02-11T23:30:00+00:00 | 2027-02-12T02:30:00+00:00 | 2027-02-12T07:30:00+08:00 | 2027-02-12T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83153 | 2026-07-01T00:31:42.7173864+00:00 | 2026-07-01T08:31:42.7173864+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:20.1882905+00:00 | 2026-07-07T10:50:20.1882905+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329523 | TRUE | TRUE | 2026-07-07T02:50:20.1882905+00:00 | 2026-07-07T10:50:20.1882905+08:00 | #83153 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-02-04T23:30:00+00:00 | 2027-02-05T02:30:00+00:00 | 2027-02-05T07:30:00+08:00 | 2027-02-05T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83152 | 2026-07-01T00:31:42.6043053+00:00 | 2026-07-01T08:31:42.6043053+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:20.6151481+00:00 | 2026-07-07T10:50:20.6151481+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329524 | TRUE | TRUE | 2026-07-07T02:50:20.6151481+00:00 | 2026-07-07T10:50:20.6151481+08:00 | #83152 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-01-28T23:30:00+00:00 | 2027-01-29T02:30:00+00:00 | 2027-01-29T07:30:00+08:00 | 2027-01-29T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83151 | 2026-07-01T00:31:42.4937799+00:00 | 2026-07-01T08:31:42.4937799+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:21.1200899+00:00 | 2026-07-07T10:50:21.1200899+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329525 | TRUE | TRUE | 2026-07-07T02:50:21.1200899+00:00 | 2026-07-07T10:50:21.1200899+08:00 | #83151 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-01-21T23:30:00+00:00 | 2027-01-22T02:30:00+00:00 | 2027-01-22T07:30:00+08:00 | 2027-01-22T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83150 | 2026-07-01T00:31:42.3846341+00:00 | 2026-07-01T08:31:42.3846341+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:21.5387644+00:00 | 2026-07-07T10:50:21.5387644+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329526 | TRUE | TRUE | 2026-07-07T02:50:21.5387644+00:00 | 2026-07-07T10:50:21.5387644+08:00 | #83150 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-01-14T23:30:00+00:00 | 2027-01-15T02:30:00+00:00 | 2027-01-15T07:30:00+08:00 | 2027-01-15T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83149 | 2026-07-01T00:31:42.2754069+00:00 | 2026-07-01T08:31:42.2754069+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:21.9745642+00:00 | 2026-07-07T10:50:21.9745642+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329527 | TRUE | TRUE | 2026-07-07T02:50:21.9745642+00:00 | 2026-07-07T10:50:21.9745642+08:00 | #83149 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2027-01-07T23:30:00+00:00 | 2027-01-08T02:30:00+00:00 | 2027-01-08T07:30:00+08:00 | 2027-01-08T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83148 | 2026-07-01T00:31:41.839624+00:00 | 2026-07-01T08:31:41.839624+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:22.457692+00:00 | 2026-07-07T10:50:22.457692+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329528 | TRUE | TRUE | 2026-07-07T02:50:22.457692+00:00 | 2026-07-07T10:50:22.457692+08:00 | #83148 - NBWT: 3hrs - CRUSHER - PRIMARY: NBWT 01 | 1.0 | TRUE |  | 2026-12-31T23:30:00+00:00 | 2027-01-01T02:30:00+00:00 | 2027-01-01T07:30:00+08:00 | 2027-01-01T10:30:00+08:00 |  |  |  |  | 3.00 | CS2101 Crusher Gap Checks |  |  | [{"equipmentGUID": "1fdf00c0-7c7b-ee11-a846-000d3acacefd", "code": "NBWTPCS01", "name": "Crusher - Primary: NBWT 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83141 | 2026-06-30T23:44:41.4123063+00:00 | 2026-07-01T07:44:41.4123063+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:22.8985951+00:00 | 2026-07-07T10:50:22.8985951+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329529 | TRUE | TRUE | 2026-07-07T02:50:22.8985951+00:00 | 2026-07-07T10:50:22.8985951+08:00 | #83141 - NBWT: 6hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-06-27T23:30:00+00:00 | 2027-06-28T05:30:00+00:00 | 2027-06-28T07:30:00+08:00 | 2027-06-28T13:30:00+08:00 |  |  |  |  | 6.00 | 48HR Post Shut Oil/Retention |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44505, "shutVersionId": 321791, "title": "#44505 - NBWT: 144hrs - PLANT: NBWT", "startDatetimeUTC": "2027-03-17T11:30:00+00:00", "endDatetimeUTC": "2027-03-23T11:30:00+00:00"}}] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83142 | 2026-06-30T23:44:41.549297+00:00 | 2026-07-01T07:44:41.549297+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:23.4046386+00:00 | 2026-07-07T10:50:23.4046386+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329530 | TRUE | TRUE | 2026-07-07T02:50:23.4046386+00:00 | 2026-07-07T10:50:23.4046386+08:00 | #83142 - NBWT: 6hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-09-27T23:30:00+00:00 | 2027-09-28T05:30:00+00:00 | 2027-09-28T07:30:00+08:00 | 2027-09-28T13:30:00+08:00 |  |  |  |  | 6.00 | 48HR Post Shut Oil/Retention |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44505, "shutVersionId": 321791, "title": "#44505 - NBWT: 144hrs - PLANT: NBWT", "startDatetimeUTC": "2027-03-17T11:30:00+00:00", "endDatetimeUTC": "2027-03-23T11:30:00+00:00"}}] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83143 | 2026-06-30T23:44:41.6772081+00:00 | 2026-07-01T07:44:41.6772081+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:23.8921517+00:00 | 2026-07-07T10:50:23.8921517+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329531 | TRUE | TRUE | 2026-07-07T02:50:23.8921517+00:00 | 2026-07-07T10:50:23.8921517+08:00 | #83143 - NBWT: 6hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-12-23T23:30:00+00:00 | 2027-12-24T05:30:00+00:00 | 2027-12-24T07:30:00+08:00 | 2027-12-24T13:30:00+08:00 |  |  |  |  | 6.00 | 48HR Post Shut Oil/Retention |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44505, "shutVersionId": 321791, "title": "#44505 - NBWT: 144hrs - PLANT: NBWT", "startDatetimeUTC": "2027-03-17T11:30:00+00:00", "endDatetimeUTC": "2027-03-23T11:30:00+00:00"}}] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83140 | 2026-06-30T23:44:40.9161377+00:00 | 2026-07-01T07:44:40.9161377+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:50:24.3779256+00:00 | 2026-07-07T10:50:24.3779256+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329532 | TRUE | TRUE | 2026-07-07T02:50:24.3779256+00:00 | 2026-07-07T10:50:24.3779256+08:00 | #83140 - NBWT: 6hrs - PLANT: NBWT | 1.0 | TRUE |  | 2027-03-25T23:30:00+00:00 | 2027-03-26T05:30:00+00:00 | 2027-03-26T07:30:00+08:00 | 2027-03-26T13:30:00+08:00 |  |  |  |  | 6.00 | 48HR Post Shut Oil/Retention |  |  | [{"equipmentGUID": "8417ee47-4b9a-ee11-a847-000d3acacefd", "code": "NBWTPLT", "name": "Plant: NBWT", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 44505, "shutVersionId": 321791, "title": "#44505 - NBWT: 144hrs - PLANT: NBWT", "startDatetimeUTC": "2027-03-17T11:30:00+00:00", "endDatetimeUTC": "2027-03-23T11:30:00+00:00"}}] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83132 | 2026-06-30T22:46:56.1435085+00:00 | 2026-07-01T06:46:56.1435085+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-09T04:26:19.7613337+00:00 | 2026-07-09T12:26:19.7613337+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329745 | TRUE | TRUE | 2026-07-09T04:26:19.7613337+00:00 | 2026-07-09T12:26:19.7613337+08:00 | #83132 - NBWT: 250hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-16T11:30:00+00:00 | 2027-09-26T21:30:00+00:00 | 2027-09-16T19:30:00+08:00 | 2027-09-27T05:30:00+08:00 |  |  |  |  | 250.00 | SGE Shutdown - Crusher Overhaul and CV2122 Belt C/O |  | SHNP2737 | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84461, "shutVersionId": 335825, "title": "#84461 - NBWT: 4hrs - CRUSHER - PRIMARY: SGE 02", "startDatetimeUTC": "2027-10-05T23:30:00+00:00", "endDatetimeUTC": "2027-10-06T03:30:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 84460, "shutVersionId": 335826, "title": "#84460 - NBWT: 4hrs - CRUSHER - PRIMARY: SGE 02", "startDatetimeUTC": "2027-09-28T23:30:00+00:00", "endDatetimeUTC": "2027-09-29T03:30:00+00:00"}}] | [{"name": "Crusher Overhaul"}] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83247 | 2026-07-01T00:34:07.9529853+00:00 | 2026-07-01T08:34:07.9529853+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:47.8787084+00:00 | 2026-07-07T10:49:47.8787084+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329429 | TRUE | TRUE | 2026-07-07T02:49:47.8787084+00:00 | 2026-07-07T10:49:47.8787084+08:00 | #83247 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-19T02:30:00+00:00 | 2027-11-19T05:30:00+00:00 | 2027-11-19T10:30:00+08:00 | 2027-11-19T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83246 | 2026-07-01T00:34:07.7922586+00:00 | 2026-07-01T08:34:07.7922586+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:48.1208149+00:00 | 2026-07-07T10:49:48.1208149+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329430 | TRUE | TRUE | 2026-07-07T02:49:48.1208149+00:00 | 2026-07-07T10:49:48.1208149+08:00 | #83246 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-12T02:30:00+00:00 | 2027-11-12T05:30:00+00:00 | 2027-11-12T10:30:00+08:00 | 2027-11-12T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83245 | 2026-07-01T00:34:07.5234951+00:00 | 2026-07-01T08:34:07.5234951+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:48.3184126+00:00 | 2026-07-07T10:49:48.3184126+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329431 | TRUE | TRUE | 2026-07-07T02:49:48.3184126+00:00 | 2026-07-07T10:49:48.3184126+08:00 | #83245 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-11-05T02:30:00+00:00 | 2027-11-05T05:30:00+00:00 | 2027-11-05T10:30:00+08:00 | 2027-11-05T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83244 | 2026-07-01T00:34:07.3150198+00:00 | 2026-07-01T08:34:07.3150198+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:48.5368996+00:00 | 2026-07-07T10:49:48.5368996+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329432 | TRUE | TRUE | 2026-07-07T02:49:48.5368996+00:00 | 2026-07-07T10:49:48.5368996+08:00 | #83244 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-29T02:30:00+00:00 | 2027-10-29T05:30:00+00:00 | 2027-10-29T10:30:00+08:00 | 2027-10-29T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83243 | 2026-07-01T00:34:07.1387506+00:00 | 2026-07-01T08:34:07.1387506+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:48.7377814+00:00 | 2026-07-07T10:49:48.7377814+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329433 | TRUE | TRUE | 2026-07-07T02:49:48.7377814+00:00 | 2026-07-07T10:49:48.7377814+08:00 | #83243 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-22T02:30:00+00:00 | 2027-10-22T05:30:00+00:00 | 2027-10-22T10:30:00+08:00 | 2027-10-22T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83242 | 2026-07-01T00:34:06.9626099+00:00 | 2026-07-01T08:34:06.9626099+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:48.9595328+00:00 | 2026-07-07T10:49:48.9595328+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329434 | TRUE | TRUE | 2026-07-07T02:49:48.9595328+00:00 | 2026-07-07T10:49:48.9595328+08:00 | #83242 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-15T02:30:00+00:00 | 2027-10-15T05:30:00+00:00 | 2027-10-15T10:30:00+08:00 | 2027-10-15T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83241 | 2026-07-01T00:34:06.7900609+00:00 | 2026-07-01T08:34:06.7900609+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:49.4789888+00:00 | 2026-07-07T10:49:49.4789888+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329435 | TRUE | TRUE | 2026-07-07T02:49:49.4789888+00:00 | 2026-07-07T10:49:49.4789888+08:00 | #83241 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-08T02:30:00+00:00 | 2027-10-08T05:30:00+00:00 | 2027-10-08T10:30:00+08:00 | 2027-10-08T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83240 | 2026-07-01T00:34:06.6201325+00:00 | 2026-07-01T08:34:06.6201325+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:49.67463+00:00 | 2026-07-07T10:49:49.67463+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329436 | TRUE | TRUE | 2026-07-07T02:49:49.67463+00:00 | 2026-07-07T10:49:49.67463+08:00 | #83240 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-10-01T02:30:00+00:00 | 2027-10-01T05:30:00+00:00 | 2027-10-01T10:30:00+08:00 | 2027-10-01T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83239 | 2026-07-01T00:34:06.4575411+00:00 | 2026-07-01T08:34:06.4575411+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:49.899878+00:00 | 2026-07-07T10:49:49.899878+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329437 | TRUE | TRUE | 2026-07-07T02:49:49.899878+00:00 | 2026-07-07T10:49:49.899878+08:00 | #83239 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-24T02:30:00+00:00 | 2027-09-24T05:30:00+00:00 | 2027-09-24T10:30:00+08:00 | 2027-09-24T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83238 | 2026-07-01T00:34:06.2956067+00:00 | 2026-07-01T08:34:06.2956067+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:50.1139703+00:00 | 2026-07-07T10:49:50.1139703+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329438 | TRUE | TRUE | 2026-07-07T02:49:50.1139703+00:00 | 2026-07-07T10:49:50.1139703+08:00 | #83238 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-17T02:30:00+00:00 | 2027-09-17T05:30:00+00:00 | 2027-09-17T10:30:00+08:00 | 2027-09-17T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83237 | 2026-07-01T00:34:06.1153586+00:00 | 2026-07-01T08:34:06.1153586+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:50.3252906+00:00 | 2026-07-07T10:49:50.3252906+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329439 | TRUE | TRUE | 2026-07-07T02:49:50.3252906+00:00 | 2026-07-07T10:49:50.3252906+08:00 | #83237 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-10T02:30:00+00:00 | 2027-09-10T05:30:00+00:00 | 2027-09-10T10:30:00+08:00 | 2027-09-10T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
83236 | 2026-07-01T00:34:05.9484896+00:00 | 2026-07-01T08:34:05.9484896+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-07-07T02:49:50.5652686+00:00 | 2026-07-07T10:49:50.5652686+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 329440 | TRUE | TRUE | 2026-07-07T02:49:50.5652686+00:00 | 2026-07-07T10:49:50.5652686+08:00 | #83236 - NBWT: 3hrs - CRUSHER - PRIMARY: SGE 02 | 1.0 | TRUE |  | 2027-09-03T02:30:00+00:00 | 2027-09-03T05:30:00+00:00 | 2027-09-03T10:30:00+08:00 | 2027-09-03T13:30:00+08:00 |  |  |  |  | 3.00 | CS2121 Crusher Gap Checks |  |  | [{"equipmentGUID": "3cf0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "SGEPCS02", "name": "Crusher - Primary: SGE 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | NBWT | Australia/Perth
75459 | 2026-02-24T00:36:44.4679884+00:00 | 2026-02-24T08:36:44.4679884+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:54.0182203+00:00 | 2026-02-24T14:37:54.0182203+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288140 | TRUE | TRUE | 2026-02-24T06:37:54.0182203+00:00 | 2026-02-24T14:37:54.0182203+08:00 | #75459 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-11-19T01:00:00+00:00 | 2027-11-19T04:00:00+00:00 | 2027-11-19T09:00:00+08:00 | 2027-11-19T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75460 | 2026-02-24T00:36:44.9224472+00:00 | 2026-02-24T08:36:44.9224472+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:55.0158609+00:00 | 2026-02-24T14:37:55.0158609+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288141 | TRUE | TRUE | 2026-02-24T06:37:55.0158609+00:00 | 2026-02-24T14:37:55.0158609+08:00 | #75460 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-11-26T01:00:00+00:00 | 2027-11-26T04:00:00+00:00 | 2027-11-26T09:00:00+08:00 | 2027-11-26T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75461 | 2026-02-24T00:36:45.3836649+00:00 | 2026-02-24T08:36:45.3836649+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:55.9924368+00:00 | 2026-02-24T14:37:55.9924368+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288142 | TRUE | TRUE | 2026-02-24T06:37:55.9924368+00:00 | 2026-02-24T14:37:55.9924368+08:00 | #75461 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-12-03T01:00:00+00:00 | 2027-12-03T04:00:00+00:00 | 2027-12-03T09:00:00+08:00 | 2027-12-03T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75462 | 2026-02-24T00:36:45.8428617+00:00 | 2026-02-24T08:36:45.8428617+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:56.9766749+00:00 | 2026-02-24T14:37:56.9766749+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288143 | TRUE | TRUE | 2026-02-24T06:37:56.9766749+00:00 | 2026-02-24T14:37:56.9766749+08:00 | #75462 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-12-10T01:00:00+00:00 | 2027-12-10T04:00:00+00:00 | 2027-12-10T09:00:00+08:00 | 2027-12-10T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75463 | 2026-02-24T00:36:46.2884194+00:00 | 2026-02-24T08:36:46.2884194+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:58.0801994+00:00 | 2026-02-24T14:37:58.0801994+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288144 | TRUE | TRUE | 2026-02-24T06:37:58.0801994+00:00 | 2026-02-24T14:37:58.0801994+08:00 | #75463 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-12-17T01:00:00+00:00 | 2027-12-17T04:00:00+00:00 | 2027-12-17T09:00:00+08:00 | 2027-12-17T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75464 | 2026-02-24T00:36:46.7402408+00:00 | 2026-02-24T08:36:46.7402408+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:37:59.1153962+00:00 | 2026-02-24T14:37:59.1153962+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288145 | TRUE | TRUE | 2026-02-24T06:37:59.1153962+00:00 | 2026-02-24T14:37:59.1153962+08:00 | #75464 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-12-24T01:00:00+00:00 | 2027-12-24T04:00:00+00:00 | 2027-12-24T09:00:00+08:00 | 2027-12-24T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
75465 | 2026-02-24T00:36:47.2209207+00:00 | 2026-02-24T08:36:47.2209207+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | 2026-02-24T06:38:00.1322464+00:00 | 2026-02-24T14:38:00.1322464+08:00 | {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "displayName": "Bermingham, Craig (RTIO)"} | {"name": "Fixed Plant"} | 288146 | TRUE | TRUE | 2026-02-24T06:38:00.1322464+00:00 | 2026-02-24T14:38:00.1322464+08:00 | #75465 - BM2: 3hrs - CRUSHER - PRIMARY: BM2 01 | 1.0 | TRUE |  | 2027-12-31T01:00:00+00:00 | 2027-12-31T04:00:00+00:00 | 2027-12-31T09:00:00+08:00 | 2027-12-31T12:00:00+08:00 |  |  |  |  | 3.00 | CR0110 Weekly Crusher Gap Check/Adjust - MP# 1505785 |  |  | [{"equipmentGUID": "cfe000c0-7c7b-ee11-a846-000d3acacefd", "code": "BM2PCS01", "name": "Crusher - Primary: BM2 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b1ea31ce-5728-4f33-973f-3ccf65a0853a", "emailAddress": "Craig.Bermingham@riotinto.com", "displayName": "Craig Bermingham"}}] | [] | [] | [] | [] | [] | Approved | Create | b1ea31ce-5728-4f33-973f-3ccf65a0853a | Bermingham, Craig (RTIO) | Scheduled | BM2 | Australia/Perth
41482 | 2021-05-24T10:05:22+00:00 | 2021-05-24T18:05:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-16T00:49:18.9545536+00:00 | 2026-10-16T08:49:18.9545536+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336140 | TRUE | TRUE | 2026-10-16T00:49:18.9545536+00:00 | 2026-10-16T08:49:18.9545536+08:00 | #41482 - BM4: 126hrs - PLANT: BM4 | 13.0 | TRUE |  | 2026-12-31T22:00:00+00:00 | 2027-01-06T04:00:00+00:00 | 2027-01-01T06:00:00+08:00 | 2027-01-06T12:00:00+08:00 |  |  |  |  | 126.00 | Baseline changed from 96h to 126h as per MOC 113812 | Removing extra requirement added back to standard shut hours |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "5906dc4e-e2e0-42d0-a791-094222a1426d", "emailAddress": "Brodie.Tyrer@riotinto.com", "displayName": "Tyrer, Brodie (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0510128.53", "name": "B4MM Fixed Plant Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
44169 | 2021-11-23T03:48:50+00:00 | 2021-11-23T11:48:50+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-16T00:49:19.1800494+00:00 | 2026-10-16T08:49:19.1800494+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336141 | TRUE | TRUE | 2026-10-16T00:49:19.1800494+00:00 | 2026-10-16T08:49:19.1800494+08:00 | #44169 - BM4: 126hrs - CRUSHER - PRIMARY: BM4 01 | 13.0 | TRUE |  | 2026-12-31T22:00:00+00:00 | 2027-01-06T04:00:00+00:00 | 2027-01-01T06:00:00+08:00 | 2027-01-06T12:00:00+08:00 |  |  |  |  | 126.00 | Baseline changed from 96h to 126h as per MOC 113812 | Removing extra requirement added back to normal shutdown duration |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}] | [] | [] | [] | [] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
44170 | 2021-11-23T03:50:06+00:00 | 2021-11-23T11:50:06+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-16T00:49:19.3690819+00:00 | 2026-10-16T08:49:19.3690819+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336142 | TRUE | TRUE | 2026-10-16T00:49:19.3690819+00:00 | 2026-10-16T08:49:19.3690819+08:00 | #44170 - BM4: 126hrs - CRUSHER - PRIMARY: BM4 02 | 13.0 | TRUE |  | 2026-12-31T22:00:00+00:00 | 2027-01-06T04:00:00+00:00 | 2027-01-01T06:00:00+08:00 | 2027-01-06T12:00:00+08:00 |  |  |  |  | 126.00 | Baseline changed from 96h to 126h as per MOC 113812 | Removing extra requirement added back to standard shutdown duration |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}] | [] | [] | [] | [] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
65357 | 2024-10-14T06:29:45+00:00 | 2024-10-14T14:29:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-19T03:52:45.3929972+00:00 | 2026-10-19T11:52:45.3929972+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336198 | TRUE | TRUE | 2026-10-19T03:52:45.3929972+00:00 | 2026-10-19T11:52:45.3929972+08:00 | #65357 - BM4: 240hrs - PLANT: BM4 | 5.0 | TRUE |  | 2027-03-27T04:00:00+00:00 | 2027-04-06T04:00:00+00:00 | 2027-03-27T12:00:00+08:00 | 2027-04-06T12:00:00+08:00 |  |  |  |  | 240.00 | Baseline changed from 96h to 126h as per MOC 113812 | Aligning common plant outage with both primary crusher outages |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "5906dc4e-e2e0-42d0-a791-094222a1426d", "emailAddress": "Brodie.Tyrer@riotinto.com", "displayName": "Tyrer, Brodie (RTIO-WORKPAC)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "01e76f26-7453-4569-95f6-dac4d237b695", "emailAddress": "Dipin.Varsani@riotinto.com", "displayName": "Varsani, Dipin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0508791", "name": "B4 MEM Workshop Expansion", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}, {"code": "P-0510128.53", "name": "B4MM Fixed Plant Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
28405 | 2018-03-15T02:32:49+00:00 | 2018-03-15T10:32:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000070b", "displayName": "Glenn Hall"} | 2026-10-15T23:22:53.7449845+00:00 | 2026-10-16T07:22:53.7449845+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336132 | TRUE | TRUE | 2026-10-15T23:22:53.7449845+00:00 | 2026-10-16T07:22:53.7449845+08:00 | #28405 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 8.0 | TRUE |  | 2027-03-07T20:00:00+00:00 | 2027-03-08T08:00:00+00:00 | 2027-03-08T04:00:00+08:00 | 2027-03-08T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut | Changed as per IOPS request |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
28403 | 2018-03-15T02:32:45+00:00 | 2018-03-15T10:32:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000070b", "displayName": "Glenn Hall"} | 2026-10-15T23:23:15.2938387+00:00 | 2026-10-16T07:23:15.2938387+08:00 | {"principalGUID": "c68e6356-78ef-4a68-ae17-c0cbad95dac2", "displayName": "McShane, Brian (RTIO)"} | {"name": "Fixed Plant"} | 336133 | TRUE | TRUE | 2026-10-15T23:23:15.2938387+00:00 | 2026-10-16T07:23:15.2938387+08:00 | #28403 - BM4: 12hrs - TRAIN LOADOUT: BM4 | 9.0 | TRUE |  | 2027-02-13T20:00:00+00:00 | 2027-02-14T08:00:00+00:00 | 2027-02-14T04:00:00+08:00 | 2027-02-14T16:00:00+08:00 |  |  |  |  | 12.00 | TLO 12hr mini shut | Changed as requested by IOPS |  | [{"equipmentGUID": "f7e200c0-7c7b-ee11-a846-000d3acacefd", "code": "BM4TLO", "name": "Train Loadout: BM4", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | c68e6356-78ef-4a68-ae17-c0cbad95dac2 | McShane, Brian (RTIO) | Scheduled | BM4 | Australia/Perth
83134 | 2026-06-30T23:09:41.0770966+00:00 | 2026-07-01T07:09:41.0770966+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:18:58.9859524+00:00 | 2026-09-29T06:18:58.9859524+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334152 | TRUE | TRUE | 2026-09-28T22:18:58.9859524+00:00 | 2026-09-29T06:18:58.9859524+08:00 | #83134 - HD1: 336hrs - 21D373 EPIROC PV271LP DRILL | 4.0 | FALSE |  | 2027-01-23T22:00:00+00:00 | 2027-02-06T22:00:00+00:00 | 2027-01-24T06:00:00+08:00 | 2027-02-07T06:00:00+08:00 |  |  |  |  | 336.00 | 21D373 12,000Hr PoaP Shut On-site | Aligned with shut schedule | SDR37327 | [{"equipmentGUID": "71d200c0-7c7b-ee11-a846-000d3acacefd", "code": "21D373", "name": "21D373 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d154a8cd-896c-4fcb-99e3-fd502405ddd8", "emailAddress": "Michael.Desker@riotinto.com", "displayName": "Michael Desker"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | HD1 | Australia/Perth |  | Drills
83135 | 2026-06-30T23:28:45.0371499+00:00 | 2026-07-01T07:28:45.0371499+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:21:33.5634015+00:00 | 2026-09-29T06:21:33.5634015+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334153 | TRUE | TRUE | 2026-09-28T22:21:33.5634015+00:00 | 2026-09-29T06:21:33.5634015+08:00 | #83135 - YAN: 336hrs - 21H220 ATLAS COPCO PV271 DRILL | 4.0 | FALSE |  | 2027-02-08T22:00:00+00:00 | 2027-02-22T22:00:00+00:00 | 2027-02-09T06:00:00+08:00 | 2027-02-23T06:00:00+08:00 |  |  |  |  | 336.00 | 21H220 Eng,PTO,Comp Major Works Shut | Aligned with Shut Schedule | SDR22027 | [{"equipmentGUID": "d06afbbf-7c7b-ee11-a846-000d3acacefd", "code": "21H220", "name": "21H220 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "17232fd8-3407-40c5-9b2f-a048e7538a2a", "emailAddress": "John.Lachmaniuk@riotinto.com", "displayName": "John Lachmaniuk"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | YAN | Australia/Perth |  | Drills
83137 | 2026-06-30T23:37:19.6346129+00:00 | 2026-07-01T07:37:19.6346129+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:22:45.3795798+00:00 | 2026-09-29T06:22:45.3795798+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334154 | TRUE | TRUE | 2026-09-28T22:22:45.3795798+00:00 | 2026-09-29T06:22:45.3795798+08:00 | #83137 - HD1: 336hrs - 21D249 EPIROC PV271LP DRILL | 4.0 | FALSE |  | 2027-02-24T22:00:00+00:00 | 2027-03-10T22:00:00+00:00 | 2027-02-25T06:00:00+08:00 | 2027-03-11T06:00:00+08:00 |  |  |  |  | 336.00 | 21D249 12,000Hr PoaP Shut On-site | Aligned with shut schedule | SDR24927 | [{"equipmentGUID": "672ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "21D249", "name": "21D249 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d154a8cd-896c-4fcb-99e3-fd502405ddd8", "emailAddress": "Michael.Desker@riotinto.com", "displayName": "Michael Desker"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | HD1 | Australia/Perth |  | Drills
83282 | 2026-07-01T08:11:03.2535405+00:00 | 2026-07-01T16:11:03.2535405+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:24:54.5155071+00:00 | 2026-09-29T06:24:54.5155071+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334155 | TRUE | TRUE | 2026-09-28T22:24:54.5155071+00:00 | 2026-09-29T06:24:54.5155071+08:00 | #83282 - MDO: 336hrs - 21H227 ATLAS COPCO PV271 DRILL | 3.0 | FALSE |  | 2027-03-12T22:00:00+00:00 | 2027-03-26T22:00:00+00:00 | 2027-03-13T06:00:00+08:00 | 2027-03-27T06:00:00+08:00 | 2027-03-12T21:00:00+00:00 |  | 2027-03-13T05:00:00+08:00 |  | 336.00 | 21H227 8000Hr & 12,000Hr PoaP Shut On-site TP | Aligned with shut schedule | SDR22727 | [{"equipmentGUID": "a1e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "21H227", "name": "21H227 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ce8ea314-99b4-483c-a906-f74dd1ea1396", "emailAddress": "Robert.Hooper@riotinto.com", "displayName": "Robert Hooper"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | MDO | Australia/Perth |  | Drills
83283 | 2026-07-01T08:24:56.3378482+00:00 | 2026-07-01T16:24:56.3378482+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:28:21.6660078+00:00 | 2026-09-29T06:28:21.6660078+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334157 | TRUE | TRUE | 2026-09-28T22:28:21.6660078+00:00 | 2026-09-29T06:28:21.6660078+08:00 | #83283 - BM4: 336hrs - 21H248 EPIROC PV271LP DRILL | 3.0 | FALSE |  | 2027-05-11T22:00:00+00:00 | 2027-05-25T22:00:00+00:00 | 2027-05-12T06:00:00+08:00 | 2027-05-26T06:00:00+08:00 |  |  |  |  | 336.00 | 21H248 12,000Hr PoaP Shut On-site TP | Aligned with shut schedule | SDR24827 | [{"equipmentGUID": "d32cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H248", "name": "21H248 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | Drills
83271 | 2026-07-01T05:22:34.6228195+00:00 | 2026-07-01T13:22:34.6228195+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:30:20.2455467+00:00 | 2026-09-29T06:30:20.2455467+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334158 | TRUE | TRUE | 2026-09-28T22:30:20.2455467+00:00 | 2026-09-29T06:30:20.2455467+08:00 | #83271 - MDO: 480hrs - 21H229 ATLAS COPCO PV271 DRILL | 5.0 | FALSE |  | 2027-04-19T22:00:00+00:00 | 2027-05-09T22:00:00+00:00 | 2027-04-20T06:00:00+08:00 | 2027-05-10T06:00:00+08:00 |  |  |  |  | 480.00 | 21H229 Major & U/C Shut | Aligned with shut schedule | SDR22927 | [{"equipmentGUID": "8933f6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H229", "name": "21H229 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ce8ea314-99b4-483c-a906-f74dd1ea1396", "emailAddress": "Robert.Hooper@riotinto.com", "displayName": "Robert Hooper"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | MDO | Australia/Perth |  | Drills
83145 | 2026-07-01T00:16:49.1774745+00:00 | 2026-07-01T08:16:49.1774745+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:31:39.0505826+00:00 | 2026-09-29T06:31:39.0505826+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334159 | TRUE | TRUE | 2026-09-28T22:31:39.0505826+00:00 | 2026-09-29T06:31:39.0505826+08:00 | #83145 - BM4: 480hrs - 21H391 EPIROC PV271LP DRILL | 5.0 | FALSE |  | 2027-05-27T22:00:00+00:00 | 2027-06-16T22:00:00+00:00 | 2027-05-28T06:00:00+08:00 | 2027-06-17T06:00:00+08:00 |  |  |  |  | 480.00 | 21H391 18,000 PoaP Shut On-site ¦ Tom Price | Aligned with shut schedule | SDR39127 | [{"equipmentGUID": "46e6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "21H391", "name": "21H391 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | Drills
83263 | 2026-07-01T05:06:05.9834378+00:00 | 2026-07-01T13:06:05.9834378+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:32:29.5310344+00:00 | 2026-09-29T06:32:29.5310344+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334160 | TRUE | TRUE | 2026-09-28T22:32:29.5310344+00:00 | 2026-09-29T06:32:29.5310344+08:00 | #83263 - BM4: 336hrs - 21H252 EPIROC PV271LP DRILL | 4.0 | FALSE |  | 2027-06-18T22:00:00+00:00 | 2027-07-02T22:00:00+00:00 | 2027-06-19T06:00:00+08:00 | 2027-07-03T06:00:00+08:00 |  |  |  |  | 336.00 | 21H252 12,000Hr PoaP Shut On-site | Aligned with shut schedule | SDR25227 | [{"equipmentGUID": "ab0dbdb9-4a8c-ee11-a847-000d3acacefd", "code": "21H252", "name": "21H252 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | Drills
83285 | 2026-07-01T08:48:30.8040069+00:00 | 2026-07-01T16:48:30.8040069+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:33:15.2890017+00:00 | 2026-09-29T06:33:15.2890017+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334161 | TRUE | TRUE | 2026-09-28T22:33:15.2890017+00:00 | 2026-09-29T06:33:15.2890017+08:00 | #83285 - HD1: 480hrs - 21D232 EPIROC PV271LP DRILL | 2.0 | FALSE |  | 2027-07-04T22:00:00+00:00 | 2027-07-24T22:00:00+00:00 | 2027-07-05T06:00:00+08:00 | 2027-07-25T06:00:00+08:00 |  |  |  |  | 480.00 | 21D232 9000Hr + 12,000Hr PoaP Shut On-site TP | Aligned with shut schedule | SDR23227 | [{"equipmentGUID": "8341e291-10a6-ef11-a856-000d3acacefd", "code": "21D232", "name": "21D232 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d154a8cd-896c-4fcb-99e3-fd502405ddd8", "emailAddress": "Michael.Desker@riotinto.com", "displayName": "Michael Desker"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | HD1 | Australia/Perth |  | Drills
83290 | 2026-07-01T09:04:16.6758761+00:00 | 2026-07-01T17:04:16.6758761+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:34:19.9110905+00:00 | 2026-09-29T06:34:19.9110905+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334162 | TRUE | TRUE | 2026-09-28T22:34:19.9110905+00:00 | 2026-09-29T06:34:19.9110905+08:00 | #83290 - GDI: 480hrs - 21B291 CAT MD6310 DRILL | 4.0 | FALSE |  | 2027-07-26T22:00:00+00:00 | 2027-08-15T22:00:00+00:00 | 2027-07-27T06:00:00+08:00 | 2027-08-16T06:00:00+08:00 |  |  |  |  | 480.00 | 21B291 15,000 PoaP Shut On-site | Aligned with shut schedule | SDR29127 | [{"equipmentGUID": "f2de00c0-7c7b-ee11-a846-000d3acacefd", "code": "21B291", "name": "21B291 CAT MD6310 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | GDI | Australia/Perth |  | Drills
83267 | 2026-07-01T05:14:20.9436568+00:00 | 2026-07-01T13:14:20.9436568+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:35:14.7253276+00:00 | 2026-09-29T06:35:14.7253276+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334163 | TRUE | TRUE | 2026-09-28T22:35:14.7253276+00:00 | 2026-09-29T06:35:14.7253276+08:00 | #83267 - BM4: 336hrs - 21H231 EPIROC PV271LP DRILL | 4.0 | FALSE |  | 2027-08-17T22:00:00+00:00 | 2027-08-31T22:00:00+00:00 | 2027-08-18T06:00:00+08:00 | 2027-09-01T06:00:00+08:00 |  |  |  |  | 336.00 | 21H231 12,000Hr PoaP Shut On-site | Aligned with shut schedule | SDR23127 | [{"equipmentGUID": "a80dbdb9-4a8c-ee11-a847-000d3acacefd", "code": "21H231", "name": "21H231 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | Drills
83292 | 2026-07-01T09:09:27.9448524+00:00 | 2026-07-01T17:09:27.9448524+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:36:24.0631765+00:00 | 2026-09-29T06:36:24.0631765+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334164 | TRUE | TRUE | 2026-09-28T22:36:24.0631765+00:00 | 2026-09-29T06:36:24.0631765+08:00 | #83292 - HD1: 480hrs - 21H226 ATLAS COPCO PV271 DRILL | 3.0 | FALSE |  | 2027-09-02T22:00:00+00:00 | 2027-09-22T22:00:00+00:00 | 2027-09-03T06:00:00+08:00 | 2027-09-23T06:00:00+08:00 |  |  |  |  | 480.00 | 21H226 Major shut onsite TP | Aligned with shut schedule | SDR22627 | [{"equipmentGUID": "192bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "21H226", "name": "21H226 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d154a8cd-896c-4fcb-99e3-fd502405ddd8", "emailAddress": "Michael.Desker@riotinto.com", "displayName": "Michael Desker"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | HD1 | Australia/Perth |  | Drills
83288 | 2026-07-01T08:59:13.8744122+00:00 | 2026-07-01T16:59:13.8744122+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:37:17.1461966+00:00 | 2026-09-29T06:37:17.1461966+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334165 | TRUE | TRUE | 2026-09-28T22:37:17.1461966+00:00 | 2026-09-29T06:37:17.1461966+08:00 | #83288 - HD4: 480hrs - 21H388 EPIROC PV271LP DRILL | 3.0 | FALSE |  | 2027-09-24T22:00:00+00:00 | 2027-10-14T22:00:00+00:00 | 2027-09-25T06:00:00+08:00 | 2027-10-15T06:00:00+08:00 |  |  |  |  | 480.00 | 21H388 12,000Hr & 24,000Hr Shut On-site TP | Aligned with shut schedule | SDR38827 | [{"equipmentGUID": "defee8bf-7c7b-ee11-a846-000d3acacefd", "code": "21H388", "name": "21H388 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "943570cd-083a-4ee4-a7f6-45ccf4f8d7ef", "emailAddress": "Damion.Kruize@riotinto.com", "displayName": "Kruize, Damion (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | HD4 | Australia/Perth |  | Drills
83295 | 2026-07-01T09:16:27.0195303+00:00 | 2026-07-01T17:16:27.0195303+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:38:20.1404762+00:00 | 2026-09-29T06:38:20.1404762+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334166 | TRUE | TRUE | 2026-09-28T22:38:20.1404762+00:00 | 2026-09-29T06:38:20.1404762+08:00 | #83295 - BM4: 360hrs - 21H251 EPIROC PV271LP DRILL | 3.0 | FALSE |  | 2027-10-16T22:00:00+00:00 | 2027-10-31T22:00:00+00:00 | 2027-10-17T06:00:00+08:00 | 2027-11-01T06:00:00+08:00 |  |  |  |  | 360.00 | 21H251 12,000 PoaP Shut On-site TP | Aligned with shut schedule | SDR25127 | [{"equipmentGUID": "aa0dbdb9-4a8c-ee11-a847-000d3acacefd", "code": "21H251", "name": "21H251 Epiroc PV271LP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "46c26e43-384c-487c-96d5-216dfa8e1884", "emailAddress": "Matthew.VandeVen@riotinto.com", "displayName": "Van de Ven, Matthew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | Drills
83297 | 2026-07-01T09:21:17.2914292+00:00 | 2026-07-01T17:21:17.2914292+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:39:17.3006056+00:00 | 2026-09-29T06:39:17.3006056+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334167 | TRUE | TRUE | 2026-09-28T22:39:17.3006056+00:00 | 2026-09-29T06:39:17.3006056+08:00 | #83297 - GDI: 480hrs - 21B378 CAT MD6250 DRILL | 4.0 | FALSE |  | 2027-11-02T22:00:00+00:00 | 2027-11-22T22:00:00+00:00 | 2027-11-03T06:00:00+08:00 | 2027-11-23T06:00:00+08:00 |  |  |  |  | 480.00 | 21B378 15,000Hr PoaP Shut On-site TP | Aligned with shut schedule | SDR37827 | [{"equipmentGUID": "3834f6bf-7c7b-ee11-a846-000d3acacefd", "code": "21B378", "name": "21B378 CAT MD6250 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | GDI | Australia/Perth |  | Drills
83615 | 2026-07-30T23:52:02.8747959+00:00 | 2026-07-31T07:52:02.8747959+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T22:40:22.2111802+00:00 | 2026-09-29T06:40:22.2111802+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334168 | TRUE | TRUE | 2026-09-28T22:40:22.2111802+00:00 | 2026-09-29T06:40:22.2111802+08:00 | #83615 - MDO: 480hrs - 21H223 ATLAS COPCO PV271 DRILL | 2.0 | FALSE |  | 2027-11-24T22:00:00+00:00 | 2027-12-14T22:00:00+00:00 | 2027-11-25T06:00:00+08:00 | 2027-12-15T06:00:00+08:00 |  |  |  |  | 480.00 | 21H223 Engine Module | Aligned with shut schedule | SDR22327 | [{"equipmentGUID": "af24f0bf-7c7b-ee11-a846-000d3acacefd", "code": "21H223", "name": "21H223 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "ce8ea314-99b4-483c-a906-f74dd1ea1396", "emailAddress": "Robert.Hooper@riotinto.com", "displayName": "Robert Hooper"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | MDO | Australia/Perth |  | Drills
83139 | 2026-06-30T23:44:33.069526+00:00 | 2026-07-01T07:44:33.069526+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-09-28T23:03:28.9509317+00:00 | 2026-09-29T07:03:28.9509317+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334169 | TRUE | TRUE | 2026-09-28T23:03:28.9509317+00:00 | 2026-09-29T07:03:28.9509317+08:00 | #83139 - YAN: 336hrs - 21H221 ATLAS COPCO PV271 DRILL | 5.0 | FALSE |  | 2027-01-07T20:00:00+00:00 | 2027-01-21T20:00:00+00:00 | 2027-01-08T04:00:00+08:00 | 2027-01-22T04:00:00+08:00 |  |  |  |  | 336.00 | 21H221 Eng,PTO,Comp Major Works Shut | 336 hours duration, not 338 | SDR22127 | [{"equipmentGUID": "5233f6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H221", "name": "21H221 Atlas Copco PV271 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "17232fd8-3407-40c5-9b2f-a048e7538a2a", "emailAddress": "John.Lachmaniuk@riotinto.com", "displayName": "John Lachmaniuk"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | YAN | Australia/Perth |  | Drills
83277 | 2026-07-01T05:59:53.1556004+00:00 | 2026-07-01T13:59:53.1556004+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-10-21T23:20:58.3016379+00:00 | 2026-10-22T07:20:58.3016379+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 336276 | TRUE | TRUE | 2026-10-21T23:20:58.3016379+00:00 | 2026-10-22T07:20:58.3016379+08:00 | #83277 - WAN: 480hrs - 21R295 CAT MD6420B DRILL | 6.0 | FALSE |  | 2027-03-28T22:00:00+00:00 | 2027-04-17T22:00:00+00:00 | 2027-03-29T06:00:00+08:00 | 2027-04-18T06:00:00+08:00 |  |  |  |  | 480.00 | 21R295 9,000Hr midlife shut TP | Changed back to original dates due to warden availability | SDR29527 | [{"equipmentGUID": "5913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "21R295", "name": "21R295 CAT MD6420B Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "8f6681f0-5a85-48dd-a3b2-8d055c4000ee", "emailAddress": "Daniel.Walker2@riotinto.com", "displayName": "Walker, Daniel 1 (RTIO)"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | WAN | Australia/Perth |  | Drills
68177 | 2025-06-30T06:51:30.8130678+00:00 | 2025-06-30T14:51:30.8130678+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-07T07:51:53.2445084+00:00 | 2026-07-07T15:51:53.2445084+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 329567 | TRUE | TRUE | 2026-07-07T07:51:53.2445084+00:00 | 2026-07-07T15:51:53.2445084+08:00 | #68177 - WAN: 384hrs - 08R350 CAT D10T2 TRACK DOZER | 9.0 | FALSE |  | 2026-11-23T22:00:00+00:00 | 2026-12-09T22:00:00+00:00 | 2026-11-24T06:00:00+08:00 | 2026-12-10T06:00:00+08:00 |  |  |  |  | 384.00 | Engine, Equaliser Bar, Final Drive, Steering Clutch & Brake | Shut moved out 1 week to align with updated shut schedule | S08R350 | [{"equipmentGUID": "1edbe8bf-7c7b-ee11-a846-000d3acacefd", "code": "08R350", "name": "08R350 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "c44eb75e-8a1f-448e-9911-1320ee0b0575", "emailAddress": "Ashleigh.Royer@riotinto.com", "displayName": "Royer, Ashleigh (RTIO)"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [{"name": "Off Site Repair"}] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
82999 | 2026-06-26T04:21:55.6932662+00:00 | 2026-06-26T12:21:55.6932662+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-10-07T07:11:31.8429135+00:00 | 2026-10-07T15:11:31.8429135+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 335427 | TRUE | TRUE | 2026-10-07T07:11:31.8429135+00:00 | 2026-10-07T15:11:31.8429135+08:00 | #82999 - MDO: 276hrs - 08H126 CAT D11T TRACK DOZER | 3.0 | FALSE |  | 2027-05-31T22:00:00+00:00 | 2027-06-12T10:00:00+00:00 | 2027-06-01T06:00:00+08:00 | 2027-06-12T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut | moved to June due to Trial Engine not at 15,000 hours | SDZ12627 | [{"equipmentGUID": "ce14f0bf-7c7b-ee11-a846-000d3acacefd", "code": "08H126", "name": "08H126 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | MDO | Australia/Perth |  | TP OSR
82998 | 2026-06-26T04:21:55.6097797+00:00 | 2026-06-26T12:21:55.6097797+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-07T03:27:44.57372+00:00 | 2026-09-07T11:27:44.57372+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 333174 | TRUE | TRUE | 2026-09-07T03:27:44.57372+00:00 | 2026-09-07T11:27:44.57372+08:00 | #82998 - MDO: 276hrs - 12H565 CAT 24 MOTOR GRADER | 2.0 | FALSE |  | 2027-01-20T22:00:00+00:00 | 2027-02-01T10:00:00+00:00 | 2027-01-21T06:00:00+08:00 | 2027-02-01T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut | Site requested to swap 12H565 with 08H126 | SGR56527 | [{"equipmentGUID": "15bbf9be-50c3-ee11-a849-000d3acacefd", "code": "12H565", "name": "12H565 CAT 24 Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | MDO | Australia/Perth |  | TP OSR
83043 | 2026-06-26T04:21:55.6992383+00:00 | 2026-06-26T12:21:55.6992383+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-08T23:34:36.3038694+00:00 | 2026-09-09T07:34:36.3038694+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 333248 | TRUE | TRUE | 2026-09-08T23:34:36.3038694+00:00 | 2026-09-09T07:34:36.3038694+08:00 | #83043 - WAN: 276hrs - 08R18 CAT D11T TRACK DOZER | 2.0 | FALSE |  | 2027-04-16T22:00:00+00:00 | 2027-04-28T10:00:00+00:00 | 2027-04-17T06:00:00+08:00 | 2027-04-28T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut | Replaced 08R333 shut in the 2027 shut calendar due to completing shut in 2026 | SDZ01827 | [{"equipmentGUID": "a221f0bf-7c7b-ee11-a846-000d3acacefd", "code": "08R18", "name": "08R18 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83042 | 2026-06-26T04:21:55.6990724+00:00 | 2026-06-26T12:21:55.6990724+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-09T01:15:36.562338+00:00 | 2026-09-09T09:15:36.562338+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 333257 | TRUE | TRUE | 2026-09-09T01:15:36.562338+00:00 | 2026-09-09T09:15:36.562338+08:00 | #83042 - GDI: 276hrs - 08B219 CAT D10T2 TRACK DOZER | 2.0 | FALSE |  | 2027-03-29T22:00:00+00:00 | 2027-04-10T10:00:00+00:00 | 2027-03-30T06:00:00+08:00 | 2027-04-10T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut | Aligned with shut schedule | SDZ21927 | [{"equipmentGUID": "33dae8bf-7c7b-ee11-a846-000d3acacefd", "code": "08B219", "name": "08B219 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | GDI | Australia/Perth |  | TP OSR
83118 | 2026-06-30T05:42:49.5370914+00:00 | 2026-06-30T13:42:49.5370914+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-09T06:34:41.2540994+00:00 | 2026-09-09T14:34:41.2540994+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 333276 | TRUE | TRUE | 2026-09-09T06:34:41.2540994+00:00 | 2026-09-09T14:34:41.2540994+08:00 | #83118 - RVA: 288hrs - 12H220 CAT 16M MOTOR GRADER | 2.0 | FALSE |  | 2027-05-02T22:00:00+00:00 | 2027-05-14T22:00:00+00:00 | 2027-05-03T06:00:00+08:00 | 2027-05-15T06:00:00+08:00 |  |  |  |  | 288.00 | 12,000hr Shut | Pushed to avoid Cyclone season & labour constraints in early Jan | SGR22027 | [{"equipmentGUID": "6bdc00c0-7c7b-ee11-a846-000d3acacefd", "code": "12H220", "name": "12H220 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [{"name": "Off Site Repair"}] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | RVA | Australia/Perth |  | TP OSR
83045 | 2026-06-26T04:21:55.6995321+00:00 | 2026-06-26T12:21:55.6995321+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-29T03:27:07.6687673+00:00 | 2026-09-29T11:27:07.6687673+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334201 | TRUE | TRUE | 2026-09-29T03:27:07.6687673+00:00 | 2026-09-29T11:27:07.6687673+08:00 | #83045 - RVJ: 336hrs - 08R19 CAT D11T TRACK DOZER | 2.0 | FALSE |  | 2027-08-10T22:00:00+00:00 | 2027-08-24T22:00:00+00:00 | 2027-08-11T06:00:00+08:00 | 2027-08-25T06:00:00+08:00 |  |  |  |  | 336.00 | 24,000hr Shut | replaced 12H537 shut to avoid labour and shut bay constraints | SDZ01927 | [{"equipmentGUID": "4c54fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08R19", "name": "08R19 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | RVJ | Australia/Perth |  | TP OSR
84070 | 2026-10-01T01:36:09.6662444+00:00 | 2026-10-01T09:36:09.6662444+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | 2026-10-01T01:36:09.6662444+00:00 | 2026-10-01T09:36:09.6662444+08:00 | {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "displayName": "Barker, Christopher (RTIO)"} | {"name": "HME"} | 334782 | TRUE | TRUE | 2026-10-01T01:36:09.6662444+00:00 | 2026-10-01T09:36:09.6662444+08:00 | #84070 - BM4: 324hrs - 12H217 CAT 16M MOTOR GRADER | 1.0 | FALSE |  | 2027-02-18T22:00:00+00:00 | 2027-03-04T10:00:00+00:00 | 2027-02-19T06:00:00+08:00 | 2027-03-04T18:00:00+08:00 |  |  |  |  | 324.00 | 12,000hr Shut |  | SGR21727 | [{"equipmentGUID": "11e100c0-7c7b-ee11-a846-000d3acacefd", "code": "12H217", "name": "12H217 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 212fb777-fe81-4143-9c36-65e455c17012 | Barker, Christopher (RTIO) | Scheduled | BM4 | Australia/Perth |  | TP OSR
69642 | 2025-10-14T02:10:31.1577033+00:00 | 2025-10-14T10:10:31.1577033+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T04:42:53.9206771+00:00 | 2026-07-03T12:42:53.9206771+08:00 | {"principalGUID": "32e3ae14-fe99-4b7f-a96b-686fd835210b", "displayName": "Walton, Sharleen (RTIO)"} | {"name": "Fixed Plant"} | 329348 | TRUE | TRUE | 2026-07-03T04:42:53.9206771+00:00 | 2026-07-03T12:42:53.9206771+08:00 | #69642 - WTS: 384hrs - CRUSHER - PRIMARY: WTS2 04 | 3.0 | TRUE |  | 2027-02-26T11:00:00+00:00 | 2027-03-14T11:00:00+00:00 | 2027-02-26T19:00:00+08:00 | 2027-03-14T19:00:00+08:00 |  |  |  |  | 384.00 | This shut start 2 day before the Conveyor shut | HG & LG require 24hrs for stockpile dozing, requiring the WTS shut to be completed 48hrs earlier. HG are unable to push their shut 24hrs back as this will cross over with the Nammuldi shut causing issues with accommodation. | SWT2708 | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "588d5f40-8c34-4d90-924a-bdfa80d84f64", "emailAddress": "Tayla.Tadman@riotinto.com", "displayName": "Tadman, Tayla (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 32e3ae14-fe99-4b7f-a96b-686fd835210b | Walton, Sharleen (RTIO) | Scheduled | WTS | Australia/Perth
69724 | 2025-10-14T04:13:16.6760499+00:00 | 2025-10-14T12:13:16.6760499+08:00 | {"principalGUID": "af6a772b-ff36-45cc-943b-b4157ff73947", "displayName": "Machura, Jason (RTIO)"} | 2026-07-03T04:42:53.5161169+00:00 | 2026-07-03T12:42:53.5161169+08:00 | {"principalGUID": "32e3ae14-fe99-4b7f-a96b-686fd835210b", "displayName": "Walton, Sharleen (RTIO)"} | {"name": "Fixed Plant"} | 329346 | TRUE | TRUE | 2026-07-03T04:42:53.5161169+00:00 | 2026-07-03T12:42:53.5161169+08:00 | #69724 - WTS: 384hrs - CRUSHER - PRIMARY: WTS2 04 | 3.0 | TRUE |  | 2027-08-26T11:00:00+00:00 | 2027-09-11T11:00:00+00:00 | 2027-08-26T19:00:00+08:00 | 2027-09-11T19:00:00+08:00 |  |  |  |  | 384.00 | This Shut is 2 days before the conveyor Shut | HG & LG require 48hrs for stockpile dozing, requiring the WTS shut to be completed 48hrs earlier. HG are unable to push their shut 48hrs back as this will cross over with the Nammuldi shut causing issues with accommodation. | SWT2734 | [{"equipmentGUID": "09efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "WTS2PCS04", "name": "Crusher - Primary: WTS2 04", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "588d5f40-8c34-4d90-924a-bdfa80d84f64", "emailAddress": "Tayla.Tadman@riotinto.com", "displayName": "Tadman, Tayla (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 32e3ae14-fe99-4b7f-a96b-686fd835210b | Walton, Sharleen (RTIO) | Scheduled | WTS | Australia/Perth
44965 | 2021-12-01T00:54:40+00:00 | 2021-12-01T08:54:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:42:53.7203049+00:00 | 2026-07-03T12:42:53.7203049+08:00 | {"principalGUID": "32e3ae14-fe99-4b7f-a96b-686fd835210b", "displayName": "Walton, Sharleen (RTIO)"} | {"name": "Fixed Plant"} | 329347 | TRUE | TRUE | 2026-07-03T04:42:53.7203049+00:00 | 2026-07-03T12:42:53.7203049+08:00 | #44965 - WTS: 336hrs - CONVEYOR: WTS1 OVERLAND & CRUSHER - PRIMARY: WTS1 03 | 12.0 | TRUE |  | 2027-02-28T11:00:00+00:00 | 2027-03-14T11:00:00+00:00 | 2027-02-28T19:00:00+08:00 | 2027-03-14T19:00:00+08:00 |  |  |  |  | 336.00 | WTS1 PLT PC4 | HG & LG require 24hrs for stockpile dozing, requiring the WTS shut to be completed 48hrs earlier. HG are unable to push their shut 24hrs back as this will cross over with the Nammuldi shut causing issues with accommodation. |  | [{"equipmentGUID": "185e242f-6f9d-ee11-a847-000d3acacefd", "code": "WTS1CVOLCV", "name": "Conveyor: WTS1 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "588d5f40-8c34-4d90-924a-bdfa80d84f64", "emailAddress": "Tayla.Tadman@riotinto.com", "displayName": "Tadman, Tayla (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 32e3ae14-fe99-4b7f-a96b-686fd835210b | Walton, Sharleen (RTIO) | Scheduled | WTS | Australia/Perth
44967 | 2021-12-01T00:55:50+00:00 | 2021-12-01T08:55:50+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-07-03T04:42:53.3244057+00:00 | 2026-07-03T12:42:53.3244057+08:00 | {"principalGUID": "32e3ae14-fe99-4b7f-a96b-686fd835210b", "displayName": "Walton, Sharleen (RTIO)"} | {"name": "Fixed Plant"} | 329345 | TRUE | TRUE | 2026-07-03T04:42:53.3244057+00:00 | 2026-07-03T12:42:53.3244057+08:00 | #44967 - WTS: 336hrs - CONVEYOR: WTS1 OVERLAND & CRUSHER - PRIMARY: WTS1 03 | 12.0 | TRUE |  | 2027-08-28T11:00:00+00:00 | 2027-09-11T11:00:00+00:00 | 2027-08-28T19:00:00+08:00 | 2027-09-11T19:00:00+08:00 |  |  |  |  | 336.00 | WTS1 PLT PC4 | HG & LG require 48hrs for stockpile dozing, requiring the WTS shut to be completed 48hrs earlier. HG are unable to push their shut 48hrs back as this will cross over with the Nammuldi shut causing issues with accommodation. |  | [{"equipmentGUID": "185e242f-6f9d-ee11-a847-000d3acacefd", "code": "WTS1CVOLCV", "name": "Conveyor: WTS1 Overland", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "f863fbbf-7c7b-ee11-a846-000d3acacefd", "code": "WTS1PCS03", "name": "Crusher - Primary: WTS1 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "588d5f40-8c34-4d90-924a-bdfa80d84f64", "emailAddress": "Tayla.Tadman@riotinto.com", "displayName": "Tadman, Tayla (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 32e3ae14-fe99-4b7f-a96b-686fd835210b | Walton, Sharleen (RTIO) | Scheduled | WTS | Australia/Perth
84048 | 2026-09-30T04:28:23.9209597+00:00 | 2026-09-30T12:28:23.9209597+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-15T23:27:43.7830122+00:00 | 2026-10-16T07:27:43.7830122+08:00 | {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "displayName": "Norman, Mathew (RTIO)"} | {"name": "Fixed Plant"} | 336135 | TRUE | TRUE | 2026-10-15T23:27:43.7830122+00:00 | 2026-10-16T07:27:43.7830122+08:00 | #84048 - EII: 36hrs - FUNCTIONAL SAFETY ST1EN/TP10EN - STANDALONE OUTAGE | 1.2 | FALSE |  | 2027-03-16T23:00:00+00:00 | 2027-03-18T11:00:00+00:00 | 2027-03-17T07:00:00+08:00 | 2027-03-18T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP10EN - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 7172c8e6-79de-4399-b1c7-67ea821d77d1 | Norman, Mathew (RTIO) | Scheduled | EII | Australia/Perth
65352 | 2024-10-14T05:15:55+00:00 | 2024-10-14T13:15:55+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-17T00:58:58.4341808+00:00 | 2025-10-17T08:58:58.4341808+08:00 | {"principalGUID": "ea26abb5-c1b5-44e2-b036-9bc36d15f619", "displayName": "Hill, Damian (RTIO)"} | {"name": "Fixed Plant"} | 259854 | TRUE | TRUE | 2025-10-17T00:58:58.4341808+00:00 | 2025-10-17T08:58:58.4341808+08:00 | #65352 - BM4: 126hrs - BS1 PROJECT SHUT #8 PC2 | 7.0 | TRUE |  | 2026-12-31T22:00:00+00:00 | 2027-01-06T04:00:00+00:00 | 2027-01-01T06:00:00+08:00 | 2027-01-06T12:00:00+08:00 |  |  |  |  | 126.00 | Shut #8 BCV210 idler installation #7 / Surge Bin BIN-0132 CNV0131 OLC tie-in | IAM Refresh |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "12196416-07ec-46a3-b856-b91b454874c3", "emailAddress": "Dean.Allbon@riotinto.com", "displayName": "Dean Allbon"}}] | [] | [] | [] | [{"code": "X", "name": "BS1 Project", "projectTeam": {"name": "D&T"}, "totalProjectTime": "96"}] | [] | Approved | Update | ea26abb5-c1b5-44e2-b036-9bc36d15f619 | Hill, Damian (RTIO) | Major Projects | BM4 | Australia/Perth
42169 | 2021-07-06T01:48:35+00:00 | 2021-07-06T09:48:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2025-10-08T04:53:02.9810186+00:00 | 2025-10-08T12:53:02.9810186+08:00 | {"principalGUID": "ea26abb5-c1b5-44e2-b036-9bc36d15f619", "displayName": "Hill, Damian (RTIO)"} | {"name": "Fixed Plant"} | 247530 | TRUE | TRUE | 2025-10-08T04:53:02.9810186+00:00 | 2025-10-08T12:53:02.9810186+08:00 | #42169 - MTP: 168hrs - TRAIN LOADOUT: MTP FINES | 5.0 | TRUE |  | 2026-12-02T11:00:00+00:00 | 2026-12-09T11:00:00+00:00 | 2026-12-02T19:00:00+08:00 | 2026-12-09T19:00:00+08:00 |  |  |  |  | 168.00 | Fines TLO shut | TLO1 not required |  | [{"equipmentGUID": "9217ee47-4b9a-ee11-a847-000d3acacefd", "code": "MTPTLOFINES", "name": "Train Loadout: MTP Fines", "assetClass": {"name": "Train Loadout"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f3c5e679-56ef-439c-830c-16d07071207a", "emailAddress": "Simon.Davidson@riotinto.com", "displayName": "Simon Davidson"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2219012e-e329-43e5-a8d7-7b27d4d84863", "emailAddress": "Isaac.Raso@riotinto.com", "displayName": "Isaac Raso"}}] | [] | [] | [] | [] | [] | Approved | Update | ea26abb5-c1b5-44e2-b036-9bc36d15f619 | Hill, Damian (RTIO) | Scheduled | MTP | Australia/Perth
84003 | 2026-09-28T04:42:28.5593179+00:00 | 2026-09-28T12:42:28.5593179+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | 2026-10-01T00:54:43.2037279+00:00 | 2026-10-01T08:54:43.2037279+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | {"name": "Fixed Plant"} | 334767 | TRUE | TRUE | 2026-10-01T00:54:43.2037279+00:00 | 2026-10-01T08:54:43.2037279+08:00 | #84003 - EII: 72hrs - CONVEYOR: EII 12E | 1.0 | FALSE |  | 2027-01-14T23:00:00+00:00 | 2027-01-17T23:00:00+00:00 | 2027-01-15T07:00:00+08:00 | 2027-01-18T07:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Shut |  |  | [{"equipmentGUID": "d627f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV12E", "name": "Conveyor: EII 12E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "emailAddress": "Kate.Wilson2@riotinto.com", "displayName": "Wilson, Kate (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 207e44ab-ed47-451d-af8f-78397723d3cd | Wilson, Kate (RTIO) | Scheduled | EII | Australia/Perth
84000 | 2026-09-27T23:41:21.3276372+00:00 | 2026-09-28T07:41:21.3276372+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | 2026-09-28T02:15:34.5719565+00:00 | 2026-09-28T10:15:34.5719565+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | {"name": "Fixed Plant"} | 334141 | TRUE | TRUE | 2026-09-28T02:15:34.5719565+00:00 | 2026-09-28T10:15:34.5719565+08:00 | #84000 - EII: 72hrs - CONVEYOR: EII 30E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Shut |  |  | [{"equipmentGUID": "12d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV30E", "name": "Conveyor: EII 30E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1c982aa6-85bd-4180-8138-4f708cadd1dc", "emailAddress": "Dean.Lombardo@riotinto.com", "displayName": "Lombardo, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 207e44ab-ed47-451d-af8f-78397723d3cd | Wilson, Kate (RTIO) | Scheduled | EII | Australia/Perth
84001 | 2026-09-27T23:44:07.2134829+00:00 | 2026-09-28T07:44:07.2134829+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | 2026-09-28T02:15:34.8376522+00:00 | 2026-09-28T10:15:34.8376522+08:00 | {"principalGUID": "207e44ab-ed47-451d-af8f-78397723d3cd", "displayName": "Wilson, Kate (RTIO)"} | {"name": "Fixed Plant"} | 334142 | TRUE | TRUE | 2026-09-28T02:15:34.8376522+00:00 | 2026-09-28T10:15:34.8376522+08:00 | #84001 - EII: 72hrs - CONVEYOR: EII 32E | 1.0 | FALSE |  | 2027-01-03T23:00:00+00:00 | 2027-01-06T23:00:00+00:00 | 2027-01-04T07:00:00+08:00 | 2027-01-07T07:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Shut |  |  | [{"equipmentGUID": "16d200c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV32E", "name": "Conveyor: EII 32E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "1c982aa6-85bd-4180-8138-4f708cadd1dc", "emailAddress": "Dean.Lombardo@riotinto.com", "displayName": "Lombardo, Dean (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 207e44ab-ed47-451d-af8f-78397723d3cd | Wilson, Kate (RTIO) | Scheduled | EII | Australia/Perth
83755 | 2026-08-25T04:59:20.4513165+00:00 | 2026-08-25T12:59:20.4513165+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | 2026-09-01T23:43:06.4211468+00:00 | 2026-09-02T07:43:06.4211468+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332416 | TRUE | TRUE | 2026-09-01T23:43:06.4211468+00:00 | 2026-09-02T07:43:06.4211468+08:00 | #83755 - RVJ: 366hrs - 07R45 KOMATSU WA1200-6 WHEEL LOADER | 1.2 | FALSE |  | 2027-01-29T22:00:00+00:00 | 2027-02-14T04:00:00+00:00 | 2027-01-30T06:00:00+08:00 | 2027-02-14T12:00:00+08:00 |  |  |  |  | 366.00 | 14,000hr Shut |  | SLD04527 | [{"equipmentGUID": "8862fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07R45", "name": "07R45 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "emailAddress": "Nebojsa.Milosevic@riotinto.com", "displayName": "Milosevic, Nebojsa (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | L-East
83759 | 2026-08-25T05:06:25.320036+00:00 | 2026-08-25T13:06:25.320036+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | 2026-08-28T06:49:40.916303+00:00 | 2026-08-28T14:49:40.916303+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332206 | TRUE | TRUE | 2026-08-28T06:49:40.916303+00:00 | 2026-08-28T14:49:40.916303+08:00 | #83759 - WAN: 336hrs - 12R486 CAT 24M MOTOR GRADER | 1.1 | FALSE |  | 2027-03-31T22:00:00+00:00 | 2027-04-14T22:00:00+00:00 | 2027-04-01T06:00:00+08:00 | 2027-04-15T06:00:00+08:00 |  |  |  |  | 336.00 | 24,000hr Shut |  | SGR48627 | [{"equipmentGUID": "9675fbbf-7c7b-ee11-a846-000d3acacefd", "code": "12R486", "name": "12R486 CAT 24M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83758 | 2026-08-25T05:05:12.9201047+00:00 | 2026-08-25T13:05:12.9201047+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | 2026-08-28T06:53:29.3092465+00:00 | 2026-08-28T14:53:29.3092465+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332220 | TRUE | TRUE | 2026-08-28T06:53:29.3092465+00:00 | 2026-08-28T14:53:29.3092465+08:00 | #83758 - WAN: 336hrs - 12R470 CAT 24M MOTOR GRADER | 1.1 | FALSE |  | 2027-01-06T22:00:00+00:00 | 2027-01-20T22:00:00+00:00 | 2027-01-07T06:00:00+08:00 | 2027-01-21T06:00:00+08:00 |  |  |  |  | 336.00 | 24,000hr Shut |  | SGR47027 | [{"equipmentGUID": "4b23f0bf-7c7b-ee11-a846-000d3acacefd", "code": "12R470", "name": "12R470 CAT 24M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "212fb777-fe81-4143-9c36-65e455c17012", "emailAddress": "Christopher.Barker2@riotinto.com", "displayName": "Barker, Christopher (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83757 | 2026-08-25T05:03:32.755074+00:00 | 2026-08-25T13:03:32.755074+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | 2026-08-28T13:33:15.3571314+00:00 | 2026-08-28T21:33:15.3571314+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332323 | TRUE | TRUE | 2026-08-28T13:33:15.3571314+00:00 | 2026-08-28T21:33:15.3571314+08:00 | #83757 - MTP: 192hrs - 07H187 CAT 992K WHEEL LOADER | 1.1 | FALSE |  | 2027-06-06T16:00:00+00:00 | 2027-06-14T16:00:00+00:00 | 2027-06-07T00:00:00+08:00 | 2027-06-15T00:00:00+08:00 |  |  |  |  | 192.00 | Eng & Axles |  | SLD18727 | [{"equipmentGUID": "405afbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H187", "name": "07H187 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "emailAddress": "Nathan.Goodgame@riotinto.com", "displayName": "Goodgame, Nathan (RTIO)"}}] | [] | [] | [{"name": "Axle Assembly Changeout"}, {"name": "Engine Changeout"}] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | L-West
83756 | 2026-08-25T05:01:40.5824386+00:00 | 2026-08-25T13:01:40.5824386+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | 2026-08-28T13:30:29.3245079+00:00 | 2026-08-28T21:30:29.3245079+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332314 | TRUE | TRUE | 2026-08-28T13:30:29.3245079+00:00 | 2026-08-28T21:30:29.3245079+08:00 | #83756 - MTP: 192hrs - 07H377 CAT 992K WHEEL LOADER | 1.1 | FALSE |  | 2027-03-05T16:00:00+00:00 | 2027-03-13T16:00:00+00:00 | 2027-03-06T00:00:00+08:00 | 2027-03-14T00:00:00+08:00 |  |  |  |  | 192.00 | Trans & Axles |  | SLD37727 | [{"equipmentGUID": "1d62fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H377", "name": "07H377 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "emailAddress": "Nathan.Goodgame@riotinto.com", "displayName": "Goodgame, Nathan (RTIO)"}}] | [] | [] | [{"name": "Axle Assembly Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | L-East
83366 | 2026-07-02T05:55:49.5816317+00:00 | 2026-07-02T13:55:49.5816317+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-09-09T22:23:42.4836491+00:00 | 2026-09-10T06:23:42.4836491+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 333295 | TRUE | TRUE | 2026-09-09T22:23:42.4836491+00:00 | 2026-09-10T06:23:42.4836491+08:00 | #83366 - WAN: 288hrs - 07R203 LETOURNEAU L2350 II WHEEL LOADER | 1.3 | FALSE |  | 2027-01-13T04:00:00+00:00 | 2027-01-25T04:00:00+00:00 | 2027-01-13T12:00:00+08:00 | 2027-01-25T12:00:00+08:00 |  |  |  |  | 288.00 | 07R203 - 12500 Midlife shut |  | SLD20327 | [{"equipmentGUID": "a42ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "07R203", "name": "07R203 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-East
83692 | 2026-08-14T01:23:12.7143015+00:00 | 2026-08-14T09:23:12.7143015+08:00 | {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "displayName": "Barlow, Scott A (RTIO)"} | 2026-08-28T08:27:53.4336953+00:00 | 2026-08-28T16:27:53.4336953+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332308 | TRUE | TRUE | 2026-08-28T08:27:53.4336953+00:00 | 2026-08-28T16:27:53.4336953+08:00 | #83692 - YAN: 288hrs - 08H145 CAT 854K WHEEL DOZER | 1.3 | FALSE |  | 2027-05-25T22:00:00+00:00 | 2027-06-06T22:00:00+00:00 | 2027-05-26T06:00:00+08:00 | 2027-06-07T06:00:00+08:00 |  |  |  |  | 288.00 | 36000 hour shut |  | SWD14527 | [{"equipmentGUID": "f1f5e8bf-7c7b-ee11-a846-000d3acacefd", "code": "08H145", "name": "08H145 CAT 854K Wheel Dozer", "assetClass": {"name": "Dozer - Wheeled"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "19ce4f54-f5b4-4bb6-9238-7d3a07e06fbc", "emailAddress": "scott.barlow@riotinto.com", "displayName": "Barlow, Scott A (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | L-East
68261 | 2025-06-30T07:55:13.2220077+00:00 | 2025-06-30T15:55:13.2220077+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-24T04:43:28.5898525+00:00 | 2026-09-24T12:43:28.5898525+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 334076 | TRUE | TRUE | 2026-09-24T04:43:28.5898525+00:00 | 2026-09-24T12:43:28.5898525+08:00 | #68261 - BM2: 216hrs - 15H415 HITACHI EX5600-7BH EXCAVATOR | 4.0 | FALSE |  | 2027-02-04T16:00:00+00:00 | 2027-02-13T16:00:00+00:00 | 2027-02-05T00:00:00+08:00 | 2027-02-14T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing | date correction | SSX41527 | [{"equipmentGUID": "e073fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H415", "name": "15H415 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | D-West
83054 | 2026-06-26T04:51:51.0288438+00:00 | 2026-06-26T12:51:51.0288438+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:55:46.1599222+00:00 | 2026-08-28T14:55:46.1599222+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332228 | TRUE | TRUE | 2026-08-28T06:55:46.1599222+00:00 | 2026-08-28T14:55:46.1599222+08:00 | #83054 - WAN: 240hrs - 08H344 CAT 854 WHEEL DOZER | 1.2 | FALSE |  | 2027-11-04T22:00:00+00:00 | 2027-11-14T22:00:00+00:00 | 2027-11-05T06:00:00+08:00 | 2027-11-15T06:00:00+08:00 |  |  |  |  | 240.00 | 18,000hr Shut |  | SWD34427 | [{"equipmentGUID": "d0266f74-3a43-ef11-a84f-000d3acacefd", "code": "08H344", "name": "08H344 CAT 854 Wheel Dozer", "assetClass": {"name": "Dozer - Wheeled"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-West
83023 | 2026-06-26T04:21:55.6964616+00:00 | 2026-06-26T12:21:55.6964616+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:50:17.5962179+00:00 | 2026-08-28T14:50:17.5962179+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332208 | TRUE | TRUE | 2026-08-28T06:50:17.5962179+00:00 | 2026-08-28T14:50:17.5962179+08:00 | #83023 - WAN: 276hrs - 08R212 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-03-15T22:00:00+00:00 | 2027-03-27T10:00:00+00:00 | 2027-03-16T06:00:00+08:00 | 2027-03-27T18:00:00+08:00 |  |  |  |  | 276.00 | 12.000hr Shut |  | SDZ21227 | [{"equipmentGUID": "98de00c0-7c7b-ee11-a846-000d3acacefd", "code": "08R212", "name": "08R212 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83002 | 2026-06-26T04:21:55.6940919+00:00 | 2026-06-26T12:21:55.6940919+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:50:33.1981549+00:00 | 2026-08-28T14:50:33.1981549+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332209 | TRUE | TRUE | 2026-08-28T06:50:33.1981549+00:00 | 2026-08-28T14:50:33.1981549+08:00 | #83002 - YAN: 324hrs - 08H704 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-03-11T16:00:00+00:00 | 2027-03-25T04:00:00+00:00 | 2027-03-12T00:00:00+08:00 | 2027-03-25T12:00:00+08:00 |  |  |  |  | 324.00 | 30,000hr Shut |  | SDZ70427 | [{"equipmentGUID": "3c64fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08H704", "name": "08H704 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | TP OSR
83022 | 2026-06-26T04:21:55.696372+00:00 | 2026-06-26T12:21:55.696372+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:51:01.3102926+00:00 | 2026-08-28T14:51:01.3102926+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332211 | TRUE | TRUE | 2026-08-28T06:51:01.3102926+00:00 | 2026-08-28T14:51:01.3102926+08:00 | #83022 - MDO: 324hrs - 08H127 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-02-25T22:00:00+00:00 | 2027-03-11T10:00:00+00:00 | 2027-02-26T06:00:00+08:00 | 2027-03-11T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SDZ12727 | [{"equipmentGUID": "9e05f0bf-7c7b-ee11-a846-000d3acacefd", "code": "08H127", "name": "08H127 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | TP OSR
83001 | 2026-06-26T04:21:55.6938537+00:00 | 2026-06-26T12:21:55.6938537+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:51:16.8709175+00:00 | 2026-08-28T14:51:16.8709175+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332212 | TRUE | TRUE | 2026-08-28T06:51:16.8709175+00:00 | 2026-08-28T14:51:16.8709175+08:00 | #83001 - YAN: 276hrs - 08H345 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-02-23T16:00:00+00:00 | 2027-03-07T04:00:00+00:00 | 2027-02-24T00:00:00+08:00 | 2027-03-07T12:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ34527 | [{"equipmentGUID": "f0ece8bf-7c7b-ee11-a846-000d3acacefd", "code": "08H345", "name": "08H345 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | TP OSR
83021 | 2026-06-26T04:21:55.6962862+00:00 | 2026-06-26T12:21:55.6962862+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:51:36.0883826+00:00 | 2026-08-28T14:51:36.0883826+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332213 | TRUE | TRUE | 2026-08-28T06:51:36.0883826+00:00 | 2026-08-28T14:51:36.0883826+08:00 | #83021 - WAN: 276hrs - 08R351 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-02-09T22:00:00+00:00 | 2027-02-21T10:00:00+00:00 | 2027-02-10T06:00:00+08:00 | 2027-02-21T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ35127 | [{"equipmentGUID": "691ff0bf-7c7b-ee11-a846-000d3acacefd", "code": "08R351", "name": "08R351 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83000 | 2026-06-26T04:21:55.6936451+00:00 | 2026-06-26T12:21:55.6936451+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:51:51.003218+00:00 | 2026-08-28T14:51:51.003218+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332214 | TRUE | TRUE | 2026-08-28T06:51:51.003218+00:00 | 2026-08-28T14:51:51.003218+08:00 | #83000 - HD4: 324hrs - 12D531 CAT 24 MOTOR GRADER | 1.2 | FALSE |  | 2027-02-05T22:00:00+00:00 | 2027-02-19T10:00:00+00:00 | 2027-02-06T06:00:00+08:00 | 2027-02-19T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR53127 | [{"equipmentGUID": "7228f6bf-7c7b-ee11-a846-000d3acacefd", "code": "12D531", "name": "12D531 CAT 24 Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | TP OSR
83020 | 2026-06-26T04:21:55.6961967+00:00 | 2026-06-26T12:21:55.6961967+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:52:22.0101387+00:00 | 2026-08-28T14:52:22.0101387+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332216 | TRUE | TRUE | 2026-08-28T06:52:22.0101387+00:00 | 2026-08-28T14:52:22.0101387+08:00 | #83020 - GDI: 276hrs - 08B354 CAT D11 TRACK DOZER | 1.2 | FALSE |  | 2027-01-24T22:00:00+00:00 | 2027-02-05T10:00:00+00:00 | 2027-01-25T06:00:00+08:00 | 2027-02-05T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ35427 | [{"equipmentGUID": "75d900c0-7c7b-ee11-a846-000d3acacefd", "code": "08B354", "name": "08B354 CAT D11 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | TP OSR
83038 | 2026-06-26T04:21:55.6983263+00:00 | 2026-06-26T12:21:55.6983263+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:37:18.4609704+00:00 | 2026-08-28T14:37:18.4609704+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332178 | TRUE | TRUE | 2026-08-28T06:37:18.4609704+00:00 | 2026-08-28T14:37:18.4609704+08:00 | #83038 - RVJ: 276hrs - 08H308 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-12-08T22:00:00+00:00 | 2027-12-20T10:00:00+00:00 | 2027-12-09T06:00:00+08:00 | 2027-12-20T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ30827 | [{"equipmentGUID": "042cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "08H308", "name": "08H308 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | TP OSR
83018 | 2026-06-26T04:21:55.6960175+00:00 | 2026-06-26T12:21:55.6960175+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:37:34.0099875+00:00 | 2026-08-28T14:37:34.0099875+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332179 | TRUE | TRUE | 2026-08-28T06:37:34.0099875+00:00 | 2026-08-28T14:37:34.0099875+08:00 | #83018 - YAN: 324hrs - 08H238 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-12-06T22:00:00+00:00 | 2027-12-20T10:00:00+00:00 | 2027-12-07T06:00:00+08:00 | 2027-12-20T18:00:00+08:00 |  |  |  |  | 324.00 | 30,000hr Shut |  | SDZ23827 | [{"equipmentGUID": "cb36f6bf-7c7b-ee11-a846-000d3acacefd", "code": "08H238", "name": "08H238 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | TP OSR
83037 | 2026-06-26T04:21:55.6981538+00:00 | 2026-06-26T12:21:55.6981538+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:37:48.0184451+00:00 | 2026-08-28T14:37:48.0184451+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332180 | TRUE | TRUE | 2026-08-28T06:37:48.0184451+00:00 | 2026-08-28T14:37:48.0184451+08:00 | #83037 - RVA: 276hrs - 08R373 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-11-22T22:00:00+00:00 | 2027-12-04T10:00:00+00:00 | 2027-11-23T06:00:00+08:00 | 2027-12-04T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ37327 | [{"equipmentGUID": "cdbbf9be-50c3-ee11-a849-000d3acacefd", "code": "08R373", "name": "08R373 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVA | Australia/Perth |  | TP OSR
83036 | 2026-06-26T04:21:55.6979835+00:00 | 2026-06-26T12:21:55.6979835+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:38:01.0661983+00:00 | 2026-08-28T14:38:01.0661983+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332181 | TRUE | TRUE | 2026-08-28T06:38:01.0661983+00:00 | 2026-08-28T14:38:01.0661983+08:00 | #83036 - NBWT: 276hrs - 08H358 CAT D11 TRACK DOZER | 1.2 | FALSE |  | 2027-11-06T22:00:00+00:00 | 2027-11-18T10:00:00+00:00 | 2027-11-07T06:00:00+08:00 | 2027-11-18T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ35827 | [{"equipmentGUID": "eae9529e-80cc-ee11-a849-000d3acacefd", "code": "08H358", "name": "08H358 CAT D11 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | TP OSR
83016 | 2026-06-26T04:21:55.6958305+00:00 | 2026-06-26T12:21:55.6958305+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:38:16.5501358+00:00 | 2026-08-28T14:38:16.5501358+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332182 | TRUE | TRUE | 2026-08-28T06:38:16.5501358+00:00 | 2026-08-28T14:38:16.5501358+08:00 | #83016 - RVJ: 276hrs - 12R534 CAT 24 MOTOR GRADER | 1.2 | FALSE |  | 2027-11-02T22:00:00+00:00 | 2027-11-14T10:00:00+00:00 | 2027-11-03T06:00:00+08:00 | 2027-11-14T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SGR53427 | [{"equipmentGUID": "36d200c0-7c7b-ee11-a846-000d3acacefd", "code": "12R534", "name": "12R534 CAT 24 Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | TP OSR
83015 | 2026-06-26T04:21:55.6957257+00:00 | 2026-06-26T12:21:55.6957257+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:38:30.3665386+00:00 | 2026-08-28T14:38:30.3665386+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332183 | TRUE | TRUE | 2026-08-28T06:38:30.3665386+00:00 | 2026-08-28T14:38:30.3665386+08:00 | #83015 - GDI: 324hrs - 12B522 CAT 18 GRADER | 1.2 | FALSE |  | 2027-10-15T22:00:00+00:00 | 2027-10-29T10:00:00+00:00 | 2027-10-16T06:00:00+08:00 | 2027-10-29T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR52227 | [{"equipmentGUID": "0d60fbbf-7c7b-ee11-a846-000d3acacefd", "code": "12B522", "name": "12B522 CAT 18 Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | TP OSR
83014 | 2026-06-26T04:21:55.6955784+00:00 | 2026-06-26T12:21:55.6955784+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:38:43.806908+00:00 | 2026-08-28T14:38:43.806908+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332184 | TRUE | TRUE | 2026-08-28T06:38:43.806908+00:00 | 2026-08-28T14:38:43.806908+08:00 | #83014 - GDI: 324hrs - 12B523 CAT 18 GRADER | 1.2 | FALSE |  | 2027-09-27T22:00:00+00:00 | 2027-10-11T10:00:00+00:00 | 2027-09-28T06:00:00+08:00 | 2027-10-11T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR52327 | [{"equipmentGUID": "d71cf0bf-7c7b-ee11-a846-000d3acacefd", "code": "12B523", "name": "12B523 CAT 18 Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | TP OSR
83033 | 2026-06-26T04:21:55.6976488+00:00 | 2026-06-26T12:21:55.6976488+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:38:55.3019204+00:00 | 2026-08-28T14:38:55.3019204+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332185 | TRUE | TRUE | 2026-08-28T06:38:55.3019204+00:00 | 2026-08-28T14:38:55.3019204+08:00 | #83033 - MDO: 324hrs - 12H446 CAT 24M MOTOR GRADER | 1.2 | FALSE |  | 2027-09-13T22:00:00+00:00 | 2027-09-27T10:00:00+00:00 | 2027-09-14T06:00:00+08:00 | 2027-09-27T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR44627 | [{"equipmentGUID": "e9f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "12H446", "name": "12H446 CAT 24M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | TP OSR
83013 | 2026-06-26T04:21:55.6953592+00:00 | 2026-06-26T12:21:55.6953592+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:39:13.915835+00:00 | 2026-08-28T14:39:13.915835+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332186 | TRUE | TRUE | 2026-08-28T06:39:13.915835+00:00 | 2026-08-28T14:39:13.915835+08:00 | #83013 - NBWT: 276hrs - 12H416 CAT 24M MOTOR GRADER | 1.2 | FALSE |  | 2027-09-11T22:00:00+00:00 | 2027-09-23T10:00:00+00:00 | 2027-09-12T06:00:00+08:00 | 2027-09-23T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SGR41627 | [{"equipmentGUID": "e815f0bf-7c7b-ee11-a846-000d3acacefd", "code": "12H416", "name": "12H416 CAT 24M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | TP OSR
83032 | 2026-06-26T04:21:55.6974562+00:00 | 2026-06-26T12:21:55.6974562+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:39:28.7740693+00:00 | 2026-08-28T14:39:28.7740693+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332187 | TRUE | TRUE | 2026-08-28T06:39:28.7740693+00:00 | 2026-08-28T14:39:28.7740693+08:00 | #83032 - RVJ: 276hrs - 08B221 CAT D10T2 TRACK DOZER | 1.2 | FALSE |  | 2027-08-28T22:00:00+00:00 | 2027-09-09T10:00:00+00:00 | 2027-08-29T06:00:00+08:00 | 2027-09-09T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ22127 | [{"equipmentGUID": "1c69fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08B221", "name": "08B221 CAT D10T2 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | TP OSR
83012 | 2026-06-26T04:21:55.6952184+00:00 | 2026-06-26T12:21:55.6952184+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:39:43.8570608+00:00 | 2026-08-28T14:39:43.8570608+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332188 | TRUE | TRUE | 2026-08-28T06:39:43.8570608+00:00 | 2026-08-28T14:39:43.8570608+08:00 | #83012 - YAN: 276hrs - 08H115 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-08-26T22:00:00+00:00 | 2027-09-07T10:00:00+00:00 | 2027-08-27T06:00:00+08:00 | 2027-09-07T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SDZ11527 | [{"equipmentGUID": "d6d300c0-7c7b-ee11-a846-000d3acacefd", "code": "08H115", "name": "08H115 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | TP OSR
83011 | 2026-06-26T04:21:55.6951055+00:00 | 2026-06-26T12:21:55.6951055+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:40:11.0909872+00:00 | 2026-08-28T14:40:11.0909872+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332189 | TRUE | TRUE | 2026-08-28T06:40:11.0909872+00:00 | 2026-08-28T14:40:11.0909872+08:00 | #83011 - MDO: 324hrs - 08H131 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-08-08T22:00:00+00:00 | 2027-08-22T10:00:00+00:00 | 2027-08-09T06:00:00+08:00 | 2027-08-22T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SDZ13127 | [{"equipmentGUID": "1846f6bf-7c7b-ee11-a846-000d3acacefd", "code": "08H131", "name": "08H131 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | TP OSR
83030 | 2026-06-26T04:21:55.6971328+00:00 | 2026-06-26T12:21:55.6971328+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:40:31.0923775+00:00 | 2026-08-28T14:40:31.0923775+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332190 | TRUE | TRUE | 2026-08-28T06:40:31.0923775+00:00 | 2026-08-28T14:40:31.0923775+08:00 | #83030 - GDI: 276hrs - 08B355 CAT D11 TRACK DOZER | 1.2 | FALSE |  | 2027-07-25T22:00:00+00:00 | 2027-08-06T10:00:00+00:00 | 2027-07-26T06:00:00+08:00 | 2027-08-06T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ35527 | [{"equipmentGUID": "7752fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08B355", "name": "08B355 CAT D11 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | TP OSR
83010 | 2026-06-26T04:21:55.6950005+00:00 | 2026-06-26T12:21:55.6950005+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:42:04.7411641+00:00 | 2026-08-28T14:42:04.7411641+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332191 | TRUE | TRUE | 2026-08-28T06:42:04.7411641+00:00 | 2026-08-28T14:42:04.7411641+08:00 | #83010 - BM2: 276hrs - 12H206 CAT 16M MOTOR GRADER | 1.2 | FALSE |  | 2027-07-23T22:00:00+00:00 | 2027-08-04T10:00:00+00:00 | 2027-07-24T06:00:00+08:00 | 2027-08-04T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SGR20627 | [{"equipmentGUID": "4864fbbf-7c7b-ee11-a846-000d3acacefd", "code": "12H206", "name": "12H206 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | TP OSR
83029 | 2026-06-26T04:21:55.6970453+00:00 | 2026-06-26T12:21:55.6970453+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:45:29.7613694+00:00 | 2026-08-28T14:45:29.7613694+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332192 | TRUE | TRUE | 2026-08-28T06:45:29.7613694+00:00 | 2026-08-28T14:45:29.7613694+08:00 | #83029 - WAN: 276hrs - 08R161 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-07-09T22:00:00+00:00 | 2027-07-21T10:00:00+00:00 | 2027-07-10T06:00:00+08:00 | 2027-07-21T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SDZ16127 | [{"equipmentGUID": "aa41f6bf-7c7b-ee11-a846-000d3acacefd", "code": "08R161", "name": "08R161 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83009 | 2026-06-26T04:21:55.6948971+00:00 | 2026-06-26T12:21:55.6948971+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:45:50.4322364+00:00 | 2026-08-28T14:45:50.4322364+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332193 | TRUE | TRUE | 2026-08-28T06:45:50.4322364+00:00 | 2026-08-28T14:45:50.4322364+08:00 | #83009 - NBWT: 276hrs - 12H452 CAT 16M MOTOR GRADER | 1.2 | FALSE |  | 2027-07-07T22:00:00+00:00 | 2027-07-19T10:00:00+00:00 | 2027-07-08T06:00:00+08:00 | 2027-07-19T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SGR45227 | [{"equipmentGUID": "c611f0bf-7c7b-ee11-a846-000d3acacefd", "code": "12H452", "name": "12H452 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | TP OSR
83028 | 2026-06-26T04:21:55.6969545+00:00 | 2026-06-26T12:21:55.6969545+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:46:30.6440298+00:00 | 2026-08-28T14:46:30.6440298+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332195 | TRUE | TRUE | 2026-08-28T06:46:30.6440298+00:00 | 2026-08-28T14:46:30.6440298+08:00 | #83028 - BM4: 276hrs - 08H348 CAT D11 TRACK DOZER | 1.2 | FALSE |  | 2027-06-23T22:00:00+00:00 | 2027-07-05T10:00:00+00:00 | 2027-06-24T06:00:00+08:00 | 2027-07-05T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ34827 | [{"equipmentGUID": "a5f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "08H348", "name": "08H348 CAT D11 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | TP OSR
83008 | 2026-06-26T04:21:55.6947901+00:00 | 2026-06-26T12:21:55.6947901+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:47:07.100887+00:00 | 2026-08-28T14:47:07.100887+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332196 | TRUE | TRUE | 2026-08-28T06:47:07.100887+00:00 | 2026-08-28T14:47:07.100887+08:00 | #83008 - PDO: 276hrs - 12W567 CAT 24 MOTOR GRADER | 1.2 | FALSE |  | 2027-06-21T22:00:00+00:00 | 2027-07-03T10:00:00+00:00 | 2027-06-22T06:00:00+08:00 | 2027-07-03T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SGR56727 | [{"equipmentGUID": "f7d5fbde-59ac-ef11-a857-000d3acacefd", "code": "12W567", "name": "12W567 CAT 24 Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | TP OSR
83027 | 2026-06-26T04:21:55.6968672+00:00 | 2026-06-26T12:21:55.6968672+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:47:20.6051996+00:00 | 2026-08-28T14:47:20.6051996+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332197 | TRUE | TRUE | 2026-08-28T06:47:20.6051996+00:00 | 2026-08-28T14:47:20.6051996+08:00 | #83027 - MTP: 324hrs - 12H535 CAT 24 MOTOR GRADER | 1.3 | FALSE |  | 2027-06-05T22:00:00+00:00 | 2027-06-19T10:00:00+00:00 | 2027-06-06T06:00:00+08:00 | 2027-06-19T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR53527 | [{"equipmentGUID": "5f6afbbf-7c7b-ee11-a846-000d3acacefd", "code": "12H535", "name": "12H535 CAT 24 Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | TP OSR
83146 | 2026-07-01T00:23:07.2255133+00:00 | 2026-07-01T08:23:07.2255133+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:48:05.600087+00:00 | 2026-08-28T14:48:05.600087+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332200 | TRUE | TRUE | 2026-08-28T06:48:05.600087+00:00 | 2026-08-28T14:48:05.600087+08:00 | #83146 - HD1: 288hrs - 08R0083 CAT D10T TRACK DOZER | 1.2 | FALSE |  | 2027-05-20T22:00:00+00:00 | 2027-06-01T22:00:00+00:00 | 2027-05-21T06:00:00+08:00 | 2027-06-02T06:00:00+08:00 |  |  |  |  | 288.00 | 12,000hr Shut |  | SDZ08327 | [{"equipmentGUID": "146efbbf-7c7b-ee11-a846-000d3acacefd", "code": "08R0083", "name": "08R0083 CAT D10T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD1 | Australia/Perth |  | TP OSR
83026 | 2026-06-26T04:21:55.6967814+00:00 | 2026-06-26T12:21:55.6967814+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:48:24.0182682+00:00 | 2026-08-28T14:48:24.0182682+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332201 | TRUE | TRUE | 2026-08-28T06:48:24.0182682+00:00 | 2026-08-28T14:48:24.0182682+08:00 | #83026 - WAN: 276hrs - 08R224 CAT D11T TRACK DOZER | 1.2 | FALSE |  | 2027-05-04T22:00:00+00:00 | 2027-05-16T10:00:00+00:00 | 2027-05-05T06:00:00+08:00 | 2027-05-16T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SDZ22427 | [{"equipmentGUID": "efcd00c0-7c7b-ee11-a846-000d3acacefd", "code": "08R224", "name": "08R224 CAT D11T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83025 | 2026-06-26T04:21:55.6966917+00:00 | 2026-06-26T12:21:55.6966917+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T06:49:22.7879289+00:00 | 2026-08-28T14:49:22.7879289+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332204 | TRUE | TRUE | 2026-08-28T06:49:22.7879289+00:00 | 2026-08-28T14:49:22.7879289+08:00 | #83025 - BM4: 276hrs - 08H330 CAT D11 TRACK DOZER | 1.1 | FALSE |  | 2027-04-18T22:00:00+00:00 | 2027-04-30T10:00:00+00:00 | 2027-04-19T06:00:00+08:00 | 2027-04-30T18:00:00+08:00 |  |  |  |  | 276.00 | 15,000hr Shut |  | SDZ33027 | [{"equipmentGUID": "b3f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "08H330", "name": "08H330 CAT D11 Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | TP OSR
83005 | 2026-06-26T04:21:55.6944741+00:00 | 2026-06-26T12:21:55.6944741+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-01T23:46:01.4447327+00:00 | 2026-09-02T07:46:01.4447327+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332686 | TRUE | TRUE | 2026-09-01T23:46:01.4447327+00:00 | 2026-09-02T07:46:01.4447327+08:00 | #83005 - HD1: 276hrs - 08D5 CAT D10T TRACK DOZER | 2.1 | FALSE |  | 2027-03-18T22:00:00+00:00 | 2027-03-30T10:00:00+00:00 | 2027-03-19T06:00:00+08:00 | 2027-03-30T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SDZ00527 | [{"equipmentGUID": "3667fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08D5", "name": "08D5 CAT D10T Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD1 | Australia/Perth |  | TP OSR
83041 | 2026-06-26T04:21:55.6989089+00:00 | 2026-06-26T12:21:55.6989089+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-01T23:47:04.5481392+00:00 | 2026-09-02T07:47:04.5481392+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332687 | TRUE | TRUE | 2026-09-01T23:47:04.5481392+00:00 | 2026-09-02T07:47:04.5481392+08:00 | #83041 - WAN: 324hrs - 08R14 CAT D11R TRACK DOZER | 1.3 | FALSE |  | 2027-02-27T22:00:00+00:00 | 2027-03-13T10:00:00+00:00 | 2027-02-28T06:00:00+08:00 | 2027-03-13T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SDZ01427 | [{"equipmentGUID": "0275fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08R14", "name": "08R14 CAT D11R Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83007 | 2026-06-26T04:21:55.6946864+00:00 | 2026-06-26T12:21:55.6946864+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-01T23:43:42.6808342+00:00 | 2026-09-02T07:43:42.6808342+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332417 | TRUE | TRUE | 2026-09-01T23:43:42.6808342+00:00 | 2026-09-02T07:43:42.6808342+08:00 | #83007 - HD4: 324hrs - 12D11 CAT 16M MOTOR GRADER | 1.3 | FALSE |  | 2027-06-03T22:00:00+00:00 | 2027-06-17T10:00:00+00:00 | 2027-06-04T06:00:00+08:00 | 2027-06-17T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR01127 | [{"equipmentGUID": "fe3ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "12D11", "name": "12D11 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | TP OSR
83040 | 2026-06-26T04:21:55.6987421+00:00 | 2026-06-26T12:21:55.6987421+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-01T23:44:07.4363196+00:00 | 2026-09-02T07:44:07.4363196+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332418 | TRUE | TRUE | 2026-09-01T23:44:07.4363196+00:00 | 2026-09-02T07:44:07.4363196+08:00 | #83040 - WAN: 324hrs - 12R09 CAT 16M MOTOR GRADER | 1.3 | FALSE |  | 2027-01-31T22:00:00+00:00 | 2027-02-14T10:00:00+00:00 | 2027-02-01T06:00:00+08:00 | 2027-02-14T18:00:00+08:00 |  |  |  |  | 324.00 | 24,000hr Shut |  | SGR00927 | [{"equipmentGUID": "b466fbbf-7c7b-ee11-a846-000d3acacefd", "code": "12R09", "name": "12R09 CAT 16M Motor Grader", "assetClass": {"name": "Grader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83044 | 2026-06-26T04:21:55.6993896+00:00 | 2026-06-26T12:21:55.6993896+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-01T23:44:42.2987579+00:00 | 2026-09-02T07:44:42.2987579+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332419 | TRUE | TRUE | 2026-09-01T23:44:42.2987579+00:00 | 2026-09-02T07:44:42.2987579+08:00 | #83044 - WAN: 276hrs - 08R15 CAT D11R TRACK DOZER | 1.3 | FALSE |  | 2027-05-27T22:00:00+00:00 | 2027-06-08T10:00:00+00:00 | 2027-05-28T06:00:00+08:00 | 2027-06-08T18:00:00+08:00 |  |  |  |  | 276.00 | 12,000hr Shut |  | SDZ01527 | [{"equipmentGUID": "161ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "08R15", "name": "08R15 CAT D11R Track Dozer", "assetClass": {"name": "Dozer - Tracked"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | TP OSR
83053 | 2026-06-26T04:51:51.0287217+00:00 | 2026-06-26T12:51:51.0287217+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T13:32:28.0058822+00:00 | 2026-08-28T21:32:28.0058822+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332320 | TRUE | TRUE | 2026-08-28T13:32:28.0058822+00:00 | 2026-08-28T21:32:28.0058822+08:00 | #83053 - WAN: 288hrs - 08H182 CAT 854K WHEEL DOZER | 1.2 | FALSE |  | 2027-07-30T22:00:00+00:00 | 2027-08-11T22:00:00+00:00 | 2027-07-31T06:00:00+08:00 | 2027-08-12T06:00:00+08:00 |  |  |  |  | 288.00 | 36,000hr Shut |  | SWD18227 | [{"equipmentGUID": "f551fbbf-7c7b-ee11-a846-000d3acacefd", "code": "08H182", "name": "08H182 CAT 854K Wheel Dozer", "assetClass": {"name": "Dozer - Wheeled"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-West
83052 | 2026-06-26T04:51:51.0286002+00:00 | 2026-06-26T12:51:51.0286002+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T13:33:48.9696682+00:00 | 2026-08-28T21:33:48.9696682+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332325 | TRUE | TRUE | 2026-08-28T13:33:48.9696682+00:00 | 2026-08-28T21:33:48.9696682+08:00 | #83052 - WAN: 240hrs - 08H209 CAT 854K WHEEL DOZER | 1.2 | FALSE |  | 2027-05-09T22:00:00+00:00 | 2027-05-19T22:00:00+00:00 | 2027-05-10T06:00:00+08:00 | 2027-05-20T06:00:00+08:00 |  |  |  |  | 240.00 | 18,000hr Shut |  | SWD20927 | [{"equipmentGUID": "0018f0bf-7c7b-ee11-a846-000d3acacefd", "code": "08H209", "name": "08H209 CAT 854K Wheel Dozer", "assetClass": {"name": "Dozer - Wheeled"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-West
68206 | 2025-06-30T06:51:33.5900384+00:00 | 2025-06-30T14:51:33.5900384+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-08-28T13:34:42.5493953+00:00 | 2026-08-28T21:34:42.5493953+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332328 | TRUE | TRUE | 2026-08-28T13:34:42.5493953+00:00 | 2026-08-28T21:34:42.5493953+08:00 | #68206 - BM2: 288hrs - 08H208 CAT 854K WHEEL DOZER | 5.2 | FALSE |  | 2027-02-21T22:00:00+00:00 | 2027-03-05T22:00:00+00:00 | 2027-02-22T06:00:00+08:00 | 2027-03-06T06:00:00+08:00 |  |  |  |  | 288.00 | Engine, Transmission, Axle Assembly, Ovhl Articulation |  | SWD20827 | [{"equipmentGUID": "8b1bf0bf-7c7b-ee11-a846-000d3acacefd", "code": "08H208", "name": "08H208 CAT 854K Wheel Dozer", "assetClass": {"name": "Dozer - Wheeled"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9999e106-8450-49a2-8e12-268f2ff94774", "emailAddress": "Scott.Casey@riotinto.com", "displayName": "Scott Casey"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83616 | 2026-07-31T00:53:33.6349225+00:00 | 2026-07-31T08:53:33.6349225+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:18:46.0068785+00:00 | 2026-08-25T10:18:46.0068785+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331593 | TRUE | TRUE | 2026-08-25T02:18:46.0068785+00:00 | 2026-08-25T10:18:46.0068785+08:00 | #83616 - WTS: 120hrs - AGCCS INSTALL-COMMISSION ¦ DAMAGE REPLACEMENT | 1.2 | FALSE |  | 2027-06-23T16:00:00+00:00 | 2027-06-28T16:00:00+00:00 | 2027-06-24T00:00:00+08:00 | 2027-06-29T00:00:00+08:00 |  |  |  |  | 120.00 | 21H471 9,000 PoaP (Mid-life / PTO / Comp) |  |  | [{"equipmentGUID": "496c1fa1-768c-f111-a819-002248933a47", "code": "302721H471", "name": "21H471 Epiroc PV271-HP-RCS5 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "631c1821-324d-4fa1-9a10-bbe4e864d5a5", "emailAddress": "Jessica.Butson@riotinto.com", "displayName": "Butson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83124 | 2026-06-30T22:36:04.7964664+00:00 | 2026-07-01T06:36:04.7964664+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:19:25.9907606+00:00 | 2026-08-25T10:19:25.9907606+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331594 | TRUE | TRUE | 2026-08-25T02:19:25.9907606+00:00 | 2026-08-25T10:19:25.9907606+08:00 | #83124 - GDI: 744hrs - 21B288 SANDVIK DI650I DRILL | 3.1 | FALSE |  | 2027-01-11T16:00:00+00:00 | 2027-02-11T16:00:00+00:00 | 2027-01-12T00:00:00+08:00 | 2027-02-12T00:00:00+08:00 |  |  |  |  | 744.00 | 21B288 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "7913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "21B288", "name": "21B288 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | OSR
83136 | 2026-06-30T23:32:42.2247237+00:00 | 2026-07-01T07:32:42.2247237+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:21:22.6443761+00:00 | 2026-08-25T10:21:22.6443761+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331595 | TRUE | TRUE | 2026-08-25T02:21:22.6443761+00:00 | 2026-08-25T10:21:22.6443761+08:00 | #83136 - NBWT: 744hrs - 21H384 EPIROC D65XLF DRILL | 2.1 | FALSE |  | 2027-02-12T16:00:00+00:00 | 2027-03-15T16:00:00+00:00 | 2027-02-13T00:00:00+08:00 | 2027-03-16T00:00:00+08:00 |  | 2027-03-15T23:00:00+00:00 |  | 2027-03-16T07:00:00+08:00 | 744.00 | 21H384 24,000Hr OSR Shut EPIROC Perth |  |  | [{"equipmentGUID": "a027f6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H384", "name": "21H384 Epiroc D65XLF Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "0f7a8ffb-d881-43d7-918a-b1d90656a531", "emailAddress": "Ray.Blair@riotinto.com", "displayName": "Ray Blair"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | OSR
83281 | 2026-07-01T08:06:18.2413387+00:00 | 2026-07-01T16:06:18.2413387+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:22:08.3991431+00:00 | 2026-08-25T10:22:08.3991431+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331596 | TRUE | TRUE | 2026-08-25T02:22:08.3991431+00:00 | 2026-08-25T10:22:08.3991431+08:00 | #83281 - GDI: 744hrs - 21B298 SANDVIK DI650I DRILL | 3.1 | FALSE |  | 2027-03-01T16:00:00+00:00 | 2027-04-01T16:00:00+00:00 | 2027-03-02T00:00:00+08:00 | 2027-04-02T00:00:00+08:00 |  |  |  |  | 744.00 | 21B298 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "f8f8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "21B298", "name": "21B298 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | OSR
83147 | 2026-07-01T00:25:19.4452981+00:00 | 2026-07-01T08:25:19.4452981+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:22:34.59622+00:00 | 2026-08-25T10:22:34.59622+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331597 | TRUE | TRUE | 2026-08-25T02:22:34.59622+00:00 | 2026-08-25T10:22:34.59622+08:00 | #83147 - PDO: 768hrs - 21H435 SANDVIK DI650I DRILL | 3.1 | FALSE |  | 2027-04-16T16:00:00+00:00 | 2027-05-18T16:00:00+00:00 | 2027-04-17T00:00:00+08:00 | 2027-05-19T00:00:00+08:00 |  | 2027-05-18T22:00:00+00:00 |  | 2027-05-19T06:00:00+08:00 | 768.00 | 21H435 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "6639f6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H435", "name": "21H435 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83144 | 2026-06-30T23:48:19.7685239+00:00 | 2026-07-01T07:48:19.7685239+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:23:10.2105642+00:00 | 2026-08-25T10:23:10.2105642+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331598 | TRUE | TRUE | 2026-08-25T02:23:10.2105642+00:00 | 2026-08-25T10:23:10.2105642+08:00 | #83144 - HD1: 768hrs - 21D330 EPIROC D65XLF DRILL | 3.1 | FALSE |  | 2027-05-07T16:00:00+00:00 | 2027-06-08T16:00:00+00:00 | 2027-05-08T00:00:00+08:00 | 2027-06-09T00:00:00+08:00 |  | 2027-06-09T01:00:00+00:00 |  | 2027-06-09T09:00:00+08:00 | 768.00 | 21D330 12,000Hr OSR Shut EPIROC Perth |  |  | [{"equipmentGUID": "2281cebd-cc44-ef11-a84f-000d3acacefd", "code": "21D330", "name": "21D330 Epiroc D65XLF Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "d154a8cd-896c-4fcb-99e3-fd502405ddd8", "emailAddress": "Michael.Desker@riotinto.com", "displayName": "Michael Desker"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD1 | Australia/Perth |  | OSR
83265 | 2026-07-01T05:09:54.9316911+00:00 | 2026-07-01T13:09:54.9316911+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:23:41.3761026+00:00 | 2026-08-25T10:23:41.3761026+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331599 | TRUE | TRUE | 2026-08-25T02:23:41.3761026+00:00 | 2026-08-25T10:23:41.3761026+08:00 | #83265 - PDO: 744hrs - 21W436 SANDVIK DI650I DRILL | 3.1 | FALSE |  | 2027-05-21T16:00:00+00:00 | 2027-06-21T16:00:00+00:00 | 2027-05-22T00:00:00+08:00 | 2027-06-22T00:00:00+08:00 |  |  |  |  | 744.00 | 21W436 12,000 OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "bebbf9be-50c3-ee11-a849-000d3acacefd", "code": "21W436", "name": "21W436 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83269 | 2026-07-01T05:17:38.4235519+00:00 | 2026-07-01T13:17:38.4235519+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:24:11.4302231+00:00 | 2026-08-25T10:24:11.4302231+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331600 | TRUE | TRUE | 2026-08-25T02:24:11.4302231+00:00 | 2026-08-25T10:24:11.4302231+08:00 | #83269 - NBWT: 768hrs - 21H335 EPIROC D65XLF DRILL | 3.1 | FALSE |  | 2027-06-11T16:00:00+00:00 | 2027-07-13T16:00:00+00:00 | 2027-06-12T00:00:00+08:00 | 2027-07-14T00:00:00+08:00 |  | 2027-07-14T01:00:00+00:00 |  | 2027-07-14T09:00:00+08:00 | 768.00 | 21H335 12,000Hr OSR Shut EPIROC Perth |  |  | [{"equipmentGUID": "80aeecc7-feb1-ef11-a857-000d3acacefd", "code": "21H335", "name": "21H335 Epiroc D65XLF Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "0f7a8ffb-d881-43d7-918a-b1d90656a531", "emailAddress": "Ray.Blair@riotinto.com", "displayName": "Ray Blair"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | OSR
83278 | 2026-07-01T06:02:33.7077243+00:00 | 2026-07-01T14:02:33.7077243+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:24:34.8410534+00:00 | 2026-08-25T10:24:34.8410534+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331601 | TRUE | TRUE | 2026-08-25T02:24:34.8410534+00:00 | 2026-08-25T10:24:34.8410534+08:00 | #83278 - PDO: 744hrs - 21W437 SANDVIK DI650I DRILL | 2.1 | FALSE |  | 2027-06-25T16:00:00+00:00 | 2027-07-26T16:00:00+00:00 | 2027-06-26T00:00:00+08:00 | 2027-07-27T00:00:00+08:00 |  |  |  |  | 744.00 | 21W437 12,000 PoaP OSR Shut EPIROC Perth |  |  | [{"equipmentGUID": "bfbbf9be-50c3-ee11-a849-000d3acacefd", "code": "21W437", "name": "21W437 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83122 | 2026-06-30T22:20:40.7234296+00:00 | 2026-07-01T06:20:40.7234296+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:25:01.6399231+00:00 | 2026-08-25T10:25:01.6399231+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331602 | TRUE | TRUE | 2026-08-25T02:25:01.6399231+00:00 | 2026-08-25T10:25:01.6399231+08:00 | #83122 - RVJ: 768hrs - 21R455 EPIROC D65XLF DRILL | 3.1 | FALSE |  | 2027-07-16T16:00:00+00:00 | 2027-08-17T16:00:00+00:00 | 2027-07-17T00:00:00+08:00 | 2027-08-18T00:00:00+08:00 |  | 2027-08-18T01:00:00+00:00 |  | 2027-08-18T09:00:00+08:00 | 768.00 | 21R455 12,000hr OSR Shut EPIROC PERTH |  | S21R455 | [{"equipmentGUID": "c919924b-6072-ef11-a852-000d3acacefd", "code": "21R455", "name": "21R455 Epiroc D65XLF Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "90e77c6e-2221-429b-a8ae-0db167219024", "emailAddress": "Adam.Mehlert@riotinto.com", "displayName": "Adam Mehlert"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | OSR
83284 | 2026-07-01T08:45:10.3456535+00:00 | 2026-07-01T16:45:10.3456535+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:25:22.9860142+00:00 | 2026-08-25T10:25:22.9860142+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331603 | TRUE | TRUE | 2026-08-25T02:25:22.9860142+00:00 | 2026-08-25T10:25:22.9860142+08:00 | #83284 - PDO: 744hrs - 21W482 SANDVIK DI650I DRILL | 2.1 | FALSE |  | 2027-07-30T16:00:00+00:00 | 2027-08-30T16:00:00+00:00 | 2027-07-31T00:00:00+08:00 | 2027-08-31T00:00:00+08:00 |  |  |  |  | 744.00 | 21W482 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "312e86ee-1540-ef11-a84f-000d3acacefd", "code": "21W482", "name": "21W482 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83289 | 2026-07-01T09:02:04.9027062+00:00 | 2026-07-01T17:02:04.9027062+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:26:01.1418844+00:00 | 2026-08-25T10:26:01.1418844+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331604 | TRUE | TRUE | 2026-08-25T02:26:01.1418844+00:00 | 2026-08-25T10:26:01.1418844+08:00 | #83289 - PDO: 744hrs - 21W438 SANDVIK DI650I DRILL | 2.1 | FALSE |  | 2027-09-03T16:00:00+00:00 | 2027-10-04T16:00:00+00:00 | 2027-09-04T00:00:00+08:00 | 2027-10-05T00:00:00+08:00 |  |  |  |  | 744.00 | 21W438 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "17bcf9be-50c3-ee11-a849-000d3acacefd", "code": "21W438", "name": "21W438 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83293 | 2026-07-01T09:11:47.2063469+00:00 | 2026-07-01T17:11:47.2063469+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:26:38.3868253+00:00 | 2026-08-25T10:26:38.3868253+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331605 | TRUE | TRUE | 2026-08-25T02:26:38.3868253+00:00 | 2026-08-25T10:26:38.3868253+08:00 | #83293 - PDO: 744hrs - 21W481 SANDVIK DI650I DRILL | 2.1 | FALSE |  | 2027-10-08T16:00:00+00:00 | 2027-11-08T16:00:00+00:00 | 2027-10-09T00:00:00+08:00 | 2027-11-09T00:00:00+08:00 |  |  |  |  | 744.00 | 21W481 12,000Hr OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "d02d86ee-1540-ef11-a84f-000d3acacefd", "code": "21W481", "name": "21W481 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f9daf2bd-7243-4f95-b02c-859d6038f5d7", "emailAddress": "Romeo.Brighi@riotinto.com", "displayName": "Romeo Brighi"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | OSR
83296 | 2026-07-01T09:18:46.4257315+00:00 | 2026-07-01T17:18:46.4257315+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:27:08.0633464+00:00 | 2026-08-25T10:27:08.0633464+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331606 | TRUE | TRUE | 2026-08-25T02:27:08.0633464+00:00 | 2026-08-25T10:27:08.0633464+08:00 | #83296 - GDI: 744hrs - 21B379 SANDVIK DI650I DRILL | 1.1 | FALSE |  | 2027-11-12T16:00:00+00:00 | 2027-12-13T16:00:00+00:00 | 2027-11-13T00:00:00+08:00 | 2027-12-14T00:00:00+08:00 |  |  |  |  | 744.00 | 21B379 12,000 OSR Shut SANDVIK Perth |  |  | [{"equipmentGUID": "9edce8bf-7c7b-ee11-a846-000d3acacefd", "code": "21B379", "name": "21B379 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "f09f2cdf-4d98-41ea-9ed5-81c5f1f570d9", "emailAddress": "Joshua.Duffy@riotinto.com", "displayName": "Duffy, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | OSR
83291 | 2026-07-01T09:06:27.9014411+00:00 | 2026-07-01T17:06:27.9014411+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:27:26.1379792+00:00 | 2026-08-25T10:27:26.1379792+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331607 | TRUE | TRUE | 2026-08-25T02:27:26.1379792+00:00 | 2026-08-25T10:27:26.1379792+08:00 | #83291 - NBWT: 744hrs - 21H383 EPIROC D65XLF DRILL | 2.1 | FALSE |  | 2027-11-05T16:00:00+00:00 | 2027-12-06T16:00:00+00:00 | 2027-11-06T00:00:00+08:00 | 2027-12-07T00:00:00+08:00 |  |  |  |  | 744.00 | 21H383 24,000Hr OSR Shut EPIROC Perth |  |  | [{"equipmentGUID": "452df6bf-7c7b-ee11-a846-000d3acacefd", "code": "21H383", "name": "21H383 Epiroc D65XLF Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "0f7a8ffb-d881-43d7-918a-b1d90656a531", "emailAddress": "Ray.Blair@riotinto.com", "displayName": "Ray Blair"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | OSR
83287 | 2026-07-01T08:56:03.6072984+00:00 | 2026-07-01T16:56:03.6072984+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:28:22.0582882+00:00 | 2026-08-25T10:28:22.0582882+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331608 | TRUE | TRUE | 2026-08-25T02:28:22.0582882+00:00 | 2026-08-25T10:28:22.0582882+08:00 | #83287 - WTS: 144hrs - 21H472 EPIROC PV271-HP DRILL | 1.1 | FALSE |  | 2027-08-11T16:00:00+00:00 | 2027-08-17T16:00:00+00:00 | 2027-08-12T00:00:00+08:00 | 2027-08-18T00:00:00+08:00 |  |  |  |  | 144.00 | 21H472 9000Hr PoaP Shut Onsite |  |  | [{"equipmentGUID": "37f6404e-627d-f011-a802-002248933a47", "code": "21H472", "name": "21H472 Epiroc PV271-HP Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "631c1821-324d-4fa1-9a10-bbe4e864d5a5", "emailAddress": "Jessica.Butson@riotinto.com", "displayName": "Butson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83286 | 2026-07-01T08:52:42.3265348+00:00 | 2026-07-01T16:52:42.3265348+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:29:00.3801758+00:00 | 2026-08-25T10:29:00.3801758+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331609 | TRUE | TRUE | 2026-08-25T02:29:00.3801758+00:00 | 2026-08-25T10:29:00.3801758+08:00 | #83286 - WTS: 144hrs - 21H473 EPIROC PV271-HP-RCS5 DRILL | 2.1 | FALSE |  | 2027-08-24T16:00:00+00:00 | 2027-08-30T16:00:00+00:00 | 2027-08-25T00:00:00+08:00 | 2027-08-31T00:00:00+08:00 |  |  |  |  | 144.00 | 21H473 9000Hr PoaP Midlife Shut Onsite |  |  | [{"equipmentGUID": "36aa566a-3f74-f111-a817-002248933a47", "code": "21H473", "name": "21H473 Epiroc PV271-HP-RCS5 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "631c1821-324d-4fa1-9a10-bbe4e864d5a5", "emailAddress": "Jessica.Butson@riotinto.com", "displayName": "Butson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83294 | 2026-07-01T09:13:52.6675305+00:00 | 2026-07-01T17:13:52.6675305+08:00 | {"principalGUID": "b00e8cc6-e6d3-4f82-ac49-49651caa42f7", "displayName": "Macchia, Stephen (RTIO)"} | 2026-08-25T02:29:39.2585343+00:00 | 2026-08-25T10:29:39.2585343+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 331610 | TRUE | TRUE | 2026-08-25T02:29:39.2585343+00:00 | 2026-08-25T10:29:39.2585343+08:00 | #83294 - WTS: 312hrs - 21H280 ATLAS COPCO PV275 DRILL | 1.1 | FALSE |  | 2027-10-19T16:00:00+00:00 | 2027-11-01T16:00:00+00:00 | 2027-10-20T00:00:00+08:00 | 2027-11-02T00:00:00+08:00 |  |  |  |  | 312.00 | 21H280 Major shut Onsite TP |  |  | [{"equipmentGUID": "8be3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "21H280", "name": "21H280 Atlas Copco PV275 Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "631c1821-324d-4fa1-9a10-bbe4e864d5a5", "emailAddress": "Jessica.Butson@riotinto.com", "displayName": "Butson, Jessica (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WTS | Australia/Perth |  | Site Team
83439 | 2026-07-02T22:47:05.002958+00:00 | 2026-07-03T06:47:05.002958+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-09-23T03:06:20.4378612+00:00 | 2026-09-23T11:06:20.4378612+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 333731 | TRUE | TRUE | 2026-09-23T03:06:20.4378612+00:00 | 2026-09-23T11:06:20.4378612+08:00 | #83439 - HD4: 288hrs - 07D264 KOMATSU WE2350 WHEEL LOADER | 2.0 | FALSE |  | 2027-09-19T16:00:00+00:00 | 2027-10-01T16:00:00+00:00 | 2027-09-20T00:00:00+08:00 | 2027-10-02T00:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut | cause dates wrong :) | SLD26427 | [{"equipmentGUID": "78c77768-5f7d-f011-a802-002248933a47", "code": "07D264", "name": "07D264 Komatsu WE2350 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | L-East
83360 | 2026-07-02T05:55:49.4968032+00:00 | 2026-07-02T13:55:49.4968032+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T07:09:27.0655987+00:00 | 2026-08-28T15:09:27.0655987+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332262 | TRUE | TRUE | 2026-08-28T07:09:27.0655987+00:00 | 2026-08-28T15:09:27.0655987+08:00 | #83360 - GDI: 240hrs - 15B405 CAT 6060 EXCAVATOR | 1.2 | FALSE |  | 2027-01-05T04:00:00+00:00 | 2027-01-15T04:00:00+00:00 | 2027-01-05T12:00:00+08:00 | 2027-01-15T12:00:00+08:00 |  |  |  |  | 240.00 | 15,000hr Shut |  | SSX40527 | [{"equipmentGUID": "e7bbf9be-50c3-ee11-a849-000d3acacefd", "code": "15B405", "name": "15B405 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
83362 | 2026-07-02T05:55:49.5811795+00:00 | 2026-07-02T13:55:49.5811795+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T07:07:56.7888451+00:00 | 2026-08-28T15:07:56.7888451+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332256 | TRUE | TRUE | 2026-08-28T07:07:56.7888451+00:00 | 2026-08-28T15:07:56.7888451+08:00 | #83362 - GDI: 336hrs - 15B362 CAT 6060 EXCAVATOR | 1.2 | FALSE |  | 2027-04-06T04:00:00+00:00 | 2027-04-20T04:00:00+00:00 | 2027-04-06T12:00:00+08:00 | 2027-04-20T12:00:00+08:00 |  |  |  |  | 336.00 | 30,000hr Shut |  | SSX36227 | [{"equipmentGUID": "1745f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15B362", "name": "15B362 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
83361 | 2026-07-02T05:55:49.5808879+00:00 | 2026-07-02T13:55:49.5808879+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T07:09:02.9898488+00:00 | 2026-08-28T15:09:02.9898488+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332260 | TRUE | TRUE | 2026-08-28T07:09:02.9898488+00:00 | 2026-08-28T15:09:02.9898488+08:00 | #83361 - GDI: 336hrs - 15B300 CAT 6060 EXCAVATOR | 1.2 | FALSE |  | 2027-02-04T04:00:00+00:00 | 2027-02-18T04:00:00+00:00 | 2027-02-04T12:00:00+08:00 | 2027-02-18T12:00:00+08:00 |  |  |  |  | 336.00 | 30,000hr Shut |  | SSX30027 | [{"equipmentGUID": "ff64fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15B300", "name": "15B300 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
83363 | 2026-07-02T05:55:49.5812989+00:00 | 2026-07-02T13:55:49.5812989+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T07:06:58.5057727+00:00 | 2026-08-28T15:06:58.5057727+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332253 | TRUE | TRUE | 2026-08-28T07:06:58.5057727+00:00 | 2026-08-28T15:06:58.5057727+08:00 | #83363 - GDI: 216hrs - 15B289 CAT 6040 EXCAVATOR | 1.2 | FALSE |  | 2027-05-21T04:00:00+00:00 | 2027-05-30T04:00:00+00:00 | 2027-05-21T12:00:00+08:00 | 2027-05-30T12:00:00+08:00 |  |  |  |  | 216.00 | 22,500hr Shut |  | SSX28927 | [{"equipmentGUID": "440ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "15B289", "name": "15B289 CAT 6040 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
83364 | 2026-07-02T05:55:49.5814079+00:00 | 2026-07-02T13:55:49.5814079+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T07:05:30.9045977+00:00 | 2026-08-28T15:05:30.9045977+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332246 | TRUE | TRUE | 2026-08-28T07:05:30.9045977+00:00 | 2026-08-28T15:05:30.9045977+08:00 | #83364 - MDO: 216hrs - 15H402 CAT 6060 EXCAVATOR | 1.2 | FALSE |  | 2027-08-17T04:00:00+00:00 | 2027-08-26T04:00:00+00:00 | 2027-08-17T12:00:00+08:00 | 2027-08-26T12:00:00+08:00 |  |  |  |  | 216.00 | 7,500hr + Under |  | SSX40227 | [{"equipmentGUID": "906efbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H402", "name": "15H402 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | D-East
83392 | 2026-07-02T05:55:49.5846534+00:00 | 2026-07-02T13:55:49.5846534+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:59:04.7105942+00:00 | 2026-08-28T14:59:04.7105942+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332241 | TRUE | TRUE | 2026-08-28T06:59:04.7105942+00:00 | 2026-08-28T14:59:04.7105942+08:00 | #83392 - BM2: 240hrs - 07H276 LETOURNEAU L1350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-09-18T04:00:00+00:00 | 2027-09-28T04:00:00+00:00 | 2027-09-18T12:00:00+08:00 | 2027-09-28T12:00:00+08:00 |  |  |  |  | 240.00 | Eng Module |  | SLD27627 | [{"equipmentGUID": "9806f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H276", "name": "07H276 LeTourneau L1350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83393 | 2026-07-02T05:55:49.5847611+00:00 | 2026-07-02T13:55:49.5847611+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:58:01.445426+00:00 | 2026-08-28T14:58:01.445426+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332238 | TRUE | TRUE | 2026-08-28T06:58:01.445426+00:00 | 2026-08-28T14:58:01.445426+08:00 | #83393 - BM4: 240hrs - 07H233 CAT 992 WHEEL LOADER | 1.2 | FALSE |  | 2027-10-04T04:00:00+00:00 | 2027-10-14T04:00:00+00:00 | 2027-10-04T12:00:00+08:00 | 2027-10-14T12:00:00+08:00 |  |  |  |  | 240.00 | 18,000hr Shut |  | SLD23327 | [{"equipmentGUID": "b4bbf9be-50c3-ee11-a849-000d3acacefd", "code": "07H233", "name": "07H233 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | L-West
83379 | 2026-07-02T05:55:49.5831609+00:00 | 2026-07-02T13:55:49.5831609+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:57:13.3579446+00:00 | 2026-08-28T14:57:13.3579446+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332235 | TRUE | TRUE | 2026-08-28T06:57:13.3579446+00:00 | 2026-08-28T14:57:13.3579446+08:00 | #83379 - MDO: 240hrs - 15H218 KOMATSU PC4000-6FS FACE SHOVEL | 1.2 | FALSE |  | 2027-10-07T04:00:00+00:00 | 2027-10-17T04:00:00+00:00 | 2027-10-07T12:00:00+08:00 | 2027-10-17T12:00:00+08:00 |  |  |  |  | 240.00 | 15,000hr Shut |  | SSX21827 | [{"equipmentGUID": "fee0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "15H218", "name": "15H218 Komatsu PC4000-6FS Face Shovel", "assetClass": {"name": "Shovel - Face"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | L-East
83380 | 2026-07-02T05:55:49.583347+00:00 | 2026-07-02T13:55:49.583347+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:56:25.6233852+00:00 | 2026-08-28T14:56:25.6233852+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332231 | TRUE | TRUE | 2026-08-28T06:56:25.6233852+00:00 | 2026-08-28T14:56:25.6233852+08:00 | #83380 - WAN: 240hrs - 07R424 KOMATSU WA900-3E0 WHEEL LOADER | 1.2 | FALSE |  | 2027-10-22T04:00:00+00:00 | 2027-11-01T04:00:00+00:00 | 2027-10-22T12:00:00+08:00 | 2027-11-01T12:00:00+08:00 |  |  |  |  | 240.00 | 18,000hr Shut |  | SLD42427 | [{"equipmentGUID": "24e2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07R424", "name": "07R424 Komatsu WA900-3E0 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-East
83437 | 2026-07-02T22:43:16.1934283+00:00 | 2026-07-03T06:43:16.1934283+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:56:39.824191+00:00 | 2026-08-28T14:56:39.824191+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332232 | TRUE | TRUE | 2026-08-28T06:56:39.824191+00:00 | 2026-08-28T14:56:39.824191+08:00 | #83437 - PDO: 288hrs - 07W458 KOMATSU WE1850-3 WHEEL LOADER | 1.2 | FALSE |  | 2027-10-18T16:00:00+00:00 | 2027-10-30T16:00:00+00:00 | 2027-10-19T00:00:00+08:00 | 2027-10-31T00:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD45827 | [{"equipmentGUID": "f524c4a8-637d-f011-a802-002248933a47", "code": "07W458", "name": "07W458 Komatsu WE1850-3 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | L-West
83438 | 2026-07-02T22:45:13.5950899+00:00 | 2026-07-03T06:45:13.5950899+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:55:03.6309075+00:00 | 2026-08-28T14:55:03.6309075+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332224 | TRUE | TRUE | 2026-08-28T06:55:03.6309075+00:00 | 2026-08-28T14:55:03.6309075+08:00 | #83438 - BM4: 288hrs - 07H520 KOMATSU WE2350 WHEEL LOADER | 1.2 | FALSE |  | 2027-11-19T16:00:00+00:00 | 2027-12-01T16:00:00+00:00 | 2027-11-20T00:00:00+08:00 | 2027-12-02T00:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD52027 | [{"equipmentGUID": "797d0e28-617d-f011-a802-002248933a47", "code": "07H520", "name": "07H520 Komatsu WE2350 Wheel Loader", "assetClass": {"name": "Loader - Wheeled >5T"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | L-West
83365 | 2026-07-02T05:55:49.5815253+00:00 | 2026-07-02T13:55:49.5815253+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T06:55:58.9539784+00:00 | 2026-08-28T14:55:58.9539784+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332229 | TRUE | TRUE | 2026-08-28T06:55:58.9539784+00:00 | 2026-08-28T14:55:58.9539784+08:00 | #83365 - GDI: 168hrs - 15B291 CAT 6060 EXCAVATOR | 1.2 | FALSE |  | 2027-11-01T04:00:00+00:00 | 2027-11-08T04:00:00+00:00 | 2027-11-01T12:00:00+08:00 | 2027-11-08T12:00:00+08:00 |  |  |  |  | 168.00 | 7,500hr Shut |  | SSX29127 | [{"equipmentGUID": "126afbbf-7c7b-ee11-a846-000d3acacefd", "code": "15B291", "name": "15B291 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "b0857c5c-c066-4f05-bc7e-b9918eed4639", "emailAddress": "Bonnie.Warren@riotinto.com", "displayName": "Warren, Bonnie (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
83386 | 2026-07-02T05:55:49.5840165+00:00 | 2026-07-02T13:55:49.5840165+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:34:07.4908015+00:00 | 2026-08-28T21:34:07.4908015+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332326 | TRUE | TRUE | 2026-08-28T13:34:07.4908015+00:00 | 2026-08-28T21:34:07.4908015+08:00 | #83386 - BM2: 336hrs - 07H425 CAT 992K WHEEL LOADER | 1.2 | FALSE |  | 2027-04-21T04:00:00+00:00 | 2027-05-05T04:00:00+00:00 | 2027-04-21T12:00:00+08:00 | 2027-05-05T12:00:00+08:00 |  |  |  |  | 336.00 | 36,000hr Shut |  | SLD42527 | [{"equipmentGUID": "b62cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "07H425", "name": "07H425 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83385 | 2026-07-02T05:55:49.5839108+00:00 | 2026-07-02T13:55:49.5839108+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:34:22.0567659+00:00 | 2026-08-28T21:34:22.0567659+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332327 | TRUE | TRUE | 2026-08-28T13:34:22.0567659+00:00 | 2026-08-28T21:34:22.0567659+08:00 | #83385 - BM4: 240hrs - 07H327 CAT 992 WHEEL LOADER | 1.2 | FALSE |  | 2027-03-11T04:00:00+00:00 | 2027-03-21T04:00:00+00:00 | 2027-03-11T12:00:00+08:00 | 2027-03-21T12:00:00+08:00 |  |  |  |  | 240.00 | 18,000hr Shut |  | SLD32727 | [{"equipmentGUID": "9f56fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H327", "name": "07H327 CAT 992 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | L-West
83390 | 2026-07-02T05:55:49.5844395+00:00 | 2026-07-02T13:55:49.5844395+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:32:42.5242058+00:00 | 2026-08-28T21:32:42.5242058+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332321 | TRUE | TRUE | 2026-08-28T13:32:42.5242058+00:00 | 2026-08-28T21:32:42.5242058+08:00 | #83390 - BM2: 216hrs - 07H126 CAT 993K WHEEL LOADER | 1.2 | FALSE |  | 2027-07-05T04:00:00+00:00 | 2027-07-14T04:00:00+00:00 | 2027-07-05T12:00:00+08:00 | 2027-07-14T12:00:00+08:00 |  |  |  |  | 216.00 | Midlife, Trans, Torque Converter |  | SLD12627 | [{"equipmentGUID": "9b0af0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H126", "name": "07H126 CAT 993K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83389 | 2026-07-02T05:55:49.5843355+00:00 | 2026-07-02T13:55:49.5843355+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:32:58.3564761+00:00 | 2026-08-28T21:32:58.3564761+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332322 | TRUE | TRUE | 2026-08-28T13:32:58.3564761+00:00 | 2026-08-28T21:32:58.3564761+08:00 | #83389 - BM2: 240hrs - 07H128 CAT 993K WHEEL LOADER | 1.2 | FALSE |  | 2027-06-21T04:00:00+00:00 | 2027-07-01T04:00:00+00:00 | 2027-06-21T12:00:00+08:00 | 2027-07-01T12:00:00+08:00 |  |  |  |  | 240.00 | Eng, Trans, Torque Converter, Artic |  | SLD12827 | [{"equipmentGUID": "ef2bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "07H128", "name": "07H128 CAT 993K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83387 | 2026-07-02T05:55:49.5841224+00:00 | 2026-07-02T13:55:49.5841224+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:33:32.5187702+00:00 | 2026-08-28T21:33:32.5187702+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332324 | TRUE | TRUE | 2026-08-28T13:33:32.5187702+00:00 | 2026-08-28T21:33:32.5187702+08:00 | #83387 - RVJ: 192hrs - 07H177 KOMATSU WA1200-6 WHEEL LOADER | 1.3 | FALSE |  | 2027-05-25T04:00:00+00:00 | 2027-06-02T04:00:00+00:00 | 2027-05-25T12:00:00+08:00 | 2027-06-02T12:00:00+08:00 |  |  |  |  | 192.00 | Trans & Bits |  | SLD17727 | [{"equipmentGUID": "d8e3e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07H177", "name": "07H177 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | L-West
83378 | 2026-07-02T05:55:49.5830514+00:00 | 2026-07-02T13:55:49.5830514+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:25:28.9129318+00:00 | 2026-08-28T16:25:28.9129318+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332302 | TRUE | TRUE | 2026-08-28T08:25:28.9129318+00:00 | 2026-08-28T16:25:28.9129318+08:00 | #83378 - YAN: 288hrs - 07H302 LETOURNEAU L2350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-09-03T04:00:00+00:00 | 2027-09-15T04:00:00+00:00 | 2027-09-03T12:00:00+08:00 | 2027-09-15T12:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD30227 | [{"equipmentGUID": "0fe100c0-7c7b-ee11-a846-000d3acacefd", "code": "07H302", "name": "07H302 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | L-East
83377 | 2026-07-02T05:55:49.5829438+00:00 | 2026-07-02T13:55:49.5829438+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:26:25.2005013+00:00 | 2026-08-28T16:26:25.2005013+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332304 | TRUE | TRUE | 2026-08-28T08:26:25.2005013+00:00 | 2026-08-28T16:26:25.2005013+08:00 | #83377 - BM4: 288hrs - 07H421 LETOURNEAU L2350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-08-18T04:00:00+00:00 | 2027-08-30T04:00:00+00:00 | 2027-08-18T12:00:00+08:00 | 2027-08-30T12:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD42127 | [{"equipmentGUID": "d726f6bf-7c7b-ee11-a846-000d3acacefd", "code": "07H421", "name": "07H421 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | L-East
83376 | 2026-07-02T05:55:49.5828319+00:00 | 2026-07-02T13:55:49.5828319+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:26:39.1942354+00:00 | 2026-08-28T16:26:39.1942354+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332305 | TRUE | TRUE | 2026-08-28T08:26:39.1942354+00:00 | 2026-08-28T16:26:39.1942354+08:00 | #83376 - WAN: 240hrs - 07R467 KOMATSU WA900-8R WHEEL LOADER | 1.2 | FALSE |  | 2027-08-02T04:00:00+00:00 | 2027-08-12T04:00:00+00:00 | 2027-08-02T12:00:00+08:00 | 2027-08-12T12:00:00+08:00 |  |  |  |  | 240.00 | Eng & Axles |  | SLD46727 | [{"equipmentGUID": "c6ce00c0-7c7b-ee11-a846-000d3acacefd", "code": "07R467", "name": "07R467 Komatsu WA900-8R Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-East
83374 | 2026-07-02T05:55:49.582605+00:00 | 2026-07-02T13:55:49.582605+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:27:03.9813627+00:00 | 2026-08-28T16:27:03.9813627+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332306 | TRUE | TRUE | 2026-08-28T08:27:03.9813627+00:00 | 2026-08-28T16:27:03.9813627+08:00 | #83374 - WAN: 240hrs - 07R390 KOMATSU WA900-3EO WHEEL LOADER | 1.2 | FALSE |  | 2027-06-29T04:00:00+00:00 | 2027-07-09T04:00:00+00:00 | 2027-06-29T12:00:00+08:00 | 2027-07-09T12:00:00+08:00 |  |  |  |  | 240.00 | Axles, Artic |  | SLD39027 | [{"equipmentGUID": "bc13f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07R390", "name": "07R390 Komatsu WA900-3EO Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-East
83372 | 2026-07-02T05:55:49.5822743+00:00 | 2026-07-02T13:55:49.5822743+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:28:12.5829044+00:00 | 2026-08-28T16:28:12.5829044+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332309 | TRUE | TRUE | 2026-08-28T08:28:12.5829044+00:00 | 2026-08-28T16:28:12.5829044+08:00 | #83372 - GDI: 336hrs - 07B381 CAT 994K WHEEL LOADER | 1.2 | FALSE |  | 2027-05-06T04:00:00+00:00 | 2027-05-20T04:00:00+00:00 | 2027-05-06T12:00:00+08:00 | 2027-05-20T12:00:00+08:00 |  |  |  |  | 336.00 | 24,000hr Shut |  | SLD38127 | [{"equipmentGUID": "1363fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07B381", "name": "07B381 CAT 994K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | GDI | Australia/Perth |  | L-East
83371 | 2026-07-02T05:55:49.5821643+00:00 | 2026-07-02T13:55:49.5821643+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T08:28:35.6861382+00:00 | 2026-08-28T16:28:35.6861382+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332310 | TRUE | TRUE | 2026-08-28T08:28:35.6861382+00:00 | 2026-08-28T16:28:35.6861382+08:00 | #83371 - WAN: 288hrs - 07R373 LETOURNEAU L2350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-04-19T04:00:00+00:00 | 2027-05-01T04:00:00+00:00 | 2027-04-19T12:00:00+08:00 | 2027-05-01T12:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD37327 | [{"equipmentGUID": "65df00c0-7c7b-ee11-a846-000d3acacefd", "code": "07R373", "name": "07R373 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | L-East
83370 | 2026-07-02T05:55:49.5820593+00:00 | 2026-07-02T13:55:49.5820593+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:29:57.2385968+00:00 | 2026-08-28T21:29:57.2385968+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332312 | TRUE | TRUE | 2026-08-28T13:29:57.2385968+00:00 | 2026-08-28T21:29:57.2385968+08:00 | #83370 - YAN: 288hrs - 07H309 LETOURNEAU L2350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-04-01T04:00:00+00:00 | 2027-04-13T04:00:00+00:00 | 2027-04-01T12:00:00+08:00 | 2027-04-13T12:00:00+08:00 |  |  |  |  | 288.00 | 12,500hr Shut |  | SLD30927 | [{"equipmentGUID": "6cf4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "07H309", "name": "07H309 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | L-East
83369 | 2026-07-02T05:55:49.5819538+00:00 | 2026-07-02T13:55:49.5819538+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:30:11.8963452+00:00 | 2026-08-28T21:30:11.8963452+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332313 | TRUE | TRUE | 2026-08-28T13:30:11.8963452+00:00 | 2026-08-28T21:30:11.8963452+08:00 | #83369 - RVA: 192hrs - 07R333 KOMATSU WA1200-6 WHEEL LOADER | 1.3 | FALSE |  | 2027-03-19T04:00:00+00:00 | 2027-03-27T04:00:00+00:00 | 2027-03-19T12:00:00+08:00 | 2027-03-27T12:00:00+08:00 |  |  |  |  | 192.00 | Eng, MCV, Switch Pump |  | SLD33327 | [{"equipmentGUID": "0756fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07R333", "name": "07R333 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVA | Australia/Perth |  | L-East
83367 | 2026-07-02T05:55:49.5817425+00:00 | 2026-07-02T13:55:49.5817425+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:30:47.9017576+00:00 | 2026-08-28T21:30:47.9017576+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332315 | TRUE | TRUE | 2026-08-28T13:30:47.9017576+00:00 | 2026-08-28T21:30:47.9017576+08:00 | #83367 - MDO: 288hrs - 07H246 KOMATSU WA1200-6 WHEEL LOADER | 1.2 | FALSE |  | 2027-02-18T04:00:00+00:00 | 2027-03-02T04:00:00+00:00 | 2027-02-18T12:00:00+08:00 | 2027-03-02T12:00:00+08:00 |  |  |  |  | 288.00 | Major Shut |  | SLD24627 | [{"equipmentGUID": "1529f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H246", "name": "07H246 Komatsu WA1200-6 Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "732550ef-b964-41a5-8253-8decd9e77f9d", "emailAddress": "Mathew.Vanderleer@riotinto.com", "displayName": "Van Der Leer, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MDO | Australia/Perth |  | L-East
83404 | 2026-07-02T06:13:15.3312265+00:00 | 2026-07-02T14:13:15.3312265+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:31:53.3986637+00:00 | 2026-08-28T21:31:53.3986637+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332318 | TRUE | TRUE | 2026-08-28T13:31:53.3986637+00:00 | 2026-08-28T21:31:53.3986637+08:00 | #83404 - MTP: 336hrs - 07H595 LETOURNEAU L1850-II WHEEL LOADER | 1.2 | FALSE |  | 2027-08-29T16:00:00+00:00 | 2027-09-12T16:00:00+00:00 | 2027-08-30T00:00:00+08:00 | 2027-09-13T00:00:00+08:00 |  |  |  |  | 336.00 | 25,000hr Shut |  | SLD59527 | [{"equipmentGUID": "275afbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H595", "name": "07H595 LeTourneau L1850-II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | L-West
83391 | 2026-07-02T05:55:49.5845469+00:00 | 2026-07-02T13:55:49.5845469+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:32:08.0969786+00:00 | 2026-08-28T21:32:08.0969786+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332319 | TRUE | TRUE | 2026-08-28T13:32:08.0969786+00:00 | 2026-08-28T21:32:08.0969786+08:00 | #83391 - PDO: 192hrs - 07H375 CAT 992K WHEEL LOADER | 1.2 | FALSE |  | 2027-08-17T04:00:00+00:00 | 2027-08-25T04:00:00+00:00 | 2027-08-17T12:00:00+08:00 | 2027-08-25T12:00:00+08:00 |  |  |  |  | 192.00 | Eng & Trans |  | SLD37527 | [{"equipmentGUID": "1c61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H375", "name": "07H375 CAT 992K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | L-West
83384 | 2026-07-02T05:55:49.5838066+00:00 | 2026-07-02T13:55:49.5838066+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:34:57.3125164+00:00 | 2026-08-28T21:34:57.3125164+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332329 | TRUE | TRUE | 2026-08-28T13:34:57.3125164+00:00 | 2026-08-28T21:34:57.3125164+08:00 | #83384 - BM2: 216hrs - 07H335 CAT 993K WHEEL LOADER | 1.2 | FALSE |  | 2027-02-08T04:00:00+00:00 | 2027-02-17T04:00:00+00:00 | 2027-02-08T12:00:00+08:00 | 2027-02-17T12:00:00+08:00 |  |  |  |  | 216.00 | Eng, Axle Front |  | SLD33527 | [{"equipmentGUID": "7b5cfbbf-7c7b-ee11-a846-000d3acacefd", "code": "07H335", "name": "07H335 CAT 993K Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
83382 | 2026-07-02T05:55:49.5835916+00:00 | 2026-07-02T13:55:49.5835916+08:00 | {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "displayName": "Milosevic, Nebojsa (RTIO)"} | 2026-08-28T13:35:28.6703944+00:00 | 2026-08-28T21:35:28.6703944+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332331 | TRUE | TRUE | 2026-08-28T13:35:28.6703944+00:00 | 2026-08-28T21:35:28.6703944+08:00 | #83382 - BM2: 240hrs - 07H169 LETOURNEAU L2350 II WHEEL LOADER | 1.2 | FALSE |  | 2027-01-11T04:00:00+00:00 | 2027-01-21T04:00:00+00:00 | 2027-01-11T12:00:00+08:00 | 2027-01-21T12:00:00+08:00 |  |  |  |  | 240.00 | Eng Module |  | SLD16927 | [{"equipmentGUID": "7b29f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H169", "name": "07H169 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "emailAddress": "Ryan.Shanks2@riotinto.com", "displayName": "Shanks, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM2 | Australia/Perth |  | L-West
82970 | 2026-06-24T01:31:27.7881967+00:00 | 2026-06-24T09:31:27.7881967+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:43:44.445861+00:00 | 2026-08-28T15:43:44.445861+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332283 | TRUE | TRUE | 2026-08-28T07:43:44.445861+00:00 | 2026-08-28T15:43:44.445861+08:00 | #82970 - RVA: 240hrs - 15R239 HITACHI EX3600-7BH EXCAVATOR | 1.3 | FALSE |  | 2027-09-01T16:00:00+00:00 | 2027-09-11T16:00:00+00:00 | 2027-09-02T00:00:00+08:00 | 2027-09-12T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX23927 | [{"equipmentGUID": "b2e000c0-7c7b-ee11-a846-000d3acacefd", "code": "15R239", "name": "15R239 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVA | Australia/Perth |  | D-West
82969 | 2026-06-24T01:29:20.0842667+00:00 | 2026-06-24T09:29:20.0842667+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:45:01.2914544+00:00 | 2026-08-28T15:45:01.2914544+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332284 | TRUE | TRUE | 2026-08-28T07:45:01.2914544+00:00 | 2026-08-28T15:45:01.2914544+08:00 | #82969 - BM4: 288hrs - 15H274 HITACHI EX5600-6BH EXCAVATOR | 1.3 | FALSE |  | 2027-08-01T16:00:00+00:00 | 2027-08-13T16:00:00+00:00 | 2027-08-02T00:00:00+08:00 | 2027-08-14T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut |  | SSX27427 | [{"equipmentGUID": "b1f6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "15H274", "name": "15H274 Hitachi EX5600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82967 | 2026-06-24T01:26:01.6861459+00:00 | 2026-06-24T09:26:01.6861459+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:45:20.4283365+00:00 | 2026-08-28T15:45:20.4283365+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332285 | TRUE | TRUE | 2026-08-28T07:45:20.4283365+00:00 | 2026-08-28T15:45:20.4283365+08:00 | #82967 - NBWT: 216hrs - 15H417 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-07-05T16:00:00+00:00 | 2027-07-14T16:00:00+00:00 | 2027-07-06T00:00:00+08:00 | 2027-07-15T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX41727 | [{"equipmentGUID": "6729f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15H417", "name": "15H417 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | D-West
82966 | 2026-06-24T01:24:27.6595018+00:00 | 2026-06-24T09:24:27.6595018+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:20:40.5836125+00:00 | 2026-08-28T16:20:40.5836125+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332287 | TRUE | TRUE | 2026-08-28T08:20:40.5836125+00:00 | 2026-08-28T16:20:40.5836125+08:00 | #82966 - RVJ: 240hrs - 15R284 HITACHI EX3600-7BH EXCAVATOR | 1.3 | FALSE |  | 2027-06-20T16:00:00+00:00 | 2027-06-30T16:00:00+00:00 | 2027-06-21T00:00:00+08:00 | 2027-07-01T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX28427 | [{"equipmentGUID": "a842f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15R284", "name": "15R284 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVJ | Australia/Perth |  | D-West
82968 | 2026-06-24T01:27:35.5663778+00:00 | 2026-06-24T09:27:35.5663778+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:20:53.1474779+00:00 | 2026-08-28T16:20:53.1474779+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332288 | TRUE | TRUE | 2026-08-28T08:20:53.1474779+00:00 | 2026-08-28T16:20:53.1474779+08:00 | #82968 - BM4: 192hrs - 15H316 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-06-19T16:00:00+00:00 | 2027-06-27T16:00:00+00:00 | 2027-06-20T00:00:00+08:00 | 2027-06-28T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX31627 | [{"equipmentGUID": "d54ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H316", "name": "15H316 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82965 | 2026-06-24T01:20:30.2901303+00:00 | 2026-06-24T09:20:30.2901303+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:21:06.6649639+00:00 | 2026-08-28T16:21:06.6649639+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332289 | TRUE | TRUE | 2026-08-28T08:21:06.6649639+00:00 | 2026-08-28T16:21:06.6649639+08:00 | #82965 - BM4: 288hrs - 15H263 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-06-02T16:00:00+00:00 | 2027-06-14T16:00:00+00:00 | 2027-06-03T00:00:00+08:00 | 2027-06-15T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Module Shut ,MCV, Cntr Frame , Swing Brg, Cab |  | SSX26327 | [{"equipmentGUID": "0ae100c0-7c7b-ee11-a846-000d3acacefd", "code": "15H263", "name": "15H263 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82964 | 2026-06-24T01:18:48.4275579+00:00 | 2026-06-24T09:18:48.4275579+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:21:29.6067269+00:00 | 2026-08-28T16:21:29.6067269+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332290 | TRUE | TRUE | 2026-08-28T08:21:29.6067269+00:00 | 2026-08-28T16:21:29.6067269+08:00 | #82964 - BM4: 216hrs - 15H412 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-05-19T16:00:00+00:00 | 2027-05-28T16:00:00+00:00 | 2027-05-20T00:00:00+08:00 | 2027-05-29T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX41227 | [{"equipmentGUID": "313bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H412", "name": "15H412 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82963 | 2026-06-24T01:17:05.0706433+00:00 | 2026-06-24T09:17:05.0706433+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:21:43.7637807+00:00 | 2026-08-28T16:21:43.7637807+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332291 | TRUE | TRUE | 2026-08-28T08:21:43.7637807+00:00 | 2026-08-28T16:21:43.7637807+08:00 | #82963 - MTP: 240hrs - 15H429 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-05-04T16:00:00+00:00 | 2027-05-14T16:00:00+00:00 | 2027-05-05T00:00:00+08:00 | 2027-05-15T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX42927 | [{"equipmentGUID": "3d61fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H429", "name": "15H429 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
82962 | 2026-06-24T01:15:10.9533651+00:00 | 2026-06-24T09:15:10.9533651+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:21:59.5958403+00:00 | 2026-08-28T16:21:59.5958403+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332292 | TRUE | TRUE | 2026-08-28T08:21:59.5958403+00:00 | 2026-08-28T16:21:59.5958403+08:00 | #82962 - MTP: 192hrs - 15H202 HITACHI EX3600-6BH EXCAVATOR | 1.3 | FALSE |  | 2027-04-20T16:00:00+00:00 | 2027-04-28T16:00:00+00:00 | 2027-04-21T00:00:00+08:00 | 2027-04-29T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr shut |  | SSX20227 | [{"equipmentGUID": "77fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "15H202", "name": "15H202 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
83125 | 2026-06-30T22:37:25.9325662+00:00 | 2026-07-01T06:37:25.9325662+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:22:18.1233113+00:00 | 2026-08-28T16:22:18.1233113+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332293 | TRUE | TRUE | 2026-08-28T08:22:18.1233113+00:00 | 2026-08-28T16:22:18.1233113+08:00 | #83125 - PDO: 192hrs - 15W409 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-04-07T16:00:00+00:00 | 2027-04-15T16:00:00+00:00 | 2027-04-08T00:00:00+08:00 | 2027-04-16T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX40927 | [{"equipmentGUID": "abf910f8-637d-f011-a802-002248933a47", "code": "15W409", "name": "15W409 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | PDO | Australia/Perth |  | D-West
82961 | 2026-06-24T01:12:03.7453012+00:00 | 2026-06-24T09:12:03.7453012+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:22:31.5002197+00:00 | 2026-08-28T16:22:31.5002197+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332294 | TRUE | TRUE | 2026-08-28T08:22:31.5002197+00:00 | 2026-08-28T16:22:31.5002197+08:00 | #82961 - BM4: 192hrs - 15H275 HITACHI EX5600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-04-07T16:00:00+00:00 | 2027-04-15T16:00:00+00:00 | 2027-04-08T00:00:00+08:00 | 2027-04-16T00:00:00+08:00 |  |  |  |  | 192.00 | Track Frames, Centre Frame, S/Brg, Hosing |  | SSX27527 | [{"equipmentGUID": "bd28f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15H275", "name": "15H275 Hitachi EX5600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82960 | 2026-06-24T01:10:07.5676636+00:00 | 2026-06-24T09:10:07.5676636+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:22:50.1015617+00:00 | 2026-08-28T16:22:50.1015617+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332295 | TRUE | TRUE | 2026-08-28T08:22:50.1015617+00:00 | 2026-08-28T16:22:50.1015617+08:00 | #82960 - MTP: 192hrs - 15H204 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-03-25T16:00:00+00:00 | 2027-04-02T16:00:00+00:00 | 2027-03-26T00:00:00+08:00 | 2027-04-03T00:00:00+08:00 |  |  |  |  | 192.00 | Track Frame Modules, Cntr Frame, Swing Brg, Cab |  | SSX20427 | [{"equipmentGUID": "4371fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H204", "name": "15H204 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
82959 | 2026-06-24T00:48:10.1708939+00:00 | 2026-06-24T08:48:10.1708939+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:23:27.8452788+00:00 | 2026-08-28T16:23:27.8452788+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332296 | TRUE | TRUE | 2026-08-28T08:23:27.8452788+00:00 | 2026-08-28T16:23:27.8452788+08:00 | #82959 - BM4: 288hrs - 15H292 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-03-21T16:00:00+00:00 | 2027-04-02T16:00:00+00:00 | 2027-03-22T00:00:00+08:00 | 2027-04-03T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX29227 | [{"equipmentGUID": "1433f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H292", "name": "15H292 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82958 | 2026-06-24T00:41:06.1973852+00:00 | 2026-06-24T08:41:06.1973852+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:23:44.1102368+00:00 | 2026-08-28T16:23:44.1102368+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332297 | TRUE | TRUE | 2026-08-28T08:23:44.1102368+00:00 | 2026-08-28T16:23:44.1102368+08:00 | #82958 - RVA: 240hrs - 15R381 HITACHI EX3600-7BH EXCAVATOR | 1.3 | FALSE |  | 2027-03-05T16:00:00+00:00 | 2027-03-15T16:00:00+00:00 | 2027-03-06T00:00:00+08:00 | 2027-03-16T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX38127 | [{"equipmentGUID": "6019f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15R381", "name": "15R381 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | RVA | Australia/Perth |  | D-West
82957 | 2026-06-24T00:39:35.7392758+00:00 | 2026-06-24T08:39:35.7392758+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:23:57.5729154+00:00 | 2026-08-28T16:23:57.5729154+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332298 | TRUE | TRUE | 2026-08-28T08:23:57.5729154+00:00 | 2026-08-28T16:23:57.5729154+08:00 | #82957 - BM4: 216hrs - 15H411 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-02-18T16:00:00+00:00 | 2027-02-27T16:00:00+00:00 | 2027-02-19T00:00:00+08:00 | 2027-02-28T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX41127 | [{"equipmentGUID": "8041f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H411", "name": "15H411 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82956 | 2026-06-24T00:37:26.2742636+00:00 | 2026-06-24T08:37:26.2742636+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:24:16.4745948+00:00 | 2026-08-28T16:24:16.4745948+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332299 | TRUE | TRUE | 2026-08-28T08:24:16.4745948+00:00 | 2026-08-28T16:24:16.4745948+08:00 | #82956 - MTP: 240hrs - 15H430 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-01-20T16:00:00+00:00 | 2027-01-30T16:00:00+00:00 | 2027-01-21T00:00:00+08:00 | 2027-01-31T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX43027 | [{"equipmentGUID": "2e22f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H430", "name": "15H430 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
82955 | 2026-06-24T00:36:10.6743905+00:00 | 2026-06-24T08:36:10.6743905+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T08:24:35.6852057+00:00 | 2026-08-28T16:24:35.6852057+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332300 | TRUE | TRUE | 2026-08-28T08:24:35.6852057+00:00 | 2026-08-28T16:24:35.6852057+08:00 | #82955 - NBWT: 192hrs - 15H211 HITACHI EX8000-6FS FACE SHOVEL | 1.2 | FALSE |  | 2027-01-06T16:00:00+00:00 | 2027-01-14T16:00:00+00:00 | 2027-01-07T00:00:00+08:00 | 2027-01-15T00:00:00+08:00 |  |  |  |  | 192.00 | Pump Modules, Undercarriage |  | SSX21127 | [{"equipmentGUID": "7e26f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H211", "name": "15H211 Hitachi EX8000-6FS Face Shovel", "assetClass": {"name": "Shovel - Face"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | NBWT | Australia/Perth |  | D-West
82953 | 2026-06-24T00:25:55.2736147+00:00 | 2026-06-24T08:25:55.2736147+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:55:15.9722717+00:00 | 2026-08-28T14:55:15.9722717+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332225 | TRUE | TRUE | 2026-08-28T06:55:15.9722717+00:00 | 2026-08-28T14:55:15.9722717+08:00 | #82953 - WAN: 216hrs - 15R431 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-11-12T16:00:00+00:00 | 2027-11-21T16:00:00+00:00 | 2027-11-13T00:00:00+08:00 | 2027-11-22T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX43127 | [{"equipmentGUID": "30efe8bf-7c7b-ee11-a846-000d3acacefd", "code": "15R431", "name": "15R431 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | D-East
82975 | 2026-06-24T01:40:55.4779436+00:00 | 2026-06-24T09:40:55.4779436+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:54:35.1717182+00:00 | 2026-08-28T14:54:35.1717182+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332222 | TRUE | TRUE | 2026-08-28T06:54:35.1717182+00:00 | 2026-08-28T14:54:35.1717182+08:00 | #82975 - MTP: 288hrs - 15H380 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-11-24T16:00:00+00:00 | 2027-12-06T16:00:00+00:00 | 2027-11-25T00:00:00+08:00 | 2027-12-07T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Module Shut ,MCV, Cntr Frame , Swing Brg, Cab |  | SSX38027 | [{"equipmentGUID": "cd63fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H380", "name": "15H380 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
82973 | 2026-06-24T01:36:21.1994097+00:00 | 2026-06-24T09:36:21.1994097+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:56:12.8948412+00:00 | 2026-08-28T14:56:12.8948412+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332230 | TRUE | TRUE | 2026-08-28T06:56:12.8948412+00:00 | 2026-08-28T14:56:12.8948412+08:00 | #82973 - BM4: 288hrs - 15H305 HITACHI EX5600-7LD FACE SHOVEL | 1.2 | FALSE |  | 2027-10-22T16:00:00+00:00 | 2027-11-03T16:00:00+00:00 | 2027-10-23T00:00:00+08:00 | 2027-11-04T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut , FS to BH Conversion |  | SSX30527 | [{"equipmentGUID": "fd55fbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H305", "name": "15H305 Hitachi EX5600-7LD Face Shovel", "assetClass": {"name": "Shovel - Face"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
82952 | 2026-06-24T00:24:19.4345536+00:00 | 2026-06-24T08:24:19.4345536+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:56:57.0274725+00:00 | 2026-08-28T14:56:57.0274725+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332233 | TRUE | TRUE | 2026-08-28T06:56:57.0274725+00:00 | 2026-08-28T14:56:57.0274725+08:00 | #82952 - WAN: 240hrs - 15R297 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-10-15T16:00:00+00:00 | 2027-10-25T16:00:00+00:00 | 2027-10-16T00:00:00+08:00 | 2027-10-26T00:00:00+08:00 |  |  |  |  | 240.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX29727 | [{"equipmentGUID": "4e3cf6bf-7c7b-ee11-a846-000d3acacefd", "code": "15R297", "name": "15R297 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | D-East
82972 | 2026-06-24T01:35:03.065756+00:00 | 2026-06-24T09:35:03.065756+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:57:46.1697062+00:00 | 2026-08-28T14:57:46.1697062+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332237 | TRUE | TRUE | 2026-08-28T06:57:46.1697062+00:00 | 2026-08-28T14:57:46.1697062+08:00 | #82972 - BM4: 288hrs - 15H363 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-10-05T16:00:00+00:00 | 2027-10-17T16:00:00+00:00 | 2027-10-06T00:00:00+08:00 | 2027-10-18T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX36327 | [{"equipmentGUID": "abbbf9be-50c3-ee11-a849-000d3acacefd", "code": "15H363", "name": "15H363 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | BM4 | Australia/Perth |  | D-West
83131 | 2026-06-30T22:43:24.654243+00:00 | 2026-07-01T06:43:24.654243+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:58:15.7156435+00:00 | 2026-08-28T14:58:15.7156435+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332239 | TRUE | TRUE | 2026-08-28T06:58:15.7156435+00:00 | 2026-08-28T14:58:15.7156435+08:00 | #83131 - HD4: 216hrs - 15D369 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-10-01T16:00:00+00:00 | 2027-10-10T16:00:00+00:00 | 2027-10-02T00:00:00+08:00 | 2027-10-11T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX36927 | [{"equipmentGUID": "362a9077-5f7d-f011-a802-002248933a47", "code": "15D369", "name": "15D369 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | D-East
82971 | 2026-06-24T01:33:07.9727391+00:00 | 2026-06-24T09:33:07.9727391+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T06:59:19.9495113+00:00 | 2026-08-28T14:59:19.9495113+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332242 | TRUE | TRUE | 2026-08-28T06:59:19.9495113+00:00 | 2026-08-28T14:59:19.9495113+08:00 | #82971 - MTP: 288hrs - 15H242 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-09-17T16:00:00+00:00 | 2027-09-29T16:00:00+00:00 | 2027-09-18T00:00:00+08:00 | 2027-09-30T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Module Shut ,MCV, Cntr Frame , Swing Brg, Cab |  | SSX24227 | [{"equipmentGUID": "cb4ffbbf-7c7b-ee11-a846-000d3acacefd", "code": "15H242", "name": "15H242 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | MTP | Australia/Perth |  | D-West
82951 | 2026-06-24T00:21:55.4311465+00:00 | 2026-06-24T08:21:55.4311465+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:05:07.359648+00:00 | 2026-08-28T15:05:07.359648+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332244 | TRUE | TRUE | 2026-08-28T07:05:07.359648+00:00 | 2026-08-28T15:05:07.359648+08:00 | #82951 - WAN: 288hrs - 15R251 HITACHI EX5600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-09-13T16:00:00+00:00 | 2027-09-25T16:00:00+00:00 | 2027-09-14T00:00:00+08:00 | 2027-09-26T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX25127 | [{"equipmentGUID": "00d800c0-7c7b-ee11-a846-000d3acacefd", "code": "15R251", "name": "15R251 Hitachi EX5600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | D-East
82950 | 2026-06-24T00:20:24.266087+00:00 | 2026-06-24T08:20:24.266087+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:05:18.3643266+00:00 | 2026-08-28T15:05:18.3643266+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332245 | TRUE | TRUE | 2026-08-28T07:05:18.3643266+00:00 | 2026-08-28T15:05:18.3643266+08:00 | #82950 - HD1: 216hrs - 15D262 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-08-30T16:00:00+00:00 | 2027-09-08T16:00:00+00:00 | 2027-08-31T00:00:00+08:00 | 2027-09-09T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX26227 | [{"equipmentGUID": "e924f0bf-7c7b-ee11-a846-000d3acacefd", "code": "15D262", "name": "15D262 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD1 | Australia/Perth |  | D-East
83128 | 2026-06-30T22:40:47.0149765+00:00 | 2026-07-01T06:40:47.0149765+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:05:42.6031717+00:00 | 2026-08-28T15:05:42.6031717+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332247 | TRUE | TRUE | 2026-08-28T07:05:42.6031717+00:00 | 2026-08-28T15:05:42.6031717+08:00 | #83128 - HD4: 216hrs - 15D365 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-08-02T16:00:00+00:00 | 2027-08-11T16:00:00+00:00 | 2027-08-03T00:00:00+08:00 | 2027-08-12T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX36527 | [{"equipmentGUID": "59bfe343-5f7d-f011-a802-002248933a47", "code": "15D365", "name": "15D365 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | D-East
82944 | 2026-06-23T05:22:05.8536359+00:00 | 2026-06-23T13:22:05.8536359+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:05:55.3851278+00:00 | 2026-08-28T15:05:55.3851278+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332248 | TRUE | TRUE | 2026-08-28T07:05:55.3851278+00:00 | 2026-08-28T15:05:55.3851278+08:00 | #82944 - WAN: 216hrs - 15R349 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-07-18T16:00:00+00:00 | 2027-07-27T16:00:00+00:00 | 2027-07-19T00:00:00+08:00 | 2027-07-28T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut , Swing Bearing |  | SSX34927 | [{"equipmentGUID": "e51ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "15R349", "name": "15R349 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | D-East
83127 | 2026-06-30T22:39:18.2902054+00:00 | 2026-07-01T06:39:18.2902054+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:06:09.7902466+00:00 | 2026-08-28T15:06:09.7902466+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332249 | TRUE | TRUE | 2026-08-28T07:06:09.7902466+00:00 | 2026-08-28T15:06:09.7902466+08:00 | #83127 - HD4: 216hrs - 15D471 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-07-04T16:00:00+00:00 | 2027-07-13T16:00:00+00:00 | 2027-07-05T00:00:00+08:00 | 2027-07-14T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX47127 | [{"equipmentGUID": "e3b76059-5f7d-f011-a802-002248933a47", "code": "15D471", "name": "15D471 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | D-East
82943 | 2026-06-23T05:19:19.4189031+00:00 | 2026-06-23T13:19:19.4189031+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:06:25.1858741+00:00 | 2026-08-28T15:06:25.1858741+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332250 | TRUE | TRUE | 2026-08-28T07:06:25.1858741+00:00 | 2026-08-28T15:06:25.1858741+08:00 | #82943 - YAN: 288hrs - 15H433 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-06-17T16:00:00+00:00 | 2027-06-29T16:00:00+00:00 | 2027-06-18T00:00:00+08:00 | 2027-06-30T00:00:00+08:00 |  |  |  |  | 288.00 | 24,000 hr Full Module Shut , Boom & Arm |  | SSX43327 | [{"equipmentGUID": "733ef6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H433", "name": "15H433 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | D-East
82942 | 2026-06-23T05:14:31.8789542+00:00 | 2026-06-23T13:14:31.8789542+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:06:40.1215582+00:00 | 2026-08-28T15:06:40.1215582+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332251 | TRUE | TRUE | 2026-08-28T07:06:40.1215582+00:00 | 2026-08-28T15:06:40.1215582+08:00 | #82942 - HD1: 192hrs - 15D407 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-06-03T16:00:00+00:00 | 2027-06-11T16:00:00+00:00 | 2027-06-04T00:00:00+08:00 | 2027-06-12T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX40727 | [{"equipmentGUID": "1e0df0bf-7c7b-ee11-a846-000d3acacefd", "code": "15D407", "name": "15D407 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD1 | Australia/Perth |  | D-East
82939 | 2026-06-23T05:09:24.4978382+00:00 | 2026-06-23T13:09:24.4978382+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:08:14.4192363+00:00 | 2026-08-28T15:08:14.4192363+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332257 | TRUE | TRUE | 2026-08-28T07:08:14.4192363+00:00 | 2026-08-28T15:08:14.4192363+08:00 | #82939 - WAN: 216hrs - 15R283 HITACHI EX5600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-03-22T16:00:00+00:00 | 2027-03-31T16:00:00+00:00 | 2027-03-23T00:00:00+08:00 | 2027-04-01T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX28327 | [{"equipmentGUID": "2edf00c0-7c7b-ee11-a846-000d3acacefd", "code": "15R283", "name": "15R283 Hitachi EX5600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | WAN | Australia/Perth |  | D-East
83116 | 2026-06-30T03:52:20.4896901+00:00 | 2026-06-30T11:52:20.4896901+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:08:34.1281474+00:00 | 2026-08-28T15:08:34.1281474+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332258 | TRUE | TRUE | 2026-08-28T07:08:34.1281474+00:00 | 2026-08-28T15:08:34.1281474+08:00 | #83116 - HD4: 216hrs - 15D487 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-03-07T16:00:00+00:00 | 2027-03-16T16:00:00+00:00 | 2027-03-08T00:00:00+08:00 | 2027-03-17T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX48727 | [{"equipmentGUID": "b8f26e8f-8073-f111-a817-002248933a47", "code": "15D487", "name": "15D487 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | HD4 | Australia/Perth |  | D-East
82938 | 2026-06-23T05:06:40.1873138+00:00 | 2026-06-23T13:06:40.1873138+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:08:48.569407+00:00 | 2026-08-28T15:08:48.569407+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332259 | TRUE | TRUE | 2026-08-28T07:08:48.569407+00:00 | 2026-08-28T15:08:48.569407+08:00 | #82938 - YAN: 192hrs - 15H285 HITACHI EX3600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-02-22T16:00:00+00:00 | 2027-03-02T16:00:00+00:00 | 2027-02-23T00:00:00+08:00 | 2027-03-03T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX28527 | [{"equipmentGUID": "402af6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H285", "name": "15H285 Hitachi EX3600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | D-East
82941 | 2026-06-23T05:12:45.2912733+00:00 | 2026-06-23T13:12:45.2912733+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:07:24.84149+00:00 | 2026-08-28T15:07:24.84149+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332254 | TRUE | TRUE | 2026-08-28T07:07:24.84149+00:00 | 2026-08-28T15:07:24.84149+08:00 | #82941 - YAN: 192hrs - 15H301 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-05-07T16:00:00+00:00 | 2027-05-15T16:00:00+00:00 | 2027-05-08T00:00:00+08:00 | 2027-05-16T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX30127 | [{"equipmentGUID": "fa3af6bf-7c7b-ee11-a846-000d3acacefd", "code": "15H301", "name": "15H301 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | D-East
82940 | 2026-06-23T05:11:08.8314967+00:00 | 2026-06-23T13:11:08.8314967+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:07:42.636146+00:00 | 2026-08-28T15:07:42.636146+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332255 | TRUE | TRUE | 2026-08-28T07:07:42.636146+00:00 | 2026-08-28T15:07:42.636146+08:00 | #82940 - YAN: 192hrs - 15H223 HITACHI EX3600-6BH EXCAVATOR | 1.2 | FALSE |  | 2027-04-25T16:00:00+00:00 | 2027-05-03T16:00:00+00:00 | 2027-04-26T00:00:00+08:00 | 2027-05-04T00:00:00+08:00 |  |  |  |  | 192.00 | 12,000 hr Shut |  | SSX22327 | [{"equipmentGUID": "aae6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "15H223", "name": "15H223 Hitachi EX3600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | D-East
83123 | 2026-06-30T22:35:52.420933+00:00 | 2026-07-01T06:35:52.420933+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-08-28T07:09:15.4925438+00:00 | 2026-08-28T15:09:15.4925438+08:00 | {"principalGUID": "6e528eca-1bdf-46e9-a161-ee26d2ada88a", "displayName": "Goodgame, Nathan (RTIO)"} | {"name": "HME"} | 332261 | TRUE | TRUE | 2026-08-28T07:09:15.4925438+00:00 | 2026-08-28T15:09:15.4925438+08:00 | #83123 - YAN: 216hrs - 15H322 HITACHI EX5600-7BH EXCAVATOR | 1.2 | FALSE |  | 2027-01-19T16:00:00+00:00 | 2027-01-28T16:00:00+00:00 | 2027-01-20T00:00:00+08:00 | 2027-01-29T00:00:00+08:00 |  |  |  |  | 216.00 | 12,000 hr Shut |  | SSX32227 | [{"equipmentGUID": "648529d6-5f7d-f011-a802-002248933a47", "code": "15H322", "name": "15H322 Hitachi EX5600-7BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "emailAddress": "Dale.Solomon@riotinto.com", "displayName": "Solomon, Dale (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 6e528eca-1bdf-46e9-a161-ee26d2ada88a | Goodgame, Nathan (RTIO) | Scheduled | YAN | Australia/Perth |  | D-East
83980 | 2026-09-23T02:26:06.537222+00:00 | 2026-09-23T10:26:06.537222+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T07:27:35.0102101+00:00 | 2026-10-07T15:27:35.0102101+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 335434 | TRUE | TRUE | 2026-10-07T07:27:35.0102101+00:00 | 2026-10-07T15:27:35.0102101+08:00 | #83980 - EII: 6hrs - FUNCTIONAL SAFETY RD1E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-07-25T23:00:00+00:00 | 2027-07-26T05:00:00+00:00 | 2027-07-26T07:00:00+08:00 | 2027-07-26T13:00:00+08:00 |  |  |  |  | 6.00 | FUNCTIONAL SAFETY RD1E - Standalone Outage Outage moved to 26th July / Duration 6HR |  |  | [{"equipmentGUID": "856c6fd5-4a81-ef11-a853-000d3acacefd", "code": "EIISA01", "name": "Sample Station: EII Outloading", "assetClass": {"name": "Sample Station"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
83952 | 2026-09-22T02:13:03.6436717+00:00 | 2026-09-22T10:13:03.6436717+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-08T00:04:48.3167275+00:00 | 2026-10-08T08:04:48.3167275+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 335451 | TRUE | TRUE | 2026-10-08T00:04:48.3167275+00:00 | 2026-10-08T08:04:48.3167275+08:00 | #83952 - EII: 12hrs - FUNCTIONAL SAFETY TCAR - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-12-01T23:00:00+00:00 | 2027-12-02T11:00:00+00:00 | 2027-12-02T07:00:00+08:00 | 2027-12-02T19:00:00+08:00 |  |  |  |  | 12.00 | FUNCTIONAL SAFETY TCAR - Standalone Outage |  |  | [{"equipmentGUID": "9afae8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIITCAR", "name": "Transfer Car: EII", "assetClass": {"name": "Transfer Car"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
83943 | 2026-09-21T01:09:07.8176293+00:00 | 2026-09-21T09:09:07.8176293+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-09-30T05:22:01.9221595+00:00 | 2026-09-30T13:22:01.9221595+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 334653 | TRUE | TRUE | 2026-09-30T05:22:01.9221595+00:00 | 2026-09-30T13:22:01.9221595+08:00 | #83943 - EII: 60hrs - FUNCTIONAL SAFETY ST3EN - STANDALONE OUTAGE | 1.1 | FALSE |  | 2026-11-29T23:00:00+00:00 | 2026-12-02T11:00:00+00:00 | 2026-11-30T07:00:00+08:00 | 2026-12-02T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY ST3EN - Standalone Outage |  |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
84041 | 2026-09-30T01:20:29.1083323+00:00 | 2026-09-30T09:20:29.1083323+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-08T00:10:54.3323513+00:00 | 2026-10-08T08:10:54.3323513+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 335455 | TRUE | TRUE | 2026-10-08T00:10:54.3323513+00:00 | 2026-10-08T08:10:54.3323513+08:00 | #84041 - EII: 36hrs - FUNCTIONAL SAFETY TP11EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-12-16T23:00:00+00:00 | 2027-12-18T11:00:00+00:00 | 2027-12-17T07:00:00+08:00 | 2027-12-18T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP11EN - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
84049 | 2026-09-30T04:49:52.0147616+00:00 | 2026-09-30T12:49:52.0147616+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-02T05:15:55.841339+00:00 | 2026-10-02T13:15:55.841339+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 334986 | TRUE | TRUE | 2026-10-02T05:15:55.841339+00:00 | 2026-10-02T13:15:55.841339+08:00 | #84049 - EII: 60hrs - FUNCTIONAL SAFETY ST2EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-03-04T23:00:00+00:00 | 2027-03-07T11:00:00+00:00 | 2027-03-05T07:00:00+08:00 | 2027-03-07T19:00:00+08:00 |  |  |  |  | 60.00 | FUNCTIONAL SAFETY ST2EN - Standalone Outage |  |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83956, "shutVersionId": 333718, "title": "#83956 - EII: 60hrs - FUNCTIONAL SAFETY TP8EN - STANDALONE OUTAGE", "startDatetimeUTC": "2027-03-04T23:00:00+00:00", "endDatetimeUTC": "2027-03-07T11:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
84051 | 2026-09-30T05:31:50.3064322+00:00 | 2026-09-30T13:31:50.3064322+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-01T00:06:18.6192064+00:00 | 2026-10-01T08:06:18.6192064+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 334754 | TRUE | TRUE | 2026-10-01T00:06:18.6192064+00:00 | 2026-10-01T08:06:18.6192064+08:00 | #84051 - EII: 36hrs - FUNCTIONAL SAFETY TR11E - STANDALONE OUTAGE | 1.0 | FALSE |  | 2026-12-10T23:00:00+00:00 | 2026-12-12T11:00:00+00:00 | 2026-12-11T07:00:00+08:00 | 2026-12-12T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TR11E - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83945, "shutVersionId": 334747, "title": "#83945 - EII: 36hrs - FUNCTIONAL SAFETY TR11E - STANDALONE OUTAGE", "startDatetimeUTC": "2026-12-10T23:00:00+00:00", "endDatetimeUTC": "2026-12-12T11:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
83945 | 2026-09-21T01:20:24.9406376+00:00 | 2026-09-21T09:20:24.9406376+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-10-01T00:00:18.8322982+00:00 | 2026-10-01T08:00:18.8322982+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | {"name": "Fixed Plant"} | 334747 | TRUE | TRUE | 2026-10-01T00:00:18.8322982+00:00 | 2026-10-01T08:00:18.8322982+08:00 | #83945 - EII: 36hrs - FUNCTIONAL SAFETY TR11E - STANDALONE OUTAGE | 2.0 | FALSE |  | 2026-12-10T23:00:00+00:00 | 2026-12-12T11:00:00+00:00 | 2026-12-11T07:00:00+08:00 | 2026-12-12T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TR11E - Standalone Outage | Reduce Duration |  | [{"equipmentGUID": "4375fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV11E", "name": "Conveyor: EII 11E", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "055bd3e7-4a8c-ee11-a847-000d3acacefd", "code": "EIITP11E", "name": "Tripper: EII 11E Long Travel System", "assetClass": {"name": "Tripper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 84051, "shutVersionId": 334754, "title": "#84051 - EII: 36hrs - FUNCTIONAL SAFETY TR11E - STANDALONE OUTAGE", "startDatetimeUTC": "2026-12-10T23:00:00+00:00", "endDatetimeUTC": "2026-12-12T11:00:00+00:00"}}] | [] | [] | [] | Approved | Update | 1e80254d-7a81-489d-b12d-bdda6decb952 | Parad, Edi (RTIO) | Scheduled | EII | Australia/Perth
71466 | 2025-10-27T02:23:27.3235633+00:00 | 2025-10-27T10:23:27.3235633+08:00 | {"principalGUID": "f0731cb1-b9e2-4f23-9860-f27d8e017dcf", "displayName": "Cawthray, Jodie (RTIO)"} | 2026-09-10T00:26:09.1298212+00:00 | 2026-09-10T08:26:09.1298212+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | {"name": "Utilities"} | 333300 | TRUE | TRUE | 2026-09-10T00:26:09.1298212+00:00 | 2026-09-10T08:26:09.1298212+08:00 | #71466 - UTL: 3950hrs - GENERATION: YMPS GTG6 | 2.1 | FALSE |  | 2026-07-19T20:00:00+00:00 | 2026-12-31T10:00:00+00:00 | 2026-07-20T04:00:00+08:00 | 2026-12-31T18:00:00+08:00 |  |  |  |  | 3950.00 | GTG6 HSR GTG6 HPC Top Case GTG6 LPT Removal *************************************************************************** ALSO SHUT #66034: PLACEHOLDER. ---> To be confirmed New AVR and Protection Relay + R2 Testing Running with Load limit. 6 Weeks - Installation + Commissioning of AVR (Testing) - Unit Offline 3 Weeks - Protection Injection Testing + IO Testing (Protection Relays and AVR) + ATE (unit offline not running) 4 Weeks - R2 Testing - Note GTG is running with load limitation. (Unit Running but with load limitation) project work to align with LPT. Package will be empty. Opportunities to do work while engine is offline. To be confirmed by YMPS site stakeholders and Network operation team. 21/11 - 220kV GTG6 6Y CB119051 Maintenance - Hitachi 21/11 - GTG6 MV Frame Partial Discharge Commissioning - Txmonitor |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG6 YMPS", "name": "Generation: YMPS GTG6", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 896842ce-51f5-473e-be8c-96554dbd7a57 | Johns, Kirsten (RTIO-WORKPAC) | Major Projects |  | Australia/Perth
83763 | 2026-08-25T10:00:14.7766884+00:00 | 2026-08-25T18:00:14.7766884+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | 2026-09-11T06:59:06.388907+00:00 | 2026-09-11T14:59:06.388907+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | {"name": "Utilities"} | 333364 | TRUE | TRUE | 2026-09-11T06:59:06.388907+00:00 | 2026-09-11T14:59:06.388907+08:00 | #83763 - UTL: 182hrs - GENERATION: YMPS GTG4 | 2.1 | FALSE |  | 2026-11-24T20:00:00+00:00 | 2026-12-02T10:00:00+00:00 | 2026-11-25T04:00:00+08:00 | 2026-12-02T18:00:00+08:00 |  |  |  |  | 182.00 | 25/11 - 220kV GTG4 6Y CB119011 Maintenance - Hitachi 25/11 - GTG4 MV Frame Partial Discharge Commissioning - Txmonitor GTG4 Borescope Insp GTG4 LM6000PD 8000hr Insp GTG4 8000H LUBE HX Cleaning GTG4 8000H AIRS INST CAL - E/I GTG4 8000H LUBT INST CALIBRATIONS GTG4 8000H LUBE CV Offline Cal - E/I GTG4 8000H LUBG INST CALIBRATIONS GTG4 8000H DRNS OFFLINE INSP - MECH GTG4 8000H COOL INST CAL - E/I GTG4 8000H SPNT INST CALIBRATIONS GTG4 8000H FGCS INST CALIBRATIONS GTG4 8000HR RG LUBE OIL FILTERS GTG4 4000HR GT LUBE OIL FILTERS GTG4 HYSU OFFLINE INSPECTIONS - MECH GTG4 AIRS OFFLINE INSP - E/I GTG4 WTRW Offline Insp - Mech GTG4 TURB OFFLINE INSP - E/I GTG4 FGSS OFFLINE INSP - E/I GTG4 FGSS OFFLINE INSPECTIONS - MECH GTG4 GNRT Inst Inspection-EI GTG4 AIRS OFFLINE INSPECTIONS - MECH GTG4 HYSU Inst Calibration Offline - E/I GTG4 COOL OFFLINE INSP - E/I GTG4 SPNT OFFLINE INSP - E/I MECH GTG4 LUBT OFFLINE INSP GTG4 HYSU OFFLINE INSP - E/I GTG4 NDT acoustic baffles 4000hrs GTG4 COOL OFFLINE INSPECTIONS - MECH GTG4 LUBT OFFLINE INSP - E/I GTG4 LUBG OFFLINE INSPECTIONS - MECH |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG4 YMPS", "name": "Generation: YMPS GTG4", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 896842ce-51f5-473e-be8c-96554dbd7a57 | Johns, Kirsten (RTIO-WORKPAC) | Scheduled |  | Australia/Perth
83764 | 2026-08-25T10:02:30.2670697+00:00 | 2026-08-25T18:02:30.2670697+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | 2026-08-25T22:26:39.7180758+00:00 | 2026-08-26T06:26:39.7180758+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | {"name": "Utilities"} | 331787 | TRUE | TRUE | 2026-08-25T22:26:39.7180758+00:00 | 2026-08-26T06:26:39.7180758+08:00 | #83764 - UTL: 158hrs - GENERATION: YMPS GTG5 | 1.0 | FALSE |  | 2026-12-16T20:00:00+00:00 | 2026-12-23T10:00:00+00:00 | 2026-12-17T04:00:00+08:00 | 2026-12-23T18:00:00+08:00 |  |  |  |  | 158.00 | GTG5 8000H Offline Maintenance GTG5 Borescope Inspection |  |  | [{"equipmentGUID": "", "code": "UTLGENGTG5 YMPS", "name": "Generation: YMPS GTG5", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 896842ce-51f5-473e-be8c-96554dbd7a57 | Johns, Kirsten (RTIO-WORKPAC) | Scheduled |  | Australia/Perth
83947 | 2026-09-21T03:57:34.4541393+00:00 | 2026-09-21T11:57:34.4541393+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | 2026-10-17T08:07:19.6722338+00:00 | 2026-10-17T16:07:19.6722338+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | {"name": "Utilities"} | 336178 | TRUE | TRUE | 2026-10-17T08:07:19.6722338+00:00 | 2026-10-17T16:07:19.6722338+08:00 | #83947 - UTL: 60hrs - GENERATION: CLPS CLG2 | 3.0 | FALSE |  | 2026-12-02T22:00:00+00:00 | 2026-12-05T10:00:00+00:00 | 2026-12-03T06:00:00+08:00 | 2026-12-05T18:00:00+08:00 |  |  |  |  | 60.00 | IHI CLG2 Seasonal Mapping | Reduced capacity to support mapping activities, so pushed back 1 day. |  | [{"equipmentGUID": "", "code": "UTLGENCLG2 CLPS", "name": "Generation: CLPS CLG2", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 896842ce-51f5-473e-be8c-96554dbd7a57 | Johns, Kirsten (RTIO-WORKPAC) | Site Constraint |  | Australia/Perth
83893 | 2026-09-08T01:11:13.6697707+00:00 | 2026-09-08T09:11:13.6697707+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | 2026-09-08T09:35:47.0362844+00:00 | 2026-09-08T17:35:47.0362844+08:00 | {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"} | {"name": "Utilities"} | 333239 | TRUE | TRUE | 2026-09-08T09:35:47.0362844+00:00 | 2026-09-08T17:35:47.0362844+08:00 | #83893 - UTL: 134hrs - GENERATION: CLPS CLG1 | 1.0 | FALSE |  | 2026-12-02T20:00:00+00:00 | 2026-12-08T10:00:00+00:00 | 2026-12-03T04:00:00+08:00 | 2026-12-08T18:00:00+08:00 |  |  |  |  | 134.00 | CLG1 Offline Maintenance |  |  | [{"equipmentGUID": "", "code": "UTLGENCLG1 CLPS", "name": "Generation: CLPS CLG1", "assetClass": {"name": "Generation"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "896842ce-51f5-473e-be8c-96554dbd7a57", "emailAddress": "Kirsten.Johns@riotinto.com", "displayName": "Johns, Kirsten (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 896842ce-51f5-473e-be8c-96554dbd7a57 | Johns, Kirsten (RTIO-WORKPAC) | Scheduled |  | Australia/Perth
68116 | 2025-06-30T06:34:15.3251098+00:00 | 2025-06-30T14:34:15.3251098+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-09-16T03:17:44.6248791+00:00 | 2026-09-16T11:17:44.6248791+08:00 | {"principalGUID": "bf99c16c-f81a-4c00-8a66-0bce2d17ba1f", "displayName": "Hughes, Rory (RTIO)"} | {"name": "HME"} | 333434 | TRUE | TRUE | 2026-09-16T03:17:44.6248791+00:00 | 2026-09-16T11:17:44.6248791+08:00 | #68116 - WAN: 1512hrs - 06R754 CAT 785C WATER TRUCK | 4.0 | FALSE |  | 2027-04-30T22:00:00+00:00 | 2027-07-02T22:00:00+00:00 | 2027-05-01T06:00:00+08:00 | 2027-07-03T06:00:00+08:00 |  |  |  |  | 1512.00 | Cabin?, Engine, Major Components.O/H Major | Shut dates are not yet confirmed with OSR Specialist |  | [{"equipmentGUID": "b823f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06R754", "name": "06R754 CAT 785C Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "d02f8c57-5dce-4935-bccb-22784ffc8eea", "emailAddress": "Tammera.Bellman@riotinto.com", "displayName": "Bellman, Tammera (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | bf99c16c-f81a-4c00-8a66-0bce2d17ba1f | Hughes, Rory (RTIO) | Placeholder | WAN | Australia/Perth |  | OSR
82868 | 2026-06-10T00:09:04.4243022+00:00 | 2026-06-10T08:09:04.4243022+08:00 | {"principalGUID": "6dc018a2-cf34-45b0-ac23-0d4c22b4f6d8", "displayName": "Twyford, William (RTIO)"} | 2026-10-15T00:07:12.9470473+00:00 | 2026-10-15T08:07:12.9470473+08:00 | {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "displayName": "Maksimovic, Aleksandra (RTIO)"} | {"name": "HME"} | 335901 | TRUE | TRUE | 2026-10-15T00:07:12.9470473+00:00 | 2026-10-15T08:07:12.9470473+08:00 | #82868 - NBWT: 336hrs - 15H220 HITACHI EX5600-6BH EXCAVATOR | 4.0 | FALSE |  | 2027-03-02T16:00:00+00:00 | 2027-03-16T16:00:00+00:00 | 2027-03-03T00:00:00+08:00 | 2027-03-17T00:00:00+08:00 |  |  |  |  | 336.00 | Upper main frame crack repairs MOs 74310315 73015322 73272534 74296348 74296350 74429024 | This work is being rescoped and has been penciled in for March 2027. | SXX22027 | [{"equipmentGUID": "2bece8bf-7c7b-ee11-a846-000d3acacefd", "code": "15H220", "name": "15H220 Hitachi EX5600-6BH Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "339b0e7a-e623-4bd7-bfbe-a66fcd773b74", "emailAddress": "Paul.Lucas2@riotinto.com", "displayName": "Paul Lucas"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | dd627053-1751-4788-a180-11d3ab8c2efe | Maksimovic, Aleksandra (RTIO) | Scheduled | NBWT | Australia/Perth |  | Site Team
84479 | 2026-10-15T04:09:06.3041027+00:00 | 2026-10-15T12:09:06.3041027+08:00 | {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "displayName": "Maksimovic, Aleksandra (RTIO)"} | 2026-10-15T04:09:06.3041027+00:00 | 2026-10-15T12:09:06.3041027+08:00 | {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "displayName": "Maksimovic, Aleksandra (RTIO)"} | {"name": "HME"} | 336093 | TRUE | TRUE | 2026-10-15T04:09:06.3041027+00:00 | 2026-10-15T12:09:06.3041027+08:00 | #84479 - NBWT: 192hrs - 06H296 KOMATSU 930E-4 HAUL TRUCK & 06H299 KOMATSU 930E-4AT HAUL TRUCK | 1.0 | FALSE |  | 2027-12-05T16:00:00+00:00 | 2027-12-13T16:00:00+00:00 | 2027-12-06T00:00:00+08:00 | 2027-12-14T00:00:00+08:00 |  |  |  |  | 192.00 | 930E Tray C/O - Q4 |  |  | [{"equipmentGUID": "ccde00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H538", "name": "06H538 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "ca20f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H296", "name": "06H296 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "f469fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H531", "name": "06H531 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "6f13f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H851", "name": "06H851 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "623bf6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H793", "name": "06H793 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "7f16f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H299", "name": "06H299 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d80ff0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H330", "name": "06H330 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "emailAddress": "Aleksandra.Maksimovic@riotinto.com", "displayName": "Maksimovic, Aleksandra (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6dc018a2-cf34-45b0-ac23-0d4c22b4f6d8", "emailAddress": "William.Twyford@riotinto.com", "displayName": "Twyford, William (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | dd627053-1751-4788-a180-11d3ab8c2efe | Maksimovic, Aleksandra (RTIO) | Placeholder | NBWT | Australia/Perth |  | Site Team
84478 | 2026-10-15T04:06:33.146608+00:00 | 2026-10-15T12:06:33.146608+08:00 | {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "displayName": "Maksimovic, Aleksandra (RTIO)"} | 2026-10-15T04:09:54.7328997+00:00 | 2026-10-15T12:09:54.7328997+08:00 | {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "displayName": "Maksimovic, Aleksandra (RTIO)"} | {"name": "HME"} | 336094 | TRUE | TRUE | 2026-10-15T04:09:54.7328997+00:00 | 2026-10-15T12:09:54.7328997+08:00 | #84478 - NBWT: 192hrs - 06H297 KOMATSU 930E-4AT HAUL TRUCK & 06H298 KOMATSU 930E-4 HAUL TRUCK | 1.1 | FALSE |  | 2027-06-20T16:00:00+00:00 | 2027-06-28T16:00:00+00:00 | 2027-06-21T00:00:00+08:00 | 2027-06-29T00:00:00+08:00 |  |  |  |  | 192.00 | 930E Tray C/O - Quarter 2 |  |  | [{"equipmentGUID": "91ebe8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H574", "name": "06H574 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "d7fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H297", "name": "06H297 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "722af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H298", "name": "06H298 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "4634f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H580", "name": "06H580 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "b627f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H852", "name": "06H852 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "79da00c0-7c7b-ee11-a846-000d3acacefd", "code": "06H783", "name": "06H783 Komatsu 930E-4 Haul Truck", "assetClass": {"name": "Truck - Haul"}}, {"equipmentGUID": "86d600c0-7c7b-ee11-a846-000d3acacefd", "code": "06H835", "name": "06H835 Komatsu 930E-4AT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "dd627053-1751-4788-a180-11d3ab8c2efe", "emailAddress": "Aleksandra.Maksimovic@riotinto.com", "displayName": "Maksimovic, Aleksandra (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6dc018a2-cf34-45b0-ac23-0d4c22b4f6d8", "emailAddress": "William.Twyford@riotinto.com", "displayName": "Twyford, William (RTIO)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Update | dd627053-1751-4788-a180-11d3ab8c2efe | Maksimovic, Aleksandra (RTIO) | Placeholder | NBWT | Australia/Perth |  | Site Team
83408 | 2026-07-02T06:21:34.922413+00:00 | 2026-07-02T14:21:34.922413+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-02T06:21:34.922413+00:00 | 2026-07-02T14:21:34.922413+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329236 | TRUE | TRUE | 2026-07-02T06:21:34.922413+00:00 | 2026-07-02T14:21:34.922413+08:00 | #83408 - GDI: 348hrs - 06B361 CAT 793F-RBT HAUL TRUCK | 1.0 | FALSE |  | 2027-09-30T22:00:00+00:00 | 2027-10-15T10:00:00+00:00 | 2027-10-01T06:00:00+08:00 | 2027-10-15T18:00:00+08:00 | 2027-09-30T20:00:00+00:00 |  | 2027-10-01T04:00:00+08:00 |  | 348.00 | 06B361 shut |  |  | [{"equipmentGUID": "c5e13d2b-637d-f011-a802-002248933a47", "code": "06B361", "name": "06B361 CAT 793F-RBT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83409 | 2026-07-02T06:26:46.1075477+00:00 | 2026-07-02T14:26:46.1075477+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-02T06:26:46.1075477+00:00 | 2026-07-02T14:26:46.1075477+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329237 | TRUE | TRUE | 2026-07-02T06:26:46.1075477+00:00 | 2026-07-02T14:26:46.1075477+08:00 | #83409 - GDI: 348hrs - 06B363 CAT 793F-RBT HAUL TRUCK | 1.0 | FALSE |  | 2027-10-18T22:00:00+00:00 | 2027-11-02T10:00:00+00:00 | 2027-10-19T06:00:00+08:00 | 2027-11-02T18:00:00+08:00 | 2027-10-18T20:00:00+00:00 |  | 2027-10-19T04:00:00+08:00 |  | 348.00 | 06B363 shut |  |  | [{"equipmentGUID": "81dcf534-637d-f011-a802-002248933a47", "code": "06B363", "name": "06B363 CAT 793F-RBT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83410 | 2026-07-02T06:29:37.736259+00:00 | 2026-07-02T14:29:37.736259+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-02T06:29:37.736259+00:00 | 2026-07-02T14:29:37.736259+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329238 | TRUE | TRUE | 2026-07-02T06:29:37.736259+00:00 | 2026-07-02T14:29:37.736259+08:00 | #83410 - GDI: 348hrs - 06B359 CAT 793F-RBT HAUL TRUCK | 1.0 | FALSE |  | 2027-11-04T22:00:00+00:00 | 2027-11-19T10:00:00+00:00 | 2027-11-05T06:00:00+08:00 | 2027-11-19T18:00:00+08:00 | 2027-11-04T20:00:00+00:00 |  | 2027-11-05T04:00:00+08:00 |  | 348.00 | 06B359 shut |  |  | [{"equipmentGUID": "616c8123-637d-f011-a802-002248933a47", "code": "06B359", "name": "06B359 CAT 793F-RBT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83640 | 2026-08-04T01:28:48.3818424+00:00 | 2026-08-04T09:28:48.3818424+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-08-04T01:28:48.3818424+00:00 | 2026-08-04T09:28:48.3818424+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 330812 | TRUE | TRUE | 2026-08-04T01:28:48.3818424+00:00 | 2026-08-04T09:28:48.3818424+08:00 | #83640 - MDO: 324hrs - 06H555 CAT SERVICE TRUCK | 1.0 | FALSE |  | 2027-01-21T22:00:00+00:00 | 2027-02-04T10:00:00+00:00 | 2027-01-22T06:00:00+08:00 | 2027-02-04T18:00:00+08:00 | 2027-01-21T20:00:00+00:00 |  | 2027-01-22T04:00:00+08:00 |  | 324.00 | 06H555 site shut - all major components including Engine |  |  | [{"equipmentGUID": "7cd100c0-7c7b-ee11-a846-000d3acacefd", "code": "06H555", "name": "06H555 CAT Service Truck", "assetClass": {"name": "Truck - Service"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83641 | 2026-08-04T01:41:22.8855222+00:00 | 2026-08-04T09:41:22.8855222+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-08-04T01:41:22.8855222+00:00 | 2026-08-04T09:41:22.8855222+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 330813 | TRUE | TRUE | 2026-08-04T01:41:22.8855222+00:00 | 2026-08-04T09:41:22.8855222+08:00 | #83641 - MDO: 324hrs - 06H166 CAT 777F WATER TRUCK | 1.0 | FALSE |  | 2027-02-08T22:00:00+00:00 | 2027-02-22T10:00:00+00:00 | 2027-02-09T06:00:00+08:00 | 2027-02-22T18:00:00+08:00 | 2027-02-08T20:00:00+00:00 |  | 2027-02-09T04:00:00+08:00 |  | 324.00 | 06H166 sites shut - 36,000Hr |  |  | [{"equipmentGUID": "4532f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H166", "name": "06H166 CAT 777F Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Radiator Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83642 | 2026-08-04T03:26:53.6118825+00:00 | 2026-08-04T11:26:53.6118825+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-08-04T03:26:53.6118825+00:00 | 2026-08-04T11:26:53.6118825+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 330820 | TRUE | TRUE | 2026-08-04T03:26:53.6118825+00:00 | 2026-08-04T11:26:53.6118825+08:00 | #83642 - MDO: 240hrs - 06H553 CAT 777G WATER TRUCK | 1.0 | FALSE |  | 2027-05-24T22:00:00+00:00 | 2027-06-03T22:00:00+00:00 | 2027-05-25T06:00:00+08:00 | 2027-06-04T06:00:00+08:00 | 2027-05-03T20:00:00+00:00 |  | 2027-05-04T04:00:00+08:00 |  | 240.00 | 06H553 OSR shut |  |  | [{"equipmentGUID": "8837f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H553", "name": "06H553 CAT 777G Water Truck", "assetClass": {"name": "Truck - Water"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | OSR
82985 | 2026-06-26T02:44:09.5091763+00:00 | 2026-06-26T10:44:09.5091763+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T02:44:09.5091763+00:00 | 2026-06-26T10:44:09.5091763+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328503 | TRUE | TRUE | 2026-06-26T02:44:09.5091763+00:00 | 2026-06-26T10:44:09.5091763+08:00 | #82985 - GDI: 348hrs - 06B846 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-01-11T22:00:00+00:00 | 2027-01-26T10:00:00+00:00 | 2027-01-12T06:00:00+08:00 | 2027-01-26T18:00:00+08:00 | 2027-01-11T20:00:00+00:00 |  | 2027-01-12T04:00:00+08:00 |  | 348.00 | 06B846 - 36000 hour shut. |  |  | [{"equipmentGUID": "6b6dfbbf-7c7b-ee11-a846-000d3acacefd", "code": "06B846", "name": "06B846 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82986 | 2026-06-26T02:49:39.5758237+00:00 | 2026-06-26T10:49:39.5758237+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T02:49:39.5758237+00:00 | 2026-06-26T10:49:39.5758237+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328504 | TRUE | TRUE | 2026-06-26T02:49:39.5758237+00:00 | 2026-06-26T10:49:39.5758237+08:00 | #82986 - GDI: 348hrs - 06B843 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-01-28T22:00:00+00:00 | 2027-02-12T10:00:00+00:00 | 2027-01-29T06:00:00+08:00 | 2027-02-12T18:00:00+08:00 | 2027-01-28T20:00:00+00:00 |  | 2027-01-29T04:00:00+08:00 |  | 348.00 | 06B843 - 36000 hour shut. |  |  | [{"equipmentGUID": "52e8e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B843", "name": "06B843 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82987 | 2026-06-26T03:03:22.2539665+00:00 | 2026-06-26T11:03:22.2539665+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:03:22.2539665+00:00 | 2026-06-26T11:03:22.2539665+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328505 | TRUE | TRUE | 2026-06-26T03:03:22.2539665+00:00 | 2026-06-26T11:03:22.2539665+08:00 | #82987 - GDI: 348hrs - 06B805 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-02-15T22:00:00+00:00 | 2027-03-02T10:00:00+00:00 | 2027-02-16T06:00:00+08:00 | 2027-03-02T18:00:00+08:00 | 2027-02-15T20:00:00+00:00 |  | 2027-02-16T04:00:00+08:00 |  | 348.00 | 06B805 - 36000 hour shut. |  |  | [{"equipmentGUID": "1b39f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06B805", "name": "06B805 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82988 | 2026-06-26T03:17:27.4225261+00:00 | 2026-06-26T11:17:27.4225261+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:17:27.4225261+00:00 | 2026-06-26T11:17:27.4225261+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328506 | TRUE | TRUE | 2026-06-26T03:17:27.4225261+00:00 | 2026-06-26T11:17:27.4225261+08:00 | #82988 - GDI: 348hrs - 06B842 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-03-04T22:00:00+00:00 | 2027-03-19T10:00:00+00:00 | 2027-03-05T06:00:00+08:00 | 2027-03-19T18:00:00+08:00 | 2027-03-04T20:00:00+00:00 |  | 2027-03-05T04:00:00+08:00 |  | 348.00 | 06B842 - 36000 hour shut. |  |  | [{"equipmentGUID": "98e000c0-7c7b-ee11-a846-000d3acacefd", "code": "06B842", "name": "06B842 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82989 | 2026-06-26T03:21:48.2843646+00:00 | 2026-06-26T11:21:48.2843646+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:21:48.2843646+00:00 | 2026-06-26T11:21:48.2843646+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328507 | TRUE | TRUE | 2026-06-26T03:21:48.2843646+00:00 | 2026-06-26T11:21:48.2843646+08:00 | #82989 - GDI: 348hrs - 06B840 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-03-22T22:00:00+00:00 | 2027-04-06T10:00:00+00:00 | 2027-03-23T06:00:00+08:00 | 2027-04-06T18:00:00+08:00 | 2027-03-22T20:00:00+00:00 |  | 2027-03-23T04:00:00+08:00 |  | 348.00 | 06B840 - 36000 hour shut. |  |  | [{"equipmentGUID": "05f2e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B840", "name": "06B840 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82990 | 2026-06-26T03:32:12.6337964+00:00 | 2026-06-26T11:32:12.6337964+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:32:12.6337964+00:00 | 2026-06-26T11:32:12.6337964+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328508 | TRUE | TRUE | 2026-06-26T03:32:12.6337964+00:00 | 2026-06-26T11:32:12.6337964+08:00 | #82990 - GDI: 348hrs - 06B844 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-04-08T22:00:00+00:00 | 2027-04-23T10:00:00+00:00 | 2027-04-09T06:00:00+08:00 | 2027-04-23T18:00:00+08:00 | 2027-04-08T20:00:00+00:00 |  | 2027-04-09T04:00:00+08:00 |  | 348.00 | 06B844 - 36000 hour shut. |  |  | [{"equipmentGUID": "c420f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06B844", "name": "06B844 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82991 | 2026-06-26T03:38:26.1600885+00:00 | 2026-06-26T11:38:26.1600885+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:38:26.1600885+00:00 | 2026-06-26T11:38:26.1600885+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328510 | TRUE | TRUE | 2026-06-26T03:38:26.1600885+00:00 | 2026-06-26T11:38:26.1600885+08:00 | #82991 - GDI: 348hrs - 06B845 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-04-26T22:00:00+00:00 | 2027-05-11T10:00:00+00:00 | 2027-04-27T06:00:00+08:00 | 2027-05-11T18:00:00+08:00 | 2027-04-26T20:00:00+00:00 |  | 2027-04-27T04:00:00+08:00 |  | 348.00 | 06B845 - 36000 hour shut. |  |  | [{"equipmentGUID": "90dce8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B845", "name": "06B845 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82992 | 2026-06-26T03:42:22.9414206+00:00 | 2026-06-26T11:42:22.9414206+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:42:22.9414206+00:00 | 2026-06-26T11:42:22.9414206+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328511 | TRUE | TRUE | 2026-06-26T03:42:22.9414206+00:00 | 2026-06-26T11:42:22.9414206+08:00 | #82992 - GDI: 348hrs - 06B838 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-05-13T22:00:00+00:00 | 2027-05-28T10:00:00+00:00 | 2027-05-14T06:00:00+08:00 | 2027-05-28T18:00:00+08:00 | 2027-05-13T20:00:00+00:00 |  | 2027-05-14T04:00:00+08:00 |  | 348.00 | 06B838 - 36000 hour shut. |  |  | [{"equipmentGUID": "1772fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06B838", "name": "06B838 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82993 | 2026-06-26T03:46:25.9310525+00:00 | 2026-06-26T11:46:25.9310525+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:46:25.9310525+00:00 | 2026-06-26T11:46:25.9310525+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328512 | TRUE | TRUE | 2026-06-26T03:46:25.9310525+00:00 | 2026-06-26T11:46:25.9310525+08:00 | #82993 - GDI: 348hrs - 06B352 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-05-31T22:00:00+00:00 | 2027-06-15T10:00:00+00:00 | 2027-06-01T06:00:00+08:00 | 2027-06-15T18:00:00+08:00 | 2027-05-31T20:00:00+00:00 |  | 2027-06-01T04:00:00+08:00 |  | 348.00 | 06B352 - 36000 hour shut. |  |  | [{"equipmentGUID": "01f6e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B352", "name": "06B352 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82994 | 2026-06-26T03:49:59.9362794+00:00 | 2026-06-26T11:49:59.9362794+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:49:59.9362794+00:00 | 2026-06-26T11:49:59.9362794+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328513 | TRUE | TRUE | 2026-06-26T03:49:59.9362794+00:00 | 2026-06-26T11:49:59.9362794+08:00 | #82994 - GDI: 348hrs - 06B356 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-06-17T22:00:00+00:00 | 2027-07-02T10:00:00+00:00 | 2027-06-18T06:00:00+08:00 | 2027-07-02T18:00:00+08:00 | 2027-06-17T20:00:00+00:00 |  | 2027-06-18T04:00:00+08:00 |  | 348.00 | 06B356 - 36000 hour shut. |  |  | [{"equipmentGUID": "1af4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06B356", "name": "06B356 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82995 | 2026-06-26T03:55:19.6262556+00:00 | 2026-06-26T11:55:19.6262556+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:55:19.6262556+00:00 | 2026-06-26T11:55:19.6262556+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328514 | TRUE | TRUE | 2026-06-26T03:55:19.6262556+00:00 | 2026-06-26T11:55:19.6262556+08:00 | #82995 - GDI: 348hrs - 06B357 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-07-05T22:00:00+00:00 | 2027-07-20T10:00:00+00:00 | 2027-07-06T06:00:00+08:00 | 2027-07-20T18:00:00+08:00 | 2027-07-05T20:00:00+00:00 |  | 2027-07-06T04:00:00+08:00 |  | 348.00 | 06B357 - 36000 hour shut. |  |  | [{"equipmentGUID": "ad24f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06B357", "name": "06B357 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82996 | 2026-06-26T03:59:02.4897716+00:00 | 2026-06-26T11:59:02.4897716+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T03:59:02.4897716+00:00 | 2026-06-26T11:59:02.4897716+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328515 | TRUE | TRUE | 2026-06-26T03:59:02.4897716+00:00 | 2026-06-26T11:59:02.4897716+08:00 | #82996 - GDI: 348hrs - 06B355 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-07-22T22:00:00+00:00 | 2027-08-06T10:00:00+00:00 | 2027-07-23T06:00:00+08:00 | 2027-08-06T18:00:00+08:00 | 2027-07-22T20:00:00+00:00 |  | 2027-07-23T04:00:00+08:00 |  | 348.00 | 06B355 - 36000 hour shut. |  |  | [{"equipmentGUID": "352af0bf-7c7b-ee11-a846-000d3acacefd", "code": "06B355", "name": "06B355 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
82997 | 2026-06-26T04:02:31.845807+00:00 | 2026-06-26T12:02:31.845807+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T04:02:31.845807+00:00 | 2026-06-26T12:02:31.845807+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328517 | TRUE | TRUE | 2026-06-26T04:02:31.845807+00:00 | 2026-06-26T12:02:31.845807+08:00 | #82997 - GDI: 348hrs - 06B358 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-08-09T22:00:00+00:00 | 2027-08-24T10:00:00+00:00 | 2027-08-10T06:00:00+08:00 | 2027-08-24T18:00:00+08:00 | 2027-08-09T20:00:00+00:00 |  | 2027-08-10T04:00:00+08:00 |  | 348.00 | 06B358 - 36000 hour shut. |  |  | [{"equipmentGUID": "16e100c0-7c7b-ee11-a846-000d3acacefd", "code": "06B358", "name": "06B358 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83048 | 2026-06-26T04:42:32.721108+00:00 | 2026-06-26T12:42:32.721108+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T04:42:32.721108+00:00 | 2026-06-26T12:42:32.721108+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328570 | TRUE | TRUE | 2026-06-26T04:42:32.721108+00:00 | 2026-06-26T12:42:32.721108+08:00 | #83048 - GDI: 348hrs - 06B353 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-08-26T22:00:00+00:00 | 2027-09-10T10:00:00+00:00 | 2027-08-27T06:00:00+08:00 | 2027-09-10T18:00:00+08:00 | 2027-08-26T20:00:00+00:00 |  | 2027-08-27T04:00:00+08:00 |  | 348.00 | 06B353 - 36000 hour shut. |  |  | [{"equipmentGUID": "1fe000c0-7c7b-ee11-a846-000d3acacefd", "code": "06B353", "name": "06B353 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83049 | 2026-06-26T04:45:53.1644071+00:00 | 2026-06-26T12:45:53.1644071+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-06-26T04:45:53.1644071+00:00 | 2026-06-26T12:45:53.1644071+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 328571 | TRUE | TRUE | 2026-06-26T04:45:53.1644071+00:00 | 2026-06-26T12:45:53.1644071+08:00 | #83049 - GDI: 348hrs - 06H313 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-11-22T22:00:00+00:00 | 2027-12-07T10:00:00+00:00 | 2027-11-23T06:00:00+08:00 | 2027-12-07T18:00:00+08:00 | 2027-11-22T20:00:00+00:00 |  | 2027-11-23T04:00:00+08:00 |  | 348.00 | 06H313 - 18000 hour shut. |  |  | [{"equipmentGUID": "b938f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H313", "name": "06H313 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
83256 | 2026-07-01T04:02:54.3882194+00:00 | 2026-07-01T12:02:54.3882194+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:02:54.3882194+00:00 | 2026-07-01T12:02:54.3882194+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329026 | TRUE | TRUE | 2026-07-01T04:02:54.3882194+00:00 | 2026-07-01T12:02:54.3882194+08:00 | #83256 - MDO: 324hrs - 06H547 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-02-25T22:00:00+00:00 | 2027-03-11T10:00:00+00:00 | 2027-02-26T06:00:00+08:00 | 2027-03-11T18:00:00+08:00 | 2027-02-25T20:00:00+00:00 |  | 2027-02-26T04:00:00+08:00 |  | 324.00 | 06H547shut |  |  | [{"equipmentGUID": "0352fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H547", "name": "06H547 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83257 | 2026-07-01T04:09:06.194929+00:00 | 2026-07-01T12:09:06.194929+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:09:06.194929+00:00 | 2026-07-01T12:09:06.194929+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329027 | TRUE | TRUE | 2026-07-01T04:09:06.194929+00:00 | 2026-07-01T12:09:06.194929+08:00 | #83257 - MDO: 324hrs - 06H311 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-03-15T22:00:00+00:00 | 2027-03-29T10:00:00+00:00 | 2027-03-16T06:00:00+08:00 | 2027-03-29T18:00:00+08:00 | 2027-03-15T20:00:00+00:00 |  | 2027-03-16T04:00:00+08:00 |  | 324.00 | 06H311 shut |  |  | [{"equipmentGUID": "b925f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H311", "name": "06H311 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83258 | 2026-07-01T04:16:35.9065836+00:00 | 2026-07-01T12:16:35.9065836+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:16:35.9065836+00:00 | 2026-07-01T12:16:35.9065836+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329028 | TRUE | TRUE | 2026-07-01T04:16:35.9065836+00:00 | 2026-07-01T12:16:35.9065836+08:00 | #83258 - MDO: 324hrs - 06H618 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-04-01T22:00:00+00:00 | 2027-04-15T10:00:00+00:00 | 2027-04-02T06:00:00+08:00 | 2027-04-15T18:00:00+08:00 | 2027-04-01T20:00:00+00:00 |  | 2027-04-02T04:00:00+08:00 |  | 324.00 | 06H618 shut |  |  | [{"equipmentGUID": "95f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H618", "name": "06H618 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83259 | 2026-07-01T04:37:03.9762185+00:00 | 2026-07-01T12:37:03.9762185+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:37:03.9762185+00:00 | 2026-07-01T12:37:03.9762185+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329029 | TRUE | TRUE | 2026-07-01T04:37:03.9762185+00:00 | 2026-07-01T12:37:03.9762185+08:00 | #83259 - MDO: 324hrs - 06H548 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-04-19T22:00:00+00:00 | 2027-05-03T10:00:00+00:00 | 2027-04-20T06:00:00+08:00 | 2027-05-03T18:00:00+08:00 | 2027-04-19T20:00:00+00:00 |  | 2027-04-20T04:00:00+08:00 |  | 324.00 | 06H548 shut |  |  | [{"equipmentGUID": "cfd200c0-7c7b-ee11-a846-000d3acacefd", "code": "06H548", "name": "06H548 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83260 | 2026-07-01T04:43:42.0927898+00:00 | 2026-07-01T12:43:42.0927898+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:43:42.0927898+00:00 | 2026-07-01T12:43:42.0927898+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329030 | TRUE | TRUE | 2026-07-01T04:43:42.0927898+00:00 | 2026-07-01T12:43:42.0927898+08:00 | #83260 - MDO: 324hrs - 06H323 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-05-06T22:00:00+00:00 | 2027-05-20T10:00:00+00:00 | 2027-05-07T06:00:00+08:00 | 2027-05-20T18:00:00+08:00 | 2027-05-06T20:00:00+00:00 |  | 2027-05-07T04:00:00+08:00 |  | 324.00 | 06H323 shut |  |  | [{"equipmentGUID": "b60df0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H323", "name": "06H323 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83261 | 2026-07-01T04:49:01.7701281+00:00 | 2026-07-01T12:49:01.7701281+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T04:49:01.7701281+00:00 | 2026-07-01T12:49:01.7701281+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329031 | TRUE | TRUE | 2026-07-01T04:49:01.7701281+00:00 | 2026-07-01T12:49:01.7701281+08:00 | #83261 - MDO: 324hrs - 06H550 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-06-10T22:00:00+00:00 | 2027-06-24T10:00:00+00:00 | 2027-06-11T06:00:00+08:00 | 2027-06-24T18:00:00+08:00 | 2027-06-10T20:00:00+00:00 |  | 2027-06-11T04:00:00+08:00 |  | 324.00 | 06H550 shut |  |  | [{"equipmentGUID": "f8ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H550", "name": "06H550 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83262 | 2026-07-01T05:00:18.4790489+00:00 | 2026-07-01T13:00:18.4790489+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:00:18.4790489+00:00 | 2026-07-01T13:00:18.4790489+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329032 | TRUE | TRUE | 2026-07-01T05:00:18.4790489+00:00 | 2026-07-01T13:00:18.4790489+08:00 | #83262 - MDO: 324hrs - 06H619 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-06-28T22:00:00+00:00 | 2027-07-12T10:00:00+00:00 | 2027-06-29T06:00:00+08:00 | 2027-07-12T18:00:00+08:00 | 2027-06-28T20:00:00+00:00 |  | 2027-06-29T04:00:00+08:00 |  | 324.00 | 06H619 shut |  |  | [{"equipmentGUID": "eefde8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H619", "name": "06H619 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83264 | 2026-07-01T05:06:57.6054689+00:00 | 2026-07-01T13:06:57.6054689+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:06:57.6054689+00:00 | 2026-07-01T13:06:57.6054689+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329034 | TRUE | TRUE | 2026-07-01T05:06:57.6054689+00:00 | 2026-07-01T13:06:57.6054689+08:00 | #83264 - MDO: 324hrs - 06H318 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-07-15T22:00:00+00:00 | 2027-07-29T10:00:00+00:00 | 2027-07-16T06:00:00+08:00 | 2027-07-29T18:00:00+08:00 | 2027-07-15T20:00:00+00:00 |  | 2027-07-16T04:00:00+08:00 |  | 324.00 | 06H318 shut |  |  | [{"equipmentGUID": "4f23f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H318", "name": "06H318 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Other"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83266 | 2026-07-01T05:12:21.3291753+00:00 | 2026-07-01T13:12:21.3291753+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:12:21.3291753+00:00 | 2026-07-01T13:12:21.3291753+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329036 | TRUE | TRUE | 2026-07-01T05:12:21.3291753+00:00 | 2026-07-01T13:12:21.3291753+08:00 | #83266 - MDO: 324hrs - 06H546 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-08-02T22:00:00+00:00 | 2027-08-16T10:00:00+00:00 | 2027-08-03T06:00:00+08:00 | 2027-08-16T18:00:00+08:00 | 2027-08-02T20:00:00+00:00 |  | 2027-08-03T04:00:00+08:00 |  | 324.00 | 06H546 shut |  |  | [{"equipmentGUID": "8c36f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H546", "name": "06H546 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83268 | 2026-07-01T05:15:56.645165+00:00 | 2026-07-01T13:15:56.645165+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:15:56.645165+00:00 | 2026-07-01T13:15:56.645165+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329038 | TRUE | TRUE | 2026-07-01T05:15:56.645165+00:00 | 2026-07-01T13:15:56.645165+08:00 | #83268 - MDO: 324hrs - 06H737 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-08-19T22:00:00+00:00 | 2027-09-02T10:00:00+00:00 | 2027-08-20T06:00:00+08:00 | 2027-09-02T18:00:00+08:00 | 2027-08-19T20:00:00+00:00 |  | 2027-08-20T04:00:00+08:00 |  | 324.00 | 06H737 shut |  |  | [{"equipmentGUID": "beede8bf-7c7b-ee11-a846-000d3acacefd", "code": "06H737", "name": "06H737 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83270 | 2026-07-01T05:19:26.4504836+00:00 | 2026-07-01T13:19:26.4504836+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:19:26.4504836+00:00 | 2026-07-01T13:19:26.4504836+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329040 | TRUE | TRUE | 2026-07-01T05:19:26.4504836+00:00 | 2026-07-01T13:19:26.4504836+08:00 | #83270 - MDO: 324hrs - 06H112 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-09-06T22:00:00+00:00 | 2027-09-20T10:00:00+00:00 | 2027-09-07T06:00:00+08:00 | 2027-09-20T18:00:00+08:00 | 2027-09-06T20:00:00+00:00 |  | 2027-09-07T04:00:00+08:00 |  | 324.00 | 06H112 shut |  |  | [{"equipmentGUID": "f51ef0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H112", "name": "06H112 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83272 | 2026-07-01T05:25:28.1416897+00:00 | 2026-07-01T13:25:28.1416897+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:25:28.1416897+00:00 | 2026-07-01T13:25:28.1416897+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329042 | TRUE | TRUE | 2026-07-01T05:25:28.1416897+00:00 | 2026-07-01T13:25:28.1416897+08:00 | #83272 - MDO: 324hrs - 06H266 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-09-23T22:00:00+00:00 | 2027-10-07T10:00:00+00:00 | 2027-09-24T06:00:00+08:00 | 2027-10-07T18:00:00+08:00 | 2027-09-23T20:00:00+00:00 |  | 2027-09-24T04:00:00+08:00 |  | 324.00 | 06H266 shut |  |  | [{"equipmentGUID": "7907f0bf-7c7b-ee11-a846-000d3acacefd", "code": "06H266", "name": "06H266 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83274 | 2026-07-01T05:31:10.6347323+00:00 | 2026-07-01T13:31:10.6347323+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:31:10.6347323+00:00 | 2026-07-01T13:31:10.6347323+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329044 | TRUE | TRUE | 2026-07-01T05:31:10.6347323+00:00 | 2026-07-01T13:31:10.6347323+08:00 | #83274 - MDO: 324hrs - 06H623 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-10-11T22:00:00+00:00 | 2027-10-25T10:00:00+00:00 | 2027-10-12T06:00:00+08:00 | 2027-10-25T18:00:00+08:00 | 2027-10-11T20:00:00+00:00 |  | 2027-10-12T04:00:00+08:00 |  | 324.00 | 06H623 shut |  |  | [{"equipmentGUID": "d366fbbf-7c7b-ee11-a846-000d3acacefd", "code": "06H623", "name": "06H623 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Diff Changeout"}, {"name": "Engine Changeout"}, {"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83275 | 2026-07-01T05:35:56.2242447+00:00 | 2026-07-01T13:35:56.2242447+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:35:56.2242447+00:00 | 2026-07-01T13:35:56.2242447+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329045 | TRUE | TRUE | 2026-07-01T05:35:56.2242447+00:00 | 2026-07-01T13:35:56.2242447+08:00 | #83275 - MDO: 324hrs - 06H264 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-10-28T22:00:00+00:00 | 2027-11-11T10:00:00+00:00 | 2027-10-29T06:00:00+08:00 | 2027-11-11T18:00:00+08:00 | 2027-10-28T20:00:00+00:00 |  | 2027-10-29T04:00:00+08:00 |  | 324.00 | 06H264 shut |  |  | [{"equipmentGUID": "1436f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H264", "name": "06H264 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83276 | 2026-07-01T05:39:02.1088692+00:00 | 2026-07-01T13:39:02.1088692+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-01T05:39:02.1088692+00:00 | 2026-07-01T13:39:02.1088692+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329046 | TRUE | TRUE | 2026-07-01T05:39:02.1088692+00:00 | 2026-07-01T13:39:02.1088692+08:00 | #83276 - MDO: 324hrs - 06H551 CAT 793F HAUL TRUCK | 1.0 | FALSE |  | 2027-11-15T22:00:00+00:00 | 2027-11-29T10:00:00+00:00 | 2027-11-16T06:00:00+08:00 | 2027-11-29T18:00:00+08:00 | 2027-11-15T20:00:00+00:00 |  | 2027-11-16T04:00:00+08:00 |  | 324.00 | 06H551 shut |  |  | [{"equipmentGUID": "2e30f6bf-7c7b-ee11-a846-000d3acacefd", "code": "06H551", "name": "06H551 CAT 793F Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "6153eb4d-404f-41e4-9b21-fd802bc1bdb4", "emailAddress": "Petrina.Jones@riotinto.com", "displayName": "Petrina Jones"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "3f65d5f6-be87-44a1-860f-3ec7103ce30c", "emailAddress": "jackson.mehan@riotinto.com", "displayName": "Mehan, Jackson (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "e585c3f9-54bf-48f3-8102-6e70ccb8fa74", "emailAddress": "Matthew.Bunt@riotinto.com", "displayName": "Bunt, Matthew (RTIO-UNTAPPEDRESOURCES)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | MDO | Australia/Perth |  | Site Team
83405 | 2026-07-02T06:17:58.9283711+00:00 | 2026-07-02T14:17:58.9283711+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | 2026-07-02T06:17:58.9283711+00:00 | 2026-07-02T14:17:58.9283711+08:00 | {"principalGUID": "a716b019-2e0d-4c5c-9d97-7a1f323efd67", "displayName": "Du Toit, Sume (RTIO)"} | {"name": "HME"} | 329233 | TRUE | TRUE | 2026-07-02T06:17:58.9283711+00:00 | 2026-07-02T14:17:58.9283711+08:00 | #83405 - GDI: 348hrs - 06B362 CAT 793F-RBT HAUL TRUCK | 1.0 | FALSE |  | 2027-09-13T22:00:00+00:00 | 2027-09-28T10:00:00+00:00 | 2027-09-14T06:00:00+08:00 | 2027-09-28T18:00:00+08:00 | 2027-09-13T20:00:00+00:00 |  | 2027-09-14T04:00:00+08:00 |  | 348.00 | 06B362 shut |  |  | [{"equipmentGUID": "535b5e3e-637d-f011-a802-002248933a47", "code": "06B362", "name": "06B362 CAT 793F-RBT Haul Truck", "assetClass": {"name": "Truck - Haul"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "23ae2135-9610-45ab-b91b-2949f07f4134", "emailAddress": "Mason.Sloot@riotinto.com", "displayName": "Sloot, Mason (RTIO)"}}, {"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "cb59d4ec-60d9-4b83-9668-8bb154cb6bfb", "emailAddress": "Wayne.Parker@riotinto.com", "displayName": "Parker, Wayne (RTIO-WORKMANAGEMENT)"}}] | [] | [] | [{"name": "Transmission Changeout"}] | [] | [] | Approved | Create | a716b019-2e0d-4c5c-9d97-7a1f323efd67 | Du Toit, Sume (RTIO) | Scheduled | GDI | Australia/Perth |  | Site Team
56121 | 2023-06-23T00:18:43+00:00 | 2023-06-23T08:18:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000849", "displayName": "Malcolm Boyd"} | 2026-10-22T06:15:49.6260276+00:00 | 2026-10-22T14:15:49.6260276+08:00 | {"principalGUID": "31761cac-b4ce-42f7-984d-f82cb80701b5", "displayName": "Mathew, Roney (RTIO)"} | {"name": "Fixed Plant"} | 336294 | TRUE | TRUE | 2026-10-22T06:15:49.6260276+00:00 | 2026-10-22T14:15:49.6260276+08:00 | #56121 - GDI: 120hrs - CRUSHER - SECONDARY: GDI 0401 | 8.0 | FALSE |  | 2026-12-11T04:00:00+00:00 | 2026-12-16T04:00:00+00:00 | 2026-12-11T12:00:00+08:00 | 2026-12-16T12:00:00+08:00 |  |  |  |  | 120.00 | GDI CS0401/CS0402 - Bowl and mantle change, inspect eccentric both crusher + rebuild CS0401 bowl to install in CS0402. Includes mainframe liners and arm guard liners (+24hr / crusher). 24hr for dry+wet commissioning CS0401 + rundown and isolation of CS0402. | Aligning to better flight timings | SGDS2650 | [{"equipmentGUID": "2062fbbf-7c7b-ee11-a846-000d3acacefd", "code": "GDISCS0401", "name": "Crusher - Secondary: GDI 0401", "assetClass": {"name": "Crusher - Secondary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "a82d3977-faf2-4e08-b86a-1daf7c8f285a", "emailAddress": "Paul.Davis4@riotinto.com", "displayName": "Paul Davis"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "89c9ff67-fb08-429c-90cd-9f1940df40e6", "emailAddress": "Brendan.Cho@riotinto.com", "displayName": "Cho, Brendan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 31761cac-b4ce-42f7-984d-f82cb80701b5 | Mathew, Roney (RTIO) | Scheduled | GDI | Australia/Perth
82648 | 2026-06-01T05:56:24.2005157+00:00 | 2026-06-01T13:56:24.2005157+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:28:11.662783+00:00 | 2026-06-10T14:28:11.662783+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327628 | TRUE | TRUE | 2026-06-10T06:28:11.662783+00:00 | 2026-06-10T14:28:11.662783+08:00 | #82648 - WAN: 48hrs - CONVEYOR: WAN 050 PRODUCT SCREENS FEED | 1.0 | TRUE |  | 2027-03-07T22:30:00+00:00 | 2027-03-09T22:30:00+00:00 | 2027-03-08T06:30:00+08:00 | 2027-03-10T06:30:00+08:00 |  |  |  |  | 48.00 | Poke scheduled 48hr outage for required offline maintenance - Part of 13week scheduled strategy |  |  | [{"equipmentGUID": "4a6bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV050", "name": "Conveyor: WAN 050 Product Screens Feed", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a00c46b-21d4-49f4-9ba7-794d24550e97", "emailAddress": "Craig.Boyce@riotinto.com", "displayName": "Boyce, Craig (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82650 | 2026-06-01T05:56:24.9392985+00:00 | 2026-06-01T13:56:24.9392985+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:28:25.8456399+00:00 | 2026-06-10T14:28:25.8456399+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327629 | TRUE | TRUE | 2026-06-10T06:28:25.8456399+00:00 | 2026-06-10T14:28:25.8456399+08:00 | #82650 - WAN: 48hrs - CONVEYOR: WAN 050 PRODUCT SCREENS FEED | 1.0 | TRUE |  | 2027-09-05T22:30:00+00:00 | 2027-09-07T22:30:00+00:00 | 2027-09-06T06:30:00+08:00 | 2027-09-08T06:30:00+08:00 |  |  |  |  | 48.00 | Poke scheduled 48hr outage for required offline maintenance - Part of 13week scheduled strategy |  |  | [{"equipmentGUID": "4a6bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV050", "name": "Conveyor: WAN 050 Product Screens Feed", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a00c46b-21d4-49f4-9ba7-794d24550e97", "emailAddress": "Craig.Boyce@riotinto.com", "displayName": "Boyce, Craig (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82581 | 2026-05-20T22:15:11.1646807+00:00 | 2026-05-21T06:15:11.1646807+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:29:31.6868899+00:00 | 2026-06-10T14:29:31.6868899+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327631 | TRUE | TRUE | 2026-06-10T06:29:31.6868899+00:00 | 2026-06-10T14:29:31.6868899+08:00 | #82581 - WAN: 12hrs - PLANT: WAN CSI 01 | 1.0 | TRUE |  | 2026-12-26T22:00:00+00:00 | 2026-12-27T10:00:00+00:00 | 2026-12-27T06:00:00+08:00 | 2026-12-27T18:00:00+08:00 |  |  |  |  | 12.00 | Scheduled Shutdown CSI Plant 1 12 Hours |  |  | [{"equipmentGUID": "c09c25bb-0591-ef11-a854-000d3acacefd", "code": "WANPLTCSI01", "name": "Plant: WAN CSI 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2a5afafa-e9b0-4581-ae37-d1a945129ed2", "emailAddress": "Ryan.Carter2@riotinto.com", "displayName": "Carter, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82580 | 2026-05-20T22:15:11.0449099+00:00 | 2026-05-21T06:15:11.0449099+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:30:00.428415+00:00 | 2026-06-10T14:30:00.428415+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327632 | TRUE | TRUE | 2026-06-10T06:30:00.428415+00:00 | 2026-06-10T14:30:00.428415+08:00 | #82580 - WAN: 12hrs - PLANT: WAN CSI 01 | 1.0 | TRUE |  | 2026-12-19T22:00:00+00:00 | 2026-12-20T10:00:00+00:00 | 2026-12-20T06:00:00+08:00 | 2026-12-20T18:00:00+08:00 |  |  |  |  | 12.00 | Scheduled Shutdown CSI Plant 1 12 Hours |  |  | [{"equipmentGUID": "c09c25bb-0591-ef11-a854-000d3acacefd", "code": "WANPLTCSI01", "name": "Plant: WAN CSI 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2a5afafa-e9b0-4581-ae37-d1a945129ed2", "emailAddress": "Ryan.Carter2@riotinto.com", "displayName": "Carter, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82579 | 2026-05-20T22:15:10.9253811+00:00 | 2026-05-21T06:15:10.9253811+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:30:17.1859811+00:00 | 2026-06-10T14:30:17.1859811+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327633 | TRUE | TRUE | 2026-06-10T06:30:17.1859811+00:00 | 2026-06-10T14:30:17.1859811+08:00 | #82579 - WAN: 12hrs - PLANT: WAN CSI 01 | 1.0 | TRUE |  | 2026-12-12T22:00:00+00:00 | 2026-12-13T10:00:00+00:00 | 2026-12-13T06:00:00+08:00 | 2026-12-13T18:00:00+08:00 |  |  |  |  | 12.00 | Scheduled Shutdown CSI Plant 1 12 Hours |  |  | [{"equipmentGUID": "c09c25bb-0591-ef11-a854-000d3acacefd", "code": "WANPLTCSI01", "name": "Plant: WAN CSI 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2a5afafa-e9b0-4581-ae37-d1a945129ed2", "emailAddress": "Ryan.Carter2@riotinto.com", "displayName": "Carter, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82578 | 2026-05-20T22:15:10.8194186+00:00 | 2026-05-21T06:15:10.8194186+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:30:31.6197763+00:00 | 2026-06-10T14:30:31.6197763+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327634 | TRUE | TRUE | 2026-06-10T06:30:31.6197763+00:00 | 2026-06-10T14:30:31.6197763+08:00 | #82578 - WAN: 12hrs - PLANT: WAN CSI 01 | 1.0 | TRUE |  | 2026-12-05T22:00:00+00:00 | 2026-12-06T10:00:00+00:00 | 2026-12-06T06:00:00+08:00 | 2026-12-06T18:00:00+08:00 |  |  |  |  | 12.00 | Scheduled Shutdown CSI Plant 1 12 Hours |  |  | [{"equipmentGUID": "c09c25bb-0591-ef11-a854-000d3acacefd", "code": "WANPLTCSI01", "name": "Plant: WAN CSI 01", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "emailAddress": "Darren.Butler@riotinto.com", "displayName": "Butler, Darren (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "2a5afafa-e9b0-4581-ae37-d1a945129ed2", "emailAddress": "Ryan.Carter2@riotinto.com", "displayName": "Carter, Ryan (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82651 | 2026-06-01T05:56:25.0638314+00:00 | 2026-06-01T13:56:25.0638314+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:27:46.8565202+00:00 | 2026-06-10T14:27:46.8565202+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327626 | TRUE | TRUE | 2026-06-10T06:27:46.8565202+00:00 | 2026-06-10T14:27:46.8565202+08:00 | #82651 - WAN: 48hrs - CONVEYOR: WAN 050 PRODUCT SCREENS FEED | 1.0 | TRUE |  | 2027-12-05T22:30:00+00:00 | 2027-12-07T22:30:00+00:00 | 2027-12-06T06:30:00+08:00 | 2027-12-08T06:30:00+08:00 |  |  |  |  | 48.00 | Poke scheduled 48hr outage for required offline maintenance - Part of 13week scheduled strategy |  |  | [{"equipmentGUID": "4a6bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV050", "name": "Conveyor: WAN 050 Product Screens Feed", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a00c46b-21d4-49f4-9ba7-794d24550e97", "emailAddress": "Craig.Boyce@riotinto.com", "displayName": "Boyce, Craig (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82649 | 2026-06-01T05:56:24.8204119+00:00 | 2026-06-01T13:56:24.8204119+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | 2026-06-10T06:27:59.5612693+00:00 | 2026-06-10T14:27:59.5612693+08:00 | {"principalGUID": "74a940b0-27a9-4a1a-a2fd-5a5617f77777", "displayName": "Butler, Darren (RTIO)"} | {"name": "Fixed Plant"} | 327627 | TRUE | TRUE | 2026-06-10T06:27:59.5612693+00:00 | 2026-06-10T14:27:59.5612693+08:00 | #82649 - WAN: 48hrs - CONVEYOR: WAN 050 PRODUCT SCREENS FEED | 1.0 | TRUE |  | 2027-06-06T22:30:00+00:00 | 2027-06-08T22:30:00+00:00 | 2027-06-07T06:30:00+08:00 | 2027-06-09T06:30:00+08:00 |  |  |  |  | 48.00 | Poke scheduled 48hr outage for required offline maintenance - Part of 13week scheduled strategy |  |  | [{"equipmentGUID": "4a6bfbbf-7c7b-ee11-a846-000d3acacefd", "code": "WANCV050", "name": "Conveyor: WAN 050 Product Screens Feed", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9a00c46b-21d4-49f4-9ba7-794d24550e97", "emailAddress": "Craig.Boyce@riotinto.com", "displayName": "Boyce, Craig (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 74a940b0-27a9-4a1a-a2fd-5a5617f77777 | Butler, Darren (RTIO) | Scheduled | WAN | Australia/Perth
82373 | 2026-04-22T05:32:00.8953894+00:00 | 2026-04-22T13:32:00.8953894+08:00 | {"principalGUID": "07aaa40c-2256-4571-a2ed-dd7c35be746c", "displayName": "Thomas, Brent (RTIO)"} | 2026-04-22T07:40:10.7786521+00:00 | 2026-04-22T15:40:10.7786521+08:00 | {"principalGUID": "07aaa40c-2256-4571-a2ed-dd7c35be746c", "displayName": "Thomas, Brent (RTIO)"} | {"name": "Fixed Plant"} | 325723 | TRUE | TRUE | 2026-04-22T07:40:10.7786521+00:00 | 2026-04-22T15:40:10.7786521+08:00 | #82373 - PPT: 106hrs - CONVEYOR: PPT 102P | 1.0 | FALSE |  | 2026-12-13T23:00:00+00:00 | 2026-12-18T09:00:00+00:00 | 2026-12-14T07:00:00+08:00 | 2026-12-18T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM |  |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 07aaa40c-2256-4571-a2ed-dd7c35be746c | Thomas, Brent (RTIO) | Scheduled | PPT | Australia/Perth
65262 | 2024-10-11T03:36:18+00:00 | 2024-10-11T11:36:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-02-05T05:44:17.9588961+00:00 | 2026-02-05T13:44:17.9588961+08:00 | {"principalGUID": "07aaa40c-2256-4571-a2ed-dd7c35be746c", "displayName": "Thomas, Brent (RTIO)"} | {"name": "Fixed Plant"} | 285978 | TRUE | TRUE | 2026-02-05T05:44:17.9588961+00:00 | 2026-02-05T13:44:17.9588961+08:00 | #65262 - EII: 108hrs - STACKER: EII 3EN | 3.0 | FALSE |  | 2028-01-02T22:00:00+00:00 | 2028-01-07T10:00:00+00:00 | 2028-01-03T06:00:00+08:00 | 2028-01-07T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | IAM - Sequence Update |  | [{"equipmentGUID": "2913f0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST3EN", "name": "Stacker: EII 3EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 07aaa40c-2256-4571-a2ed-dd7c35be746c | Thomas, Brent (RTIO) | Scheduled | EII | Australia/Perth
68262 | 2025-06-30T07:55:13.3166928+00:00 | 2025-06-30T15:55:13.3166928+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2025-10-06T07:28:32.4281498+00:00 | 2025-10-06T15:28:32.4281498+08:00 | {"principalGUID": "a322c2c7-2f18-4d6e-aafb-5ec22999a6ae", "displayName": "Sawyer, Trent (RTIO)"} | {"name": "HME"} | 245754 | TRUE | TRUE | 2025-10-06T07:28:32.4281498+00:00 | 2025-10-06T15:28:32.4281498+08:00 | #68262 - GDI: 192hrs - 15B290 CAT 6060 EXCAVATOR | 2.0 | FALSE |  | 2026-11-28T10:00:00+00:00 | 2026-12-06T10:00:00+00:00 | 2026-11-28T18:00:00+08:00 | 2026-12-06T18:00:00+08:00 | 2026-11-25T22:00:00+00:00 | 2026-12-08T22:00:00+00:00 | 2026-11-26T06:00:00+08:00 | 2026-12-09T06:00:00+08:00 | 192.00 | Eng Midlife's, Undercarriage, Boom Cyls, Bucket Cyl LH | Start Time/Date Change - Revision added - Pre/Post Added | S15B290 | [{"equipmentGUID": "0325f6bf-7c7b-ee11-a846-000d3acacefd", "code": "15B290", "name": "15B290 CAT 6060 Excavator", "assetClass": {"name": "Excavator - Tracked"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "emailAddress": "Nebojsa.Milosevic@riotinto.com", "displayName": "Milosevic, Nebojsa (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | a322c2c7-2f18-4d6e-aafb-5ec22999a6ae | Sawyer, Trent (RTIO) | Scheduled | GDI | Australia/Perth |  | D-East
68081 | 2025-06-30T01:15:23.9438247+00:00 | 2025-06-30T09:15:23.9438247+08:00 | {"principalGUID": "cf08fc0e-7e97-4396-ad44-b9c93bcc13c7", "displayName": "Manlod, Rogelio (RTIO)"} | 2026-07-03T05:29:43.890232+00:00 | 2026-07-03T13:29:43.890232+08:00 | {"principalGUID": "7a664c57-db81-4e2b-8aee-da60ca2c770e", "displayName": "Shanks, Ryan (RTIO)"} | {"name": "HME"} | 329352 | TRUE | TRUE | 2026-07-03T05:29:43.890232+00:00 | 2026-07-03T13:29:43.890232+08:00 | #68081 - BM4: 336hrs - 07H267 LETOURNEAU L2350 II WHEEL LOADER | 2.0 | FALSE |  | 2026-11-25T16:00:00+00:00 | 2026-12-09T16:00:00+00:00 | 2026-11-26T00:00:00+08:00 | 2026-12-10T00:00:00+08:00 |  | 2026-12-10T22:00:00+00:00 |  | 2026-12-11T06:00:00+08:00 | 336.00 | Eng Midlife, Dr&WM Rotation, Hosing, Main Pumps | Major Works Completing shut now, changed to suit new dates | S07H267 | [{"equipmentGUID": "0b19f0bf-7c7b-ee11-a846-000d3acacefd", "code": "07H267", "name": "07H267 LeTourneau L2350 II Wheel Loader", "assetClass": {"name": "Loader - Wheeled"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "295b44c4-31e0-4da6-88f8-4a466e0deb1c", "emailAddress": "Nebojsa.Milosevic@riotinto.com", "displayName": "Milosevic, Nebojsa (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 7a664c57-db81-4e2b-8aee-da60ca2c770e | Shanks, Ryan (RTIO) | Scheduled | BM4 | Australia/Perth |  | L-West
71687 | 2025-10-28T04:39:17.3558779+00:00 | 2025-10-28T12:39:17.3558779+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-05-12T07:25:29.3388115+00:00 | 2026-05-12T15:25:29.3388115+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326534 | TRUE | TRUE | 2026-05-12T07:25:29.3388115+00:00 | 2026-05-12T15:25:29.3388115+08:00 | #71687 - PPT: 106hrs - BIN: PPT 02 SURGE & SCREENHOUSE: PPT 2P | 3.0 | FALSE |  | 2027-11-02T18:00:00+00:00 | 2027-11-07T04:00:00+00:00 | 2027-11-03T02:00:00+08:00 | 2027-11-07T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Approved IAM Outage Week Change |  | [{"equipmentGUID": "33fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH2P", "name": "Screenhouse: PPT 2P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7521f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN02", "name": "Bin: PPT 02 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
71685 | 2025-10-28T04:39:16.6134223+00:00 | 2025-10-28T12:39:16.6134223+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-05-12T07:25:27.7482139+00:00 | 2026-05-12T15:25:27.7482139+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326525 | TRUE | TRUE | 2026-05-12T07:25:27.7482139+00:00 | 2026-05-12T15:25:27.7482139+08:00 | #71685 - PPT: 106hrs - BIN: PPT 02 SURGE & SCREENHOUSE: PPT 2P | 4.0 | FALSE |  | 2027-05-04T18:00:00+00:00 | 2027-05-09T04:00:00+00:00 | 2027-05-05T02:00:00+08:00 | 2027-05-09T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Approved IAM Outage Week Change |  | [{"equipmentGUID": "33fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH2P", "name": "Screenhouse: PPT 2P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7521f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN02", "name": "Bin: PPT 02 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
71686 | 2025-10-28T04:39:16.9917886+00:00 | 2025-10-28T12:39:16.9917886+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-05-12T07:25:28.4345302+00:00 | 2026-05-12T15:25:28.4345302+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326529 | TRUE | TRUE | 2026-05-12T07:25:28.4345302+00:00 | 2026-05-12T15:25:28.4345302+08:00 | #71686 - PPT: 106hrs - BIN: PPT 02 SURGE & SCREENHOUSE: PPT 2P | 3.0 | FALSE |  | 2027-08-03T18:00:00+00:00 | 2027-08-08T04:00:00+00:00 | 2027-08-04T02:00:00+08:00 | 2027-08-08T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Approved IAM Outage Week Change |  | [{"equipmentGUID": "33fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH2P", "name": "Screenhouse: PPT 2P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7521f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN02", "name": "Bin: PPT 02 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
66811 | 2025-03-12T05:16:51.4676985+00:00 | 2025-03-12T13:16:51.4676985+08:00 | {"principalGUID": "2a17f19f-14db-4d5d-915b-d2a45c51cd0e", "displayName": "McMurray, Sarah J (RTIO)"} | 2026-10-02T04:15:06.186727+00:00 | 2026-10-02T12:15:06.186727+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334963 | TRUE | TRUE | 2026-10-02T04:15:06.186727+00:00 | 2026-10-02T12:15:06.186727+08:00 | #66811 - PPT: 106hrs - CAR DUMPER: PPT 3P | 4.0 | TRUE |  | 2027-03-22T11:00:00+00:00 | 2027-03-26T21:00:00+00:00 | 2027-03-22T19:00:00+08:00 | 2027-03-27T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Start time changed to new standard start time of 19:00 hrs (previous 18:00 hrs). |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
82493 | 2026-05-12T05:37:25.3914549+00:00 | 2026-05-12T13:37:25.3914549+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-05-12T05:37:25.5287148+00:00 | 2026-05-12T13:37:25.5287148+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326434 | TRUE | TRUE | 2026-05-12T05:37:25.5287148+00:00 | 2026-05-12T13:37:25.5287148+08:00 | #82493 - EII: 80hrs - CONVEYOR: EII 8E | 1.0 | FALSE |  | 2028-01-23T23:00:00+00:00 | 2028-01-27T07:00:00+00:00 | 2028-01-24T07:00:00+08:00 | 2028-01-27T15:00:00+08:00 |  |  |  |  | 80.00 | IAM Conveyor: EII 8E |  |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
82490 | 2026-05-12T05:37:24.9690919+00:00 | 2026-05-12T13:37:24.9690919+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-05-12T07:25:27.4021646+00:00 | 2026-05-12T15:25:27.4021646+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326523 | TRUE | TRUE | 2026-05-12T07:25:27.4021646+00:00 | 2026-05-12T15:25:27.4021646+08:00 | #82490 - EII: 80hrs - CONVEYOR: EII 8E | 1.0 | FALSE |  | 2027-04-25T23:00:00+00:00 | 2027-04-29T07:00:00+00:00 | 2027-04-26T07:00:00+08:00 | 2027-04-29T15:00:00+08:00 |  |  |  |  | 80.00 | IAM Conveyor: EII 8E |  |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
82492 | 2026-05-12T05:37:25.2552587+00:00 | 2026-05-12T13:37:25.2552587+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-05-12T07:25:28.7746122+00:00 | 2026-05-12T15:25:28.7746122+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326531 | TRUE | TRUE | 2026-05-12T07:25:28.7746122+00:00 | 2026-05-12T15:25:28.7746122+08:00 | #82492 - EII: 80hrs - CONVEYOR: EII 8E | 1.0 | FALSE |  | 2027-10-24T23:00:00+00:00 | 2027-10-28T07:00:00+00:00 | 2027-10-25T07:00:00+08:00 | 2027-10-28T15:00:00+08:00 |  |  |  |  | 80.00 | IAM Conveyor: EII 8E |  |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
82491 | 2026-05-12T05:37:25.106669+00:00 | 2026-05-12T13:37:25.106669+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-05-12T07:25:28.0969959+00:00 | 2026-05-12T15:25:28.0969959+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 326527 | TRUE | TRUE | 2026-05-12T07:25:28.0969959+00:00 | 2026-05-12T15:25:28.0969959+08:00 | #82491 - EII: 80hrs - CONVEYOR: EII 8E | 1.0 | FALSE |  | 2027-07-25T23:00:00+00:00 | 2027-07-29T07:00:00+00:00 | 2027-07-26T07:00:00+08:00 | 2027-07-29T15:00:00+08:00 |  |  |  |  | 80.00 | IAM Conveyor: EII 8E |  |  | [{"equipmentGUID": "d5d400c0-7c7b-ee11-a846-000d3acacefd", "code": "EIICV8E", "name": "Conveyor: EII 8E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83577 | 2026-07-22T05:07:36.2271102+00:00 | 2026-07-22T13:07:36.2271102+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-09-28T03:51:20.180069+00:00 | 2026-09-28T11:51:20.180069+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334144 | TRUE | TRUE | 2026-09-28T03:51:20.180069+00:00 | 2026-09-28T11:51:20.180069+08:00 | #83577 - PPT: 106hrs - CONVEYOR: PPT 122P & CONVEYOR: PPT 123P | 4.0 | FALSE |  | 2027-10-11T23:00:00+00:00 | 2027-10-16T09:00:00+00:00 | 2027-10-12T07:00:00+08:00 | 2027-10-16T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT Bulking Circuit | Conveyors 122P, 123P & 129P go out with the bulking circuit (and aligned with ST3P). |  | [{"equipmentGUID": "58fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV122P", "name": "Conveyor: PPT 122P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8b34f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV123P", "name": "Conveyor: PPT 123P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "51df00c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV129P", "name": "Conveyor: PPT 129P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83578 | 2026-07-22T05:07:36.3984013+00:00 | 2026-07-22T13:07:36.3984013+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-09-25T01:17:26.2862216+00:00 | 2026-09-25T09:17:26.2862216+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334090 | TRUE | TRUE | 2026-09-25T01:17:26.2862216+00:00 | 2026-09-25T09:17:26.2862216+08:00 | #83578 - PPT: 106hrs - CONVEYOR: PPT BULKING CIRCUIT | 2.0 | FALSE |  | 2028-01-10T23:00:00+00:00 | 2028-01-15T09:00:00+00:00 | 2028-01-11T07:00:00+08:00 | 2028-01-15T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT Bulking Circuit | Stacker IAM drumbeat move, MOC #138247 - now 2, 15, 28 & 41 (previous 10, 23, 36, 49) - Site requet |  | [{"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83571 | 2026-07-22T05:02:18.8144069+00:00 | 2026-07-22T13:02:18.8144069+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-09-25T01:18:11.2707783+00:00 | 2026-09-25T09:18:11.2707783+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334092 | TRUE | TRUE | 2026-09-25T01:18:11.2707783+00:00 | 2026-09-25T09:18:11.2707783+08:00 | #83571 - PPT: 106hrs - CONVEYOR: PPT 120P | 2.0 | FALSE |  | 2028-01-10T23:00:00+00:00 | 2028-01-15T09:00:00+00:00 | 2028-01-11T07:00:00+08:00 | 2028-01-15T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 120P | Stacker IAM drumbeat move, MOC #138247 - now 2, 15, 28 & 41 (previous 10, 23, 36, 49) - Site request. |  | [{"equipmentGUID": "17e4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV120P", "name": "Conveyor: PPT 120P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83575 | 2026-07-22T05:04:11.6373998+00:00 | 2026-07-22T13:04:11.6373998+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-09-25T01:18:42.3419836+00:00 | 2026-09-25T09:18:42.3419836+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334094 | TRUE | TRUE | 2026-09-25T01:18:42.3419836+00:00 | 2026-09-25T09:18:42.3419836+08:00 | #83575 - PPT: 106hrs - CONVEYOR: PPT 220P | 2.0 | FALSE |  | 2028-01-10T23:00:00+00:00 | 2028-01-15T09:00:00+00:00 | 2028-01-11T07:00:00+08:00 | 2028-01-15T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 220P | Stacker IAM drumbeat move, MOC #138247 - now 2, 15, 28 & 41 (previous 10, 23, 36, 49) - Site request. |  | [{"equipmentGUID": "1246f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV220P", "name": "Conveyor: PPT 220P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83467 | 2026-07-08T02:09:38.213042+00:00 | 2026-07-08T10:09:38.213042+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T07:32:37.4920799+00:00 | 2026-10-15T15:32:37.4920799+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336113 | TRUE | TRUE | 2026-10-15T07:32:37.4920799+00:00 | 2026-10-15T15:32:37.4920799+08:00 | #83467 - PPT: 240hrs - RMP 101P/102P TRANSFER CHUTE | 1.0 | FALSE |  | 2027-09-12T23:00:00+00:00 | 2027-09-22T23:00:00+00:00 | 2027-09-13T07:00:00+08:00 | 2027-09-23T07:00:00+08:00 |  |  |  |  | 240.00 | 102P Project Work - Chutes Project |  |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83462 | 2026-07-08T01:39:03.0159376+00:00 | 2026-07-08T09:39:03.0159376+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T02:02:15.6516961+00:00 | 2026-10-15T10:02:15.6516961+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336009 | TRUE | TRUE | 2026-10-15T02:02:15.6516961+00:00 | 2026-10-15T10:02:15.6516961+08:00 | #83462 - PPT: 240hrs - RMP 101P/107P TRANSFER CHUTE | 1.3 | FALSE |  | 2027-09-22T23:00:00+00:00 | 2027-10-02T23:00:00+00:00 | 2027-09-23T07:00:00+08:00 | 2027-10-03T07:00:00+08:00 |  |  |  |  | 240.00 | 107P Project Works - Chutes Project |  |  | [{"equipmentGUID": "9bcf00c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV107P", "name": "Conveyor: PPT 107P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8b34f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV123P", "name": "Conveyor: PPT 123P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}, {"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "b8e5fb30-b7cb-49b8-a31d-19c8d72acde6", "emailAddress": "Robin.Smith@riotinto.com", "displayName": "Smith, Robin (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83460 | 2026-07-08T01:18:06.4185397+00:00 | 2026-07-08T09:18:06.4185397+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T02:02:53.7530441+00:00 | 2026-10-15T10:02:53.7530441+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336010 | TRUE | TRUE | 2026-10-15T02:02:53.7530441+00:00 | 2026-10-15T10:02:53.7530441+08:00 | #83460 - PPT: 360hrs - RMP CD3P AF01/02 TO 101P TRANSFER CHUTE REPLACEMENT | 1.2 | TRUE |  | 2027-10-02T23:00:00+00:00 | 2027-10-17T23:00:00+00:00 | 2027-10-03T07:00:00+08:00 | 2027-10-18T07:00:00+08:00 |  |  |  |  | 360.00 | CD3P, 101P - APRON FEEDER PROJECT WORK |  |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}, {"equipmentGUID": "f313f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV101P", "name": "Conveyor: PPT 101P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}, {"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83472 | 2026-07-08T03:09:57.4010306+00:00 | 2026-07-08T11:09:57.4010306+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:56:59.4892051+00:00 | 2026-10-15T09:56:59.4892051+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336000 | TRUE | TRUE | 2026-10-15T01:56:59.4892051+00:00 | 2026-10-15T09:56:59.4892051+08:00 | #83472 - PPT: 96hrs - RMP SDN REPAIR | 1.1 | FALSE |  | 2027-01-18T11:00:00+00:00 | 2027-01-22T11:00:00+00:00 | 2027-01-18T19:00:00+08:00 | 2027-01-22T19:00:00+08:00 |  |  |  |  | 96.00 | RMP - SDN Repair |  |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83473 | 2026-07-08T03:13:25.642441+00:00 | 2026-07-08T11:13:25.642441+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:58:32.2622537+00:00 | 2026-10-15T09:58:32.2622537+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336001 | TRUE | TRUE | 2026-10-15T01:58:32.2622537+00:00 | 2026-10-15T09:58:32.2622537+08:00 | #83473 - PPT: 96hrs - RMP SDN REPAIR | 1.1 | FALSE |  | 2027-01-24T23:00:00+00:00 | 2027-01-28T23:00:00+00:00 | 2027-01-25T07:00:00+08:00 | 2027-01-29T07:00:00+08:00 |  |  |  |  | 96.00 | PMP - SDN Repair (from Novembers inspection) |  |  | [{"equipmentGUID": "043ff6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC3P", "name": "Reclaimer: PPT 3P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
84043 | 2026-09-30T02:28:49.5558221+00:00 | 2026-09-30T10:28:49.5558221+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-21T01:10:03.7068204+00:00 | 2026-10-21T09:10:03.7068204+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336245 | TRUE | TRUE | 2026-10-21T01:10:03.7068204+00:00 | 2026-10-21T09:10:03.7068204+08:00 | #84043 - EII: 36hrs - FUNCTIONAL SAFETY ST1EN/TP12EN - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-05-30T23:00:00+00:00 | 2027-06-01T11:00:00+00:00 | 2027-05-31T07:00:00+08:00 | 2027-06-01T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY ST1EN - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
84042 | 2026-09-30T02:02:53.2742019+00:00 | 2026-09-30T10:02:53.2742019+08:00 | {"principalGUID": "1e80254d-7a81-489d-b12d-bdda6decb952", "displayName": "Parad, Edi (RTIO)"} | 2026-10-16T01:25:26.1138884+00:00 | 2026-10-16T09:25:26.1138884+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336151 | TRUE | TRUE | 2026-10-16T01:25:26.1138884+00:00 | 2026-10-16T09:25:26.1138884+08:00 | #84042 - EII: 36hrs - FUNCTIONAL SAFETY ST1EN/TP7EN - STANDALONE OUTAGE | 1.1 | FALSE |  | 2027-08-01T23:00:00+00:00 | 2027-08-03T11:00:00+00:00 | 2027-08-02T07:00:00+08:00 | 2027-08-03T19:00:00+08:00 |  |  |  |  | 36.00 | FUNCTIONAL SAFETY TP7EN - Standalone Outage |  |  | [{"equipmentGUID": "b537f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST1EN", "name": "Stacker: EII 1EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "7172c8e6-79de-4399-b1c7-67ea821d77d1", "emailAddress": "Mathew.Norman@riotinto.com", "displayName": "Norman, Mathew (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83576 | 2026-07-22T05:07:35.5985127+00:00 | 2026-07-22T13:07:35.5985127+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-07T07:23:23.5109756+00:00 | 2026-10-07T15:23:23.5109756+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335433 | TRUE | TRUE | 2026-10-07T07:23:23.5109756+00:00 | 2026-10-07T15:23:23.5109756+08:00 | #83576 - PPT: 106hrs - CONVEYOR: PPT 122P & CONVEYOR: PPT 123P | 4.0 | FALSE |  | 2027-07-12T23:00:00+00:00 | 2027-07-17T09:00:00+00:00 | 2027-07-13T07:00:00+08:00 | 2027-07-17T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT Bulking Circuit | Conveyors 122P, 123P & 129P go out with the bulking circuit (and aligned with ST3P). |  | [{"equipmentGUID": "58fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV122P", "name": "Conveyor: PPT 122P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8b34f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV123P", "name": "Conveyor: PPT 123P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "51df00c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV129P", "name": "Conveyor: PPT 129P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
84077 | 2026-10-01T01:59:35.117294+00:00 | 2026-10-01T09:59:35.117294+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-02T02:02:30.2510998+00:00 | 2026-10-02T10:02:30.2510998+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334953 | TRUE | TRUE | 2026-10-02T02:02:30.2510998+00:00 | 2026-10-02T10:02:30.2510998+08:00 | #84077 - PPT: 1519hrs - PPSS RCL1P REPLACEMENT PROJECT - INSTALLATION RCL4P | 1.0 | FALSE |  | 2027-07-31T16:00:00+00:00 | 2027-10-02T23:00:00+00:00 | 2027-08-01T00:00:00+08:00 | 2027-10-03T07:00:00+08:00 |  |  |  |  | 1519.00 | ST3P Wil be unavailable for the duration of REC4P installation |  |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 50545, "shutVersionId": 327916, "title": "#50545 - PPT: 2016hrs - PPSS RCL1P REPLACEMENT PROJECT - INSTALLATION RCL4P", "startDatetimeUTC": "2027-07-31T16:00:00+00:00", "endDatetimeUTC": "2027-10-23T16:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83495 | 2026-07-09T04:40:52.349688+00:00 | 2026-07-09T12:40:52.349688+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-07-10T05:52:44.3782641+00:00 | 2026-07-10T13:52:44.3782641+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 329792 | TRUE | TRUE | 2026-07-10T05:52:44.3782641+00:00 | 2026-07-10T13:52:44.3782641+08:00 | #83495 - EII: 76hrs - STACKER: EII 2EN | 1.0 | FALSE |  | 2027-01-29T10:00:00+00:00 | 2027-02-01T14:00:00+00:00 | 2027-01-29T18:00:00+08:00 | 2027-02-01T22:00:00+08:00 |  |  |  |  | 76.00 | RMP defects - blast and paint |  |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83568 | 2026-07-22T05:02:17.673507+00:00 | 2026-07-22T13:02:17.673507+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T05:55:24.7070904+00:00 | 2026-08-28T13:55:24.7070904+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332152 | TRUE | TRUE | 2026-08-28T05:55:24.7070904+00:00 | 2026-08-28T13:55:24.7070904+08:00 | #83568 - PPT: 106hrs - CONVEYOR: PPT 120P | 3.0 | FALSE |  | 2027-04-12T23:00:00+00:00 | 2027-04-17T09:00:00+00:00 | 2027-04-13T07:00:00+08:00 | 2027-04-17T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 120P | Identified change for labour optimisation |  | [{"equipmentGUID": "17e4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV120P", "name": "Conveyor: PPT 120P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83572 | 2026-07-22T05:04:10.5839747+00:00 | 2026-07-22T13:04:10.5839747+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T05:55:54.2950337+00:00 | 2026-08-28T13:55:54.2950337+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332155 | TRUE | TRUE | 2026-08-28T05:55:54.2950337+00:00 | 2026-08-28T13:55:54.2950337+08:00 | #83572 - PPT: 106hrs - CONVEYOR: PPT 220P | 3.0 | FALSE |  | 2027-04-12T23:00:00+00:00 | 2027-04-17T09:00:00+00:00 | 2027-04-13T07:00:00+08:00 | 2027-04-17T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 220P | Identified change for labour optimisation |  | [{"equipmentGUID": "1246f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV220P", "name": "Conveyor: PPT 220P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83569 | 2026-07-22T05:02:18.3779966+00:00 | 2026-07-22T13:02:18.3779966+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T05:57:29.4243107+00:00 | 2026-08-28T13:57:29.4243107+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332159 | TRUE | TRUE | 2026-08-28T05:57:29.4243107+00:00 | 2026-08-28T13:57:29.4243107+08:00 | #83569 - PPT: 106hrs - CONVEYOR: PPT 120P | 3.0 | FALSE |  | 2027-07-12T23:00:00+00:00 | 2027-07-17T09:00:00+00:00 | 2027-07-13T07:00:00+08:00 | 2027-07-17T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 120P | Identified change for labour optimisation |  | [{"equipmentGUID": "17e4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV120P", "name": "Conveyor: PPT 120P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83573 | 2026-07-22T05:04:11.200515+00:00 | 2026-07-22T13:04:11.200515+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T05:57:57.2108328+00:00 | 2026-08-28T13:57:57.2108328+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332162 | TRUE | TRUE | 2026-08-28T05:57:57.2108328+00:00 | 2026-08-28T13:57:57.2108328+08:00 | #83573 - PPT: 106hrs - CONVEYOR: PPT 220P | 3.0 | FALSE |  | 2027-07-12T23:00:00+00:00 | 2027-07-17T09:00:00+00:00 | 2027-07-13T07:00:00+08:00 | 2027-07-17T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 220P | Identified change for labour optimisation |  | [{"equipmentGUID": "1246f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV220P", "name": "Conveyor: PPT 220P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83570 | 2026-07-22T05:02:18.5946637+00:00 | 2026-07-22T13:02:18.5946637+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T05:59:49.8837775+00:00 | 2026-08-28T13:59:49.8837775+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332167 | TRUE | TRUE | 2026-08-28T05:59:49.8837775+00:00 | 2026-08-28T13:59:49.8837775+08:00 | #83570 - PPT: 106hrs - CONVEYOR: PPT 120P | 3.0 | FALSE |  | 2027-10-11T23:00:00+00:00 | 2027-10-16T09:00:00+00:00 | 2027-10-12T07:00:00+08:00 | 2027-10-16T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 120P | Identified change for labour optimisation |  | [{"equipmentGUID": "17e4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV120P", "name": "Conveyor: PPT 120P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83574 | 2026-07-22T05:04:11.4263368+00:00 | 2026-07-22T13:04:11.4263368+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-08-28T06:00:19.0245676+00:00 | 2026-08-28T14:00:19.0245676+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332169 | TRUE | TRUE | 2026-08-28T06:00:19.0245676+00:00 | 2026-08-28T14:00:19.0245676+08:00 | #83574 - PPT: 106hrs - CONVEYOR: PPT 220P | 3.0 | FALSE |  | 2027-10-11T23:00:00+00:00 | 2027-10-16T09:00:00+00:00 | 2027-10-12T07:00:00+08:00 | 2027-10-16T17:00:00+08:00 |  |  |  |  | 106.00 | PPT: 106hrs - CONVEYOR: PPT 220P | Identified change for labour optimisation |  | [{"equipmentGUID": "1246f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV220P", "name": "Conveyor: PPT 220P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "357d0bbf-8a5b-45ae-97a7-31e8a6c1df1e", "emailAddress": "Rooshabh.Shah@riotinto.com", "displayName": "Shah, Rooshabh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83486 | 2026-07-09T04:08:44.7620726+00:00 | 2026-07-09T12:08:44.7620726+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:44:19.1651084+00:00 | 2026-10-15T09:44:19.1651084+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335987 | TRUE | TRUE | 2026-10-15T01:44:19.1651084+00:00 | 2026-10-15T09:44:19.1651084+08:00 | #83486 - PPT: 138hrs - RMP - SDN DEFECT - BOOM BELT C/O & BOOM REPAIRS | 1.1 | FALSE |  | 2027-02-09T08:00:00+00:00 | 2027-02-15T02:00:00+00:00 | 2027-02-09T16:00:00+08:00 | 2027-02-15T10:00:00+08:00 |  |  |  |  | 138.00 | RMP Repairs - SDN defect repair_boom belt c/o and RMP boom repairs |  |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83492 | 2026-07-09T04:29:43.5671722+00:00 | 2026-07-09T12:29:43.5671722+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:42:34.4592767+00:00 | 2026-10-15T09:42:34.4592767+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335982 | TRUE | TRUE | 2026-10-15T01:42:34.4592767+00:00 | 2026-10-15T09:42:34.4592767+08:00 | #83492 - PPT: 186hrs - RMP CORROSION REPAIRS | 3.1 | FALSE |  | 2027-02-12T07:00:00+00:00 | 2027-02-20T01:00:00+00:00 | 2027-02-12T15:00:00+08:00 | 2027-02-20T09:00:00+08:00 |  |  |  |  | 186.00 | RMP corrosion repairs - outstanding defects |  |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83490 | 2026-07-09T04:24:15.2294145+00:00 | 2026-07-09T12:24:15.2294145+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:42:00.5038071+00:00 | 2026-10-15T09:42:00.5038071+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335980 | TRUE | TRUE | 2026-10-15T01:42:00.5038071+00:00 | 2026-10-15T09:42:00.5038071+08:00 | #83490 - PPT: 132hrs - RMP CORROSION REPAIRS | 1.1 | FALSE |  | 2027-04-11T16:00:00+00:00 | 2027-04-17T04:00:00+00:00 | 2027-04-12T00:00:00+08:00 | 2027-04-17T12:00:00+08:00 |  |  |  |  | 132.00 | RMP corrosion repairs |  |  | [{"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83487 | 2026-07-09T04:17:05.8610817+00:00 | 2026-07-09T12:17:05.8610817+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:35:21.5875381+00:00 | 2026-10-15T09:35:21.5875381+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335971 | TRUE | TRUE | 2026-10-15T01:35:21.5875381+00:00 | 2026-10-15T09:35:21.5875381+08:00 | #83487 - PPT: 144hrs - RMP CORROSION REPAIRS | 1.1 | FALSE |  | 2027-08-19T16:00:00+00:00 | 2027-08-25T16:00:00+00:00 | 2027-08-20T00:00:00+08:00 | 2027-08-26T00:00:00+08:00 |  |  |  |  | 144.00 | RMP corrosion repairs |  |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83859 | 2026-08-28T05:46:29.9159402+00:00 | 2026-08-28T13:46:29.9159402+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-15T01:33:22.1040561+00:00 | 2026-10-15T09:33:22.1040561+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335968 | TRUE | TRUE | 2026-10-15T01:33:22.1040561+00:00 | 2026-10-15T09:33:22.1040561+08:00 | #83859 - PPT: 48hrs - CAR DUMPER TESTING REQUIREMENTS | 1.2 | TRUE |  | 2027-10-17T23:00:00+00:00 | 2027-10-19T23:00:00+00:00 | 2027-10-18T07:00:00+08:00 | 2027-10-20T07:00:00+08:00 |  |  |  |  | 48.00 | This has been created for Car Dumper testing requirements - The New Dumper Cell is expected to be 100% in operation from installation; however, intermittent testing will need to be completed; therefore, SL needs to be allocated. Email attached |  |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "9a10e71a-5a7b-4405-8777-b88a1561de62", "emailAddress": "Steven.Medling@riotinto.com", "displayName": "Medling, Steven (RTIO)"}}] | [] | [] | [] | [] | [{"name": "Other"}] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Site Constraint | PPT | Australia/Perth
84075 | 2026-10-01T01:54:22.6132355+00:00 | 2026-10-01T09:54:22.6132355+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | 2026-10-02T05:54:33.3777489+00:00 | 2026-10-02T13:54:33.3777489+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334995 | TRUE | TRUE | 2026-10-02T05:54:33.3777489+00:00 | 2026-10-02T13:54:33.3777489+08:00 | #84075 - PPT: 1350hrs - PPSS RCL3P REPLACEMENT PROJECT - INSTALLATION RCL6P | 1.0 | FALSE |  | 2027-03-07T16:00:00+00:00 | 2027-05-02T22:00:00+00:00 | 2027-03-08T00:00:00+08:00 | 2027-05-03T06:00:00+08:00 |  |  |  |  | 1350.00 | ST5P Unable to be used for the duration of REC6P Installation |  |  | [{"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "46d63d1c-edd6-44a8-b5e2-eb32fa895f5e", "emailAddress": "George.Williams3@riotinto.com", "displayName": "George Williams"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 50440, "shutVersionId": 327917, "title": "#50440 - PPT: 2016hrs - PPSS RCL3P REPLACEMENT PROJECT - INSTALLATION RCL6P", "startDatetimeUTC": "2027-03-07T16:00:00+00:00", "endDatetimeUTC": "2027-05-30T16:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
82855 | 2026-06-08T01:02:26.6226601+00:00 | 2026-06-08T09:02:26.6226601+08:00 | {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "displayName": "Bouyer, Scott (RTIO)"} | 2026-10-05T06:22:51.255937+00:00 | 2026-10-05T14:22:51.255937+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335267 | TRUE | TRUE | 2026-10-05T06:22:51.255937+00:00 | 2026-10-05T14:22:51.255937+08:00 | #82855 - PPT: 130hrs - PPSS - REC1P SMPT STRUCTURAL MODIFICATIONS | 3.0 | FALSE |  | 2027-06-27T23:00:00+00:00 | 2027-07-03T09:00:00+00:00 | 2027-06-28T07:00:00+08:00 | 2027-07-03T17:00:00+08:00 |  |  |  |  | 130.00 | PPSS - REC1P SMPT Structural Modifications Bechtel/DHHI to complete SMPT Structural mods to strengthen the machine for removal in major shut | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "9674c013-0b77-4a25-b794-5b4a8c769734", "emailAddress": "Scott.Bouyer@riotinto.com", "displayName": "Bouyer, Scott (RTIO)"}}] | [] | [] | [{"name": "Reclaimer Replacement"}] | [{"code": "P-0505178", "name": "Parker Point Stockyard Sustaining", "projectTeam": {"name": "D&T"}, "totalProjectTime": "130"}] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Major Projects | PPT | Australia/Perth
71684 | 2025-10-28T04:39:16.2422444+00:00 | 2025-10-28T12:39:16.2422444+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-09-17T23:40:25.7675445+00:00 | 2026-09-18T07:40:25.7675445+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333534 | TRUE | TRUE | 2026-09-17T23:40:25.7675445+00:00 | 2026-09-18T07:40:25.7675445+08:00 | #71684 - PPT: 106hrs - BIN: PPT 02 SURGE & SCREENHOUSE: PPT 2P | 4.0 | FALSE |  | 2027-02-02T23:00:00+00:00 | 2027-02-07T09:00:00+00:00 | 2027-02-03T07:00:00+08:00 | 2027-02-07T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Site request to change Start time |  | [{"equipmentGUID": "33fce8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH2P", "name": "Screenhouse: PPT 2P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "7521f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN02", "name": "Bin: PPT 02 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
71709 | 2025-10-28T05:36:16.9298674+00:00 | 2025-10-28T13:36:16.9298674+08:00 | {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "displayName": "Carlton, Clint (RTIO)"} | 2026-10-02T05:20:26.5652031+00:00 | 2026-10-02T13:20:26.5652031+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334991 | TRUE | TRUE | 2026-10-02T05:20:26.5652031+00:00 | 2026-10-02T13:20:26.5652031+08:00 | #71709 - PPT: 106hrs - BIN: PPT 03 SURGE & SCREENHOUSE: PPT 3P | 4.0 | FALSE |  | 2027-03-08T18:00:00+00:00 | 2027-03-13T04:00:00+00:00 | 2027-03-09T02:00:00+08:00 | 2027-03-13T12:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM | Aligning Week 10 to the remaining of 2027 drumbeat - aligning start day (Tuesday) and start time (2:00 am). |  | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}, {"equipmentGUID": "1725f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTBN03", "name": "Bin: PPT 03 Surge", "assetClass": {"name": "Bin"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
39470 | 2020-12-21T00:01:32+00:00 | 2020-12-21T08:01:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-09-25T02:30:29.4282727+00:00 | 2026-09-25T10:30:29.4282727+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334114 | TRUE | TRUE | 2026-09-25T02:30:29.4282727+00:00 | 2026-09-25T10:30:29.4282727+08:00 | #39470 - PPT: 840hrs - CD3P CELL BARREL REPLACEMENT | 11.0 | TRUE |  | 2027-09-12T23:00:00+00:00 | 2027-10-17T23:00:00+00:00 | 2027-09-13T07:00:00+08:00 | 2027-10-18T07:00:00+08:00 |  |  |  |  | 840.00 | CD3P Dumper Cells Replacement 6 Weeks. Pilbara Projects Construction Lead Orion Daley-Coers - 0497 784 100. Asset Management Representative James Brakespeare 0436 845 127. | Reduction Identified to enable a return of SL - see email attached (FW_ P-0509542-PPT CD3P Dumper Cell Replacement - MSF Outages affecting CD4P) |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "813f4be3-9659-4f1c-be05-188a74883d51", "emailAddress": "Orion.Daley-Coers@riotinto.com", "displayName": "Daley-Coers, Orion (RTIO-WORKPAC)"}}] | [] | [] | [{"name": "Dumper Cell Replacement"}] | [{"code": "P-0509542", "name": "Dumper Cell Replacement", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "682"}] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Major Projects | PPT | Australia/Perth
64958 | 2024-10-04T02:59:44+00:00 | 2024-10-04T10:59:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-20T05:54:08.5102728+00:00 | 2026-10-20T13:54:08.5102728+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336221 | TRUE | TRUE | 2026-10-20T05:54:08.5102728+00:00 | 2026-10-20T13:54:08.5102728+08:00 | #64958 - EII: 72hrs - SCREENHOUSE: EII 1E | 6.0 | FALSE |  | 2027-05-27T23:00:00+00:00 | 2027-05-30T23:00:00+00:00 | 2027-05-28T07:00:00+08:00 | 2027-05-31T07:00:00+08:00 |  |  |  |  | 72.00 | Standard IAM Maintenance | Aligning to new standard outage "feed off' time of 7:00 am (was sitting at 6:00 am previously) |  | [{"equipmentGUID": "5740f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIISCH1E", "name": "Screenhouse: EII 1E", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
62555 | 2024-07-09T01:44:01+00:00 | 2024-07-09T09:44:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-09-28T03:35:30.7859051+00:00 | 2026-09-28T11:35:30.7859051+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334143 | TRUE | TRUE | 2026-09-28T03:35:30.7859051+00:00 | 2026-09-28T11:35:30.7859051+08:00 | #62555 - PPT: 106hrs - CONVEYOR: PPT 122P & CONVEYOR: PPT 123P | 5.0 | FALSE |  | 2027-04-12T23:00:00+00:00 | 2027-04-17T09:00:00+00:00 | 2027-04-13T07:00:00+08:00 | 2027-04-17T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Conveyors 122P, 123P & 129P go out with the bulking circuit (and aligned with ST3P). |  | [{"equipmentGUID": "58fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV122P", "name": "Conveyor: PPT 122P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8b34f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV123P", "name": "Conveyor: PPT 123P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "51df00c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV129P", "name": "Conveyor: PPT 129P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
61717 | 2024-05-28T02:34:34+00:00 | 2024-05-28T10:34:34+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-09-17T23:50:16.4228834+00:00 | 2026-09-18T07:50:16.4228834+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333539 | TRUE | TRUE | 2026-09-17T23:50:16.4228834+00:00 | 2026-09-18T07:50:16.4228834+08:00 | #61717 - PPT: 130hrs - RECLAIMER: PPT 2P | 5.0 | FALSE |  | 2027-02-14T23:00:00+00:00 | 2027-02-20T09:00:00+00:00 | 2027-02-15T07:00:00+08:00 | 2027-02-20T17:00:00+08:00 |  |  |  |  | 130.00 | Shut created to balance maintenance times between shuts while reclaimer replacements are happening. | Site request to change start time (see email attached) - standardising to a 7:00 am start time (from 6:00 am) |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
64128 | 2024-09-11T05:07:18+00:00 | 2024-09-11T13:07:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-10-12T07:14:01.5190913+00:00 | 2026-10-12T15:14:01.5190913+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335855 | TRUE | TRUE | 2026-10-12T07:14:01.5190913+00:00 | 2026-10-12T15:14:01.5190913+08:00 | #64128 - PPT: 130hrs - SL2P CORROSION CONTROL | 9.0 | TRUE |  | 2027-05-11T13:00:00+00:00 | 2027-05-16T23:00:00+00:00 | 2027-05-11T21:00:00+08:00 | 2027-05-17T07:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control | Change feed off to accommodate site constraints / safety for resourcing - change approval in email attached (proposal for shiploader corrosion) |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
64569 | 2024-10-02T02:13:45+00:00 | 2024-10-02T10:13:45+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000310", "displayName": "Nick Corfield"} | 2026-10-05T06:22:56.1482452+00:00 | 2026-10-05T14:22:56.1482452+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335289 | TRUE | TRUE | 2026-10-05T06:22:56.1482452+00:00 | 2026-10-05T14:22:56.1482452+08:00 | #64569 - PPT: 130hrs - RECLAIMER: PPT 4P | 4.0 | FALSE |  | 2027-12-26T23:00:00+00:00 | 2028-01-01T09:00:00+00:00 | 2027-12-27T07:00:00+08:00 | 2028-01-01T17:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "e98e6472-f09b-ef11-a856-000d3acacefd", "code": "PPTRC4P", "name": "Reclaimer: PPT 4P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49122 | 2022-11-01T07:09:47+00:00 | 2022-11-01T15:09:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:55.6564811+00:00 | 2026-10-05T14:22:55.6564811+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335287 | TRUE | TRUE | 2026-10-05T06:22:55.6564811+00:00 | 2026-10-05T14:22:55.6564811+08:00 | #49122 - PPT: 130hrs - BERTH: PPT 02 | 6.0 | FALSE |  | 2027-12-26T11:00:00+00:00 | 2027-12-31T21:00:00+00:00 | 2027-12-26T19:00:00+08:00 | 2028-01-01T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00). |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49138 | 2022-11-01T07:10:12+00:00 | 2022-11-01T15:10:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:55.890323+00:00 | 2026-10-05T14:22:55.890323+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335288 | TRUE | TRUE | 2026-10-05T06:22:55.890323+00:00 | 2026-10-05T14:22:55.890323+08:00 | #49138 - PPT: 130hrs - BERTH: PPT 03 | 6.0 | FALSE |  | 2027-12-26T11:00:00+00:00 | 2027-12-31T21:00:00+00:00 | 2027-12-26T19:00:00+08:00 | 2028-01-01T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00). |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44424 | 2021-11-25T02:57:07+00:00 | 2021-11-25T10:57:07+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:55.1785025+00:00 | 2026-10-05T14:22:55.1785025+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335285 | TRUE | TRUE | 2026-10-05T06:22:55.1785025+00:00 | 2026-10-05T14:22:55.1785025+08:00 | #44424 - PPT: 154hrs - CAR DUMPER + BIN LINER: PPT 3P | 8.0 | TRUE |  | 2027-12-20T11:00:00+00:00 | 2027-12-26T21:00:00+00:00 | 2027-12-20T19:00:00+08:00 | 2027-12-27T05:00:00+08:00 |  |  |  |  | 154.00 | Standard IAM Maintenance + Bin liner Shut | Aligning start time with new IAM standard start time of 19:00 (previous 18:00) |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
40391 | 2021-02-24T07:16:10+00:00 | 2021-02-24T15:16:10+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:53.5818876+00:00 | 2026-10-05T14:22:53.5818876+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335278 | TRUE | TRUE | 2026-10-05T06:22:53.5818876+00:00 | 2026-10-05T14:22:53.5818876+08:00 | #40391 - PPT: 106hrs - STACKER: PPT 5P | 7.0 | FALSE |  | 2027-10-31T23:00:00+00:00 | 2027-11-05T09:00:00+00:00 | 2027-11-01T07:00:00+08:00 | 2027-11-05T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "3c71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV121P", "name": "Conveyor: PPT 121P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44440 | 2021-11-25T03:00:22+00:00 | 2021-11-25T11:00:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:53.7975423+00:00 | 2026-10-05T14:22:53.7975423+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335279 | TRUE | TRUE | 2026-10-05T06:22:53.7975423+00:00 | 2026-10-05T14:22:53.7975423+08:00 | #44440 - PPT: 106hrs - CAR DUMPER: PPT 4P | 7.0 | TRUE |  | 2027-11-08T11:00:00+00:00 | 2027-11-12T21:00:00+00:00 | 2027-11-08T19:00:00+08:00 | 2027-11-13T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM start time of 19:00 (previous 18:00) |  | [{"equipmentGUID": "0937f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD4P", "name": "Car Dumper: PPT 4P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49225 | 2022-11-02T03:00:28+00:00 | 2022-11-02T11:00:28+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:49.2667707+00:00 | 2026-10-05T14:22:49.2667707+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335257 | TRUE | TRUE | 2026-10-05T06:22:49.2667707+00:00 | 2026-10-05T14:22:49.2667707+08:00 | #49225 - PPT: 130hrs - RECLAIMER: PPT 1P | 9.0 | FALSE |  | 2027-03-28T11:00:00+00:00 | 2027-04-02T21:00:00+00:00 | 2027-03-28T19:00:00+08:00 | 2027-04-03T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance - Aligned with Shiploader due to Reclaimer EOL Replacement N.C 27.05.24 | Changed to new 'Feed off' standard start time of 19:00 hrs. |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
40390 | 2021-02-24T07:16:09+00:00 | 2021-02-24T15:16:09+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:49.457954+00:00 | 2026-10-05T14:22:49.457954+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335258 | TRUE | TRUE | 2026-10-05T06:22:49.457954+00:00 | 2026-10-05T14:22:49.457954+08:00 | #40390 - PPT: 106hrs - STACKER: PPT 5P | 7.0 | FALSE |  | 2027-05-02T23:00:00+00:00 | 2027-05-07T09:00:00+00:00 | 2027-05-03T07:00:00+08:00 | 2027-05-07T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "3c71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV121P", "name": "Conveyor: PPT 121P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44438 | 2021-11-25T03:00:19+00:00 | 2021-11-25T11:00:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:49.634629+00:00 | 2026-10-05T14:22:49.634629+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335259 | TRUE | TRUE | 2026-10-05T06:22:49.634629+00:00 | 2026-10-05T14:22:49.634629+08:00 | #44438 - PPT: 106hrs - CAR DUMPER: PPT 4P | 7.0 | TRUE |  | 2027-05-10T11:00:00+00:00 | 2027-05-14T21:00:00+00:00 | 2027-05-10T19:00:00+08:00 | 2027-05-15T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard start time of 19:00 |  | [{"equipmentGUID": "0937f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD4P", "name": "Car Dumper: PPT 4P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
60601 | 2024-02-15T07:03:49+00:00 | 2024-02-15T15:03:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:49.8234985+00:00 | 2026-10-05T14:22:49.8234985+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335260 | TRUE | TRUE | 2026-10-05T06:22:49.8234985+00:00 | 2026-10-05T14:22:49.8234985+08:00 | #60601 - PPT: 292hrs - CD4P IAM + AF1 & 2 C/O | 8.0 | TRUE |  | 2027-05-10T11:00:00+00:00 | 2027-05-22T15:00:00+00:00 | 2027-05-10T19:00:00+08:00 | 2027-05-22T23:00:00+08:00 |  |  |  |  | 292.00 | CD4P IAM + AF1 & 2 C/O | Aligning work to IAM start time to accommodate for equipment availability and asset constraints. |  | [{"equipmentGUID": "0937f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD4P", "name": "Car Dumper: PPT 4P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [{"name": "Apron Feeder Overhaul"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44455 | 2021-11-25T03:06:20+00:00 | 2021-11-25T11:06:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T03:20:35.7609674+00:00 | 2026-10-05T11:20:35.7609674+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335226 | TRUE | TRUE | 2026-10-05T03:20:35.7609674+00:00 | 2026-10-05T11:20:35.7609674+08:00 | #44455 - PPT: 130hrs - SHIPLOADER: PPT 2P | 6.0 | TRUE |  | 2027-08-15T11:00:00+00:00 | 2027-08-20T21:00:00+00:00 | 2027-08-15T19:00:00+08:00 | 2027-08-21T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44471 | 2021-11-25T03:10:02+00:00 | 2021-11-25T11:10:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T03:20:35.9687423+00:00 | 2026-10-05T11:20:35.9687423+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335227 | TRUE | TRUE | 2026-10-05T03:20:35.9687423+00:00 | 2026-10-05T11:20:35.9687423+08:00 | #44471 - PPT: 80hrs - SHIPLOADER: PPT 3P | 6.0 | TRUE |  | 2027-09-26T11:00:00+00:00 | 2027-09-29T19:00:00+00:00 | 2027-09-26T19:00:00+08:00 | 2027-09-30T03:00:00+08:00 |  |  |  |  | 80.00 | Standard IAM Maintenance | Site request to reduce IAM to 80 Hours to accommodate RMP corrosion work (tagged onto the end)- PACE workshop (reduce 2027 SL) Email attached for verification. |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44456 | 2021-11-25T03:06:22+00:00 | 2021-11-25T11:06:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T03:20:36.1765329+00:00 | 2026-10-05T11:20:36.1765329+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335228 | TRUE | TRUE | 2026-10-05T03:20:36.1765329+00:00 | 2026-10-05T11:20:36.1765329+08:00 | #44456 - PPT: 130hrs - SHIPLOADER: PPT 2P | 6.0 | TRUE |  | 2027-11-14T11:00:00+00:00 | 2027-11-19T21:00:00+00:00 | 2027-11-14T19:00:00+08:00 | 2027-11-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44472 | 2021-11-25T03:10:03+00:00 | 2021-11-25T11:10:03+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T03:20:36.3710822+00:00 | 2026-10-05T11:20:36.3710822+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335229 | TRUE | TRUE | 2026-10-05T03:20:36.3710822+00:00 | 2026-10-05T11:20:36.3710822+08:00 | #44472 - PPT: 130hrs - SHIPLOADER: PPT 3P | 6.0 | TRUE |  | 2027-12-26T11:00:00+00:00 | 2027-12-31T21:00:00+00:00 | 2027-12-26T19:00:00+08:00 | 2028-01-01T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49327 | 2022-11-02T03:43:59+00:00 | 2022-11-02T11:43:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:54.2424163+00:00 | 2026-10-05T14:22:54.2424163+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335281 | TRUE | TRUE | 2026-10-05T06:22:54.2424163+00:00 | 2026-10-05T14:22:54.2424163+08:00 | #49327 - PPT: 130hrs - RECLAIMER: PPT 2P | 12.0 | FALSE |  | 2027-11-14T11:00:00+00:00 | 2027-11-19T21:00:00+00:00 | 2027-11-14T19:00:00+08:00 | 2027-11-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49084 | 2022-11-01T06:58:36+00:00 | 2022-11-01T14:58:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:54.4654287+00:00 | 2026-10-05T14:22:54.4654287+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335282 | TRUE | TRUE | 2026-10-05T06:22:54.4654287+00:00 | 2026-10-05T14:22:54.4654287+08:00 | #49084 - PPT: 130hrs - BERTH: PPT 04 | 6.0 | FALSE |  | 2027-11-14T11:00:00+00:00 | 2027-11-19T21:00:00+00:00 | 2027-11-14T19:00:00+08:00 | 2027-11-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00). |  | [{"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49100 | 2022-11-01T06:59:01+00:00 | 2022-11-01T14:59:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:54.701791+00:00 | 2026-10-05T14:22:54.701791+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335283 | TRUE | TRUE | 2026-10-05T06:22:54.701791+00:00 | 2026-10-05T14:22:54.701791+08:00 | #49100 - PPT: 130hrs - BERTH: PPT 05 | 6.0 | FALSE |  | 2027-11-14T11:00:00+00:00 | 2027-11-19T21:00:00+00:00 | 2027-11-14T19:00:00+08:00 | 2027-11-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00). |  | [{"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49121 | 2022-11-01T07:09:46+00:00 | 2022-11-01T15:09:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:52.9324192+00:00 | 2026-10-05T14:22:52.9324192+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335275 | TRUE | TRUE | 2026-10-05T06:22:52.9324192+00:00 | 2026-10-05T14:22:52.9324192+08:00 | #49121 - PPT: 130hrs - BERTH: PPT 02 | 6.0 | FALSE |  | 2027-09-26T11:00:00+00:00 | 2027-10-01T21:00:00+00:00 | 2027-09-26T19:00:00+08:00 | 2027-10-02T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49137 | 2022-11-01T07:10:12+00:00 | 2022-11-01T15:10:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:53.1402795+00:00 | 2026-10-05T14:22:53.1402795+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335276 | TRUE | TRUE | 2026-10-05T06:22:53.1402795+00:00 | 2026-10-05T14:22:53.1402795+08:00 | #49137 - PPT: 130hrs - BERTH: PPT 03 | 6.0 | FALSE |  | 2027-09-26T11:00:00+00:00 | 2027-10-01T21:00:00+00:00 | 2027-09-26T19:00:00+08:00 | 2027-10-02T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00). |  | [{"equipmentGUID": "", "code": "PPTBTH03", "name": "Berth: PPT 03", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44442 | 2021-11-25T03:00:23+00:00 | 2021-11-25T11:00:23+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:51.6794548+00:00 | 2026-10-05T14:22:51.6794548+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335269 | TRUE | TRUE | 2026-10-05T06:22:51.6794548+00:00 | 2026-10-05T14:22:51.6794548+08:00 | #44442 - PPT: 154hrs - CAR DUMPER + BIN LINER: PPT 4P | 9.0 | TRUE |  | 2027-08-09T11:00:00+00:00 | 2027-08-15T21:00:00+00:00 | 2027-08-09T19:00:00+08:00 | 2027-08-16T05:00:00+08:00 |  |  |  |  | 154.00 | Standard IAM Maintenance + Bin Liner shut | Changing to new IAM start time of 19:00 (previous 18:00) |  | [{"equipmentGUID": "0937f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD4P", "name": "Car Dumper: PPT 4P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49083 | 2022-11-01T06:58:35+00:00 | 2022-11-01T14:58:35+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:52.0912585+00:00 | 2026-10-05T14:22:52.0912585+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335271 | TRUE | TRUE | 2026-10-05T06:22:52.0912585+00:00 | 2026-10-05T14:22:52.0912585+08:00 | #49083 - PPT: 130hrs - BERTH: PPT 04 | 6.0 | FALSE |  | 2027-08-15T11:00:00+00:00 | 2027-08-20T21:00:00+00:00 | 2027-08-15T19:00:00+08:00 | 2027-08-21T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49099 | 2022-11-01T06:59:01+00:00 | 2022-11-01T14:59:01+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:52.2958831+00:00 | 2026-10-05T14:22:52.2958831+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335272 | TRUE | TRUE | 2026-10-05T06:22:52.2958831+00:00 | 2026-10-05T14:22:52.2958831+08:00 | #49099 - PPT: 130hrs - BERTH: PPT 05 | 6.0 | FALSE |  | 2027-08-15T11:00:00+00:00 | 2027-08-20T21:00:00+00:00 | 2027-08-15T19:00:00+08:00 | 2027-08-21T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49227 | 2022-11-02T03:00:32+00:00 | 2022-11-02T11:00:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:52.5062232+00:00 | 2026-10-05T14:22:52.5062232+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335273 | TRUE | TRUE | 2026-10-05T06:22:52.5062232+00:00 | 2026-10-05T14:22:52.5062232+08:00 | #49227 - PPT: 130hrs - RECLAIMER: PPT 1P | 6.0 | FALSE |  | 2027-09-05T23:00:00+00:00 | 2027-09-11T09:00:00+00:00 | 2027-09-06T07:00:00+08:00 | 2027-09-11T17:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance *final shut before change out, likely deletion if C/O date stays in July 2027 | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49082 | 2022-11-01T06:58:31+00:00 | 2022-11-01T14:58:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:50.4157793+00:00 | 2026-10-05T14:22:50.4157793+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335263 | TRUE | TRUE | 2026-10-05T06:22:50.4157793+00:00 | 2026-10-05T14:22:50.4157793+08:00 | #49082 - PPT: 130hrs - BERTH: PPT 04 | 5.0 | FALSE |  | 2027-05-16T11:00:00+00:00 | 2027-05-21T21:00:00+00:00 | 2027-05-16T19:00:00+08:00 | 2027-05-22T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49098 | 2022-11-01T06:59:00+00:00 | 2022-11-01T14:59:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:50.6035384+00:00 | 2026-10-05T14:22:50.6035384+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335264 | TRUE | TRUE | 2026-10-05T06:22:50.6035384+00:00 | 2026-10-05T14:22:50.6035384+08:00 | #49098 - PPT: 130hrs - BERTH: PPT 05 | 5.0 | FALSE |  | 2027-05-16T11:00:00+00:00 | 2027-05-21T21:00:00+00:00 | 2027-05-16T19:00:00+08:00 | 2027-05-22T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44422 | 2021-11-25T02:57:04+00:00 | 2021-11-25T10:57:04+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:50.7978681+00:00 | 2026-10-05T14:22:50.7978681+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335265 | TRUE | TRUE | 2026-10-05T06:22:50.7978681+00:00 | 2026-10-05T14:22:50.7978681+08:00 | #44422 - PPT: 154hrs - CAR DUMPER + BIN LINER: PPT 3P | 10.0 | TRUE |  | 2027-06-21T11:00:00+00:00 | 2027-06-27T21:00:00+00:00 | 2027-06-21T19:00:00+08:00 | 2027-06-28T05:00:00+08:00 |  |  |  |  | 154.00 | Standard IAM Maintenance | Aligning start time to new IAM standard start time of 19:00 (previous 18:00) |  | [{"equipmentGUID": "57fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD3P", "name": "Car Dumper: PPT 3P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49226 | 2022-11-02T03:00:29+00:00 | 2022-11-02T11:00:29+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-05T06:22:50.9948895+00:00 | 2026-10-05T14:22:50.9948895+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335266 | TRUE | TRUE | 2026-10-05T06:22:50.9948895+00:00 | 2026-10-05T14:22:50.9948895+08:00 | #49226 - PPT: 130hrs - RECLAIMER: PPT 1P | 9.0 | FALSE |  | 2027-06-27T23:00:00+00:00 | 2027-07-03T09:00:00+00:00 | 2027-06-28T07:00:00+08:00 | 2027-07-03T17:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance - Moved outage for reclaimer availability during the other reclaimers EOL replacement N.C 27.05.24 | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44454 | 2021-11-25T03:06:19+00:00 | 2021-11-25T11:06:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-12T07:14:01.3489196+00:00 | 2026-10-12T15:14:01.3489196+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335854 | TRUE | TRUE | 2026-10-12T07:14:01.3489196+00:00 | 2026-10-12T15:14:01.3489196+08:00 | #44454 - PPT: 120hrs - SHIPLOADER: PPT 2P | 9.0 | TRUE |  | 2027-05-16T23:00:00+00:00 | 2027-05-21T23:00:00+00:00 | 2027-05-17T07:00:00+08:00 | 2027-05-22T07:00:00+08:00 |  |  |  |  | 120.00 | Standard IAM Maintenance | 10 hours reduced due to corrosion work |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
40361 | 2021-02-24T06:06:48+00:00 | 2021-02-24T14:06:48+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-09-17T05:34:39.2597839+00:00 | 2026-09-17T13:34:39.2597839+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333486 | TRUE | TRUE | 2026-09-17T05:34:39.2597839+00:00 | 2026-09-17T13:34:39.2597839+08:00 | #40361 - PPT: 72hrs - CONVEYOR: PPT 122P & CONVEYOR: PPT 123P | 7.0 | FALSE |  | 2027-01-11T23:00:00+00:00 | 2027-01-14T23:00:00+00:00 | 2027-01-12T07:00:00+08:00 | 2027-01-15T07:00:00+08:00 |  |  |  |  | 72.00 | BULKING IN OUTAGE - 129P is key driver | Identified change for labour optimisation |  | [{"equipmentGUID": "58fee8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV122P", "name": "Conveyor: PPT 122P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8b34f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV123P", "name": "Conveyor: PPT 123P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "51df00c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV129P", "name": "Conveyor: PPT 129P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "", "code": "PPTCVCCTBULKING", "name": "Conveyor: PPT Bulking Circuit", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "81421b48-796b-4195-8980-88518d49621f", "emailAddress": "Brett.mccormack@riotinto.com", "displayName": "Brett McCormack"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
60795 | 2024-02-26T02:42:32+00:00 | 2024-02-26T10:42:32+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-000000000508", "displayName": "Troy Drewett"} | 2026-10-07T07:17:43.0485554+00:00 | 2026-10-07T15:17:43.0485554+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335430 | TRUE | TRUE | 2026-10-07T07:17:43.0485554+00:00 | 2026-10-07T15:17:43.0485554+08:00 | #60795 - PPT: 372hrs - BERTH 2 - MARINE STRUCTUAL LIFE EXTENSION WORKS | 9.0 | FALSE |  | 2027-06-21T23:00:00+00:00 | 2027-07-07T11:00:00+00:00 | 2027-06-22T07:00:00+08:00 | 2027-07-07T19:00:00+08:00 |  |  |  |  | 372.00 | SUS CAP SI_ Campaign 1 Marine Structural Life Extension Berth Works - Extended to align with Ship Loader SDN repairs. | PPT B:02 Outage time change - Requested by the SUS Cap Project Team & Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "", "code": "PPTBTH02", "name": "Berth: PPT 02", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "bc521488-59eb-4d88-8834-d789fcc969eb", "emailAddress": "Lewis.Buckland@riotinto.com", "displayName": "Buckland, Lewis (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Major Projects | PPT | Australia/Perth
44453 | 2021-11-25T03:06:19+00:00 | 2021-11-25T11:06:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T01:14:57.8624338+00:00 | 2026-10-01T09:14:57.8624338+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334774 | TRUE | TRUE | 2026-10-01T01:14:57.8624338+00:00 | 2026-10-01T09:14:57.8624338+08:00 | #44453 - PPT: 130hrs - SHIPLOADER: PPT 2P | 7.0 | TRUE |  | 2027-02-14T11:00:00+00:00 | 2027-02-19T21:00:00+00:00 | 2027-02-14T19:00:00+08:00 | 2027-02-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new standard starting time of 19:00 (7:00 PM) |  | [{"equipmentGUID": "f3ede8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD2P", "name": "Shiploader: PPT 2P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44469 | 2021-11-25T03:10:00+00:00 | 2021-11-25T11:10:00+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-01T04:13:12.4271741+00:00 | 2026-10-01T12:13:12.4271741+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334807 | TRUE | TRUE | 2026-10-01T04:13:12.4271741+00:00 | 2026-10-01T12:13:12.4271741+08:00 | #44469 - PPT: 130hrs - SHIPLOADER: PPT 3P | 6.0 | TRUE |  | 2027-03-28T11:00:00+00:00 | 2027-04-02T21:00:00+00:00 | 2027-03-28T19:00:00+08:00 | 2027-04-03T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | New feed off time from review - excel attachment in email attached |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
44437 | 2021-11-25T03:00:18+00:00 | 2021-11-25T11:00:18+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-15T02:10:20.6667218+00:00 | 2026-10-15T10:10:20.6667218+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336019 | TRUE | TRUE | 2026-10-15T02:10:20.6667218+00:00 | 2026-10-15T10:10:20.6667218+08:00 | #44437 - PPT: 154hrs - CAR DUMPER + BIN LINER: PPT 4P | 7.1 | TRUE |  | 2027-02-08T11:00:00+00:00 | 2027-02-14T21:00:00+00:00 | 2027-02-08T19:00:00+08:00 | 2027-02-15T05:00:00+08:00 |  |  |  |  | 154.00 | Standard IAM Maintenance |  |  | [{"equipmentGUID": "0937f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCD4P", "name": "Car Dumper: PPT 4P", "assetClass": {"name": "Car Dumper"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
57796 | 2023-08-18T06:27:46+00:00 | 2023-08-18T14:27:46+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-09T01:05:10.5245647+00:00 | 2026-10-09T09:05:10.5245647+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335487 | TRUE | TRUE | 2026-10-09T01:05:10.5245647+00:00 | 2026-10-09T09:05:10.5245647+08:00 | #57796 - PPT: 130hrs - SL3P CORROSION CONTROL | 10.0 | TRUE |  | 2027-09-29T18:00:00+00:00 | 2027-10-05T04:00:00+00:00 | 2027-09-30T02:00:00+08:00 | 2027-10-05T12:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control | Identified in PACE workshop, this has been brought forward to reduce Schedule Loss - Site request to start 80 hours into IAM. See email attached with action workbook. |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
65437 | 2024-10-23T00:53:54+00:00 | 2024-10-23T08:53:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-07-10T05:19:25.2358163+00:00 | 2026-07-10T13:19:25.2358163+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 329789 | TRUE | TRUE | 2026-07-10T05:19:25.2358163+00:00 | 2026-07-10T13:19:25.2358163+08:00 | #65437 - PPT: 130hrs - REC2P CORROSION REPAIRS - STANDALONE | 4.0 | FALSE |  | 2027-09-05T23:00:00+00:00 | 2027-09-11T09:00:00+00:00 | 2027-09-06T07:00:00+08:00 | 2027-09-11T17:00:00+08:00 |  |  |  |  | 130.00 | STANDALONE outage to complete crack and corrosion repairs | Requested to align to Ship loader 3P outage |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
40379 | 2021-02-24T06:46:27+00:00 | 2021-02-24T14:46:27+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-09-17T23:38:39.7620776+00:00 | 2026-09-18T07:38:39.7620776+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333532 | TRUE | TRUE | 2026-09-17T23:38:39.7620776+00:00 | 2026-09-18T07:38:39.7620776+08:00 | #40379 - PPT: 106hrs - STACKER: PPT 3P | 6.0 | FALSE |  | 2027-01-11T23:00:00+00:00 | 2027-01-16T09:00:00+00:00 | 2027-01-12T07:00:00+08:00 | 2027-01-16T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Identified change for labour optimisation |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49081 | 2022-11-01T06:58:31+00:00 | 2022-11-01T14:58:31+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-02T05:10:47.6309874+00:00 | 2026-10-02T13:10:47.6309874+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334982 | TRUE | TRUE | 2026-10-02T05:10:47.6309874+00:00 | 2026-10-02T13:10:47.6309874+08:00 | #49081 - PPT: 130hrs - BERTH: PPT 04 | 5.0 | FALSE |  | 2027-02-14T11:00:00+00:00 | 2027-02-19T21:00:00+00:00 | 2027-02-14T19:00:00+08:00 | 2027-02-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH04", "name": "Berth: PPT 04", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
49097 | 2022-11-01T06:58:56+00:00 | 2022-11-01T14:58:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-10-02T05:10:47.8060094+00:00 | 2026-10-02T13:10:47.8060094+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334983 | TRUE | TRUE | 2026-10-02T05:10:47.8060094+00:00 | 2026-10-02T13:10:47.8060094+08:00 | #49097 - PPT: 130hrs - BERTH: PPT 05 | 5.0 | FALSE |  | 2027-02-14T11:00:00+00:00 | 2027-02-19T21:00:00+00:00 | 2027-02-14T19:00:00+08:00 | 2027-02-20T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance / BERTH 5 - MARINE STRUCTUAL LIFE EXTENSION WORKS | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "", "code": "PPTBTH05", "name": "Berth: PPT 05", "assetClass": {"name": "Berth"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45691 | 2022-01-20T09:15:44+00:00 | 2022-01-20T17:15:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-08T00:02:55.5816066+00:00 | 2026-10-08T08:02:55.5816066+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335447 | TRUE | TRUE | 2026-10-08T00:02:55.5816066+00:00 | 2026-10-08T08:02:55.5816066+08:00 | #45691 - PPT: 106hrs - STACKER: PPT 3P | 7.0 | FALSE |  | 2027-10-11T23:00:00+00:00 | 2027-10-16T09:00:00+00:00 | 2027-10-12T07:00:00+08:00 | 2027-10-16T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Identified change for labour optimisation |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45688 | 2022-01-20T09:10:47+00:00 | 2022-01-20T17:10:47+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-07T07:18:32.8858169+00:00 | 2026-10-07T15:18:32.8858169+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335431 | TRUE | TRUE | 2026-10-07T07:18:32.8858169+00:00 | 2026-10-07T15:18:32.8858169+08:00 | #45688 - PPT: 80hrs - STACKER: PPT 4P | 9.0 | FALSE |  | 2027-06-21T23:00:00+00:00 | 2027-06-25T07:00:00+00:00 | 2027-06-22T07:00:00+08:00 | 2027-06-25T15:00:00+08:00 |  |  |  |  | 80.00 | Standard IAM Maintenance | Changing start time to accommodate CD3P washdown (12 hours) |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
54814 | 2023-04-05T05:18:22+00:00 | 2023-04-05T13:18:22+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:53.3578182+00:00 | 2026-10-05T14:22:53.3578182+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335277 | TRUE | TRUE | 2026-10-05T06:22:53.3578182+00:00 | 2026-10-05T14:22:53.3578182+08:00 | #54814 - PPT: 130hrs - RECLAIMER: PPT 6P | 10.0 | FALSE |  | 2027-09-26T23:00:00+00:00 | 2027-10-02T09:00:00+00:00 | 2027-09-27T07:00:00+08:00 | 2027-10-02T17:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance 112P, 117P, 114P. Out of week alignment due to RCL1P replacement major works | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "eb8e6472-f09b-ef11-a856-000d3acacefd", "code": "PPTRC6P", "name": "Reclaimer: PPT 6P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45698 | 2022-01-20T09:31:15+00:00 | 2022-01-20T17:31:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:54.9383884+00:00 | 2026-10-05T14:22:54.9383884+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335284 | TRUE | TRUE | 2026-10-05T06:22:54.9383884+00:00 | 2026-10-05T14:22:54.9383884+08:00 | #45698 - PPT: 130hrs - RECLAIMER: PPT 6P | 9.0 | FALSE |  | 2027-11-28T23:00:00+00:00 | 2027-12-04T09:00:00+00:00 | 2027-11-29T07:00:00+08:00 | 2027-12-04T17:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance Additional Info: 112P, 117P, 114P | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "eb8e6472-f09b-ef11-a856-000d3acacefd", "code": "PPTRC6P", "name": "Reclaimer: PPT 6P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45678 | 2022-01-20T08:46:20+00:00 | 2022-01-20T16:46:20+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T04:57:34.4751411+00:00 | 2026-10-02T12:57:34.4751411+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 334980 | TRUE | TRUE | 2026-10-02T04:57:34.4751411+00:00 | 2026-10-02T12:57:34.4751411+08:00 | #45678 - PPT: 80hrs - STACKER: PPT 6P | 8.0 | FALSE |  | 2027-02-08T23:00:00+00:00 | 2027-02-12T07:00:00+00:00 | 2027-02-09T07:00:00+08:00 | 2027-02-12T15:00:00+08:00 |  |  |  |  | 80.00 | Standard IAM Maintenance 103, 3P | Changing start time to accommodate washdown - starting with CD4P washdown follow on to ST6P. |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45680 | 2022-01-20T08:49:21+00:00 | 2022-01-20T16:49:21+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:50.0299406+00:00 | 2026-10-05T14:22:50.0299406+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335261 | TRUE | TRUE | 2026-10-05T06:22:50.0299406+00:00 | 2026-10-05T14:22:50.0299406+08:00 | #45680 - PPT: 106hrs - STACKER: PPT 6P | 7.0 | FALSE |  | 2027-05-10T23:00:00+00:00 | 2027-05-15T09:00:00+00:00 | 2027-05-11T07:00:00+08:00 | 2027-05-15T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance 103p, 3P | Changing start time for washdown - Start with CD4P on to ST6P |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45703 | 2022-01-20T09:37:43+00:00 | 2022-01-20T17:37:43+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:50.2144587+00:00 | 2026-10-05T14:22:50.2144587+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335262 | TRUE | TRUE | 2026-10-05T06:22:50.2144587+00:00 | 2026-10-05T14:22:50.2144587+08:00 | #45703 - PPT: 130hrs - RECLAIMER: PPT 2P | 13.0 | FALSE |  | 2027-05-16T11:00:00+00:00 | 2027-05-21T21:00:00+00:00 | 2027-05-16T19:00:00+08:00 | 2027-05-22T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance - Moved outage for reclaimer availability during the other reclaimers EOL replacement N.C 23.08.24 | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45704 | 2022-01-20T09:38:49+00:00 | 2022-01-20T17:38:49+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:51.885431+00:00 | 2026-10-05T14:22:51.885431+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335270 | TRUE | TRUE | 2026-10-05T06:22:51.885431+00:00 | 2026-10-05T14:22:51.885431+08:00 | #45704 - PPT: 130hrs - RECLAIMER: PPT 2P | 10.0 | FALSE |  | 2027-08-15T11:00:00+00:00 | 2027-08-20T21:00:00+00:00 | 2027-08-15T19:00:00+08:00 | 2027-08-21T05:00:00+08:00 |  |  |  |  | 130.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 19:00 (previous 18:00) |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45685 | 2022-01-20T09:00:26+00:00 | 2022-01-20T17:00:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:51.4835638+00:00 | 2026-10-05T14:22:51.4835638+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335268 | TRUE | TRUE | 2026-10-05T06:22:51.4835638+00:00 | 2026-10-05T14:22:51.4835638+08:00 | #45685 - PPT: 106hrs - STACKER: PPT 5P | 8.0 | FALSE |  | 2027-08-01T23:00:00+00:00 | 2027-08-06T09:00:00+00:00 | 2027-08-02T07:00:00+08:00 | 2027-08-06T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "3c71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV121P", "name": "Conveyor: PPT 121P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45687 | 2022-01-20T09:08:39+00:00 | 2022-01-20T17:08:39+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:52.7172234+00:00 | 2026-10-05T14:22:52.7172234+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335274 | TRUE | TRUE | 2026-10-05T06:22:52.7172234+00:00 | 2026-10-05T14:22:52.7172234+08:00 | #45687 - PPT: 106hrs - STACKER: PPT 4P | 8.0 | FALSE |  | 2027-09-19T23:00:00+00:00 | 2027-09-24T09:00:00+00:00 | 2027-09-20T07:00:00+08:00 | 2027-09-24T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time to 07:00 (previous 6:00) |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45681 | 2022-01-20T08:50:30+00:00 | 2022-01-20T16:50:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:54.0174823+00:00 | 2026-10-05T14:22:54.0174823+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335280 | TRUE | TRUE | 2026-10-05T06:22:54.0174823+00:00 | 2026-10-05T14:22:54.0174823+08:00 | #45681 - PPT: 106hrs - STACKER: PPT 6P | 7.0 | FALSE |  | 2027-11-08T23:00:00+00:00 | 2027-11-13T09:00:00+00:00 | 2027-11-09T07:00:00+08:00 | 2027-11-13T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance 103P, 3P | Aligning to accommodate CD4P washdown (ST6P + 12 hrs from CD4P feed off) |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45689 | 2022-01-20T09:12:59+00:00 | 2022-01-20T17:12:59+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-05T06:22:55.4232704+00:00 | 2026-10-05T14:22:55.4232704+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335286 | TRUE | TRUE | 2026-10-05T06:22:55.4232704+00:00 | 2026-10-05T14:22:55.4232704+08:00 | #45689 - PPT: 106hrs - STACKER: PPT 4P | 8.0 | FALSE |  | 2027-12-20T23:00:00+00:00 | 2027-12-25T09:00:00+00:00 | 2027-12-21T07:00:00+08:00 | 2027-12-25T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Changing start time to accommodate CD3P washdown (+12 hours). |  | [{"equipmentGUID": "67d900c0-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV102P", "name": "Conveyor: PPT 102P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "f93dd50b-e81f-44a0-a820-d892c3d3a2d0", "emailAddress": "Josh.Azzopardi@riotinto.com", "displayName": "Azzopardi, Josh (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45665 | 2022-01-20T08:17:30+00:00 | 2022-01-20T16:17:30+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-06-11T02:48:53.0805846+00:00 | 2026-06-11T10:48:53.0805846+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 327696 | TRUE | TRUE | 2026-06-11T02:48:53.0805846+00:00 | 2026-06-11T10:48:53.0805846+08:00 | #45665 - EII: 108hrs - STACKER: EII 2EN | 5.0 | FALSE |  | 2028-01-23T22:00:00+00:00 | 2028-01-28T10:00:00+00:00 | 2028-01-24T06:00:00+08:00 | 2028-01-28T18:00:00+08:00 |  |  |  |  | 108.00 | Standard IAM Maintenance | Approved IAM Outage Week Change |  | [{"equipmentGUID": "071af0bf-7c7b-ee11-a846-000d3acacefd", "code": "EIIST2EN", "name": "Stacker: EII 2EN ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
45690 | 2022-01-20T09:14:40+00:00 | 2022-01-20T17:14:40+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-18T04:18:46.1755792+00:00 | 2026-09-18T12:18:46.1755792+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333569 | TRUE | TRUE | 2026-09-18T04:18:46.1755792+00:00 | 2026-09-18T12:18:46.1755792+08:00 | #45690 - PPT: 106hrs - STACKER: PPT 3P | 7.0 | FALSE |  | 2027-04-12T23:00:00+00:00 | 2027-04-17T09:00:00+00:00 | 2027-04-13T07:00:00+08:00 | 2027-04-17T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Identified change for labour optimisation |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45682 | 2022-01-20T08:55:26+00:00 | 2022-01-20T16:55:26+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-18T05:15:22.2828565+00:00 | 2026-09-18T13:15:22.2828565+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333583 | TRUE | TRUE | 2026-09-18T05:15:22.2828565+00:00 | 2026-09-18T13:15:22.2828565+08:00 | #45682 - PPT: 106hrs - STACKER: PPT 3P | 6.0 | FALSE |  | 2027-07-12T23:00:00+00:00 | 2027-07-17T09:00:00+00:00 | 2027-07-13T07:00:00+08:00 | 2027-07-17T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance 107P | Identified change for labour optimisation |  | [{"equipmentGUID": "273af6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST3P", "name": "Stacker: PPT 3P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
45667 | 2022-01-20T08:26:54+00:00 | 2022-01-20T16:26:54+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-20T05:54:08.3617764+00:00 | 2026-10-20T13:54:08.3617764+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336220 | TRUE | TRUE | 2026-10-20T05:54:08.3617764+00:00 | 2026-10-20T13:54:08.3617764+08:00 | #45667 - EII: 96hrs - RECLAIMER: EII 1E | 6.0 | FALSE |  | 2027-05-23T23:00:00+00:00 | 2027-05-27T23:00:00+00:00 | 2027-05-24T07:00:00+08:00 | 2027-05-28T07:00:00+08:00 |  |  |  |  | 96.00 | Standard IAM Maintenance | Aligning to new IAM standard 'Feed off' time - adjusted to 7:00 (previous 19:00) to accommodate integration with other shut |  | [{"equipmentGUID": "d056fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIIRC1E", "name": "Reclaimer: EII 1E ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
45684 | 2022-01-20T08:59:14+00:00 | 2022-01-20T16:59:14+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-17T05:43:57.0405204+00:00 | 2026-09-17T13:43:57.0405204+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 333499 | TRUE | TRUE | 2026-09-17T05:43:57.0405204+00:00 | 2026-09-17T13:43:57.0405204+08:00 | #45684 - PPT: 106hrs - STACKER: PPT 5P | 8.0 | FALSE |  | 2027-01-31T11:00:00+00:00 | 2027-02-04T21:00:00+00:00 | 2027-01-31T19:00:00+08:00 | 2027-02-05T05:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Requested by site (aim for on site labor optimisation) |  | [{"equipmentGUID": "3c71fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV121P", "name": "Conveyor: PPT 121P", "assetClass": {"name": "Conveyor"}}, {"equipmentGUID": "8d26f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST5P", "name": "Stacker: PPT 5P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
84076 | 2026-10-01T01:56:35.0167622+00:00 | 2026-10-01T09:56:35.0167622+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T01:54:44.784918+00:00 | 2026-10-07T09:54:44.784918+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335387 | TRUE | TRUE | 2026-10-07T01:54:44.784918+00:00 | 2026-10-07T09:54:44.784918+08:00 | #84076 - EII: 36hrs - CONVEYOR: EII 12E | 1.0 | FALSE |  | 2027-02-21T23:00:00+00:00 | 2027-02-23T11:00:00+00:00 | 2027-02-22T07:00:00+08:00 | 2027-02-23T19:00:00+08:00 |  |  |  |  | 36.00 | EII Stockyard Isolator Project |  |  | [{"equipmentGUID": "d627f6bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV12E", "name": "Conveyor: EII 12E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b9ec4e2a-3784-4d87-9441-b26e047c5279", "emailAddress": "Chris.Burg@riotinto.com", "displayName": "Burg, Christopher (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
84074 | 2026-10-01T01:50:21.41584+00:00 | 2026-10-01T09:50:21.41584+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-07T01:54:44.9890762+00:00 | 2026-10-07T09:54:44.9890762+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335388 | TRUE | TRUE | 2026-10-07T01:54:44.9890762+00:00 | 2026-10-07T09:54:44.9890762+08:00 | #84074 - EII: 36hrs - CONVEYOR: EII 11E | 1.0 | FALSE |  | 2027-02-23T23:00:00+00:00 | 2027-02-25T11:00:00+00:00 | 2027-02-24T07:00:00+08:00 | 2027-02-25T19:00:00+08:00 |  |  |  |  | 36.00 | EII Stockyard Isolator Project |  |  | [{"equipmentGUID": "4375fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV11E", "name": "Conveyor: EII 11E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "b9ec4e2a-3784-4d87-9441-b26e047c5279", "emailAddress": "Chris.Burg@riotinto.com", "displayName": "Burg, Christopher (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83464 | 2026-07-08T01:53:03.9071241+00:00 | 2026-07-08T09:53:03.9071241+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-06T00:14:19.4286326+00:00 | 2026-10-06T08:14:19.4286326+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335335 | TRUE | TRUE | 2026-10-06T00:14:19.4286326+00:00 | 2026-10-06T08:14:19.4286326+08:00 | #83464 - EII: 192hrs - 9E/13E TRANSFER CHUTE REPLACEMENT | 1.1 | FALSE |  | 2027-04-22T10:00:00+00:00 | 2027-04-30T10:00:00+00:00 | 2027-04-22T18:00:00+08:00 | 2027-04-30T18:00:00+08:00 |  |  |  |  | 192.00 | Outage For 9E Chute Project Works. |  |  | [{"equipmentGUID": "5361fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV9E", "name": "Conveyor: EII 9E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83468 | 2026-07-08T02:16:38.3926782+00:00 | 2026-07-08T10:16:38.3926782+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-06T00:17:39.3587675+00:00 | 2026-10-06T08:17:39.3587675+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335337 | TRUE | TRUE | 2026-10-06T00:17:39.3587675+00:00 | 2026-10-06T08:17:39.3587675+08:00 | #83468 - EII: 192hrs - 10E/13E TRANSFER CHUTE REPLACEMENT | 1.1 | FALSE |  | 2027-07-22T10:00:00+00:00 | 2027-07-30T10:00:00+00:00 | 2027-07-22T18:00:00+08:00 | 2027-07-30T18:00:00+08:00 |  |  |  |  | 192.00 | 10E Belt Chute Project Works |  |  | [{"equipmentGUID": "73f0e8bf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV10E", "name": "Conveyor: EII 10E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Project Contact"}, "contact": {"principalGUID": "60f3ecad-1585-46c7-88c6-3071f214504e", "emailAddress": "Janine.Fisher@riotinto.com", "displayName": "Barry, Neen (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
83972 | 2026-09-22T08:14:47.5460061+00:00 | 2026-09-22T16:14:47.5460061+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-20T05:56:33.9024401+00:00 | 2026-10-20T13:56:33.9024401+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336223 | TRUE | TRUE | 2026-10-20T05:56:33.9024401+00:00 | 2026-10-20T13:56:33.9024401+08:00 | #83972 - PPT: 12hrs - CAPD ST6P - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-07-27T23:00:00+00:00 | 2027-07-28T11:00:00+00:00 | 2027-07-28T07:00:00+08:00 | 2027-07-28T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD ST6P - Standalone Outage |  |  | [{"equipmentGUID": "f9f9e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST6P", "name": "Stacker: PPT 6P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83976 | 2026-09-22T08:42:32.2708718+00:00 | 2026-09-22T16:42:32.2708718+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-16T01:24:48.0622885+00:00 | 2026-10-16T09:24:48.0622885+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336148 | TRUE | TRUE | 2026-10-16T01:24:48.0622885+00:00 | 2026-10-16T09:24:48.0622885+08:00 | #83976 - PPT: 12hrs - REC1P CAPD - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-03-02T23:00:00+00:00 | 2027-03-03T11:00:00+00:00 | 2027-03-03T07:00:00+08:00 | 2027-03-03T19:00:00+08:00 |  |  |  |  | 12.00 | REC1P CAPD - Standalone Outage |  |  | [{"equipmentGUID": "5871fbbf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC1P", "name": "Reclaimer: PPT 1P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83975 | 2026-09-22T08:40:55.1277316+00:00 | 2026-09-22T16:40:55.1277316+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-16T01:24:48.2217773+00:00 | 2026-10-16T09:24:48.2217773+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336149 | TRUE | TRUE | 2026-10-16T01:24:48.2217773+00:00 | 2026-10-16T09:24:48.2217773+08:00 | #83975 - PPT: 12hrs - CAPD ST4P - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-02-28T23:00:00+00:00 | 2027-03-01T11:00:00+00:00 | 2027-03-01T07:00:00+08:00 | 2027-03-01T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD ST4P - Standalone Outage |  |  | [{"equipmentGUID": "6f22f0bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTST4P", "name": "Stacker: PPT 4P ", "assetClass": {"name": "Stacker"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
82945 | 2026-06-23T07:32:42.6594002+00:00 | 2026-06-23T15:32:42.6594002+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-07-10T05:28:05.5241673+00:00 | 2026-07-10T13:28:05.5241673+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 329791 | TRUE | TRUE | 2026-07-10T05:28:05.5241673+00:00 | 2026-07-10T13:28:05.5241673+08:00 | #82945 - EII: 192hrs - CONVEYOR: EII 11E | 1.0 | FALSE |  | 2027-01-18T20:00:00+00:00 | 2027-01-26T20:00:00+00:00 | 2027-01-19T04:00:00+08:00 | 2027-01-27T04:00:00+08:00 |  |  |  |  | 192.00 | 11E / 13E Transfer Chute Replacement. |  |  | [{"equipmentGUID": "4375fbbf-7c7b-ee11-a846-000d3acacefd", "code": "EIICV11E", "name": "Conveyor: EII 11E", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "69fd6601-0041-43fa-9dc9-048345c28da8", "emailAddress": "Katrina.Obenza@riotinto.com", "displayName": "Obenza, Katrina (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 83877, "shutVersionId": 333112, "title": "#83877 - EII: 192hrs - STOCKPILE: EII 11.1", "startDatetimeUTC": "2027-01-18T20:00:00+00:00", "endDatetimeUTC": "2027-01-26T20:00:00+00:00"}}] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | EII | Australia/Perth
76475 | 2026-02-26T00:41:24.5994533+00:00 | 2026-02-26T08:41:24.5994533+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-09T01:05:10.726317+00:00 | 2026-10-09T09:05:10.726317+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 335488 | TRUE | TRUE | 2026-10-09T01:05:10.726317+00:00 | 2026-10-09T09:05:10.726317+08:00 | #76475 - PPT: 130hrs - SL3P CORROSION CONTROL | 2.0 | TRUE |  | 2027-10-04T12:00:00+00:00 | 2027-10-09T22:00:00+00:00 | 2027-10-04T20:00:00+08:00 | 2027-10-10T06:00:00+08:00 |  |  |  |  | 130.00 | Corrosion Control | Identified in PACE workshop, this has been moved to IAM to reduce Schedule Loss (email attached requesting change) |  | [{"equipmentGUID": "24f4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSLD3P", "name": "Shiploader: PPT 3P", "assetClass": {"name": "Shiploader"}}] | [{"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "emailAddress": "Troy.Drewett@riotinto.com", "displayName": "Drewett, Troy (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
83973 | 2026-09-22T08:24:39.0343776+00:00 | 2026-09-22T16:24:39.0343776+08:00 | {"principalGUID": "df667c75-45d9-4943-a1a3-282393b957c2", "displayName": "Drewett, Troy (RTIO)"} | 2026-10-20T05:58:23.9913037+00:00 | 2026-10-20T13:58:23.9913037+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 336225 | TRUE | TRUE | 2026-10-20T05:58:23.9913037+00:00 | 2026-10-20T13:58:23.9913037+08:00 | #83973 - PPT: 12hrs - CAPD REC2P - STANDALONE OUTAGE | 1.0 | FALSE |  | 2027-12-06T23:00:00+00:00 | 2027-12-07T11:00:00+00:00 | 2027-12-07T07:00:00+08:00 | 2027-12-07T19:00:00+08:00 |  |  |  |  | 12.00 | CAPD REC2P - Standalone Outage |  |  | [{"equipmentGUID": "7833f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTRC2P", "name": "Reclaimer: PPT 2P ", "assetClass": {"name": "Reclaimer"}}] | [{"role": {"name": "Short Term Planner"}, "contact": {"principalGUID": "de5432e8-0dda-4c34-b773-d7b9f536f315", "emailAddress": "Clint.Carlton2@riotinto.com", "displayName": "Carlton, Clint (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
42290 | 2021-07-22T04:39:36+00:00 | 2021-07-22T12:39:36+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-08-28T05:51:38.571496+00:00 | 2026-08-28T13:51:38.571496+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332146 | TRUE | TRUE | 2026-08-28T05:51:38.571496+00:00 | 2026-08-28T13:51:38.571496+08:00 | #42290 - PPT: 106hrs - CONVEYOR: PPT 120P | 5.0 | FALSE |  | 2027-01-11T23:00:00+00:00 | 2027-01-16T09:00:00+00:00 | 2027-01-12T07:00:00+08:00 | 2027-01-16T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Identified change for labour optimisation |  | [{"equipmentGUID": "17e4e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV120P", "name": "Conveyor: PPT 120P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
42300 | 2021-07-22T04:42:12+00:00 | 2021-07-22T12:42:12+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000098b", "displayName": "Sarah McMurray"} | 2026-08-28T05:52:12.4228371+00:00 | 2026-08-28T13:52:12.4228371+08:00 | {"principalGUID": "2861210b-9ee6-4d32-8e30-b92fc9a5e72d", "displayName": "Battle, Sarah (RTIO)"} | {"name": "Fixed Plant"} | 332148 | TRUE | TRUE | 2026-08-28T05:52:12.4228371+00:00 | 2026-08-28T13:52:12.4228371+08:00 | #42300 - PPT: 106hrs - CONVEYOR: PPT 220P | 5.0 | FALSE |  | 2027-01-11T23:00:00+00:00 | 2027-01-16T09:00:00+00:00 | 2027-01-12T07:00:00+08:00 | 2027-01-16T17:00:00+08:00 |  |  |  |  | 106.00 | Standard IAM Maintenance | Identified change for labour optimisation |  | [{"equipmentGUID": "1246f6bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTCV220P", "name": "Conveyor: PPT 220P", "assetClass": {"name": "Conveyor"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "aff7c16d-ae11-4a07-b529-e60375c7f609", "emailAddress": "Craig.Bell@riotinto.com", "displayName": "Craig Bell"}}] | [] | [] | [] | [] | [] | Approved | Update | 2861210b-9ee6-4d32-8e30-b92fc9a5e72d | Battle, Sarah (RTIO) | Scheduled | PPT | Australia/Perth
70825 | 2025-10-16T07:27:07.2575273+00:00 | 2025-10-16T15:27:07.2575273+08:00 | {"principalGUID": "2ac89c59-444d-4f1a-8210-22c8b8cbcb01", "displayName": "Corfield, Nick (RTIO)"} | 2026-10-21T00:54:24.6104594+00:00 | 2026-10-21T08:54:24.6104594+08:00 | {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "displayName": "Azizah, Ailsa (RTA)"} | {"name": "Fixed Plant"} | 336239 | TRUE | TRUE | 2026-10-21T00:54:24.6104594+00:00 | 2026-10-21T08:54:24.6104594+08:00 | #70825 - RVA: 4hrs - DP CHANGEOVER | 4.0 | TRUE |  | 2026-12-12T22:00:00+00:00 | 2026-12-13T02:00:00+00:00 | 2026-12-13T06:00:00+08:00 | 2026-12-13T10:00:00+08:00 |  |  |  |  | 4.00 | Tailings DP Changeover outage | Change of timing as per DP Plan issued 15 Oct 26 by Tailings Engineer |  | [{"equipmentGUID": "7517ee47-4b9a-ee11-a847-000d3acacefd", "code": "RVAPLTWET", "name": "Plant: RVA Wet", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Other"}, "contact": {"principalGUID": "6c7df4b7-984b-4daf-810a-1ce37c069eb3", "emailAddress": "Ross.Prunster@riotinto.com", "displayName": "Prunster, Ross (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1", "emailAddress": "Ailsa.Azizah@riotinto.com", "displayName": "Azizah, Ailsa (RTA)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "2338a0ba-997d-4d5f-b6fd-67fb6ad41f3d", "emailAddress": "Robert.Tolich@riotinto.com", "displayName": "Tolich, Robert (RTIO)"}}, {"role": {"name": "Other"}, "contact": {"principalGUID": "46124aef-041c-4a7a-9922-b05f727893af", "emailAddress": "Hilda.Ogando@riotinto.com", "displayName": "Ogando, Hilda (RTIO-WORKPAC)"}}] | [] | [] | [] | [] | [] | Approved | Update | 1d6d0e39-4317-4bfe-92f7-b91d4b69b8f1 | Azizah, Ailsa (RTA) | Scheduled | RVA | Australia/Perth
69109 | 2025-09-22T05:20:46.8385278+00:00 | 2025-09-22T13:20:46.8385278+08:00 | {"principalGUID": "f1658d5a-306e-4ca3-b60a-20b36f47a157", "displayName": "Solomon, Dale (RTIO)"} | 2026-02-12T00:17:30.7431647+00:00 | 2026-02-12T08:17:30.7431647+08:00 | {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "displayName": "Pulko, Pierre (RTIO)"} | {"name": "HME"} | 286779 | TRUE | TRUE | 2026-02-12T00:17:30.7431647+00:00 | 2026-02-12T08:17:30.7431647+08:00 | #69109 - WTS: 504hrs - 21H443 SANDVIK DI650I DRILL | 3.0 | FALSE |  | 2026-11-24T22:00:00+00:00 | 2026-12-15T22:00:00+00:00 | 2026-11-25T06:00:00+08:00 | 2026-12-16T06:00:00+08:00 |  |  |  |  | 504.00 | Poap 12,000 hr shut | TP Alignment | S21H443 | [{"equipmentGUID": "6307f0bf-7c7b-ee11-a846-000d3acacefd", "code": "21H443", "name": "21H443 Sandvik DI650I Drill", "assetClass": {"name": "Drill - Blast Hole"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "2cc0705a-f24a-4fa6-a44d-abc2c5105f90", "emailAddress": "Pierre.Pulko@riotinto.com", "displayName": "Pierre Pulko"}}] | [] | [] | [] | [] | [] | Approved | Update | 2cc0705a-f24a-4fa6-a44d-abc2c5105f90 | Pulko, Pierre (RTIO) | Scheduled | WTS | Australia/Perth |  | Drills
48179 | 2022-09-15T06:39:38+00:00 | 2022-09-15T14:39:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-09-09T01:51:26.9311547+00:00 | 2026-09-09T09:51:26.9311547+08:00 | {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "displayName": "Introna, Thomas (RTIO)"} | {"name": "Fixed Plant"} | 333261 | TRUE | TRUE | 2026-09-09T01:51:26.9311547+00:00 | 2026-09-09T09:51:26.9311547+08:00 | #48179 - PDO: 204hrs - PLANT: CHR & PLANT: ERS | 8.0 | TRUE |  | 2026-11-23T22:00:00+00:00 | 2026-12-02T10:00:00+00:00 | 2026-11-24T06:00:00+08:00 | 2026-12-02T18:00:00+08:00 |  |  |  |  | 204.00 | ER plant shut - Will run normal 156hr duration BIN604 Structural Repairs (Removed from WK40 Central Shutdown) - requires 204hr duration (no feed from ER/Channar) - 168hr Tooltime | Duration of Bin604 works requires 168hrs tooltime, resulting in a 204hr shut duration for both Eastern Range & Channar, as no feed is permissible for the BIN604 works. |  | [{"equipmentGUID": "8017ee47-4b9a-ee11-a847-000d3acacefd", "code": "CHRPLT", "name": "Plant: CHR", "assetClass": {"name": "Plant"}}, {"equipmentGUID": "c35a111b-5a28-ef11-a84d-000d3acacefd", "code": "ERSPLT", "name": "Plant: ERS", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "bc603b78-7172-47d0-9987-18fc62a13a1b", "emailAddress": "Harley.Newcombe@riotinto.com", "displayName": "Newcombe, Harley (RTIO)"}}, {"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "emailAddress": "Thomas.Introna@riotinto.com", "displayName": "Introna, Thomas (RTIO)"}}] | [] | [] | [{"name": "Structural Repairs"}] | [] | [] | Approved | Update | 0dc76275-d588-42c3-9ba9-f81a6af8e3cb | Introna, Thomas (RTIO) | Scheduled | PDO | Australia/Perth
83734 | 2026-08-24T04:29:14.190373+00:00 | 2026-08-24T12:29:14.190373+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-10-21T02:51:09.8137589+00:00 | 2026-10-21T10:51:09.8137589+08:00 | {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "displayName": "Introna, Thomas (RTIO)"} | {"name": "Fixed Plant"} | 336253 | TRUE | TRUE | 2026-10-21T02:51:09.8137589+00:00 | 2026-10-21T10:51:09.8137589+08:00 | #83734 - PDO: 80hrs - MODULE - PLANT: PDO FINES B | 2.0 | FALSE |  | 2026-12-11T06:00:00+00:00 | 2026-12-14T14:00:00+00:00 | 2026-12-11T14:00:00+08:00 | 2026-12-14T22:00:00+08:00 |  |  |  |  | 80.00 | MOD B Outage | Alignment with Para Primary Crusher Shutdown to enable Supervisor by the Shut Team |  | [{"equipmentGUID": "8e2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODBFINES", "name": "Module - Plant: PDO Fines B", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "345b0127-6e29-4f20-8795-7283902082d4", "emailAddress": "Travis.Pitt@riotinto.com", "displayName": "Pitt, Travis (RTAYARWUN)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0dc76275-d588-42c3-9ba9-f81a6af8e3cb | Introna, Thomas (RTIO) | Scheduled | PDO | Australia/Perth
83729 | 2026-08-24T04:24:09.9370097+00:00 | 2026-08-24T12:24:09.9370097+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-10-21T02:51:09.9676897+00:00 | 2026-10-21T10:51:09.9676897+08:00 | {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "displayName": "Introna, Thomas (RTIO)"} | {"name": "Fixed Plant"} | 336254 | TRUE | TRUE | 2026-10-21T02:51:09.9676897+00:00 | 2026-10-21T10:51:09.9676897+08:00 | #83729 - PDO: 80hrs - MODULE - PLANT: PDO FINES A | 2.0 | FALSE |  | 2026-12-07T22:00:00+00:00 | 2026-12-11T06:00:00+00:00 | 2026-12-08T06:00:00+08:00 | 2026-12-11T14:00:00+08:00 |  |  |  |  | 80.00 | MOD A Outage | Alignment with Para Primary Crusher Shutdown to enable Supervisor by the Shut Team |  | [{"equipmentGUID": "8c2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODAFINES", "name": "Module - Plant: PDO Fines A", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "345b0127-6e29-4f20-8795-7283902082d4", "emailAddress": "Travis.Pitt@riotinto.com", "displayName": "Pitt, Travis (RTAYARWUN)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0dc76275-d588-42c3-9ba9-f81a6af8e3cb | Introna, Thomas (RTIO) | Scheduled | PDO | Australia/Perth
83740 | 2026-08-25T00:07:43.2032126+00:00 | 2026-08-25T08:07:43.2032126+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-10-21T02:51:10.1199701+00:00 | 2026-10-21T10:51:10.1199701+08:00 | {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "displayName": "Introna, Thomas (RTIO)"} | {"name": "Fixed Plant"} | 336255 | TRUE | TRUE | 2026-10-21T02:51:10.1199701+00:00 | 2026-10-21T10:51:10.1199701+08:00 | #83740 - PDO: 80hrs - MODULE - PLANT: PDO FINES C | 2.0 | FALSE |  | 2026-12-14T14:00:00+00:00 | 2026-12-17T22:00:00+00:00 | 2026-12-14T22:00:00+08:00 | 2026-12-18T06:00:00+08:00 |  |  |  |  | 80.00 | MOD C Outage | Alignment with Para Primary Crusher Shutdown to enable Supervisor by the Shut Team |  | [{"equipmentGUID": "8d2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODCFINES", "name": "Module - Plant: PDO Fines C", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "345b0127-6e29-4f20-8795-7283902082d4", "emailAddress": "Travis.Pitt@riotinto.com", "displayName": "Pitt, Travis (RTAYARWUN)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0dc76275-d588-42c3-9ba9-f81a6af8e3cb | Introna, Thomas (RTIO) | Scheduled | PDO | Australia/Perth
83745 | 2026-08-25T00:09:51.6674219+00:00 | 2026-08-25T08:09:51.6674219+08:00 | {"principalGUID": "0157e3f4-358d-4f0a-a40f-919420280981", "displayName": "Cabassi, Karenza (RTIO)"} | 2026-10-21T02:51:10.2743231+00:00 | 2026-10-21T10:51:10.2743231+08:00 | {"principalGUID": "0dc76275-d588-42c3-9ba9-f81a6af8e3cb", "displayName": "Introna, Thomas (RTIO)"} | {"name": "Fixed Plant"} | 336256 | TRUE | TRUE | 2026-10-21T02:51:10.2743231+00:00 | 2026-10-21T10:51:10.2743231+08:00 | #83745 - PDO: 80hrs - MODULE - PLANT: PDO FINES D | 2.0 | FALSE |  | 2026-12-17T22:00:00+00:00 | 2026-12-21T06:00:00+00:00 | 2026-12-18T06:00:00+08:00 | 2026-12-21T14:00:00+08:00 |  |  |  |  | 80.00 | MOD D Outage | Alignment with Para Primary Crusher Shutdown to enable Supervisor by the Shut Team |  | [{"equipmentGUID": "8f2d8caa-06e1-ee11-a84a-000d3acacefd", "code": "PDOPLTMODDFINES", "name": "Module - Plant: PDO Fines D", "assetClass": {"name": "Module"}}] | [{"role": {"name": "Shut Planner / Scheduler"}, "contact": {"principalGUID": "345b0127-6e29-4f20-8795-7283902082d4", "emailAddress": "Travis.Pitt@riotinto.com", "displayName": "Pitt, Travis (RTAYARWUN)"}}] | [] | [] | [] | [] | [] | Approved | Update | 0dc76275-d588-42c3-9ba9-f81a6af8e3cb | Introna, Thomas (RTIO) | Scheduled | PDO | Australia/Perth
84484 | 2026-10-15T05:48:38.1957205+00:00 | 2026-10-15T13:48:38.1957205+08:00 | {"principalGUID": "744222a6-3075-41d7-a01a-7ec018d5a5d2", "displayName": "jacobs, Salomon (RTIO-CHANDLERMACLEOD)"} | 2026-10-15T06:31:22.3766563+00:00 | 2026-10-15T14:31:22.3766563+08:00 | {"principalGUID": "744222a6-3075-41d7-a01a-7ec018d5a5d2", "displayName": "jacobs, Salomon (RTIO-CHANDLERMACLEOD)"} | {"name": "Fixed Plant"} | 336103 | TRUE | TRUE | 2026-10-15T06:31:22.3766563+00:00 | 2026-10-15T14:31:22.3766563+08:00 | #84484 - PPT: 48hrs - SCREENHOUSE: PPT 3P | 1.0 | FALSE |  | 2026-12-11T10:00:00+00:00 | 2026-12-13T10:00:00+00:00 | 2026-12-11T18:00:00+08:00 | 2026-12-13T18:00:00+08:00 |  |  |  |  | 48.00 | Week 49 over capacity |  | SPYD2650 | [{"equipmentGUID": "e0f7e8bf-7c7b-ee11-a846-000d3acacefd", "code": "PPTSCH3P", "name": "Screenhouse: PPT 3P", "assetClass": {"name": "Screenhouse"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "e2a84cf5-e222-446a-8a27-475adb783402", "emailAddress": "Joshua.Cruice@riotinto.com", "displayName": "Cruice, Joshua (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Create | 744222a6-3075-41d7-a01a-7ec018d5a5d2 | jacobs, Salomon (RTIO-CHANDLERMACLEOD) | Scheduled | PPT | Australia/Perth
44185 | 2021-11-23T06:53:56+00:00 | 2021-11-23T14:53:56+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:58:47.7280381+00:00 | 2026-10-02T14:58:47.7280381+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335171 | TRUE | TRUE | 2026-10-02T06:58:47.7280381+00:00 | 2026-10-02T14:58:47.7280381+08:00 | #44185 - BM4: 168hrs - PLANT: BM4 | 12.0 | TRUE |  | 2027-09-30T04:00:00+00:00 | 2027-10-07T04:00:00+00:00 | 2027-09-30T12:00:00+08:00 | 2027-10-07T12:00:00+08:00 |  |  |  |  | 168.00 | Baseline changed from 96h to 126h as per MOC 113812 | Request to extend current shut to align with pre-existing PC2 shut, as we are looking to execute BS1 tie in/commissioning during this period. |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "5906dc4e-e2e0-42d0-a791-094222a1426d", "emailAddress": "Brodie.Tyrer@riotinto.com", "displayName": "Tyrer, Brodie (RTIO-WORKPAC)"}}] | [] | [] | [] | [{"code": "P-0510128.53", "name": "B4MM Fixed Plant Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "168"}] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
44186 | 2021-11-23T06:54:44+00:00 | 2021-11-23T14:54:44+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:58:47.8858845+00:00 | 2026-10-02T14:58:47.8858845+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335172 | TRUE | TRUE | 2026-10-02T06:58:47.8858845+00:00 | 2026-10-02T14:58:47.8858845+08:00 | #44186 - BM4: 168hrs - CRUSHER - PRIMARY: BM4 01 | 10.0 | TRUE |  | 2027-09-30T04:00:00+00:00 | 2027-10-07T04:00:00+00:00 | 2027-09-30T12:00:00+08:00 | 2027-10-07T12:00:00+08:00 |  |  |  |  | 168.00 | Baseline changed from 96h to 126h as per MOC 113812 | Request to extend current shut to align with pre-existing PC2 shut, as we are looking to execute BS1 tie in/commissioning during this period. |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
44183 | 2021-11-23T06:52:19+00:00 | 2021-11-23T14:52:19+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:56:11.3530833+00:00 | 2026-10-02T14:56:11.3530833+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335050 | TRUE | TRUE | 2026-10-02T06:56:11.3530833+00:00 | 2026-10-02T14:56:11.3530833+08:00 | #44183 - BM4: 168hrs - CRUSHER - PRIMARY: BM4 01 | 12.0 | TRUE |  | 2027-06-30T04:00:00+00:00 | 2027-07-07T04:00:00+00:00 | 2027-06-30T12:00:00+08:00 | 2027-07-07T12:00:00+08:00 |  |  |  |  | 168.00 | Standard IAM Maintenance | Request from Shutdown team & Project team to allow more time for washdowns and isolations before power outage (see email for context). New dates have been provided on 30 September that supersede these requested dates. |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
44182 | 2021-11-23T06:51:17+00:00 | 2021-11-23T14:51:17+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:56:11.523163+00:00 | 2026-10-02T14:56:11.523163+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335051 | TRUE | TRUE | 2026-10-02T06:56:11.523163+00:00 | 2026-10-02T14:56:11.523163+08:00 | #44182 - BM4: 168hrs - PLANT: BM4 | 14.0 | TRUE |  | 2027-06-30T04:00:00+00:00 | 2027-07-07T04:00:00+00:00 | 2027-06-30T12:00:00+08:00 | 2027-07-07T12:00:00+08:00 |  |  |  |  | 168.00 | Baseline changed from 96h to 126h as per MOC 113812 | Request from Shutdown team & Project team to allow more time for washdowns and isolations before power outage (see email for context) |  | [{"equipmentGUID": "9417ee47-4b9a-ee11-a847-000d3acacefd", "code": "BM4PLT", "name": "Plant: BM4", "assetClass": {"name": "Plant"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [{"relationshipType": null, "shut": {"shutId": 74859, "shutVersionId": 327173, "title": "#74859 - NBWT: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE", "startDatetimeUTC": "2027-07-01T22:00:00+00:00", "endDatetimeUTC": "2027-07-02T22:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 74858, "shutVersionId": 327174, "title": "#74858 - BM2: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE", "startDatetimeUTC": "2027-07-01T22:00:00+00:00", "endDatetimeUTC": "2027-07-02T22:00:00+00:00"}}, {"relationshipType": null, "shut": {"shutId": 74857, "shutVersionId": 327175, "title": "#74857 - BM4: 24hrs - BROCKMAN BULK SUBSTATION UPGRADE - REGIONAL POWER OUTAGE", "startDatetimeUTC": "2027-07-01T22:00:00+00:00", "endDatetimeUTC": "2027-07-02T22:00:00+00:00"}}] | [] | [{"code": "P-0508792", "name": "GBO Bulk substation upgrade 220kv", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}, {"code": "P-0510128.53", "name": "B4MM Fixed Plant Upgrades", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
44184 | 2021-11-23T06:53:02+00:00 | 2021-11-23T14:53:02+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:56:11.7128552+00:00 | 2026-10-02T14:56:11.7128552+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335052 | TRUE | TRUE | 2026-10-02T06:56:11.7128552+00:00 | 2026-10-02T14:56:11.7128552+08:00 | #44184 - BM4: 168hrs - CRUSHER - PRIMARY: BM4 02 | 10.0 | TRUE |  | 2027-06-30T04:00:00+00:00 | 2027-07-07T04:00:00+00:00 | 2027-06-30T12:00:00+08:00 | 2027-07-07T12:00:00+08:00 |  |  |  |  | 168.00 | Baseline changed from 96h to 126h as per MOC 113812 | Request from Shutdown team & Project team to allow more time for washdowns and isolations before power outage (see email for context) |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "fcf12def-72ff-4fd8-867e-6d68ebdf2a3b", "emailAddress": "Travis.Heys@riotinto.com", "displayName": "Travis Heys"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "7d9c9185-ad19-4a2b-a604-17564b2bd8ae", "emailAddress": "Craig.McDonald@riotinto.com", "displayName": "Craig McDonald"}}, {"role": {"name": "Specialist Planner"}, "contact": {"principalGUID": "851a3d3b-771c-456e-be38-8e8780acd0f8", "emailAddress": "Aleks.Radevic@riotinto.com", "displayName": "Radevic, Aleks (RTIO)"}}] | [] | [] | [] | [] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
44180 | 2021-11-23T06:49:05+00:00 | 2021-11-23T14:49:05+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:58:47.1299095+00:00 | 2026-10-02T14:58:47.1299095+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335167 | TRUE | TRUE | 2026-10-02T06:58:47.1299095+00:00 | 2026-10-02T14:58:47.1299095+08:00 | #44180 - BM4: 240hrs - CRUSHER - PRIMARY: BM4 01 | 10.0 | TRUE |  | 2027-03-27T04:00:00+00:00 | 2027-04-06T04:00:00+00:00 | 2027-03-27T12:00:00+08:00 | 2027-04-06T12:00:00+08:00 |  |  |  |  | 240.00 | Baseline changed from 96h to 126h as per MOC 113812. Shut changed from 120hrs to 240hrs as requested by A. Radevic and N. Anderson. | Request to extend to align with pre-existing PC2 shut, as we are looking to execute the BS1 tie in during this period. New dates have been provided on 30 September that supersede these requested dates. |  | [{"equipmentGUID": "470af0bf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS01", "name": "Crusher - Primary: BM4 01", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}, {"role": {"name": "Project Contact"}, "contact": {"principalGUID": "01e76f26-7453-4569-95f6-dac4d237b695", "emailAddress": "Dipin.Varsani@riotinto.com", "displayName": "Varsani, Dipin (RTIO-GUIDANTGLOBAL)"}}] | [] | [] | [] | [{"code": "P-0508791", "name": "B4 MEM Workshop Expansion", "projectTeam": {"name": "Sustaining Capital"}, "totalProjectTime": "120"}] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
65355 | 2024-10-14T05:21:38+00:00 | 2024-10-14T13:21:38+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:58:47.2918964+00:00 | 2026-10-02T14:58:47.2918964+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335168 | TRUE | TRUE | 2026-10-02T06:58:47.2918964+00:00 | 2026-10-02T14:58:47.2918964+08:00 | #65355 - BM4: 174hrs - BS1 PROJECT SHUT #11 PC2 | 6.0 | TRUE |  | 2027-09-29T22:00:00+00:00 | 2027-10-07T04:00:00+00:00 | 2027-09-30T06:00:00+08:00 | 2027-10-07T12:00:00+08:00 |  |  |  |  | 174.00 | Shut #11 Contingency Shutdown | Request to extend current shut to align with pre-existing PC2 shut, as we are looking to execute BS1 tie in/commissioning during this period. |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "12196416-07ec-46a3-b856-b91b454874c3", "emailAddress": "Dean.Allbon@riotinto.com", "displayName": "Dean Allbon"}}] | [] | [] | [] | [{"code": "X", "name": "BS1 Project", "projectTeam": {"name": "D&T"}, "totalProjectTime": "96"}] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Major Projects | BM4 | Australia/Perth
44187 | 2021-11-23T06:55:15+00:00 | 2021-11-23T14:55:15+08:00 | {"principalGUID": "abefcdab-0000-0000-0000-00000000003d", "displayName": "Clare Campbell-Cooke"} | 2026-10-02T06:58:47.4366133+00:00 | 2026-10-02T14:58:47.4366133+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335169 | TRUE | TRUE | 2026-10-02T06:58:47.4366133+00:00 | 2026-10-02T14:58:47.4366133+08:00 | #44187 - BM4: 174hrs - CRUSHER - PRIMARY: BM4 02 | 10.0 | TRUE |  | 2027-09-29T22:00:00+00:00 | 2027-10-07T04:00:00+00:00 | 2027-09-30T06:00:00+08:00 | 2027-10-07T12:00:00+08:00 |  |  |  |  | 174.00 | Baseline changed from 96h to 126h as per MOC 113812 | Request to extend current shut to align with pre-existing PC2 shut, as we are looking to execute BS1 tie in/commissioning during this period. |  | [{"equipmentGUID": "7c74fbbf-7c7b-ee11-a846-000d3acacefd", "code": "BM4PCS02", "name": "Crusher - Primary: BM4 02", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth
71542 | 2025-10-28T02:08:23.3306117+00:00 | 2025-10-28T10:08:23.3306117+08:00 | {"principalGUID": "03d795ee-90c4-4b6f-a129-052c82e6ff79", "displayName": "Campbell-Cooke, Clare (RTIO)"} | 2026-10-02T06:58:47.5832999+00:00 | 2026-10-02T14:58:47.5832999+08:00 | {"principalGUID": "2d1218fa-8f18-4b5f-81fd-485231d5f0df", "displayName": "McKee, Lara (RTIO)"} | {"name": "Fixed Plant"} | 335170 | TRUE | TRUE | 2026-10-02T06:58:47.5832999+00:00 | 2026-10-02T14:58:47.5832999+08:00 | #71542 - BM4: 174hrs - CRUSHER - PRIMARY: BM4 03 | 4.0 | TRUE |  | 2027-09-29T22:00:00+00:00 | 2027-10-07T04:00:00+00:00 | 2027-09-30T06:00:00+08:00 | 2027-10-07T12:00:00+08:00 |  |  |  |  | 174.00 | IAM Standard Maintenance | Request to extend current shut to align with pre-existing PC2 shut, as we are looking to execute BS1 tie in/commissioning during this period. |  | [{"equipmentGUID": "ea0a3330-54a1-ef11-a856-000d3acacefd", "code": "BM4PCS03", "name": "Crusher - Primary: BM4 03", "assetClass": {"name": "Crusher - Primary"}}] | [{"role": {"name": "Shut Supervisor / Coordinator"}, "contact": {"principalGUID": "441c2aef-4c18-4954-9c9c-a4870e13cc01", "emailAddress": "Marius.Lindeque@riotinto.com", "displayName": "Marius Lindeque"}}] | [] | [] | [] | [] | [] | Approved | Update | 2d1218fa-8f18-4b5f-81fd-485231d5f0df | McKee, Lara (RTIO) | Scheduled | BM4 | Australia/Perth